## Slide 1: sPHENIX Director’s Review
Robert Pisani
April 10-11, 2019
WBS 2.04: Infrastructure

## Slide 2: The Infrastructure Technical Overview
SPHENIX
Infrastructure Work Packages
4/5/2019
sPHENIX Integration and Installation
2
2.04: sPHENIX Infrastructure
2.04.02.01: Line Electric Power Distribution
2.04.02.02: Detector Support Services Systems Components
2.04.02.03: Detector Electronics Racks and Rack generic support
2.04.02.04: Detector Gas and Cooling Services Systems
2.04.02.05: Detector Safety Subsystems Work Package
2.04.02.06: Gas Mixing House & Gas Pad Components
2.04.02.07: Rack Room Modifications
2.04.02.08: Control Room Work Package
2.04.01: Detector Support Systems
2.04.02:Facility Support Systems
2.04.02.01: Magnet Cryo, Electrical & Control Structural Support in IR
2.04.02.02: Beampipe and Vacuum Work Package
2.04.02.03: IR HVAC Work Package
2.04.02.04: IR Electronics Cooling Water Distribution System
2.04.02.05: IR/AH Safety Subsystems Components Work Package
2.04.02.06: Assembly Hall Modifications

## Slide 3: Infrastructure Overview
Detector special gasses
storage/mixing facility
1008F
Electronics cooling water
pump house/piping network
Electric power substations
13.8/480/208/120V distribution
Detector/Facility Safety System
Detector supports racks, cable trays support equipment
HVAC
CRYO Support
Hall Modifications

## Slide 4: Scope
Detector Support Systems
  Modify existing Power Distribution in IR and PRR and their components.
  Detector Support Cables and Cable trays
  Racks (Reuse), Rack power, rack cooling & layout
  Support services for detector gas and detector cooling and layout
  On Carriage detector safety systems
  Modification of existing Support Services for Gas Mixing house and gas pads
  PHENIX Rack Room modifications and updates
  PHENIX Control room modifications and updates.
Facility Support Systems
Cryo routing, electrical support components, and layout
Existing Beampipe and vacuum line modification
Modification and maintenance of Existing HVAC for IR, PRR, Counting house as needed
Existing Electronics cooling water distribution modification to IR, Carriage and PRR
IR and Assembly Hall detector subsystem safety modification and new components.
Assembly Hall modification for sPHENIX
April 10-11, 2019
Reconfiguring much of the existing infrastructure
Generally includes labor involved in planning, design and procurement.
All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.02(Infrastructure Installation).

## Slide 5: Infrastructure: Key Personnel
  Robert Pisani --sPHENIX Infrastructure Interim L2 Mgr
  James Mills --sPHENIX Project Engineer
  Russell Feder --- sPHENIX Chief Mechanical Engineer
  Roberto Than/Paul Orfin ---CAD Cryogenic Support
  Charlie Folz --- CAD Engineering Support
  Jon Hock --- CAD Engineering Support
  Brian Streckenbach --- CAD Engineering Support
  C. Biggs ----sPHENIX Lead Technician

## Slide 6: Basis of Estimate & Resource-Loaded Schedule
One file for 2.04.01 Detector Support Systems
One File For 2.04.02 Facility Support Systems
Within each file, one Summary and one Details page per Work Package
Fully Consistent w/ P6 RLS
(Excel “snapshot” of RLS)
Navigation links Imbedded and by Tab

## Slide 7: Schedule Drivers
Schedule driven by when items need to be ready for installation (2.05.02)
    Design/Safety Review
    Deliverable ready for installation
    No Items on critical path
    Most items have over 100 days of float before becoming critical
  Few Key Items:
  MoA with CAD– Spring 2019
  Line Power Distribution-- April 2020
  Cyro Support –May 2020
  sPHENIX Safety System –July 2021
  Beampipe Modifications—September 2021

## Slide 8: Schedule Drivers
Milestones for Infrastructure
Facility Support
Detector Support

## Slide 9: Cost Drivers WBS 2.4 Infrastructure
Infrastructure Cost Drivers:
Predominantly driven by labor cost.
Mostly Engineers and Technical support
Few key items:
Beampipe design and modification
Cryogenic support structures
Electrical and cooling water rerouting and distribution
Hall Modifications

## Slide 10: Estimate Uncertainty Breakdown WBS 2.04 Infrastructure
Majority Preliminary Labor estimates based on previous experience from PHENIX
M&S Professional Estimates from similar work done for PHENIX

## Slide 11: 2.4 Infrastructure Risks

## Slide 12: Issues and Concerns
Senior Electrical Engineer Retired-- Transition Responsibilities, New Hire
Availability of non-sPHENIX Engineering and technical staff
  MoA with Other BNL Departments, including schedule and resource requirements
Availability of funding as needed
  Funding profiles and EVMS planning to meet required schedules
Failure of Major Facility Component
  Contingency plans for repair or replacement.

## Slide 13: Summary of Status
Facility Support
IP8 Cryogenic Layout almost complete—Early Design Stage for structural supports underway
Beampipe parameters close to finalized through integration group.—Pre-design stage
HVAC requirements being developed and analyzed-Pre-Design Stage
Cooling water requirement identified --Early Design Stage for distribution
IR/AH Safety Subsystem Components- Conceptual Stage
Assembly Hall Modifications underway
Detector Support
Power Distribution –Early Design Stage
Detector Support –Cable tray, cooling lines, and gas lines requirement being developed– Early Design Stage
Electronic Rack and supports- Carriage rack location and assignments close to final –Design Stage
Detector Gas and Cooling -- Off detector support needs identified– Early Design Stage
Detector Safety System– Conceptual Stage
Gas Mixing house and Pad—Early Design Stage
Rack Room Modifications– Work has started
Control Room– Early Design stage