## Slide 1: sPHENIX Director’s Review Time Projection Chamber Mechanics
Klaus Dehmelt
April 9-11, 2019
BNL

## Slide 2: The L3 Component: 1.02.01
1.02.01: TPC Mechanics
Outer Field Cage O-FC, R = 78 cm, L = 211 cm
Inner Field Cage I-FC, R = 20 cm , L = 211 cm
  Central Membrane CM
  Endplates EP, 2 in z
  Modules, 12 in f, 3 in r
Quad-GEM Gain Stage
Operated @ Low Ion Back Flow

## Slide 3: 1.02.01 Technical Overview
Dimensions and designs dictated by
  Inner/outer radius  magnet and inner/outer detector design
  Length  pseudorapidity |h| < 1.1 (> 37 polar angle)
  Design of field cages  minimum space
  and maximum stability
  Design endplates  minimum material
  budget, maximum stability
  Design modules  maximum integrity, simplest method of manufacture, maximum performance
Full technical understanding of all components
Photograph of readout board

## Slide 4: 1.02.01 Scope
WBS 1.02.01 contains all elements that lead to the successful assembly of the TPC mechanics (WBS 1.02.01.08) and eventually make the TPC ready to install
Dependences, all on items outside MIE
  Detector Support Systems  sPHENIX Infrastructure WBS 2.09.02
  Infrastructure Installation  sPHENIX Integration and Installation WBS 2.10.02
  TPC Installation  sPHENIX Integration and Installation WBS 2.10.08

## Slide 5: 1.02.01 Scope

## Slide 6: L3 Collaborators
L2 Manager WBS 1.02 TPC: Thomas K. Hemmick (Stony Brook University)
  Distinguished Teaching Professor
L3 Manager WBS 1.02.01 TPC Mechanics: Klaus Dehmelt (Stony Brook University)
  Research Scientist
John Cozzolino (SMD BNL)
  Senior engineer
Steven Bellavia (CAD BNL)
  Senior engineer
Daniel Cacace (Physics Department BNL)
  Mechanical engineer
Connor Miraval (Instrumentation Division BNL)
  Mechanical engineer
Stony Brook Postdocs, graduate students, undergraduate students

## Slide 7: Schedule Drivers
WBS 1.02.01.06 TPC Production GEM Acquisition
  Factory production follows a Start-Start relationship to GEM production
  Module assembly takes less time than GEM production (PHENIX Hadron Blind Detector experience, ALICE TPC upgrade experience)
  GEM schedule drives module production schedule and TPC overall schedule

## Slide 8: Cost Drivers
Possible opportunity

## Slide 9: Status and Highlights
Test beam campaign at Fermilab Test Beam Facility FTBF: R2 module

## Slide 10: Status and Highlights
Test beam campaign at Fermilab Test Beam Facility FTBF
Main task: determine position resolution at B = 0 T and extrapolate to B = 1.4 T
L

## Slide 11: Status and Highlights
Test beam campaign at Fermilab Test Beam Facility FTBF
Main task: determine position resolution at B = 0 T and extrapolate to B = 1.4 T
TPC simulation follows every electron
Simulation predicts resolution
  Contains fudge factor on TPC resolution
  Roughly matches prior parametrization
Measurement better than simulation

## Slide 12: Status and Highlights
Field cage production well under way
  Inner field cage finalized
  Outer field cage in its final production
Endplates (wagon wheels) in hand, inspected and approved
GEM module v2 parts in hand
Structure for TPC assembly in hand

## Slide 13: Status and Highlights

## Slide 14: Status and Highlights

## Slide 15: Status and Highlights

## Slide 16: Status and Highlights

## Slide 17: Issues and Concerns
  GEM production exclusively at CERN
    Mitigated by hiring employed technician at CERN Workshop exclusively for sPHENIX production
    Big GEM production projects (ALICE TPC, CMS Forward Muon Detectors) have been completed in 2018  No interference with sPHENIX TPC GEM production

## Slide 18: Activities Over the Next Few Months
  QA of field cage + end plates
  Final R&D efforts on GEM modules
  Test beam campaign with TPC v2a GEM Module prototype at Fermilab FTBF
  Establishing and testing QA procedure for GEM modules
  Start of TPC Production GEM Acquisition

## Slide 19: Milestones

## Slide 20: Summary
  TPC-Mechanics well understood
  Design benefitted from previous/present TPC designs (STAR/ILC/ALICE)
  TPC-Mechanics well on design and schedule
  TPC-Mechanics will meet all performance goals for sPHENIX
  TPC-Mechanics ready for PD2/3 approval