## Slide 1: sPHENIX Director’s Review EMCal Module Production and Sector Assembly
Sean Stoll
April 9-11, 2019
BNL

## Slide 2: The L3 Component
1.03.02 EMCal – Module Production and Sector Assembly
  The goal of this WBS item is to assemble the EMCal blocks, optics, electronics, and cooling components into finished sectors that can then be installed into the EMCal structural framework in the experimental hall.
  The Module Production and Sector Assembly work will be performed at BNL
    1.03.02.01 Set Up Module Production, Sector Assembly and Test Area
    1.03.02.02 EMCal Module Production
        V2.1 Prototype  Preproduction Phase (1+12 sectors)  Final Production (52 sectors)
    1.03.02.03 EMCal Sector Assembly
        V2.1 Prototype  Preproduction Phase (1+12 sectors)  Final Production (52 sectors)

## Slide 3: L3 Technical Overview
2(±h) x 32 (f) = 64 Sectors
7.5 cm
readout
1 Full Sector = 72 Blocks
= 288 towers
~14 cm absorber
(h=0)
EMCAL radial
space allocation
Deliverable: 64 EMCAL Sectors
We have an advanced and detailed design, and are in the process of assembling our first full prototype sector.

## Slide 4: EMCal Modules and Sectors Team
L2 Manager
Craig Woody, Senior Physicist (BNL)
40+ years of detector experience (much of it with calorimetry)
L3 Managers
Caroline Riedl, Research Scientist (UIUC)
Access to large construction facilities with experienced staff in
building large detectors
Sean Stoll, Physics Associate (BNL)
25+ years in building and operating detectors
(including the PHENIX EMCAL)
BNL Team
Physicists: Craig Woody, Jin Huang, John Haggerty, Martin Purschke
Chief Engineer: Russell Feder
Mechanical Technicians: Bill Lenz, Mike Lenz
Engineers & Designers: Rich Ruggiero, Dan Cacace, Chris Pontieri
Physics Associates: Sean Stoll, Rob Pisani
Electrical Engineer and Technician: Steve Boose, Sal Polizzo
C. Riedl
Technicians and engineers with V2.1 prototype
BNL scientists and engineer with V2.1 prototype at
FermiLab for beam test.

## Slide 5: L3 Scope – Production Steps and Deliverables
W powder
epoxy
mold parts
fixtures
set up
Block
casting
dimensional
machining
end-cut
machining
Deliverable:
block
(4896)
UIUC Block Production
block
gluing jigs & fixtures
light guides
end reflectors
glue on
light guides &
end reflectors
attach pcb
w/ sipms
pcbs w/sipms
Deliverable: module
(4896)
BNL Module Production
Sector Assembly
Sector box
Mechanically
Mount and Align
Preamps and
Interface pcb
cooling
Install electronics
Cabling, cooling
cabling
Deliverable: sector
(64)
testing
QC
testing
scint fiber
screens
create
Fiber-screen
assemblies
Material
inputs
Labor
tasks

## Slide 6: Schedule Drivers
Main Schedule Drivers:
  Production of absorber blocks at UIUC and receipt of blocks at BNL
  Production of Electronics at BNL – receipt of assembled SiPM daughterboards (Critical Path)
  Obtaining components such as light guides, cooling assemblies, mechanical parts – Getting PO’s out on schedule
  Maintaining module production and sector assembly production schedules
1.03.02 consists of a series of assembly steps, and so relies on:
  Having all of the components available when needed
  Maintaining steady production/assembly rates - Our average production rate is 1 assembled sector every 6 days
Key Milestones:
Completion of V2.1 Prototype | 9/28/2018
Procure Light Guides for Sectors 1-12 – Contract Award | 3/5/2019
Completion of Sector 0 Prototype | 8/20/2019
Procure Mechanical and Cooling Parts for Sectors 1-12 | 9/13/2019
Procure Light Guides for Sectors 13-64 | 3/4/2020
Completion of Preproduction Sectors | 7/16/2020
Completion of All Sectors | 10/13/2021
Ready to Install EMCal Sectors Into sPHENIX | 10/15/2021

Complete
Complete
In progress…


## Slide 7: Cost Drivers
Total material costs $860k
Labor is BNL Contributed
Mechanical support and enclosure $390k
  Box parts, block mounting, rails, rail blocks, reflective end-plates
Acrylic Light Guides - $292k
  mold + production run, processing
Cooling System (internal to sectors) $90k for 64 sectors
Light Guides
Cooling plates

## Slide 8: More Schedule and Costs
1.03.02 Consists mainly of assembly processes and is dominated by labor costs
Labor Estimates are based on experience with the production of our prototypes, and prior experience working on similar projects.
The module production steps are well understood. Production will involve scaling up the procedures and adding parallel production lines.
For the sector assembly, we have had experience assembling prototypes, but the final sectors are more complicated given the greater number of blocks, connections, cabling, and cooling. We are learning from the Sector 0 prototype about any challenges introduced as processes are scaled up.
Estimates for fixed-cost items such as light guides are based on manufacturer’s quotes. We have ordered light guides for sectors 1-12 with an option to buy additional parts for sectors 13-64.
Estimates for mechanical support and enclosures are based on manufacturer’s quotations and engineer’s estimates for designing and producing custom parts. We are evaluating the performance of mechanical parts purchased for Sector 0 before proceeding with the subsequent orders.

## Slide 9: Status and Highlights
We refitted the V2.1 prototype with updated electronics and cooling for an SiPM/system radiation damage study
We have set up our sector assembly area in the Physics Hi-bay. We have been producing and calibrating fixtures for epoxying sectors, and test-fitting blocks.
We have been testing blocks and SiPM pcbs, and we plan to assemble Sector 0 during April.
We have made major procurements of light guides and will verify mechanical parts vendors with parts made for Sector 0.
SiPM pcbs, light guides
Sector assembly area, Physics high-bay

## Slide 10: Issues and Concerns
  We are assembling and testing our first full sector prototype (Sector 0). We will need to streamline procedures and workflow to scale up for full production.
  We need to develop procedures to test, certify, and calibrate production sectors and enlist student help from the collaboration to do this.
  Maintaining the critical path module production and sector assembly production lines over > 1 year time periods will be challenging with little float built into the schedule. Delays could be mitigated by allowing for storage of partially assembled components and sectors.
  The allocated radial space for the EMCal is very tight. We need to fit all cabling and cooling in with some safety factor to allow for any variation during production. We will test this with the Sector 0 prototype.
  We need to establish procedures for shipping and receiving production quantities of blocks from UIUC to BNL.

## Slide 11: Summary
  We have made progress developing our engineering design and testing it through our prototypes. We are progressing from CAD designs to manufactured parts and systems. We are assembling and testing our first full sector prototype (Sector 0). This will verify the design and fit of all parts prior to full production.
  We are currently streamlining procedures and organizing workflow to scale up for full production. We are training technicians to do the work and also benefiting from the experience that they bring.
  EMCal Module Production and Sector Assembly is ready for PD-2/3 approval.