## Slide 1: sPHENIX Director’s Review 1.04.02 HCal Sector Mechanics
John Lajoie
April 9-11, 2019
BNL

## Slide 2: Outer Hadronic Calorimeter
32 Sector Assemblies
  20’ long
  15 Tons
  1020 steel
Barrel Steel from WBS 2.03.03 will be populated with electronics and scintillating tile and then transported to bldg. 1008 where they will be installed around the sPHENIX magnet.
WBS 1.04.02 HCal Sector Mechanics includes lifting fixtures and splice plates, together with 2.03.03 they enable the construction and assembly of the entire outer HCAL.

## Slide 3: 1.04.02 HCal Sector Mechanics
O-HCal will consist of 32 sectors that will be assembled around the sPHENIX magnet
The carriage cradle will support the lower 15 sectors, this will occur through bolted connections from the cradle into the sector combs
After the sPHENIX magnet and Inner Detector Structural Supports are in place, the remaining 17 sectors will be installed

## Slide 4: 1.04.02 HCal Sector Mechanics
Splice Plates
Pucks
Pins
Spreader Beam
Support Stands
Rotation Fixtures
WBS 1.04.02 Sector Mechanics provides the following for this installation process
  Splice plates
    Pins and bolts will be the main connection from sector to sector
    Pucks will be used to maintain a nominal gap of 2mm in between sectors at endplates
  Rotation Fixture
    Sectors will be rotated in support stands and pinned into nominal installation angles
  Lifting Fixture
    Will be utilized to pin sector into nominal installation angle
    Take sector from support stands to installation area

## Slide 5: Scope
Engineer, analyze, design and procure a splice plate along with associated parts that will aid in the support of the Barrel Flux Return Steel individual sectors.
Deliverables
  Splice Plates
    64 Splice Plates (32 North, 32 South)
    246 Pins
    128 Pucks

## Slide 6: Preproduction M&S
Pins
Pucks
4 Preproduction Splice Plates
Made to production level specifications (material, tolerances)
Pins/Pucks
Made to production level specifications (material, tolerances)
2 sizes made to perform fit up tests

## Slide 7: Scope
Engineer and design a lifting fixture that will be utilized to rotate each sector to its nominal installation position.
Engineer and design a set of supports that will hold each sector during the rotation process.
  Deliverables
    Lifting Fixtures
      Spreader Beams
      Fixtures that permits rotating
      Sector Stands

## Slide 8: Technical Overview
Splice Plates
  Testing of Preproduction splice plates began 3/29/2019
    Confirming tolerances levels(plates, pins, pucks)
    Continuing to develop installation and assembly plan
Lifting Fixtures & Supports
  Spreader beam has proven to be adequate
  Support stands are adequate
  Additional engineering is required on the rotation fixtures

## Slide 9: Collaborators
Iowa State University
John Lajoie (Outer HCAL L2 Manager)
Brookhaven National Laboratory
Rich Ruggiero (Design/Integration)
Dan Cacace (Engineering/Analysis)
Carter Biggs (Lead Technician)
Georgia State University
Megan Connors(HCal Scintillating Tiles)
Baruch College
Stefan Bathe(HCal Assembly & Testing)

## Slide 10: Schedule Drivers
Splice Plates
  Testing sectors in assembly
    Any changes to design need to go through a design review
  Lead time for fabrication of splice plates
  At current time we are well ahead of the critical path
Lifting Fixtures and Supports
  Outer HCAL Lifting Fixture and Supports Design Complete (6-Sep-19)
  Vendor fabrication time
Snapshot of RLS

## Slide 11: Cost Drivers
Splice Plates
  Fabrication of all parts
    Preproduction PO was for 4 splice plates/16 pins/8 pucks (17k)
    Price of material (4140 HT Steel)
    Any changes to current design
Lifting Fixtures and Supports
  Off shelf items
  Fabrication of supports
  Fabrication of additional rotation fixturing
Splice Plate
Pin
Puck

## Slide 12: Status and Highlights
Splice Plates
  Preproduction Splice Plates specifications have been achieved by vendor
  Test fits to date have been successful
Lifting Fixtures and Supports
  Rotation fixture requires additional engineering and design which will be resolved in the coming months

## Slide 13: Milestones
Procure Outer HCAL Splice Plates - Contract Award(s)- 1-Oct-19
  Installation of Barrel Steel, including splice plates is in June 2021
    300+ days of float
Procure Outer HCAL Lifting Fixtures & Supports - Contract Award(s)- 13-Dec-19

## Slide 14: Activities over the next few months
Continue to utilize splice plates and accompanied hardware in sector to sector fit ups
Ensure that pin/puck sizes are appropriate for installation of all sectors
Continue to develop fixture to ensure a safe and effective rotation of sector

## Slide 15: Issues and Concerns
Issues/Concerns
Proposed Action/Resolution
Potential increase in material cost for splice plates
Potential need to redesign rotating
fixture
Review preproduction splice plates and obtain quote as soon as possible for final production amount
Utilize as much of current fixture as possible with minimal redesign

## Slide 16: Summary
Vendor was able to meet the tight tolerances on the preproduction purchases
The sPHENIX team will continue to test fit sectors to each other using these preproduction parts
We will hold additional meetings to discuss any changes that may need to be made to the splice plates
We are preparing for an internal design review in late August for any revisions of the lifting fixture and supports
We fully expect to be well within the schedule to complete the design and procurement process of this subsystem.
The HCal Sector Mechanics are ready for PD-2/3 approval

## Slide 17: Back Up

## Slide 18: Spreader Beam Information
Working Load Limit: 40,000lbs
Proof Test: 80,000lbs

## Slide 19: Splice Plate Information