## Slide 1: sPHENIX Director’s Review WBS 1.04.04 Outer HCal Assembly and Testing
Stefan Bathe
April 9-11, 2019
BNL

## Slide 2: The L3 Component
Populate barrel-flux-return-steel sectors with scintillating tiles and electronics to create outer hadronic calorimeter
  From a collection of parts to a working detector

## Slide 3: L3 Technical Overview
Technical steps for assembly and testing very similar to prototype assembly and testing: solved
Three main differences
  Size (prototype was smaller): stand to hold steel sectors horizontally
  Cosmics trigger: reconfigure electronics self-trigger for cosmic calibration
  Mass production: set up several stations for efficient assembly/testing
No technical issues that still need to be resolved

## Slide 4: L3 Scope
HCAL assembly will involve four separate steps
  Install Scintillating Tiles in steel sector
    Scintillating tiles tested at Uniplast and GSU
    Sort tiles by response and install in gap with clips
    12 different tile shapes x 2 per gap, 10 gaps/sector
  Populate Sector with Electronics
    Install and wire pre-amplifiers, LED fibers, RO boards
  LED testing and Light Tighting
    Replace/Repair as necessary
  Cosmics Testing and Final Validation
    Cosmics results for each tower to be databased for initial calibration

## Slide 5: L3 Scope (continued)
Four sectors will be worked on in parallel, one at each step
Four stations (one for each step) will be cycled through the four sectors
  easier than moving sectors around
5 days per sector, per step/station (assuming day shift only)
Full production will crank out one sector per week

## Slide 6: L3 Collaborators
6
May 23-25, 2018
John Lajoie
L2 Manager
Stefan Bathe
L3 Manager
HCAL Assembly
Megan Connors
L3 Manager
Scintillating Tiles
Chris Pontieri
L3 Manager Flux Return Sector Steel
also:
Colorado, UTK, Rutgers
UNCG, WSU

## Slide 7: Schedule Drivers
Assembly requires components:
  Flux Return Steel Sectors (infrastructure upgrade)
  Scintillating Tile Assemblies (CD3A approved)
  Calorimeter Electronics (WBS 1.05)
The assembly schedule itself is driven by labor:
  Time estimates based on experience with test beam prototypes:
    Two technicians assigned to factory
    One postdoc
    Two students per station
  Can add additional labor/shifts to maintain schedule

## Slide 8: Schedule
Advanced R&D:
  Populate Outer HCAL Sectors with Tiles Start : 19 Aug 2019
  HCAL Advanced R&D Complete: 21 Jan 2020
Production:
  Populate Outer HCAL Sectors with Tiles Start: 27 Jul 2020
  First Outer HCAL Sector Ready to Install: 04 Sep 2020
  Last Outer HCAL Sector Ready to Install: 11 Mar 2021

## Slide 9: Cost Drivers
Preparation of Assembly Area ($25k/station)
  One assembly station as part of pre-production
  Remaining three for full production
Light Tighting Materials ($0.6k/sector)
University Fixed Cost Contract (Labor, $61k)
  Support for students (travel, lodging, payroll)

## Slide 10: Status and Highlights
In all cases, the combined system meets the sPHENIX spec!
Test beams (2014/16/17/18):
21/32 Flux Return Steel Sectors at BNL
Five rounds of prototyping with Uniplast – scintillating tile design very advanced.
Outer HCAL Mechanical Prototype
Frame Prototype

## Slide 11: Status and Highlights (cont.)
Outer HCAL Assembly Factory prepared: BNL Bldg. 912
large staging area
Fully equipped tent for testing (power, AC, heat, storage racks, etc.)
40-ton overhead crane to move sectors around
Roll-up door for vendor drop-off

## Slide 12: Status and Highlights (cont.)
Set up four stands for factory-style assembly and testing

## Slide 13: Status and Highlights (cont.)
cabling mock-up to
  determine cable and fiber lengths
  decide cable routing
  demonstrate feasibility given space constraints

## Slide 14: Status and Highlights (cont.)
Set up electronics for sector LED testing and cosmics calibration
Testing with HCal prototype

## Slide 15: Issues and Concerns
Availability of contributed labor
  need ca. 5 person-years of labor total
  so far have commitments of ca. 3.5 person-years from collaborating institutions
  working on obtaining further committments

## Slide 16: Summary
Assembly area prepared and ready to start assembly as planned in August, 2019
No major issues to be resolved
The Outer HCal Assembly And Testing is ready for PD-2/3 approval

## Slide 17: Back Up