## Slide 1: sPHENIX Director’s Review Barrel Steel/Inner Detector Structural Support
Jim Mills
April 9-11, 2019
BNL

## Slide 2: Barrel Steel/Inner Detector Structural Support
Barrel Steel
  32 Individual Sectors
Inner Detector Support Ring
  2x North and a South Ring
  Structural Support
Internal Detector Supports
  IHCAL, EMCal, TPC, INTT, MVTX

## Slide 3: Technical Overview
Barrel Steel (2.03.03)
  In Production
    Engineer, design, and procure 32 steel sectors to be utilized as the enclosure for the sPHENIX magnet, serving as a major portion of the magnet flux return, as well as the OHCal.
Inner Detector Structural Supports (2.03.02)
  North and South Support Rings
    Conceptual Design stage
      Design, analyze, review, and procure an integrated support system which will support all of the sPHENIX experimental detector subsystems that are not directly supported by the cradle carriage.
  Internal Detector Supports
    Conceptual Design Stage
      Subsystems will be responsible for engineering their
      individual supports.
Inner Detectors
IHCal
EMCal
TPC
INTT
MVTX
Min Bias

## Slide 4: Scope
Inner Detector Structural Support (2.03.02)
North and South Support Rings
  Provide structural support for installation of barrel steel around the sPHENIX magnet
    Provide capabilities to manipulate Barrel steel installation
    Provide attachment points to inner radius of barrel steel
  Provide a load path and interface points for the structural support of inner detectors
    Provide Interface points for installation of inner detectors
      IHCal, EMCal, TPC, INTT, MVTX, & Min Bias
Adjustable pads to assist during installation of Barrel Steel
Connection points made to inner radius of Barrel Steel
Preliminary attachment points for inner detectors

## Slide 5: Scope
Inner Detector Structural Support (2.03.02)
Internal Detector Supports
  Provide structural supports for installation of internal detectors
    Individual subsystems are responsible for engineering
    This WBS will be responsible for reviewing, procuring, and acceptance

## Slide 6: Scope
Chimney Sector Assembly
Sector Assembly
10x 8.5mm gaps for scintillating tiles
Over 20’ long
30,000 lbs. each
Barrel Steel (2.03.03)
  Assemblies are made up of 9 absorber plates + 2 ½ absorber plates
    Creating 10 gaps that will be populated with scintillating tiles and electronics for use in an Outer Hadronic Calorimeter
    3 of the assemblies will fabricated with a cutout to allow for the sPHENIX magnets chimney
  When assembled, the sector will make up the majority of the flux return for the sPHENIX magnet

## Slide 7: Collaborators
Barrel Steel- sPHENIX Engineers
Inner Detector Structural Support- sPHENIX Engineers
MVTX- MIT Engineers
TPC- Superconducting Magnet Division (SMD)
INTT- sPHENIX Engineers
Magnet Supports- sPHENIX Engineers, SMD

## Slide 8: Schedule Drivers
Barrel Steel
  Assemblies are being produced by a single vendor. Therefore our schedule is determined by the contract
  Contract Schedule
    We receive 1 deliverable sector per week (excluding built in holiday weeks)
    Currently have 21 Sector Assemblies
  Milestone date of Aug. 2019 will be hit with 300+ float days leftover
Inner Detector Structural Supports
  North and South Support Rings
    Currently in design phase of inner detectors
  Internal Detector Supports
    Development of inner detectors structural supports is ongoing

## Slide 9: Cost Drivers
Barrel Steel
  Sector Assemblies
    Largest single component of sPHENIX procurement
    Price is fixed, we are more than half way through the receiving process
    Contract will be closed by mid August 2019
Inner Detector Structural Supports
  Fabrication of the North and South structural support rings
    Rough order of magnitude estimate
    As plans for inner detector supports begin to solidify we will be able to move forward with interface areas
  Fabrication of Internal Detector Supports
    Conceptual designs are being developed by each subsystem

## Slide 10: Status and Highlights
Barrel Steel
  Sector assemblies continue to be delivered on schedule
  Assemblies are being prepped for future installation
  Factory space has been vetted by Collider Accelerator Division as well as Physics staff
Inner Detector Structural Supports
  North and South Support Rings
    Conceptual design and engineering
  Internal Detector Supports
    MVTX- conceptual design and engineering*
    INTT-conceptual design and engineering*
    TPC- conceptual design and engineering*
  *Integration committee has been established and meet biweekly
  Inner Detectors Integration Workshop was held 3/13-3/14

## Slide 11: Milestones
Inner Detector Structural Support 2.03.02
  Design/safety reviews complete July 2019
  Procure Internal Detector Structural Support
  Components ready for installation May 2020
    Installation occurs October 2021 (300+ days of float)
Barrel Steel 2.03.03
  Barrel steel Mechanical Design Complete
  Procure Barrel Steel Structure Components – First Article Received (Nov. 2017)
  Procure Barrel Steel Mechanical Structure Components-Production (Aug. 2019)
    Installation occurs June 2021 (300+ days of float)
  Established inspection process, readying assemblies for scintillator population
    Preproduction assembly begins June 2019 (6 Sectors)

## Slide 12: Activities over the next few months
Barrel Steel
  Continue acceptance testing
  Complete barrel steel procurement
Inner Detector Structural Supports
  North and South Support Rings
    Complete overall design
    Analyze and evaluate the structural support
    Create assembly/detailed drawings
    Review design/safety of the support
    Prepare procurement package
  Inner Detector Support Structures
    Await designs from subsystems
    Review and analyze designs
    Prepare procurement packages

## Slide 13: Issues and Concerns
Issues/Concerns
Barrel Steel
  Installation process of assemblies
Inner Detector Structural Support
  Concepts to be completed and requires budgetary quotes
  Engineering Support needed for North and South support rings
Proposed Action/Resolution
  Continue development on advanced conceptual design plan. Significant studying of sectors being fitted together
  Begin process of bottoms up estimate and begin detailed drawings for budgetary quotes
  Plan to increase engineering staff to the sPHENIX project

## Slide 14: Summary
Barrel Steel
The barrel steel is currently being received at a rate of 1 per week
Milestone date of Aug. 2019 will be hit with 300+ float days leftover
Assemblies are being prepped for future installation
Continue integration discussions to formulate our interface/interaction points with the cradle
Inner Detector Structural Supports
We are in the conceptual design phase
We fully understand the scope of this subsystem and continue to collaborate with the inner detector subsystem engineer/design teams through a well established integration committee
We are moving forward with the design/detail process that will permit us to acquire budgetary quotes for the North and South Support Rings

## Slide 15: Back Up