## Slide 1: sPHENIX Director’s Review INTT Electronics
Itaru Nakagawa
April 9-11, 2019
BNL

## Slide 2: The L3 Component
Readout cables and electronics
Electronics are reuse of FVTX electronics
Succeeds established FVTX readout design
Still technical challenge in signal transmission

## Slide 3: L3 Technical Overview
40cm
120cm
Silicon
40cm
20cm
INTT
FVTX
30cm
ROC
Significantly longer (>1.2m) signal transmission
Tight space budget to fit between MVTX and TPC
High signal line density
High frequency signal 200Mbps transmission
Flexibility
Bus Extender
HDI
Conv. cable
R&D : Multilayered Flexible Print Cable
Requirements

## Slide 4: L3 Scope
HDI & conversion cables are manufactured by Yamashita Co. with relatively relaxed technological specifications compared to FVTX
Technological challenge in the 1.2m bus extender FPC
HDI
Conv. cable
Conv. cable
HDI Cable (Preproduction)
Conversion Cable (Preproduction)
7-layer structure
Specification | FVTX | INTT | Technical Challenge
Length | < 30cm | 120cm | Signal amplitude reduction
Line pitch [mm] | 40 | 120 | Constant line width
Insulation | Polymid | Liquid crystal polymer (LCP) | Peel strength
# of Cu layer | 7 | 4 | Through hole

## Slide 5: L3 Collaborators
R&D
RIKEN (Physicist)
REPIC.co
(Mech. Engineer)
TIRI (Elec. Engineer)
Print Denshi Kenkyujo Co. (Factory)
Concept, Testing
Fabrication
Design
Collaborative R&D Program for Manufacture Industry Funded by Tokyo Metropolitan Gov.
~$10k/year
~$10k
~$10k
2017, 2018, 2019*
Takashi Hachiya
+ Itaru Nakagawa
+ 3 undergraduates
*to be applied
Simulation, Infrastructure

## Slide 6: Schedule Drivers
2016 |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  | 
Prototype-II
Bus Extender
Prototype-0
Simulation & Design
Pre-Production
Prototype-II
Prototype-I
production
Silicon S/N OK
Readout OK
Pre-Production
Prototype-III
Beam test I
Beam test II
Final Design Review
Conversion Cable
Final design review after beam test-II except for the bus extender
Need another round to finalize the bus extender. Possible review in 2020
Ladder

## Slide 7: Cost Drivers
Yield Rates of Bus Extender : only 25% at this moment
  $2~4k/cable ($0.4~0.8M for total)
  Difficulty mostly originated from the large size and unestablished technology in the LCP manufacturing.
Dusts, creases, air between a mask and copper plane…
☞ broken and/or shorted signal lines
1. Exposure process
Still struggling in optimizing parameters; pressure, temperature, duration, vacuum, etc
☞ Overexpansion of LCP, imperfectly stiffened adhesive, weak peel strength, incomplete thru hole, etc
Primary Causes
2. Lamination process

## Slide 8: Status and Highlights
The Bus Extender Prototype-II
120cm FPC w/ 200Mbps
62 LVDS pairs within 5cm width
4 layers with signal/power/GND
Observed signal transmission performances are as designed.
120cm
To HDI
To ROC
Cu
LCP
Cu
Cu
LCP
Cu
Adhesive
Adhesive
Cu
Cu
LCP
Cu
Cu
LCP
Cu
Adhesive
Adhesive
Cu
LCP
LCP
Thru hole f=300mm
Cu plating t35mm
Successful
Eye-diagram
Clear opening
Signal loss ~ 30%
Reflection < 10%
200Mbps
To be tested in the beam test.

## Slide 9: Issues and Concerns
  ⇫ROC
  Reuse of 5 years of operation
  Some broken function in some ROCs
  Many components are discontinued
  Original FPGA coder left the field long time ago
☜The cu-plating on thru holes has not been established yet
☟Full chain test of readout cables to be executed soon
good
bad

## Slide 10: Summary
Recycle FVTX Readout Electronics.
  Working system
  Need to assign efforts to repair and maintenance work
Readout cables are developed based on FVTX design
  HDI & Conversion cables are relaxed technology compared to FVTX
  1.2m bus extender is under development using the cutting edge technologies.
  Another 1 more year to optimize the design and yield rate
R&D is in the final stage except for the bus extender
  Bus extender will be independently reviewed in 2021.

## Slide 11: Back Up

## Slide 12: Issues found in 1st prototype
Peel strength is too weak
  1N/cm  10N/cm improved
    Vacuuming to prevent contamination of air-bubbles and dusts when laminating FPC’s
Peel length[mm]
Peel strength[N]
Chemical1
Chemical2
New FPC
Polymide
LCP breaks at 10N/cm
Peel strength test
broken
Roughening treatment of cu surface
LCP
Cu
Cu
Adhesive
LCP
Cu
Cu
LCP
Cu
Cu
Adhesive
LCP
Cu
Cu

## Slide 13: Status and Highlights
The Bus Extender Prototype-II
120cm FPC w/ 200Mbps
62 LVDS pairs within 5cm width
4 layers with signal/power/GND
Observed signal transmission performances are as designed
120cm
L4 : VD＋VA
L3 （AGND）
L2 signal
L１ （DGND）
To HDI
To ROC
Cu
LCP
Cu
Cu
LCP
Cu
Adhesive
Adhesive
Cu
Cu
LCP
Cu
Cu
LCP
Cu
Adhesive
Adhesive
Cu
LCP
LCP
Thru hole f=300mm
Cu plating t35mm
Successful