## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Time Projection Chamber |  | 1.02 |  | TPC Support Services |  | 1.02.07
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| TPC Laser System |  | 1.02.07.01 |  | TPC Laser-Summary
| TPC Gas System |  | 1.02.07.02 |  | TPC Gas-Summary
| TPC Cooling System |  | 1.02.07.03 |  | TPC Cooling-Summary

## Laser-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-12
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 139 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Laser System |  |  |  | 1.02.07.01
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPC LASER CALIBRATION SYSTEM AND PROCURE AND CONSTRUCT THE ELEMENTS OF THE SYSTEM. WORK STATEMENT: PROVIDE ALL PARTS TO PRODUCE THE LASER CALIBRATION SYSTEM AND ASSEMBLE/INSTALL ALL PARTS.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Lasers can be used to produce ionization in the TPC volume that provides botgh a source of signals and a calibration. This includes pattern applied to the central membrane (ala STAR) as well as direct laser transmission through the gas (STAR and ALICE). In the case of STAR and ALICE, the lasers going through the gas are directed via fibers and mirror bundles to criss-cross planes at several Z locations. The fiber bundles take radial space that both STAR and ALICE can afford. Due to the small size, sPHENIX cannot afford to have a bundle running along Z. Therefore we shall use two solutions to laser calibration. First, we will shine diffuse laser laght onto the patterned centralmembrane. Second, we will allow for angled\tranjectories of laser light emanating from between the modules traveling at various angles through the gas. While not ideal it is a better solution than losing radial space.
Details of the Base Estimate (explanation of the Work)
We costed two lasers that seem appropriate for our needs and included the cost of the higher power one here with 20% Estimate Uncertainty. All other laser system parts are either from quotes with 20% Estimate Uncertainty or estimated at 40% Estimate Uncertainty.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
The full cost of the laser system includes the laser and optics up to and inside the TPC.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 221640.06 | 1392
Estimate Uncertainty
We use 20% on the vendor quoted items (laser itself plus a collection of optical components) and 40% on the laser beam conduit system and port window/beam splitter.

## Gas-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2009-02-12
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 139 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Gas System |  |  |  | 1.02.07.02
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPC GAS SYSTEM AND PROCURE AND CONSTRUCT THE ELEMENTS OF THE SYSTEM. WORK STATEMENT: PROVIDE ALL PARTS TO PRODUCE THE GAS SYSTEM AND ASSEMBLE/INSTALL ALL PARTS.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
PHENIX hosted one of the premier recirculating high purity gas systems in the world that serviced the HBD detector. The TPC detector's needs are rather similar (even less stringent) and so we feel it is conservative to use the HBD system as a cost basic.
Details of the Base Estimate (explanation of the Work)
The system is designed with all stainless plumbing for highest purity and ample contamination monitoring. It is very smilar to the PHENIX HBD system, whose purity and flow rates are beyond the needs of the TPC.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
The gas system cost is based upon designs that follow the PHENIX HBD high purity gas system, which is more stringent than typical TPC requirements.
|  |  |  | #REF! | Labor Hours
|  |  |  | 111244.59 | 5992
Estimate Uncertainty
The Estimate Uncertainty contains three levels. Manufacturer quotes are either assessed as 20% or 25% Estimate Uncertainty based upon past experience with long term price stability. All other items carry 40% Estimate Uncertainty.

## Cooling-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-12
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 139 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Cooling System |  |  |  | 1.02.07.03
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPC COOLING SYSTEM AND PROCURE AND CONSTRUCT THE ELEMENTS OF THE SYSTEM. WORK STATEMENT: PROVIDE ALL PARTS TO PRODUCE THE COOLING SYSTEM AND ASSEMBLE/INSTALL ALL PARTS.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Within sPHENIX, all systems are responsible to carry their own electronically-generated heat away. Our heat load is dominated by the SAMPA chips and is thereby well understood, allowing for reasonable accuracy on the costy estimation. The heat load is significant enough that liquid cooling is required since gas cooling will be insufficient.
Details of the Base Estimate (explanation of the Work)
The cost basis uses is extracpolated using similar systems found in the PHENIX experiment.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
The cost before Estimate Uncertainty similar to equivalent systems deployed for PHENIX.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 66499 | 2084
Estimate Uncertainty
The Estimate Uncertainty contains three levels. Manufacturer quotes are either assessed as 20% or 25% Estimate Uncertainty based upon past experience with long term price stability. All other items carry 40% Estimate Uncertainty.

## Laser-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.07.01 |  | TPC Laser System | [6 empty] | 221640.06
1.02.07.01 | 149600 | Procure TPC laser(s) | [5 empty] | 145840
|  |  | Laser | RPMC (8) | 145840 | Pending | Manufacturer Quote
1.02.07.01 | 150300 | Procure TPC optics with mirrors | [5 empty] | 58800.06
|  |  | Fibers | Fiberguide Ind. | 10816 | Pending | Manufacturer Quote
|  |  | Conventional beam splitter | CVI Optics | 14925 | Pending | Manufacturer Quote
|  |  | ND filters | Thor Labs | 983.36 | Pending | Manufacturer Quote
|  |  | Mirror mounts | Thor Labs | 1560 | Pending | Manufacturer Quote
|  |  | Mirror mounts (motorized) | Thor Labs | 11048 | Pending | Manufacturer Quote
|  |  | Motion controller | Thor Labs | 5264 | Pending | Manufacturer Quote
|  |  | VUV mirrors | Thor Labs | 2082.8 | Pending | Manufacturer Quote
|  |  | Optical table | Thor Labs | 2770 | Pending | Manufacturer Quote
|  |  | Photodiodes | Thor Labs | 368.8 | Pending | Manufacturer Quote
|  |  | Power meter | Thor Labs | 2439 | Pending | Manufacturer Quote
|  |  | Fiber couplers | Thor Labs | 5697.4 | Pending | Manufacturer Quote
|  |  | Mounts | Thor Labs | 845.7 | Pending | Manufacturer Quote
1.02.07.01 | 150500 | TPC Mirror bundles with Mechanical supports | [5 empty] | 15000
|  |  | Port Window/2-way splitter |  | 15000 | Pending | Experience
1.02.07.01 | 150800 | Install & Test TPC Laser safety interlocks | [5 empty] | 2000
[5 empty] | 2000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.07.01 | 148700 | Design TPC Laser System | Similar to STAR and ALICE | PROF | 320 | 960
|  |  |  | TECH | 320
|  |  |  | SCI | 320
1.02.07.01 | 150900 | Install TPC Laser optics with mounts | Similar to PHENIX EMC | TECH | 64 | 64
1.02.07.01 | 150700 | Install & Test TPC Laser safety interlocks | Similar to PHENIX EMC | SCI | 64 | 128
|  |  |  | PROF | 64
1.02.07.01 | 150600 | Install & Test TPC lasers | Similar to PHENIX EMC | TECH | 24 | 24
1.02.07.01 | 151000 | Install & Test TPC mirror bundles and supports | Similar to PHENIX EMC | TECH | 24 | 24
1.02.07.01 | 149000 | Procure TPC laser(s) - Provide Requirements to Procurement | Similar to STAR and ALICE | PROF | 48 | 96
|  |  |  | SCI | 48
1.02.07.01 | 150400 | Procure TPC mirror bundles with supports | Similar to STAR and ALICE | PROF | 24 | 48
|  |  |  | SCI | 24
1.02.07.01 | 149700 | Procure TPC optics with mirrors - Provide Requirements to Procurement | Similar to STAR and ALICE | PROF | 24 | 48
|  |  |  | SCI | 24
|  | Grand Total |  |  | 1392 | 1392

## Gas-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.07.02 |  | TPC Gas System | [6 empty] | 111244.59
1.02.07.02 | 151600 | Procure TPC Gas System mass flow meters | [5 empty] | 6831
|  |  | Flowcontrollers |  | 4170 | Pending | Quote
|  |  | Power supply |  | 2235 | Pending | Quote
|  |  | Cables,24v supply, |  | 426 | Pending | Quote
1.02.07.02 | 152300 | Procure TPC Gas System Analyzers (2 for redundancy) | [5 empty] | 33035
|  |  | Cf4 Analyzer (2) |  | 21790 | Pending | Quote
|  |  | Iso Analyzer |  | 10895 | Pending | Quote
|  |  | Cables |  | 350 | Pending | quote
1.02.07.02 | 152500 | Procure TPC Gas System scrubbers | [5 empty] | 7727.44
|  |  | Vessel | Swage/Mcmaster | 4687.62 | Pending | quote
|  |  | Catalyst | BASF | 962.82 | Pending | quote
|  |  | Molecular sieves | Fisher | 732 | Pending | quote
|  |  | Heater and temp controller | OMEGA | 1345 | Pending | quote
1.02.07.02 | 152700 | Procure TPC Gas System oxygen and water sensors | [5 empty] | 11164
|  |  | H2O analyzers (2) | Khan | 5210 | Pending | Quote
|  |  | O2 Analyzers (2) | GE | 5754 | Pending | Quote
|  |  | Cables |  | 200 | Pending | quote
1.02.07.02 | 153000 | Procure TPC Gas System computer controller | [5 empty] | 18401.15
|  |  | Electronics Design (contract) | CSINO | 7000 | Pending | Past Cost
|  |  | Design Control Software | CSINO | 3300 | Pending | Past Cost
|  |  | Procure Gas system Electronic Crate | Allied | 769 | Pending | Quote
|  |  | Procure Electronics Modules | CSINO | 3600 | Pending | past cost
|  |  | Procure Hardware for electronics (Cabels,termanals,Etc) | Newark | 1538.15 | Pending | Quote
|  |  | Procure Gas System Control PC | Dell | 969 | Pending | quote
|  |  | Procure Power supplies | Newark | 311 | Pending | quote
|  |  | Procure Mounting hardware | McMaster | 238 | Pending | quote
|  |  | Procure Al Panels | McMAster | 150 | Pending | quote
|  |  | Procure Electronics Rack | Newark | 526 | Pending | quote
1.02.07.02 | 153700 | Assemble and Plumb TPC Gas System | [5 empty] | 34086
|  |  | Procure Stainless compression fittings Rack | Swagelok | 6656 | Pending | quote
|  |  | Procure Stainless Tubing | Swaglok/Mcmaster | 5396 | Pending | quote
|  |  | Procure Monitoring instrumentation | Dwyer | 6607 | Pending | quote
|  |  | Procure Electronic Pressure Controller | Tescom | 1558 | Pending | quote
|  |  | Procure Compressors (2) | Aid Dimensions | 4725 | Pending | quote
|  |  | Procure Stainless Solenoids | Grainger | 3267 | Pending | quote
|  |  | Procure Stainless fittings Large | Swagelok | 4561 | Pending | quote
|  |  | Procure AL Panels | McMaster | 607 | Pending | quote
|  |  | Procure Mounting hardware | McMaster | 183 | Pending | quote
|  |  | Procure Electronics Rack | Newark | 526 | Pending | Quote
1.02.07.02 |  | Install and Test TPC Gas System Interlocks | [5 empty] | 0 |  | no parts planned now
|  |  | This is part of Computer control |  | 0 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.07.02 | 153100 | Procure TPC Gas System Components for Installation | Similar (but lesser) to PHENIX HBD. | TECH | 60 | 64
|  |  |  | PROF | 4
1.02.07.02 | 153300 | Assemble and Plumb TPC Gas System | Similar (but lesser) to PHENIX HBD. | TECH | 420 | 440
|  |  |  | PROF | 20
1.02.07.02 | 152800 | Assemble TPC Gas System controls | Similar (but lesser) to PHENIX HBD. | TECH | 480 | 2448
|  |  |  | PROF | 48
|  |  |  | STUD | 1920
1.02.07.02 | 151200 | Design TPC Gas Handling System | Similar (but lesser) to PHENIX HBD. | PROF | 800 | 2400
|  |  |  | TECH | 800
|  |  |  | SCI | 800
1.02.07.02 | 153900 | Install and Test TPC Gas System Interlocks | Similar (but lesser) to PHENIX HBD. | PROF | 40 | 40
1.02.07.02 | 151700 | Procure TPC Gas System Analyzers (2 for redundancy) - Provide Requirements to Procurement | Similar (but lesser) to PHENIX HBD. | PROF | 24 | 24
1.02.07.02 | 151500 | Procure TPC Gas System mass flow meters | Similar (but lesser) to PHENIX HBD. | PROF | 24 | 24
1.02.07.02 | 152600 | Procure TPC Gas System oxygen and water sensors | Similar (but lesser) to PHENIX HBD. | PROF | 24 | 24
1.02.07.02 | 152400 | Procure TPC Gas System scrubbers | Similar (but lesser) to PHENIX HBD. | PROF | 24 | 24
1.02.07.02 | 152900 | Set up TPC Gas System computer control | Similar (but lesser) to PHENIX HBD. | PROF | 24 | 504
|  |  |  | STUD | 480
|  | Grand Total |  |  | 5992 | 5992

## Cooling-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.07.03 |  | TPC Cooling System | [6 empty] | 66499
1.02.07.03 | 155000 | Procure TPC Cooling System equipment(pumps,heat exchanger, PH control, manifolds, tanks…) | [5 empty] | 44339
|  |  | Chillers watt 10C(3) | Thermo Scientific Merlin | 32000 | Pending | Quote
|  |  | Deionizing filters (2) | McMaster | 1644 | Pending | web Quote
|  |  | Particle filters (3) | McMaster | 720 | Pending | web Quote
|  |  | Valving for Chiller Switchover | McMaster | 825 | Pending | Web Quote
|  |  | SS Manifolds (4) 12 port | MSC | 1110 | Pending | web quote
|  |  | Hardware (panel, brackets, mnts) | Mcmaster | 650 | Pending | web Quote
|  |  | Flowmeter 24(SS) water | Dwyer | 1315 | Pending | web Quote
|  |  | Compression fittings SS (various) | Swagelok | 2500 | Pending | Quote + experience
|  |  | Bypass Valving at detector | McMaster | 1550 | Pending | web Quote
|  |  | Pressure gauges (8) | Dwyer | 450 | Pending | Web Quote
|  |  | Manifold valving (24) | Swagelok | 1575 | Pending | web Quote
1.02.07.03 | 155700 | Procure TPC Cooling System plumbing - contract | [5 empty] | 11667
|  |  | 1 1/4" thin walled SS Lines | Mcmaster | 1600 | Pending | old Quote x inflation
|  |  | 1" SS Thin walled Lines | McMaster | 1450 | Pending | old Quote x inflation
|  |  | 5/16" SS Coil (0.250 ID Min) | McMaster | 1200 | Pending | web quote
|  |  | SS Pipe fittings | Mcmaster | 700 | Pending | experience
|  |  | 1 1/4" Braided lines (316 SS) | McMaster | 946 | Pending | web quote
|  |  | Large Compression fittings SS | Swagelok | 3750 | Pending | web quote
|  |  | Poly lines to detector (Various) | MSC | 924 | Pending | web Quote
|  |  | House Water Manifolding (brass) | McMaster | 1097 | Pending | Web Quote
1.02.07.03 | 155900 | Set up TPC Cooling System Computer Controls | [5 empty] | 10493
|  |  | Pressure Transmitters (8 min) | Dwyer | 1625 | Pending | quote
|  |  | Transmitting Flowmeters (SS 1") (8) | Mcmaster | 2050 | Pending | Web Quote
|  |  | RTDs (8) | Omega | 550 | Pending | Web Quote
|  |  | RTD transmitter+local read (7) | Omega | 2986 | Pending | Web Quote
|  |  | Electronic hardware | various | 1750 | Pending | estimate
|  |  | House water Monitor (pressure) | Various | 650 | Pending | Web Quote
|  |  | Presure Relief Valves 1" (2) SS | Mcmaster | 882 | Pending | web quote
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.07.03 | 154100 | Design TPC Cooling System | Similar to PHENIX FVTX and ALICE TPC | PROF | 640 | 1492
|  |  |  | TECH | 212
|  |  |  | SCI | 640
1.02.07.03 | 155400 | Install TPC Cooling System end cap manifolds | Similar to PHENIX FVTX and ALICE TPC | TECH | 80 | 80
1.02.07.03 | 155200 | Install TPC Cooling System heat exchanger | Similar to PHENIX FVTX and ALICE TPC | TECH | 24 | 24
1.02.07.03 | 155300 | Install TPC Cooling System PH control | Similar to PHENIX FVTX and ALICE TPC | TECH | 24 | 24
1.02.07.03 | 155600 | Install TPC Cooling System plumbing | Similar to PHENIX FVTX and ALICE TPC | TECH | 240 | 240
1.02.07.03 | 155100 | Install TPC Cooling System pumps | Similar to PHENIX FVTX and ALICE TPC | TECH | 24 | 24
1.02.07.03 | 155500 | Install TPC Cooling System tanks | Similar to PHENIX FVTX and ALICE TPC | TECH | 24 | 24
1.02.07.03 | 154400 | Procure TPC Cooling System equipment(pumps, heat exchanger, PH control, manifolds, tanks…) - Provide Requirements to Procurement | Similar to PHENIX FVTX and ALICE TPC | PROF | 48 | 96
|  |  |  | TECH | 48
1.02.07.03 | 156000 | Set up and Test TPC Cooling System interlocks | Similar to PHENIX FVTX and ALICE TPC | TECH | 40 | 40
1.02.07.03 | 155800 | Set up TPC Cooling System computer controls | Similar to PHENIX FVTX and ALICE TPC | TECH | 40 | 40
|  | Grand Total |  |  | 2084 | 2084

## Quotations-Laser
Compact, 266nm DPSS laser
Diffractive optical element beam splitter
Verbal estimate for diffractive optical element (DOE) to generate 3-way split beam from primary beam from laser
3 beams are roughly equal energy pencil beams that have same divergnce and beam diam. ss primary beam; the angle of each beam with respect to
the normal to the DOE surface will be specified in a range between 5-25deg. (the beams do not have to be in the same plane)
~$20K per 20 DOE's (each 1cm diam. discs, 266nm compatible fused silica substrate) -- made from a single 200mm diam. raw silicon wafter
Will update with real quote soon!
Optical elements
Fibers
Mechanical support