## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Time Projection Chamber |  | 1.02 |  | TPC Mechanics |  | 1.02.01
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| TPC v1 Field Cage Prototype |  | 1.02.01.01 |  | TPC v1 Field Cage Prototype
| TPC v2 Field Cage |  | 1.02.01.02 |  | v2 Field Cage-Summary
| TPC Final Field Cage |  | 1.02.01.03 |  | Final Field Cage-Summary
| TPC v1 Modules |  | 1.02.01.04 |  | TPC v1 Modules-Summary
| TPC v2 Modules |  | 1.02.01.05 |  | TPC v2 Modules-Summary
| TPC Production GEM Acquisition |  | 1.02.01.06 |  | TPC Production GEM Acquisition-Summary
| TPC High Voltage System |  | 1.02.01.07 |  | TPC High Voltage System-Summary
| TPC Assembly |  | 1.02.01.08 |  | TPC Assembly-Summary

## v1 Field Cage-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-13
[7 empty] | Prepared By: | Thomas K. Hemmick
[7 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
TPC v1 Field Cage Prototype |  |  |  | 1.02.01.01
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPC FIELD CAGE PROTOTYPE VERSION 1, PERFORM R&D, DESIGN AND CONSTRUCT THE ELEMENTS OF THIS PROTOTYPE. WORK STATEMENT: PROVIDE PROTOTYPE: FIELD CAGE V1 PROTOTYPE.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
As compared to the scale of prior TPCs used in heavy ion physics (STAR, ALICE), the major difference in the sPHENIX TPC is its size (less than 1/2 the length and diameter of STAR) and requirements for precision. Both of these requirements drive the design of the field cage into the direction that we have chosen. The small size of the TPC (stretching radially from 20cm-78cm) necessitates that we waste no radial space. Therefore, the TPC design requires that the field defining electrodes and the gas containment wall be a single structure using only 0.6 inches of radial space. Furthermore, to allow the region of high electric field quality to reach as closely as possible to the field cage walls, we have turned to an extremely fine-pitched electrode structure for the field cage. The period of the electrode structure is only 2.8 mm, which is nealry a factor of four smaller than STAR or ALICE. Furthermore, we have turned to the use of surface mount resistors to match the fine structure of the field cage electrodes. The risk of using small resistors is avoided using the newly-developed HVPW (High Voltage Pulse Withstanding) devices designed to withstand lightning strikes. These are small enough that they can be present directly in the gas volume and not create significant disturbance to the electric field. The principal blessing of the realtively small size of the TPC is that the end plates (referred to as "wagon wheels" in the engineering drawings) can be hogged from a single piece of aluminum, thereby eliminating MANY places that would be vulnerable to gas leaks. We have assumed that this part of the project cost will be entirely covered using LDRD funds.
Details of the Base Estimate (explanation of the Work)
The field cage estimate is driven by several factors. The first factor is the mandrel. The mandrel is a precision cylindrical mold that will be used to form that radius of the inner and outer field cage barrels. The mandrel is outfitted in a manner similar to a large lathe, but is made from significatly lighter construction materials. For the outer field cage barrel, the mandrel is formed by a bicycle-spoke design supporting a 12-faced cylinder. each face of the cylinder is capped with a machinable foam of intermediate density (20 lbs/ft^3). Harmonic drive motors with magnetic strip position feedback rotate the mandrel cylinder with high precision under computer control and also translate a "utility stage" along the length of the cylinder. The utility stage is equipped either with a variable speed high torque brushless DC motor when cutting the foam, or with a microscope stage when aligning the field cage electrodes. The foam stage of the mandrel additionally functions as a vacuum head securing the field cage electrodes prior to capping with the insulating kapton. The mandrel system was designed at SBU using off-project labor costs (faculty and students). The mandrel assembly for the inner field cage is significantly simpler due to its smaller size and is formed from a schedule-80 PVC pipe that is machined in the SBU shop to precise radius. Since only one mandrel is in use at any given time, the motor and positioning hardware is shared by the two systems. This cancels errors due to manufacturer variance in the linear positioning equipment. The fine electrodes are to be manufacturer by the All-Flex company, that specializes in long circuit cards up to 40 feet in length. These will be constructed in industry and machine populated with HVPW resistors manufactured by Stackpole electronics, the leader in HVPW technology. Bench tests have shown that an 18-layer kapton insulator will provide more than a factor of five safety margin for holding voltage even at an electric field strength of 400 V/cm. However, laying up 18 layers onto a large cylinder is not a well-practiced step for physicists. For this reason, we have turned to the FW Hall company to design a custom apparatus to deliver kapton at constant tension and "press" out bubbles during the winding process. This system uses continuously running motors with tension feedback to magnetic particle clutches to achieve constant tension. Because the mandrel systems are complete, the costs are dominated by the quotes from All Flex for flexible circuit cards, from Stackpole for HVPW resistors, from FW Hall company for the tensioning apparatus, from ATLAS Tool for the field cage end rings, and from engineering estimates for the wagon wheels.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The costs of the TPC field cage v1 prototype are born by LDRD funds. These costs are overwhelmingly from already purchased items, which is what has driven the Estimate Uncertainty down.
|  |  |  | Grand Total | 0 | Labor Hours
|  |  |  | 87982 | 0 | 1784
Estimate Uncertainty
Throughout this part of the project we have used zero Estimate Uncertainty on parts that are already in hand, 20% on parts that have a manufacturer quote, and 40% on items that are merely engineering estimates. The current Estimate Uncertainty is driven promarilty by the quotes from FW Hall (tensioning apparatus), All Flex (circuit cards for electrodes), and Stackpole (HVPW resistors). Major items at the higher Estimate Uncertainty include the End rings (expensive due to being made from single-piece Al), the wagon wheels (also single piece Al), the handling cart (conceptual design only), and the central membrane (conceptual design only).

## v2 Field Cage-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC v2 Field Cage |  |  |  | 1.02.01.02
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPC FIELD CAGE PROTOTYPE VERSION 2, PERFORM R&D, DESIGN AND CONSTRUCT THE ELEMENTS OF THIS PROTOTYPE. WORK STATEMENT: PROVIDE PROTOTYPE: FIELD CAGE V2 PROTOTYPE.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Although it is quite possible that the v1 field cage prototype, if it functions well enough, could serve the full needs of sPHENIX (STAR and ALICE only built the full-sized field cage one time), we nonetheless assume that in overcoming the challenges of a smaller high-precision device we may need a second try. Therefore we have included a v2 field cage in our estimates. We assume that the basic design choices (single wall for field definition and gas enclosure) cannot be changed. We therefore benefit from a significantly reduced cost for the v2 prototype by re-using tooling parts from the v1 prototype. Indeed, we dedicate only ~$10k to tooling. The costs are therefore driven by purchases of additional kapton, flex circuits, honeycomb, resistors, and fresh machinable foam. Although it is quite possible to re-use the wagon wheel parts from the v1 prototype, we have nonetheless assumed that these will also be replaced during the v2 stage.
Details of the Base Estimate (explanation of the Work)
The concept behind the v2 field cage is to make incremental improvements over the v1 field cage and have a device that is usable (with only VERY small further modification) for the sPHENIX experiment. The field cage consiste of four major components: inner field cage, outer field cage, wagon wheels, and central membrane. Among these any or all of them could be re-used from the v1 prototype in the v2 prototype presuming that they proved worthy. For our cost assumptions we have presently assumd that we will replace all four of these major components, which is the most conservative assumption.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The costs are all based upon the same estimates as from the v1 prototype and therefore add to a similar total. Here we have applied 20% Estimate Uncertainty even to items that are already in hand for the v2 prototype as a means of being robust against future cost increases.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 148818.7 | 2444
Estimate Uncertainty
As discussed above, we use 0% Estimate Uncertainty ONLY in the case of the parts already being in hand. As an example, consider the raw kapton used for insulation. For both the v1 And v2 prototype, this is costed near $70k. However, it has 0% Estimate Uncertainty for v1 (since it is already in hand), but carries 20% Estimate Uncertainty for v2 since we would need to re-order. As for v1, all costs that are based upon engineering are taken to have 40% Estimate Uncertainty.

## Final Field Cage-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Final Field Cage |  |  |  | 1.02.01.03
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE TPCFINAL FIELD CAGE, PERFORM NECESSARY MODIFICATION TO THE V2 FIELD CAGE. WORK STATEMENT: PROVIDE PROTOTYPES: MODIFY V2 FIELD CAGE PROTOTYPE AND TESTING, INCLUDING PROCURING PARTS THAT HAVE BEEN DEVELOPED DURING PROTOTYPING.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Our intention is that the v2 field cage will be used in the experiment. However, because we are proceeding with the designs of v1 and v2 at an early stage of the overall sPHENIX design, it is always possible that there are last-minute modifications required onto a full-functional field cage. An example would be if the routing of services from one of the inner detectors (INNT, MAPS) requires tie-off points on the TPC, these would have to be retrofitted onto the device. We do not have knowledge of specific work to be performed for these last-minute refits and therefore we are assuming that $6k in costs with a 40% Estimate Uncertainty will be required.
Details of the Base Estimate (explanation of the Work)
This category is merely the voice of experience driving minor re-works of the TPC field cage to accommodate necessary items that cannot be estimated at the early stage of design (e.g. mechnical support for services to detectors housed inside the TPC inner radius). The costs is taken purely from past experience and assigned large Estimate Uncertainty.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
We have assumed that minor reworks of the v2 field cage to make it suitable would cost $6k or $8.4k with Estimate Uncertainty. This is based purely on past experience.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 6000 | 400
Estimate Uncertainty
Because the cost is based purely on past experience, we have assumed 40% Estimate Uncertainty.

## v1 Modules-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC v1 Modules |  |  |  | 1.02.01.04
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE GEM READOUT MODULE PROTOTYPE VERSION 1, DESIGN AND CONSTRUCT THE ELEMENTS OF THIS PROTOTYPE. WORK STATEMENT: PROVIDE GEM READOUT MODULE V1 PROTOTYPE AND MATERIAL/EQUIPMENT TO PRODUCE THE MODULES.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Although there is NO plan to change the interface between the field cage (speficically the wagon wheel) and the modules themselves, we nonetheless assume that this is possible. Therefore prototype modules are assumed to either be compatable with the v1 or the v2 field cage prototype and not with both. Therefore the definition of THIS workpackage to to produce prototype modules that are compatible with the v1 fiele cage mechanics. The module MUST provide a sufficient avalanche gain to see signals well above noise and thereby provide precise coordinate measurements. Our present design is based upon the low Ion Back Flow (IBF) chambers developed for the ALICE upgrade. These are the first TPC modules designed to be operated without a gating grid and thereby provide continuous readout necessary for the high collision rate anticipated for sPHENIX. This quad-GEM avalanche structure will be coupled to a fine-pitched Zig-Zag pad pattern already developed by our colleagues for the EIC as part of the EIC R&D efforts. The principle differences between the existing EIC prototypes and the sPHENIX prototypes include the detector shape (EIC prototypes are square), number of GEMs (EIC uses 3), the gas mixture (sPHENIX require Neon-based gas), and the field termination grid. The latter small detail is critical since in sPHENIX the field terminatuion grid serves double-duty as an additional IBF reducing device. For this estimate we have used our EIC experience as the basis of costs and assumed two independent v1 prototypes. It shoudl be noted that we will prototype at the v1 and v2 stages ONLY size R2 modules. The scaling of the module size to other designs will be included as part of the pre-production development.
Details of the Base Estimate (explanation of the Work)
The typical costs of a GEM-based detector modules (frames, pad plane) are all taken from experience building the chambers for the EIC R&D efforts. One additional item, involves a gas enclosure. Although the TPC field cage is, in principle, the "gas enclosure" it is far too large for bench tests. Thus in addition to the normal costs for modules, we have additionally added a specialized gas enclosure to allow simple bench tests.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The cost for two stages of prototyping (one module each stage).
|  |  |  | Grand Total | Labor Hours
|  |  |  | 10200 | 688
Estimate Uncertainty
Many of these do not suffer a significant cost increase as the shape /size changes) and for such parts, we are able to assung a Estimate Uncertainty of only 20% to these items. That said, the strongbacks (mechanical interface to a field cage), and GEMs could suffer a more significant rise and so we have applied 40% Estimate Uncertainty to these items.

## v2 Modules-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC v2 Modules |  |  |  | 1.02.01.05
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE GEM READOUT MODULE PROTOTYPE VERSION 2, DESIGN AND CONSTRUCT THE ELEMENTS OF THIS PROTOTYPE. WORK STATEMENT: PROVIDE GEM READOUT MODULE V2 PROTOTYPE AND MATERIAL/EQUIPMENT TO PRODUCE THE MODULES.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Because we are allowing for a change in the mechanical interface between the field cage and the modules as one moves from the v1 field cage to the v2 field cage, we must distinguish prototype modules on the basis of which field cage design they conform to. Thus, after completion of two v1 prototypes, we additionally allow for one v2 prototype module before moving to the pre-production stage. This WBS workpackage captures the cost of the v2 prototype module. In addition to the costs for a fresh design module, the v2 prototype also assumes the construction of a second gas enclosure (mimicing the v2 field cage module interface).
Details of the Base Estimate (explanation of the Work)
All the details of this work are highly similar to the v1 modules task. The major difference is that there is only a single prototype module made in this round and a brand new gas enclosure. It is also assumed that the expensive Enon gas was used up during teh v1 prototyping and further gas purchase is necessary.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The overall cost for this prototyping stage is similar to the prior stage.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 12900 | 1760
Estimate Uncertainty
Since most of the parts involved in this GEM chamber are VERY similar to those from EIC R&D, we have used EIC R&D costs that carry a 20% Estimate Uncertainty. The less well known costs (gas enclosure and GEMs) have been taken at 40% Estimate Uncertainty.

## GEM Acquisition-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Production GEM Acquisition |  |  |  | 1.02.01.06
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO ACQUIRE COMPONENTS FOR THE GEM FOILS AND PRODUCE THESE FOILS, INCLUDING THE TRAINING OF A TECHNICIAN DEDICATED TO THE PRODUCTION OF SPHENIX GEM FOILS. WORK STATEMENT: PROVIDE ALL PARTS AND MANPOWER TO PRODUCE THE FINAL GEM FOILS.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The ongoing GEM foil work that most closely resembles our needs is being done for the ALICE TPC Upgrade. GEM foils havea single supplier ion the world (CERN) and any hiccup in CERN GEM production is a significant project risk. To mitigate this risk, ALICE developed a model of GEM foil production that includes training and hiring a technician to work in the CERN shop. In this way, ALICE retains the authority to set the technician's priorities for work. We have decided that this risk mitigation strategy is a wise choice and so we plan to follow it exactly. We have thus based the initial costs of the GEMs upon the existing contract between ALICE and the CERN Shop. As time passes, we will need to formulate a similar contract with consent and advice from BNL management and CERN management. In the interpediate time, technical negotiations between the sPHENIX TPC group (Dehmelt) and the CERN shop (de Oliviera) have concluded several things. First, the time scheule assumed by sPHENIX is realistic. Second, the technician fee is realistic. Third, the per foil costs will be lower than "scaled ALICE". The reason for this is that current foil production in the CERN shop involves large sheets carrying multiple foils. An analysis of our smaller foils shows that we will be able to more effectively use the area of a single production step as compared to ALICE. This adjustment to the per GEM cost has been applied to the Cost Summary (FY17 DIrect) found here.
Details of the Base Estimate (explanation of the Work)
The team of Dehmelt (sPHENIX) and de Oliviera (CERN) has long experience working together since the first GEM development for the COMPASS experiment was done in collaboration by exactly these two gentlemen. Because of this relationship, we have found it easy to get detailed and realistic cost estimates from CERN.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The present estimate including the hiring and training of a CERN technician is included in the GEM acquisition.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 172280 | 1280
Estimate Uncertainty
The team of Dehmelt (sPHENIX) and de Oliviera (CERN) has long experience working together since the first GEM development for the COMPASS experiment was done in collaboration by exactly these two gentlemen. Because of this relationship, we have found it easy to get detailed and realistic cost estimates from CERN. For this reason, we are treating the current detailed CERN estimate as a "vendor quote" and asigning 20% Estimate Uncertainty.

## High Voltage System-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC High Voltage System |  |  |  | 1.02.01.07
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE HIGH VOLTAGE SUPPLY SYSTEM FOR THE GEM READOUT MODULES AND CENTRAL MEMBRANE. IC CONTAINS THE TASKS TO PROCURE THE ELEMENTS OF THESE ITEMS. WORK STATEMENT: PROVIDE ALL PARTS TO PRODUCE A HIGH VOLTAGE SUPPLY SYSTEM FOR THE TPC.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The high voltage system comprises two basic parts. The first part is the high voltage that is applied to the central membrane and thereby creates the drift field within the TPC gas volume. For this application we have selected a power supply from the same manufacturer as build the HV suply for STAR (Glassman). The second and more expeisive high voltage system is the one that supplies bias voltages to the GEMstack. Here we have taken a somewhat bold move. Despite the development of new "cascaded HV power" that is specifically designed for use in GEM detectors, developed by RD51 (SBU, Temple, and BNL are members), packages by CAEN, selected by ALICE, we have decided against cascaded power. Although the cascaded power DOES give on-the-fly flexibilty of the GEMstack voltages, it has risks assocaited with stared energy in the cables, and is not a "proven tech". Until now every successful GEM detector has used a resistor chain to set the bias, SBU and BNL have vast experience with this, and so we choose the resistor chain model for sPHENIX and reject the new CAEN module. We are aware of a new development in GEM HV undertaking by our friends in Trieste. This one is TRULY impressive as it retains the flexibility of the cascaded supply, eliminates the stored energy issue, provides INTELLIGENT monitoring that catptures high speed (faster than a spark) current waveforms and performs intelligent analysis of the waveform structure not only to throttle the data down to maneagable levels, but also to define intelligent rtip conditions. While this solution is the best we know of, it does not seem practical on our time scale.
Details of the Base Estimate (explanation of the Work)
Our present cost estimate uses off-the-shelf components from Glassman (field cage) and from CAEN (modules) using a traditional non-cascaded power supply (i.e. requiring an on-detector resistor chain).
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The HV estimates are reasonable due to the use of resistor chains rather than cascaded power supplies.
|  |  |  | Grand Total | Labor
|  |  |  | 119072.0264 | 208
Estimate Uncertainty
Estimate Uncertainty on the CAEN HV is set to 20% since we have a vendor quote. Cntingency on the Glassman power supply is set to 40% since the STAR version of this supply is NOT a starnard catalog model.

## Assembly-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 133 v4
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC Assembly |  |  |  | 1.02.01.08
WBS Dictionary Definition:
TECHNICAL SCOPE: ASSEMBLY OF FINAL TPC. WORK STATEMENT: ASSEMBLE ALL PARTS AND PRODUCING THE FINAL TPC.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Assembly of the TPC is entirely accomplished by off-project labor from Stony Brook University. Therefore this is no cost to this WBS item.
Details of the Base Estimate (explanation of the Work)
Assembly of the TPC is entirely accomplished by off-project labor from Stony Brook University. Therefore this is no cost to this WBS item.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
Assembly of the TPC is entirely accomplished by off-project labor from Stony Brook University. Therefore this is no cost to this WBS item.
|  |  |  | Grand Total | Labor
|  |  |  | 1102.08 | 11336
Estimate Uncertainty
Assembly of the TPC is entirely accomplished by off-project labor from Stony Brook University. Therefore this is no cost to this WBS item.

## v1 Field Cage--Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.01 |  | TPC v1 Field Cage Prototype | [6 empty] | 87982
1.02.01.01 | 105200 | Procure TPC v1 Mandrel Parts | [5 empty] | 0
|  |  | HVPF Boards | Sierra Express Circuits | 12564.55 | DELIVERED
|  |  | 8020 parts | McMaster-Carr | 7959.44 | DELIVERED
|  |  | Clean Hood Motor Repair | Grainger | 554.75 | DELIVERED
|  |  | Tooling for Mandrel Table | McMaster-Carr | 774.82 | DELIVERED
|  |  | Optical readout for DVM (IBF) | Mouser | 79.99 | DELIVERED
|  |  | FR4520 tooling Foam | General Plastics | 4361.98 | DELIVERED
|  |  | 2" diameter 9' long shaft | Technico | 335 | DELIVERED
|  |  | RSF-14B-30-F100-24B | Harmonic Drive | 1330 | DELIVERED
|  |  | SHA32A161SG-B12BLV-10S17b-AN | Harmonic Drive | 4674 | DELIVERED
|  |  | T-slotted framing 8020 | McMaster-Carr | 4277.84 | DELIVERED
|  |  | Laminate Trimmer | Grainger | 155 | DELIVERED
|  |  | Position Encoders | Renishaw | 1202 | DELIVERED
|  |  | Adhesive, lab supplies | McMaster-Carr | 1440.43 | DELIVERED
|  |  | Lead Screw | Lin Tech | 3456 | DELIVERED
|  |  | 2" flanged Collars for motor/encoder | McMaster-Carr | 371.66 | DELIVERED
|  |  | USB microscope | Microscope Store | 143 | DELIVERED
|  |  | Motor Controllers | Copley Controls | 1637 | DELIVERED
|  |  | SM encoder | Automation Direct | 67.25 | DELIVERED
|  |  | SM motor | MicroMo | 253.49 | DELIVERED
|  |  | Wire/connectors | DigiKey | 352.41 | DELIVERED
|  |  | PS for translation motor (24 V 24 A) | Automation Direct | 415 | DELIVERED
|  |  | PS for shaft motor (48 V 24 A) | Acopian | 1170 | DELIVERED
|  |  | Motor Controller Access. Kits | Copley Controls | 276 | DELIVERED
|  |  | Web Tension Applicator Toolset | F.W. Hall Company | 18994 | DELIVERED | Manufacturer Quote
1.02.01.01 | 105700 | Procure TPC v1 Outer Field Cage Parts | [5 empty] | 0
|  |  | Honeycomb | Plascorp | 1621.08 | DELIVERED
|  |  | Striped circuit cards | All-flex | 23400 | DELIVERED | Manufacturer Quote
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 21780 | DELIVERED
|  |  | 3 mil kapton 22" x 108 LF | Dunmore | 20350 | DELIVERED
|  |  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | DELIVERED | Manufacturer Quote
|  |  | HVPW resistors | DigiKey | 1170 | DELIVERED | Manufacturer Quote
|  |  | High Voltage Cable | Dielectric Sciences | 600 | DELIVERED | Web Search
1.02.01.01 | 106200 | Procure TPC v1 Inner Field Cage Parts | [5 empty] | 0
|  |  | Striped circuit cards | All-flex | 12000 | DELIVERED | Manufacturer Quote
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 7260 | DELIVERED
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 8140 | DELIVERED
|  |  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | DELIVERED | Manufacturer Quote
|  |  | HVPW Resistors | DigiKey | 1170 | DELIVERED | Manufacturer Quote
1.02.01.01 | 106500 | Procure TPC Field Cage Prototype v1 End Rings | [5 empty] | 0
|  |  | End Rings | Outside Vendor | 20000 | DELIVERED | BNL Shops Estimate
1.02.01.01 | 107600, 107700 | Procure TPC v1 End Cap | [5 empty] | 64982
|  |  | Aluminum | Yarde Metals | 6222 | Pending | Vendor Quote
|  |  | Machining | Outside Vendor | 58760 | Pending | PR value
1.02.01.01 | 107900 | Procure TPC v1 Central Membrane Parts | [5 empty] | 8000 |  | P6 still has $6400; fix
[5 empty] | 8000 | Pending | Experience
1.02.01.01 | 108800 | Procure TPC Handling Cart | [5 empty] | 13000
[5 empty] | 13000 | Pending | Experience
1.02.01.01 | 108500 | Procure TPC Assembly Fixtures | [5 empty] | 2000
[5 empty] | 2000 | Pending | Experience
Labor
WBS |  | Description | Justification | Category | Hours | TOTAL | Hours Complete | TOTAL Complete
1.02.01.01 | 105500 | Assemble TPC v1 Outer Field Cage - FY18 | Similar structure to PHENIX HBD and STAR TPC. | TECH | 0 | 0 | 192 | 864
|  |  |  | SCI | 0 |  | 96
|  |  |  | STUD | 0 |  | 576
1.02.01.01 | 105600 | Assemble TPC v1 Outer Field Cage - FY19 | Similar structure to PHENIX HBD and STAR TPC. | TECH | 48 | 216
|  |  |  | SCI | 24
|  |  |  | STUD | 144
1.02.01.01 | 106000 | Assemble TPC v1 Inner Field Cage - FY18 | Similar structure to PHENIX HBD and STAR TPC. | TECH | 0 | 0 | 64 | 192
|  |  |  | SCI | 0 |  | 64
|  |  |  | STUD | 0 |  | 64
1.02.01.01 | 106100 | Assemble TPC v1 Inner Field Cage - FY19 | Similar structure to PHENIX HBD and STAR TPC. | TECH | 96 | 288
|  |  |  | SCI | 96
|  |  |  | STUD | 96
1.02.01.01 | 108900 | Assemble TPC v1 Central Membrane | Similar to large windows in PHENIX RICH & Drift Chamber | TECH | 80 | 240
|  |  |  | SCI | 80
|  |  |  | STUD | 80
1.02.01.01 | 109000 | Assemble TPC v1 Field Cage Prototype | Similar structure to PHENIX HBD and STAR TPC. | TECH | 120 | 360
|  |  |  | SCI | 120
|  |  |  | STUD | 120
1.02.01.01 | 105100 | Assemble TPC v1 Mandrel | Hybrid of STAR and ILC Mandrel Design | TECH | 0 | 0 | 16 | 72
|  |  |  | SCI | 0 |  | 8
|  |  |  | STUD | 0 |  | 48
1.02.01.01 | 109100 | Benchtest TPC v1 Field Cage Prototype | Standard HV and Leak Tests | TECH | 40 | 120
|  |  |  | SCI | 40
|  |  |  | STUD | 40
1.02.01.01 | 106300 | Design TPC Field Cage Prototype v1 End Rings | Simply detailing main design. | PROF | 0 | 0 | 32 | 96
|  |  |  | TECH | 0 |  | 32
|  |  |  | SCI | 0 |  | 32
1.02.01.01 | 108300 | Design TPC Assembly Fixture | Simply detailing main design | TECH | 0 | 0 | 32 | 32
1.02.01.01 | 108600 | Design TPC Handling Cart | Significant interface work required with installation team. | PROF | 80 | 240
|  |  |  | TECH | 80
|  |  |  | SCI | 80
1.02.01.01 | 106400 | Procure TPC Field Cage Prototype v1 End Rings | Outside Vendor. | TECH | 0 | 0 | 32 | 32
1.02.01.01 | 106900 | Procure TPC v1 End Cap | Complexity exceeds 500 holes. | TECH | 0 | 0 | 480 | 480
1.02.01.01 | 108100 | Procure TPC v1 Central Membrane Parts - FY18 | In House manufacture | TECH | 0 | 0 | 64 | 64
1.02.01.01 | 108200 | Procure TPC v1 Central Membrane Parts - FY19 | In House manufacture | TECH | 256 | 256
1.02.01.01 | 108400 | Procure TPC Assembly Fixture | In House manufacture | TECH | 32 | 32
1.02.01.01 | 108700 | Procure TPC Handling Cart | Outside Vendor. | TECH | 32 | 32
1.02.01.01 | 105900 | Procure TPC v1 Inner Field Cage Parts | Many small orders | TECH | 0 | 0 | 232 | 232
1.02.01.01 | 105000 | Procure TPC v1 Mandrel Parts | Standard materials | TECH | 0 | 0 | 16 | 16
1.02.01.01 | 105400 | Procure TPC v1 Outer Field Cage Parts | Duplicate orders to Inner Field Cage | TECH | 0 | 0 | 105 | 105
1.02.01.01 | 108000 | Produce TPC v1 Central Membrane Conceptual Design | Similar to STAR and ALICE | PROF | 0 | 0 | 232 | 696
|  |  |  | TECH | 0 |  | 232
|  |  |  | SCI | 0 |  | 232
1.02.01.01 | 106600 | Produce TPC v1 End Cap Conceptual Design | Similar to STAR and ALICE, somewhat simpler (single piece) | PROF | 0 | 0 | 152 | 456
|  |  |  | TECH | 0 |  | 152
|  |  |  | SCI | 0 |  | 152
1.02.01.01 | 104800 | Produce TPC v1 Field Cage Prototype Conceptual Design | Simple intergration of other detailed parts. | PROF | 0 | 0 | 16 | 40
|  |  |  | TECH | 0 |  | 16
|  |  |  | SCI | 0 |  | 8
1.02.01.01 | 105800 | Produce TPC v1 Inner Field Cage Conceptual Design | Integration of higher level design. | PROF | 0 | 0 | 16 | 48
|  |  |  | TECH | 0 |  | 16
|  |  |  | SCI | 0 |  | 16
1.02.01.01 | 104900 | Produce TPC v1 Mandrel Conceptual Design | Similar to STAR and ILC | PROF | 0 | 0 | 16 | 72
|  |  |  | SCI | 0 |  | 8
|  |  |  | STUD | 0 |  | 48
1.02.01.01 | 105300 | Produce TPC v1 Outer Field Cage Conceptual Design | Integration of Higher Level Design | PROF | 0 | 0 | 16 | 40
|  |  |  | TECH | 0 |  | 16
|  |  |  | SCI | 0 |  | 8
|  | Grand Total |  |  | 1784 | 1784 | 2481 | 2481

## v2 FIeld Cage-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.02 |  | TPC v2 Field Cage | [6 empty] | 148818.7
1.02.01.02 | 109400 | Procure TPC v2 Mandrel Parts | [5 empty] | 10432.66
|  |  | FR4520 tooling Foam | General Plastics | 4361.98 | Pending | Existing PO
|  |  | T-slotted framing 8020 | McMaster-Carr | 4277.84 | Pending | Estimate from v1
|  |  | Adhesive, lab supplies | McMaster-Carr | 1440.43 | Pending | Estimate from v1
|  |  | Wire/connectors | DigiKey | 352.41 | Pending | Manufacturer Quote
1.02.01.02 | 110300 | Procure TPC v2 Outer Field Cage Parts | [5 empty] | 75826.88
|  |  | Honeycomb | Plascorp | 1621.08 | Pending | Existing PO
|  |  | Striped circuit cards | All-flex | 23400 | Pending | Manufacturer Quote
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 21780 | Pending | Existing PO
|  |  | 3 mil kapton 22" x 108 LF | Dunmore | 20350 | Pending | Existing PO
|  |  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | Pending | Manufacturer Quote
|  |  | HVPW resistors | DigiKey | 6930 | Pending | Manufacturer Quote
|  |  | High Voltage Cable | Dielectric Sciences | 600 | Pending | Manufacturer Quote
1.02.01.02 | 111200 | Procure TPC v2 Inner Field Cage Parts | [5 empty] | 34559.16
|  |  | Striped circuit cards | All-flex | 12000 | Pending | Manufacturer Quote
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 7260 | Pending | Manufacturer Quote
|  |  | 3 mil kapton 44" x 108 LF | Dunmore | 8140 | Pending | Manufacturer Quote
|  |  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | Pending | Manufacturer Quote
|  |  | HVPW Resistors | DigiKey | 6930 | Pending | Manufacturer Quote
1.02.01.02 | 111500 | Procure TPC Field Cage Prototype v2 End Rings | [5 empty] | 20000
|  |  | End Rings | Outside Vendor | 20000 | Pending | BNL Shops Estimate
1.02.01.02 | 111800 | Procure TPC v2 Central Membrane Parts | [5 empty] | 8000
[5 empty] | 8000 | Pend | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.02 | 111900 | Assemble TPC v2 Central Membrane | Same as v1 | TECH | 80 | 240
|  |  |  | SCI | 80
|  |  |  | STUD | 80
1.02.01.02 | 112000 | Assemble TPC v2 Field Cage Prototype | Same as v2 | TECH | 160 | 480
|  |  |  | SCI | 160
|  |  |  | STUD | 160
1.02.01.02 | 111300 | Assemble TPC v2 Inner Field Cage | Same as v3 | TECH | 80 | 240
|  |  |  | SCI | 80
|  |  |  | STUD | 80
1.02.01.02 | 109500 | Assemble TPC v2 Mandrel | Same as v4 | TECH | 40 | 180
|  |  |  | SCI | 20
|  |  |  | STUD | 120
1.02.01.02 | 110400 | Assemble TPC v2 Outer Field Cage | Same as v5 | TECH | 160 | 720
|  |  |  | SCI | 80
|  |  |  | STUD | 480
1.02.01.02 | 111400 | Design TPC Field Cage Prototype v2 End Rings | Updates to existing v1 design. | PROF | 16 | 48
|  |  |  | TECH | 16
|  |  |  | SCI | 16
1.02.01.02 | 111700 | Procure TPC v2 Central Membrane Parts | In house part production. | TECH | 320 | 320
1.02.01.02 | 111600 | Produce TPC v2 Central Membrane Conceptual Design | Updates to existing v1 design. | PROF | 16 | 48
|  |  |  | TECH | 16
|  |  |  | SCI | 16
1.02.01.02 | 109300 | Produce TPC v2 Field Cage Prototype Conceptual Design | Updates to existing v1 design. | PROF | 32 | 80
|  |  |  | TECH | 32
|  |  |  | SCI | 16
1.02.01.02 | 110500 | Produce TPC v2 Inner Field Cage Conceptual Design | Updates to existing v1 design. | PROF | 16 | 48
|  |  |  | TECH | 16
|  |  |  | SCI | 16
1.02.01.02 | 109600 | Produce TPC v2 Outer Field Cage Conceptual Design | Updates to existing v1 design. | PROF | 16 | 40
|  |  |  | TECH | 16
|  |  |  | SCI | 8
|  | Grand Total |  |  | 2444 | 2444

## Final FIeld Cage-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total | Grand Total w/ Estimate Uncertainty
1.02.01.03 |  | TPC Final Field Cage | [6 empty] | 6000 | 0
1.02.01.03 |  | Procure TPC v2 Field Cage Modification Parts | [5 empty] | 6000
[5 empty] | 6000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.03 |  | Benchtest TPC Final Field Cage | High Voltage and Gas Leaks Only. | SCI | 80 | 160
|  |  |  | STUD | 80
1.02.01.03 |  | Design TPC v2 Field Cage Modifications | Limited to trivial v2 upgrades. | PROF | 16 | 48
|  |  |  | TECH | 16
|  |  |  | SCI | 16
1.02.01.03 |  | Modify TPC v2 Field Cage | Limited to trivial v2 updagres. | SCI | 80 | 160
|  |  |  | STUD | 80
1.02.01.03 |  | Procure TPC v2 Field Cage Modification Parts | Limited to trivial v2 upgrades. | TECH | 32 | 32
|  | Grand Total |  |  | 400 | 400

## v1 Modules-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.04 |  | TPC v1 Modules | [6 empty] | 10200
1.02.01.04.01 | 113300 | Procure TPC v1 Module Gas Enclosure Parts | [5 empty] | 8000 |  | Complete
|  |  | Gas |  | 5000 | Pending | Recent Purchase
[5 empty] | 3000 | Pending | Experience
1.02.01.04.02 | 113800 | Procure TPC v1 Module Strongback | [5 empty] | 1200 |  | Complete
[5 empty] | 1200 | Pending | SBU Shop Quote
1.02.01.04.02 | 114100 | Procure TPC v1 Module Frames | [5 empty] | 1000 |  | Complete
[5 empty] | 1000 | Pending | Sbu Shop Quote
1.02.01.04.02 | 114400 | Procure TPC v1 Grid Parts | [5 empty] | 500 |  | Complete
[5 empty] | 500 | Pending | SBU Shop Quote
1.02.01.04.03 | 114900 | Procure TPC v1a Module Padplane | [5 empty] | 3700 |  | Complete
|  |  | PadPlane | Somacis | 3700 | Pending | Vendor Quote
1.02.01.04.03 | 115200 | Procure TPC v1a Module GEMs | [5 empty] | 6500 |  | Complete
|  |  | GEM Mask | CERN | 1500 | Pending | Recent Purchase
|  |  | GEMs | CERN | 5000 | Pending | Experience
1.02.01.04.04 | 116000 | Procure TPC v1b Module Padplane | [5 empty] | 3700
|  |  | PadPlane | Somacis | 3700 | Pending | Vendor Quote
1.02.01.04.04 | 116300 | Procure TPC v1b Module GEMs | [5 empty] | 6500
|  |  | GEM Mask | CERN | 1500 | Pending | Recent Purchase
|  |  | GEMs | CERN | 5000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL | Hours Completed | TOTAL Completed
1.02.01.04.02 | 114500 | Assemble TPC v1 Grid | Similar to PHENIX HBD. | STUD | 0 | 0 | 320 | 480
|  |  |  | SCI | 0 |  | 160
1.02.01.04.01 | 113400 | Assemble TPC v1 Module Gas Enclosure | Similar to Large Field Cage Prototype | STUD | 0 | 0 | 80 | 80
1.02.01.04.03 | 115600 | Assemble TPC v1a Module Prototype | Similar to PHENIX HBD | TECH | 0 | 0 | 40 | 80
|  |  |  | STUD | 0 |  | 40
1.02.01.04.04 | 116700 | Assemble TPC v1b Module Prototype | Similar to PHENIX HBD | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.04.02 | 113900 | Design TPC v1 Module Frames | Copied from v1 field cage design | PROF | 0 | 0 | 8 | 24
|  |  |  | TECH | 0 |  | 8
|  |  |  | SCI | 0 |  | 8
1.02.01.04.01 | 113100 | Design TPC v1 Module Gas Enclosure | Similar to Large Field Cage Prototype | PROF | 0 | 0 | 80 | 240
|  |  |  | TECH | 0 |  | 80
|  |  |  | SCI | 0 |  | 80
1.02.01.04.02 | 114200 | Design TPC v1 Module Grid | Copied from v1 field cage design | PROF | 0 | 0 | 8 | 24
|  |  |  | TECH | 0 |  | 8
|  |  |  | SCI | 0 |  | 8
1.02.01.04.02 | 113600 | Design TPC v1 Module Strongback | Copied from v1 field cage design | PROF | 0 | 0 | 80 | 240
|  |  |  | TECH | 0 |  | 80
|  |  |  | SCI | 0 |  | 80
1.02.01.04.03 | 115000 | Design TPC v1a Module GEMs | Similar to PHENIX HBD | PROF | 0 | 0 | 40 | 360
|  |  |  | STUD | 0 |  | 160
|  |  |  | SCI | 0 |  | 160
1.02.01.04.03 | 114700 | Design TPC v1a Module Padplane | Similar to EIC R&D from eRD6 | PROF | 0 | 0 | 80 | 320
|  |  |  | STUD | 0 |  | 160
|  |  |  | SCI | 0 |  | 80
1.02.01.04.04 | 116100 | Design TPC v1b Module GEMs | Similar to PHENIX HBD | PROF | 0 | 0 | 40 | 360
|  |  |  | STUD | 0 |  | 160
|  |  |  | SCI | 0 |  | 160
1.02.01.04.04 | 115800 | Design TPC v1b Module Padplane | Similar to EIC R&D from eRD6 | PROF | 0 | 0 | 80 | 320
|  |  |  | STUD | 0 |  | 160
|  |  |  | SCI | 0 |  | 80
1.02.01.04.03 | 115400 | Frame TPC v1a Module GEMs | Similar to PHENIX HBD and EIC R&D | TECH | 0 | 0 | 40 | 40
1.02.01.04.04 | 116500 | Frame TPC v1b Module GEMs | Similar to PHENIX HBD and EIC R&D | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.04.02 | 114300 | Procure TPC v1 Grid Parts | Vendor purchase | SCI | 0 | 0 | 13 | 13
1.02.01.04.02 | 114000 | Procure TPC v1 Module Frames | Vendor purchase | TECH | 0 | 0 | 24 | 24
1.02.01.04.01 | 113200 | Procure TPC v1 Module Gas Enclosure Parts | Multiple orders | TECH | 0 | 0 | 32 | 32
1.02.01.04.02 | 113700 | Procure TPC v1 Module Strongback | SBU machine shop | TECH | 0 | 0 | 16 | 16
1.02.01.04.03 | 115100 | Procure TPC v1a Module GEMs | Similar to EIC R&D from eRD6 | TECH | 0 | 0 | 32 | 32
1.02.01.04.03 | 114800 | Procure TPC v1a Module Padplane | Well known PC board vendor | TECH | 0 | 0 | 16 | 16
1.02.01.04.04 | 116200 | Procure TPC v1b Module GEMs | Similar to EIC R&D from eRD6 | TECH | 32 | 32
1.02.01.04.04 | 115900 | Procure TPC v1b Module Padplane | Well known PC board vendor | TECH | 16 | 16
1.02.01.04.01 | 113500 | Test TPC v1 Module Gas Enclosure | Similar to PHENIX HBD. | STUD | 0 | 0 | 40 | 80
|  |  |  | SCI | 0 |  | 40
1.02.01.04.03 | 115300 | Test TPC v1a Module Framed GEMs | Similar to PHENIX HBD. | TECH | 0 | 0 | 40 | 80
|  |  |  | STUD | 0 |  | 40
1.02.01.04.03 | 115300 | Test TPC v1a Module GEMS | Similar to PHENIX HBD. | TECH | 0 | 0 | 40 | 120
|  |  |  | STUD | 0 |  | 80
1.02.01.04.03 | 115700 | Test TPC v1a Module Prototype | Similar to PHENIX HBD. | TECH | 0 | 0 | 160 | 320
|  |  |  | STUD | 0 |  | 160
1.02.01.04.04 | 116600 | Test TPC v1b Module Framed GEMs | Similar to PHENIX HBD. | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.04.04 | 116400 | Test TPC v1b Module GEMS | Similar to PHENIX HBD. | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.04.04 | 116800 | Test TPC v1b Module Prototype | Similar to PHENIX HBD. | TECH | 160 | 320
|  |  |  | STUD | 160
|  | Grand Total |  |  | 688 | 688 | 3301 | 3301

## v2 Modules-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.05 |  | TPC v2 Modules | [6 empty] | 12900
1.02.01.05.02 | 117100 | Procure TPC v2 Module Strongback | [5 empty] | 1200
[5 empty] | 1200 | Pending | SBU Shop Quote
1.02.01.05.02 | 117400 | Procure TPC v2 Module Frames | [5 empty] | 1000
[5 empty] | 1000 | Pending | Sbu Shop Quote
1.02.01.05.02 | 117700 | Procure TPC v2 Grid Parts | [5 empty] | 500
[5 empty] | 500 | Pending | SBU Shop Quote
1.02.01.05.03 | 118100 | Procure TPC v2a Module Padplane | [5 empty] | 3700
|  |  | PadPlane | Somacis | 3700 | Pending | Vendor Quote
1.02.01.05.03 | 118400 | Procure TPC v2a Module GEMs | [5 empty] | 6500
|  |  | GEM Mask | CERN | 1500 | Pending | Recent Purchase
|  |  | GEMs | CERN | 5000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.05.02 | 117800 | Assemble TPC v2 Module Grid | Similar to PHENIX HBD. | TECH | 80 | 80
1.02.01.05.03 | 118800 | Assemble TPC v2a Module Prototype | Similar to PHENIX HBD. | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.05.02 | 117200 | Design TPC v2 Module Frames | Copied from v1 field cage design. | PROF | 8 | 24
|  |  |  | TECH | 8
|  |  |  | SCI | 8
1.02.01.05.02 | 117500 | Design TPC v2 Module Grid | Copied from v1 field cage design. | PROF | 8 | 24
|  |  |  | TECH | 8
|  |  |  | SCI | 8
1.02.01.05.02 | 116900 | Design TPC v2 Module Strongback | Copied from v1 field cage design. | PROF | 80 | 240
|  |  |  | STUD | 80
|  |  |  | SCI | 80
1.02.01.05.03 | 118200 | Design TPC v2a Module GEMs | Copied from v1 field cage design. | PROF | 40 | 360
|  |  |  | SCI | 160
|  |  |  | STUD | 160
1.02.01.05.03 | 117900 | Design TPC v2a Module Padplane | Similar to EIC R&D from eRD6 | PROF | 80 | 320
|  |  |  | STUD | 160
|  |  |  | SCI | 80
1.02.01.05.03 | 118600 | Frame TPC v2a Module GEMs | Similar to PHENIX HBD. | TECH | 40 | 40
1.02.01.05.02 | 117300 | Procure TPC v2 Module Frames | Vendor purchase | TECH | 24 | 24
1.02.01.05.02 | 117600 | Procure TPC v2 Module Grid Parts | Vendor purchase | TECH | 24 | 24
1.02.01.05.02 | 117000 | Procure TPC v2 Module Strongback | SBU shop | TECH | 16 | 16
1.02.01.05.03 | 118300 | Procure TPC v2a Module GEMs | Similar to EIC R&D from eRD6 | TECH | 32 | 32
1.02.01.05.03 | 118000 | Procure TPC v2a Module Padplane | Similar to EIC R&D from eRD7 | TECH | 16 | 16
1.02.01.05.03 | 118700 | Test TPC v2a Module Framed GEMs | Similar to PHENIX HBD. | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.05.03 | 118500 | Test TPC v2a Module GEMS | Similar to PHENIX HBD. | TECH | 40 | 80
|  |  |  | STUD | 40
1.02.01.05.03 | 118900 | Test TPC v2a Module Prototype | Similar to PHENIX HBD. | TECH | 160 | 320
|  |  |  | STUD | 160
|  | Grand Total |  |  | 1760 | 1760

## GEM Acquisition-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.06 |  | TPC Production GEM Acquisition | [6 empty] | 172280
1.02.01.06 | 120000 | Train Technician to work in CERN Shop on TPC GEMs | [5 empty] | 39080
[5 empty] | 39080 | Pending | ALICE Fee
1.02.01.06 | 120100 | Produce TPC GEM foils (includes Technician fees) | [5 empty] | 133200
|  |  | R1 GEM Foils (30 modules) | CERN | 33200 | Pending | Vendor Quotation
|  |  | R2 GEM Foils (30 modules) | CERN | 41600 | Pending | Vendor Quotation
|  |  | R3 GEM Foils (30 modules) | CERN | 58400 | Pending | Vendor Quotation
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.06 | 119300 | Procure TPC GEM Foils - Provide Requirements to Procurement | Copied from ALICE Model, verified with CERN shop. | TECH | 960 | 960
1.02.01.06 | 119200 | Train Technician to work in CERN Shop on TPC GEMs | Copied from ALICE Model, verified with CERN shop. | TECH | 320 | 320
|  | Grand Total |  |  | 1280 | 1280

## High Voltage System-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.07 |  | TPC High Voltage System | [6 empty] | 119072.0264
1.02.01.07 | 121400 | Procure TPC GEM HV Power Supplies | [5 empty] | 107922.0264
|  |  | GEM Power Supplies | Weiner/ISEG | 59024 |  | Vendor Quote
|  |  | Bipolar Mesh Power Supplies | Weiner/ISEG | 3514 |  | Vendor Quote
|  |  | High Voltage Crates | Weiner/ISEG | 7245 |  | Vendor Quote
|  |  | GEM High Voltage Cables | Pasternak | 14679 |  | Vendor Quote
|  |  | HV Divider Card | Hughes | 15849.6 |  | Vendor Quote
|  |  | SHV Panel Mount | Digikey | 3106.3795 |  | Vendor Quote
|  |  | BNC Panel Mount | Digikey | 112.96 |  | Vendor Quote
|  |  | Ohmite Resistors | Digikey | 2789.568 |  | Vendor Quote
|  |  | HV Board Caps | Digikey | 55.59 |  | Vendor Quote
|  |  | HV Board Resistors | Digikey | 15.95 |  | Vendor Quote
|  |  | HV Board Red Wire | Digikey | 369.66 |  | Vendor Quote
|  |  | HV Board Black Wire | Digikey | 369.66 |  | Vendor Quote
|  |  | HV Board Sockets | Digikey | 540.1018 |  | Vendor Quote
|  |  | HV Board Pins | Digikey | 250.5571 |  | Vendor Quote
1.02.01.07 | 120400 | Procure TPC Membrane HV Cable | [5 empty] | 600
|  |  |  | Dielectric Sciences | 600 | Pending | Web Quote
1.02.01.07 | 121500 | Procure TPC Membrane Power Supply | [5 empty] | 10550
|  |  |  | Weiner/ISEG | 10550 | Pending | Vendor Quote
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.07 | 120700 | Procure TPC GEM + Membrane HV Power Supplies - Provide Requirements to Procurement | Similar to PHENIX HBD (GEM) and STAR (Membrane) | TECH | 32 | 32
1.02.01.07 | 120300 | Procure TPC Membrane HV Cable | Similar to STAR | TECH | 32 | 64
|  |  |  | SCI | 32
1.02.01.07 | 120600 | Select TPC GEM HV Power Supplies | Similar to PHENIX HBD | SCI | 80 | 80
1.02.01.07 | 120500 | Select TPC Membrane HV Power Supply | Similar to STAR | SCI | 32 | 32
|  | Grand Total |  |  | 208 | 208

## Assembly-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.01.08 | 121650 | TPC Assembly | [5 empty] | 1102.08 | 1102.08
|  |  | Swagelok | RS Crum | 1102.08 | Pending | Vendor Quote
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.01.08 | 121700 | Install TPC Electronics | Includes installation AND testing/remediation on board. Similar to PHENIX DC. | TECH | 160 | 608
|  |  |  | SCI | 48
|  |  |  | STUD | 400
1.02.01.08 | 121600 | Install TPC Modules into Field Cage | Similar to ILC TPC Prototype. | TECH | 1920 | 7296
|  |  |  | STUD | 4800
|  |  |  | SCI | 576
1.02.01.08 | 121800 | Test TPC Prior to Installation | Similar to STAR and ALICE. | TECH | 520 | 3432
|  |  |  | SCI | 312
|  |  |  | STUD | 2600
|  | Grand Total |  |  | 11336 | 11336

## Quotations
[10 empty] | Template | 2100 | medium order pricing
[10 empty] | Design | 1500 | per template type
[10 empty] | Tooling | 2500 | per template type
[8 empty] | # in x | # in y | # per template | # of templates | # Template Types | GEM costs | Design/Tooling | Total
[7 empty] | R1 | 5 | 2 | 10 | 12 | 2 | 25200 | 8000 | 33200
[7 empty] | R2 | 4 | 2 | 8 | 16 | 2 | 33600 | 8000 | 41600
[7 empty] | R3 | 1 | 5 | 5 | 24 | 2 | 50400 | 8000 | 58400
[7 empty] | TOTAL |  |  |  | 52 |  |  |  | 133200
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
GEM Power Supplies | Weiner/ISEG | EHS |  | 8 | 7378 | 59024
Bipolar Mesh Power Supplies | Weiner/ISEG | Custom |  | 1 | 3514 | 3514
High Voltage Crates | Weiner/ISEG |  |  | 1 | 7245 | 7245
GEM High Voltage Cables | Pasternak | PE3895LF-1200 | 100' | 100 | 146.79 | 14679
HV Divider Card | Hughes | SBU-Rev 3 |  | 96 | 165.1 | 15849.6
SHV Panel Mount | Digikey | A24669-ND |  | 288 | 10.786 | 3106.3795
BNC Panel Mount | Digikey | A97548-ND |  | 100 | 1.1296 | 112.96
Ohmite Resistors | Digikey | SM104FE-4M-ND |  | 1152 | 2.4215 | 2789.568
HV Board Caps | Digikey | 1269PH-ND |  | 100 | 0.5559 | 55.59
HV Board Resistors | Digikey | BC4422CT-ND |  | 100 | 0.1595 | 15.95
HV Board Red Wire | Digikey | W2422R-50-ND |  | 2 | 184.83 | 369.66 |  |  |  | Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
HV Board Black Wire | Digikey | W2422B-50-ND |  | 2 | 184.83 | 369.66 |  |  |  | Ultra-Torr Feedthroughs for Wagon Wheel | R.S. Crum (swagelok) | SS-4-UT-1-4 |  | 48 | 22.96 | 1102.08
HV Board Sockets | Digikey | ED90282CT-ND |  | 1056 | 0.51146 | 540.1018 |  |  |  | TPC Assembly | [5 empty] | 1102.08
HV Board Pins | Digikey | ED90334-ND |  | 1056 | 0.23727 | 250.5571
Procure TPC GEM HV Power Supplies | [5 empty] | 107922.0264
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
Procure TPC Membrane Power Supply |  |  |  | 1 | 10550 | 10550