## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Time Projection Chamber |  | 1.02 |  | TPC R1 Modules |  | 1.02.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| TPC R1 Factory Preparation |  | 1.02.02.01 |  | Factory Prep-Summary
| TPC R1 Pre-Production Module |  | 1.02.02.02 |  | Pre-Production-Summary
| TPC R1 Module Production |  | 1.02.02.03 |  | Production-Summary

## Factory Prep-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-09
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 134 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC R1 Module Factory Preparation |  |  |  | 1.2.2.1
WBS Dictionary Definition:
TECHNICAL SCOPE: MAKE PRODUCTION SITES READY FOR PRODUCING R1 READOUT MODULES. WORK STATEMENT: PROCURE MATERIAL/EQUIPMENT AND INSTALL IT AT THE R1 FACTORY SITES.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The module production will happen at three different locations: PNPI (Russia), WIS (Israel), and Vanderbilt (TN). Each of these sites has experience with clean facilities. Nonetheless, GEM work in particular requires exceptionally clean facilities. Exceptioanl cleanliness is easy to achieve by placing a laminar flow table INTO an existing clean room. Such an arrangement is easily better than class 10 and more than sufficiently clean for the purposes of GEM chamber production. In this item we have included the purchase of a new 8 foot laminar table, gas, and jigs to ready the site for pre-production.
Details of the Base Estimate (explanation of the Work)
Each facility that will form a module factory for sPHENIX already contains a moderately clean space. We will augment that moderately clean space through the purchase of an 8 foot long laminar flow hood. This will provide not only a very clean work space, but enough room for working on modules side-by-side at various stages of construction. We additionally include costs for consumables (booties hoods, alcohol, chanber gas) and various custom tooling jigs necessary to handle sPHENIX modules.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The cost without Estimate Uncertainty is the same for all factories, regardless of module size.
|  |  |  | Grand Total | Labor
|  |  |  | 20019.85 | 128
Estimate Uncertainty
Because we have quotes for laminar tables and gas, these items carry 20% Estimate Uncertainty. Conuamables and jigs carry 40% Estimate Uncertainty.

## Pre-Production-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-01-09
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 134 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC R1 Pre-Production Module |  |  |  | 1.2.2.2
WBS Dictionary Definition:
TECHNICAL SCOPE: DESIGN, PROCURE, AND ASSEMBLE ALL NEEDED PARTS FOR PRODUCING R1 PRE-PRODUCTION READOUT MODULES INCLUDING TESTING. WORK STATEMENT: IDENTIFY AND PROCURE AND ASSEMBLE MATERIAL/EQUIPMENT FOR THE R1 PRE-PRODUCTION MODULES.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The pre-production modules is to be made after three different prototype modules have been made a tested: TWO v1 modules and ONE v2 module. Our presumption is that the module design is mature. We will test this prosumpation as well as the factory preparedness by the construction of a single "pre-production" module (sometimes known as a first article). The successful testing of the first article will be used to not only establish the efficacy of the design, but the readiness of the factory to begin mass production.
Details of the Base Estimate (explanation of the Work)
The Pre-production module stage bears striking resemblance to the V1 and V2 module prototyping stages since it is in effect a continuation of the very same work. It will involve strangbacks, frames, grids, and pad planes. Gas enclosures are presumed to be a part os thf "jigs" costs in the factory prep.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The cost of the single pre-production module is currently set the same for all factories.
|  |  |  | Grand Total | Labor
|  |  |  | 106400 | 1080
Estimate Uncertainty
The strongbacks, GEM frames etc are all assumed to be very well known costs based upon existing expenses from years of R&D effort. These items therefore carry only 20% Estimate Uncertainty. Also similar to the R&D efforts, we assume a 40% Estimate Uncertainty on the GEM foils since these will be of a new design.

## Production-Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-01-09
[6 empty] | Prepared By: | Thomas K. Hemmick
[6 empty] | DocNo. (refer Rev. Log) | 134 v2
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
TPC R1 Module Production |  |  |  | 1.02.02.03
WBS Dictionary Definition:
TECHNICAL SCOPE: PROCURE, ASSEMBLE AND TEST ALL NEEDED PARTS FOR FINAL PRODUCTION OF R1 READOUT MODULES. WORK STATEMENT: PROCURE AND ASSEMBLE MATERIAL/EQUIPMENT FOR THE FINAL PRODUCTION OF R1 READOUT MODULES.
Estimate Type (check all that apply):
| X | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Production is assumed to be exactly similar to pre-production with the exception of higher Estimate Uncertainty on several items. First is the pad plane. If our HV plan changes due to the Italian devleopment of SMART onboard HV systems, we would anticipate a cost increase in the pad plane. We've therefore increased the pad plane Estimate Uncertainty to allow for this flexibility. Secondly, production will involve an extra grid to be delivered with each module. This field-termination grid component may be made by photographic procedures rather than by a woven mesh. Becauser of this ambiguity we have increased the grid Estimate Uncertainty to 40%.
Details of the Base Estimate (explanation of the Work)
The estimate is effectively scaled for a higher number of modules from the estimate for a single pre-production module. That said, the production modules will carry a field termination grid (not part of prototypes) and therefore the Estimate Uncertainty for this item is high. Secondly, new developments in HV might become available and since these affect the pad plane HV sector, we have increased the Estimate Uncertainty on the pad planes.
Cost Summary (FY17 DIrect)
(follow link for detailed summary)
The full cost for all R1 modules is includes all parts except the GEMs which are costed under the Mechanics section across all module sizes.
|  |  |  | Grand Total | Labor Hours
|  |  |  | 76653.3656 | 7488
Estimate Uncertainty
The Estimate Uncertainty is 20% on familiar items and rises to 40% on the pad plane and grids for reasons mentioned above.

## Factory Prep-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.02.01 |  | TPC R1 Module Factory Preparation | [6 empty] | 20019.85
1.02.02.01 | 122100 | Prepare TPC R1 Factory Clean Facility | [5 empty] | 8019.85
|  |  | Laminar Flow Hood (8 foot) | Kats Enterprises | 6519.85 | Pending | Vendor Quote
|  |  | Garments, gloves, etc |  | 1500 | Pending | Experience
1.02.02.01 | 122300 | Prepare TPC R1 Factory Tooling | [5 empty] | 12000
|  |  | Gas |  | 5000 | Pending | Current Purchase
|  |  | Gluing jigs, small tools |  | 7000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.02.01 | 122000 | Prepare TPC R1 Factory Clean Facility | Similar to ALICE ITS Upgrade | PROF | 16 | 64
|  |  |  | TECH | 48
1.02.02.01 | 122200 | Prepare TPC R1 Factory Tooling | Similar to ALICE ITS Upgrade | PROF | 16 | 64
|  |  |  | STUD | 48
|  | Grand Total |  |  | 128 | 128

## Pre-Production-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.02.02 |  | TPC R1 Pre-Production Module | [6 empty] | 106400
1.02.02.02 | 122600 | Procure TPC R1 Pre-Production Module Stongbacks | [5 empty] | 1200
[5 empty] | 1200 | Pending | SBU Shop Quote
1.02.02.02 | 122800 | Procure TPC R1 Pre-Production Module Frames | [5 empty] | 1000
[5 empty] | 1000 | Pending | Sbu Shop Quote
1.02.02.02 | 123000 | Procure TPC R1 Pre-Production Module Grids | [5 empty] | 500
[5 empty] | 500 | Pending | SBU Shop Quote
1.02.02.02 | 123200 | Procure TPC R1 Pre-Production Module Pad Planes | [5 empty] | 3700
|  |  | PadPlane | Somacis | 3700 | Pending | Vendor Quote
1.02.02.02 | 123480 | Procure TPC R1 Pre-Production Module GEMs | [5 empty] | 5000
|  |  | Production Mask | CERN | 1500 | Pending | Current Purchase
|  |  | GEMS | CERN | 3500 | Pending | Experience
1.02.02.02 | 123700 | Common Production Line & QA Certification | [5 empty] | 95000
|  |  | WSU experience for ALICE | WSU | 95000 | Pending | Current Purchase
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.02.02 | 123500 | Assemble TPC R1 Pre-Production Module in TPC R1 Factory | Similar to PHENIX HBD | PROF | 240 | 480
|  |  |  | STUD | 240
1.02.02.02 | 122400 | Design TPC R1 Pre-Production Module (strongback, frame, grid, pad, GEMs) | Similar to PHENIX HBD | PROF | 160 | 320
|  |  |  | SCI | 160
1.02.02.02 | 122700 | Procure TPC R1 Pre-Production Module Frames - Provide Requirements to Procurement | Copies of earlier prototype orders | TECH | 24 | 24
1.02.02.02 | 122300 | Procure TPC R1 Pre-Production Module GEMs | Copies of earlier prototype orders | TECH | 24 | 24
1.02.02.02 | 122900 | Procure TPC R1 Pre-Production Module Grids | Copies of earlier prototype orders | TECH | 24 | 24
1.02.02.02 | 123100 | Procure TPC R1 Pre-Production Module Pad Planes | Copies of earlier prototype orders | TECH | 24 | 24
1.02.02.02 | 122500 | Procure TPC R1 Pre-Production Module Stongbacks | Copies of earlier prototype orders | TECH | 24 | 24
1.02.02.02 | 123600 | Test TPC R1 Pre-Production Module | Similar to ALICE ITS Upgrade. | PROF | 80 | 160
|  |  |  | STUD | 80
|  | Grand Total |  |  | 1080 | 1080

## Production-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.02.03 |  | TPC R1 Module Production | [6 empty] | 76653.3656
1.02.02.03 | 124500 | Procure TPC R1 Module frames | [5 empty] | 14601
|  |  | GEM Top Frames - Machining | D&L Custom Products | 6240 | Pending | Vendor Quote
|  |  | GEM Bot Frames 1-3 - Machining | D&L Custom Products | 4050 | Pending | Vendor Quote
|  |  | GEM Bot Frames 4 - Machining | D&L Custom Products | 1950 | Pending | Vendor Quote
|  |  | R1 GEM Frame Material (1/16") | Accurate Plastics Inc | 1852.2 | Pending | Vendor Quote
|  |  | R1 GEM Frame Material (1/8") | Accurate Plastics Inc | 508.8 | Pending | Vendor Quote
1.02.02.03 | 124800 | Procure TPC R1 Module strongbacks | [5 empty] | 8216.06
|  |  | R1 Strongbacks | Mackenzie Machining | 7050 | Pending | Vendor Quote
|  |  | Hardware (brass bolts) | McMaster-Carr | 953.28 | Pending | Vendor Quote
|  |  | O-rings | McMaster-Carr | 99.6 | Pending | Vendor Quote
|  |  | Alignment Pins | McMaster-Carr | 3.28 | Pending | Vendor Quote
|  |  | Vacuum Grease | Kurt J Lesker | 109.9 | Pending | Vendor Quote
1.02.02.03 | 125100 | Procure TPC R1 Module Pad Planes | [5 empty] | 44039.3056
|  |  | Pad Plane: Board | TTM | 35684.1 | Pending | Vendor Quote
|  |  | Pad Plane: NRE | TTM | 1200 | Pending | Vendor Quote
|  |  | Pad Plane: eTest | TTM | 250 | Pending | Vendor Quote
|  |  | High Density Interconnect | SAMETC | 2563.2 | Pending | Vendor Quote
|  |  | EEProm | Digikey | 232.0056 | Pending | Vendor Quote
|  |  | Pad Plane Stuffing | East End Assembly | 4110 | Pending | Vendor Quote
1.02.02.03 | 125400 | Procure TPC R1 Module Grids | [5 empty] | 9797
|  |  | Raw Mesh Material | TPC Inc | 1567.8 | Pending | Vendor Quote
|  |  | Mesh Frames - Machining | D&L Custom Products | 2700 | Pending | Vendor Quote
|  |  | Mesh Frames Material | Accurate Plastics Inc | 529.2 | Pending | Vendor Quote
|  |  | Consumables |  | 5000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.02.03 | 125500 | Build TPC R1 Modules | Similar to ALICE ITS Upgrade. | TECH | 960 | 3648
|  |  |  | STUD | 2400
|  |  |  | SCI | 288
1.02.02.03 | 123900 | Procure TPC R1 Module frames - Provide Requirements to Procurement | Duplicate of prototype order. | PROF | 32 | 192 | All combined into one Purchase Requisition
|  |  |  | TECH | 32
|  | Procure TPC R1 Module Grids | Duplicate of prototype order. | TECH | 32
|  | Procure TPC R1 Module Pad Planes | Duplicate of prototype order. | TECH | 32
|  | Procure TPC R1 Module strongbacks | Duplicate of prototype order. | PROF | 32
|  |  |  | TECH | 32
1.02.02.03 | 125600 | Test TPC R1 Modules | Similar to ALICE ITS Upgrade. | TECH | 960 | 3648
|  |  |  | STUD | 2400
|  |  |  | SCI | 288
|  | Grand Total |  |  | 7488 | 7488

## Quotations
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
GEM Top Frames - Machining | D&L Custom Products | R1GEM1_FrameFront_VeR1.0 1/16" thick |  | 120 | 52 | 6240
GEM Top Frames - Machining | D&L Custom Products | R1GEM1_FrameBack_VeR1.0 1/16" thick |  | 90 | 45 | 4050
GEM Top Frames - Machining | D&L Custom Products | R1GEM4_FrameBack_VeR1.0 1/8" thick |  | 30 | 65 | 1950
R1 GEM Frame Material (1/16") | Accurate Plastics Inc | GEBX.0621224N |  | 210 | 8.82 | 1852.2
R1 GEM Frame Material (1/8") | Accurate Plastics Inc | GEBX.1251224N |  | 30 | 16.96 | 508.8
Procure TPC R1 Module frames | [5 empty] | 14601
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
Strongback | Mackenzie-Machine | R1 |  | 30 | 235 | 7050
O-rings |  | R1 |  | 30 | 3.32 | 99.6
Brass Bolts (8-32 x 3/4") for Strongbacks | McMaster-Carr | 93465A197 | 10 packs | 72 | 13.24 | 953.28
Acetal Alignment Pins (1/16" x 1/8") for Strongbacks | McMaster-Carr | 97155A202 | 50 packs | 1 | 3.28 | 3.28
Apiezon L ultra high vacuum grease for SB | Kurt J Lesker | APLB |  | 1 | 109.9 | 109.9
Procure TPC R1 Module strongbacks | [5 empty] | 8216.06
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
Pad Plane | TTM | R1 | Board | 30 | 1189.47 | 35684.1
Pad Plane | TTM | R1 | NRE | 1 | 1200 | 1200
Pad Plane | TTM | R1 | eTest | 1 | 250 | 250
High Density Interconnect | SAMETC |  |  | 360 | 7.12 | 2563.2
EEProm | Digikey | DS2431P+T&RCT-ND |  | 180 | 1.2889 | 232.0056
Pad Plane Stuffing | East End Assembly |  |  | 30 | 137 | 4110
Procure TPC R1 Module Pad Planes | [5 empty] | 44039.3056
Item | Manufacturer/Distributor | Model | Qualifier | Quantity | Each | Total
Raw Mesh Material | TPC Inc | 050X050T0012W48 | sq. ft. | 120 | 13.065 | 1567.8
Mesh Frames - Machining | D&L Custom Products | same as R1GEM1_FrameBack_VeR1.0 1/16" |  | 60 | 45 | 2700
Mesh Frames Material | Accurate Plastics Inc | GEBX.0621212N |  | 60 | 8.82 | 529.2
Consumables | [5 empty] | 5000
Procure TPC R1 Module Grids | [5 empty] | 9797