## Navigation
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
sPHENIX Infrastructure |  | 2.04 |  | Facility Support Systems |  | 2.04.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| 2.04.02.01 |  | Magnet Cryo, Electrical & Control Structural Support in IR |  | Go To BoE
| 2.04.02.02 |  | Beampipe/Vacuum Work Package |  | Go To BoE
| 2.04.02.03 |  | IR HVAC Work Package |  | Go To BoE
| 2.04.02.04 |  | IR Electronics Cooling Water Distribution System Work Package |  | Go To BoE
| 2.04.02.05 |  | IR/AH Safety Subsystems Components Work Package |  | Go To BoE
| 2.04.02.06 |  | Assembly Hall Modifications |  | Go To BoE
Description of this Control Account:

## Infrastructure WBS Structure
Return to Navigation Page
Subsystems | 2.03 & 2.04: Infrastructure
Control Accounts |  | 2.03.01: Detector Mechanical and Support System | 2.04.01: Detector Support Systems | 2.04.02: Facility Support Systems
Work Packages |  |  |  |  | 2.04.02.01: Magnet Cryo, Electrical & Control Structural Support in IR
2.04.02.02: Beampipe/Vacuum Work Package
2.04.02.03: IR HVAC Work Package
2.04.02.04: IR Electronics Cooling Water Distribution System Work Package
2.04.02.05: IR/AH Safety Subsystems Components Work Package
2.04.02.06: Assembly Hall Modifications

## Facility Support Dictionary
Return to Navigation Page
WBS 2.04.02: Facility Support Systems Dictionary
WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.04.02 | Task Description
Facility Support Systems
Task
2.04.02 | Facility Support Systems
2.04.02.01 | Magnet Cryo, Electrical & Control Structural Support in IR | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIXMagnet cryogenics, electrical and control structural supports. Design of cryogenic, electrical and control services and equipment is not part of this work package (see WBS 2.02 Magnet subsystem for info on those components). Work Statement: This work package includes the following tasks: 1. Design an integrated support conceptual design for Cryogenic piping and controls wiring for the sPHENIX Magnet contained inside the Building 1008 Intersection Region (IR). 2. Create farication drawings for supports and related components. 3. Procure parts 4. Deliver to sPHENIX complex at building 1008 for installation NOTES: - The approximate 25 meter path will route from the west wall of the IR to the Magnet Valve Box which contains the refrigerated helium gas and control wiring connection points. - All Cryo lines, Magnet power and monitoring cables and related equipment are not included here; those items are part of WBS 2.02 - Installation of these components is not included here; that is part of WBS 2.05.
S337300 /S337310 | Create Cryo Routing in IR Layout Drawings | Technical Scope: Evaluate and model the system requiremenrts for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | Technical Scope: Create Structural Support assembly drawings for Cryo Structural supports in the IR Work Statement: Make appropriate detail drawings for Cryo Structural Supports.
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | Technical Scope: Review the Cryo structural supports design/safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee..
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | Technical Scope: Address action items from the design and safety reviews. Work Statement: Evaluate committee action items and address appropriately.
S337700 | Design/Safety Reviews Complete, Magnet Cryo, Electrical & Control Structural Support in IR Components Released for Production | Milestone
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | Technical Scope: Prepare the procurement package for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Prepare bid documents and initiate procurement of components.
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | Technical Scope: Evaluate the bid documents for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S338000 /S337200 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fabrication included) | Technical Scope: Procure and deliver components to the IR. Work Statement: Track and manage the procurement of all components for this item.
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | Technical Scope: Perform inspection/acceptance tests for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S338200 | Magnet cryo, electrical and control structural support components Ready for Installation | Milestone
2.04.02.02 | Beampipe/Vacuum Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX Beampipe and vacuum equipment. Work Statement: This work package includes the following tasks: 1. Evaluate the beampipe and vacuum needs for the sPHENIX detector 2. Design beampipe sections and beampipe supports and create appropriate drawings required to meet the specifications in 1. 3. Procure the beampipe components. 4. Deliver to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S338400 /S338410 | Create Beampipe/Vacuum Layout | Technical Scope: Evaluate and model the system requiremenrts for the Beampipe/Vacuum Layout in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S338500 | Create Beampipe/Vacuum Envelope Drawing | Technical Scope: Create Beampipe/Vacuum Envelope Drawings for the IR. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum envelope.
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | Technical Scope: Create Beampipe/Vacuum subassembly and detail Drawings. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum subassemblies.
S338700 S338710 | Review Beampipe/Vacuum Design/Safety | Technical Scope: Review Beampipe/Vacuum Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S338800 S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews | Technical Scope: Address Action Items from Beampipe/Vacuum Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S338900 | Design/Safety Reviews Complete, Beampipe/Vacuum components Released for Production | Milestone
S339010 /S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation | Technical Scope: Technical Scope: Prepare the procurement package for the Beampipe/Vacuum Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components.
S339100 /S339110 | Evaluate & Process Beampipe/Vacuum Components Bids | Technical Scope: Evaluate & Process Beampipe/Vacuum Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S339200 /S338300 /s339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Beampipe/Vacuum Components to the IR. Work Statement: Track and manage the procurement of all components for this item.
s339300 /S339310 | Perform Beampipe/vacuum Acceptance | Technical Scope: Perform Beampipe/vacuum inspection and acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S339400 | Beampipe/Vacuum components Ready for Installation | Milestone
2.04.02.03 | IR HVAC Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX IR HAC equipment requirements. Work Statement: This work package includes the following tasks: 1 Evaluate the existing PHENIX IR HVAC system for adequate cooling of the new sPHENIX detector. 2. Design modifications or replacements, as required for air handlers, heaters, ductwork and refrigerant piping, etc. 3. Procure the necessary equipment to upgrade the existing HVAC temperature and humidity control system 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
S339600 | Model IR HVAC Thermal Requirements | Technical Scope: Model IR HVAC Thermal Requirementsls in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | Technical Scope: Create IR HVAC Layout/schematic drawings & Design specifications . Work Statement: Make appropriate detail drawings for the IR HVAC System.
S339800 | Review IR HVAC Design/Safety | Technical Scope: Review IR HVAC Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S339900 | Address Action Items froml IR HVAC Design & Safety Reviews | Technical Scope: Address Action Items from IR HVAC Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately.
S340000 | Design/Safety Reviews Complete, IR HVAC Components Released for Production | Milestone
S340100 | Prepare IR HVAC Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the procurement package for the IR HVAC Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components.
S340200 | Evaluate & Process IR HVACComponents Bids | Technical Scope: Evaluate & Process IR HVAC Components Bids. Work Statement: Evaluate endor bids, select vendor, place contract with vendor.
S340300 /S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR HVAC Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item.
S340400 | Perform IR HVAC Components Acceptance | Technical Scope: Perform IR HVAC Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S340500 | IR HVAC components Ready for Installation | Milestone
2.04.02.04 | IR Electronics Cooling Water Distribution System Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX IR Electronics Cooling Water Distribution equipment. Work Statement: This work package includes the following tasks: 1 Evaluate the existing PHENIX Electronics Cooling Water System to adequately cool the sPHENIX detector. 2. Design modifications or replacements, as required for pumps, supply & return piping and heat exchangers. 3. Procure the necessary equipment to upgrade the existing temperature, pressure and flow control system. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
s340700 /s340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements | Technical Scope: Model IR Electronics Cooling Water Distribution Thermal Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | Technical Scope: Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Documents Work Statement: Make appropriate detail drawings for the Electronics Cooling Water System.
S340900 | Review IR Electronics cooling water System Design/Safety | Technical Scope: Review IR Electronics cooling water System Design/Safety criteria Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | Technical Scope: Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S341100 | Design/Safety Reviews Complete, IR Electronics Cooling Water Distribution System Components Released for Production | Milestone
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the IR Electronics Cooling Water Distribution System Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | Technical Scope: Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S341400 /S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR Electronics Cooling Water Distribution Components to the IR Work Statement: Track and manage the procurement of all components for this item.
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | Technical Scope: Perform IR Electronics Cooling Water Distribution System Components Acceptance tests Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S341600 | IR Electronics Cooling Water Distribution System Components Ready for Installation | Milestone
2.04.02.05 | IR/AH Safety Subsystems Components Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of the off-detector/carriage safety subsystems including in related SMCS, ODH, Fire, Smoke and Radiation safety systems. (Note On-detector/carriage safety subsystems are covered in work package WBS 2.04.01.05.) Work Statement: This work package includes the following tasks: 1 Design the individual Off Detector "Safety Monitor and Control Systems" (SMCS) to protect the sPHENIX subsystems from faults. 2. Design the new ODH detection system for personnel protection from a magnet quench. 2. Procure the necessary equipment to upgrade the existing On-Detector SMCS control system and new ODH system. 3. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
S341800 /S341810 | Analyze IR/AH Safety Subsystems Requirements | Technical Scope: Analyze Off Detector/Carriage Safety Subsystems Requirements.Work Statement: Gather all relevant information from existing PHENIX documentation.
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for Off-Detector/Carriage Safety Subsystems Work Statement: Make appropriate detail drawings for Off Detector/Carriage Safety Subsystems.
S342000 | Review IR/AH Safety Subsystems Design/Safety | Technical Scope: Review Off Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from Off Detector/Carriage Safety Subsystems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S342200 | Design/Safety Reviews Complete, IR/AH Safety Subsystems Components Released for Production | Milestone
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare Off Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | Technical Scope: Evaluate & Process Off Detector/Carriage Safety Subsystems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S342500 /S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Off Detector/Carriage Safety Subsystems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item..
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | Technical Scope: Perform Off Detector/Carriage Safety Subsystems Components Acceptanc tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S342700 | IR/AH Safety Subsystems Components Ready for Installation | Milestone
2.04.02.06 | Assembly Hall Modifications | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of Assembly Hall generic equipment/infrastructure required to support the sPHENIX upgrade. (Note IR infrastructure, detector specific equipment and services, tooling, fixtures and services specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07, WBS 2.05, WBS 3.01 and 3.02 and the other work packages in WBS 2.09 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Analyze Assembly Hall Requirements 2. Create Assembly Hall modifications Schematic Design and Specification Control Documents 3. Review Assembly Hall modifications for Design/Safety; adress action items 4. Prepare Assembly Hall modifications Procurement Package(s) 5. Evaluate & Process Assembly Hall modifications Bids 6. Procure & Deliver Assembly Hall modifications (leadtime and fabrication included) 7. PerformAssembly Hall modifications Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
S342900 | Analyze Assembly Hall Modification Requirements | Technical Scope: Analyze Assembly Hall Modification Requirements Work Statement: Gather all relevant information from existing PHENIX documentation.
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Assembly Hall Modifications Schematic Design and Specification Control Documents Work Statement: Make appropriate detail drawings for Assembly Hall Modifications.
S343100 | Review Assembly Hall Modifications Design/Safety | Technical Scope: Review Assembly Hall Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | Technical Scope: Address Action Items from Assembly Hall Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S343300 | Design/Safety Reviews Complete, Assembly Hall Modifications Components Released for Production | Milestone
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | Technical Scope: Prepare Assembly Hall Modifications Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | Technical Scope: Evaluate & Process Assembly Hall Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S342800 /S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.
S343700 | Perform Assembly Hall Modifications Components Acceptance | Technical Scope:Perform Assembly Hall Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S343800 | Assembly Hall Components Ready for Installation | Milestone

## BoE for Facility Support
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  |  | Date of Est: | 2017-03-20
[9 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  |  | WBS number: |  |  |  |  | Control Account
Facility Support Systems |  |  |  |  | 2.04.02 |  |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: WBS 2.04.02 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Magnet Cryo, Electrical & Control Structural Support in IR 2. Beampipe/Vacuum 3. IR HVAC 4. IR Electronics Cooling Water Distribution System 5. IR/AH Safety Subsystems Components 6. Assembly Hall Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 6 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below).
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material cost estimate for this control account)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX detector subsystems. 3. Chillers, Gas system source, distribution, and other services are covered by this control acounts (see WBS 2.09) or the individual detector subsystems or the Magnet subsystem. More detailed explanation for this division of responsibility is provided in the BoE's for the individual work packages under this control account. (see the navigation page to access the work package BoE;'s.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of infrastructure equipment and components as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
| WBS # |  | Work Package Description |  |  | Material Cost for this Work Package
| 2.04.02.01 |  | Magnet Cryo, Electrical & Control Structural Support in IR |  |  | 50000
| 2.04.02.02 |  | Beampipe/Vacuum Work Package |  |  | 50000
| 2.04.02.03 |  | IR HVAC Work Package |  |  | 35000
| 2.04.02.04 |  | IR Electronics Cooling Water Distribution System Work Package |  |  | 65000
| 2.04.02.05 |  | IR/AH Safety Subsystems Components Work Package |  |  | 32000
| 2.04.02.06 |  | Assembly Hall Modifications |  |  | 10000
|  |  | Total Unburdened Material Cost for CA # 2.04.02 = |  |  |  | 242000
estimate uncertainty
Estimates for the labor and material described in this Control account are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in each work package. The overall material estimate uncertainty for this control account is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual work packages. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work packages' labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02: Facility Support Systems | [5 empty] | Labor estimate uncertainty: | 25%
[7 empty] | Material estimate uncertainty: | 31.63%

## BoE for Cryo Support in IR
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Magnet Cryo, Electrical & Control Structural Support in IR |  |  |  | 2.04.02.01 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIXMagnet cryogenics, electrical and control structural supports. Design of cryogenic, electrical and control services and equipment is not part of this work package (see WBS 2.02 Magnet subsystem for info on those components). Work Statement: This work package includes the following tasks: 1. Design an integrated support conceptual design for Cryogenic piping and controls wiring for the sPHENIX Magnet contained inside the Building 1008 Intersection Region (IR). 2. Create farication drawings for supports and related components. 3. Procure parts 4. Deliver to sPHENIX complex at building 1008 for installation NOTES: - The approximate 25 meter path will route from the west wall of the IR to the Magnet Valve Box which contains the refrigerated helium gas and control wiring connection points. - All Cryo lines, Magnet power and monitoring cables and related equipment are not included here; those items are part of WBS 2.02 - Installation of these components is not included here; that is part of WBS 2.05.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX Cryogenic piping and controls wiring supports in the sPHENIX IR.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of Cryogenic piping and controls wiring supports as indicated in the "Dictionary Definition: section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $50000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.01: Magnet Cryo, Electrical & Control Structural Support in IR |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Beampipe_Vac
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Beampipe/Vacuum Work Package |  |  |  | 2.04.02.02 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX Beampipe and vacuum equipment. Work Statement: This work package includes the following tasks: 1. Evaluate the beampipe and vacuum needs for the sPHENIX detector 2. Design beampipe sections and beampipe supports and create appropriate drawings required to meet the specifications in 1. 3. Procure the beampipe components. 4. Deliver to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of beampipe components and materials based on existing PHENIX beampipe components which are similar to those needed for sPHENIX. The central Berylium beam pipe section from sPHENIX has been preserved to be repurposed from sPHENIX. This will require some rework as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Rework of the central berylium beampipe 2. Two stages of transition beampipes (from 40 mm to 3 inch OD and from 3 inch to 5 inch OD beampipes) both north and south of the berylium beampipe. 3. Bellows both north and south of the berylium section. 4. additional beampipe sections ("spools") as necessary to connect to existic RHIC beampipe. 5. Supporting fixtures as required to support and position the beampipe sections. All labor for installation of these beampipe components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $50000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.02: Beampipe/Vacuum Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for IR HVAC
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
IR HVAC Work Package |  |  |  | 2.04.02.03 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX IR HAC equipment requirements. Work Statement: This work package includes the following tasks: 1 Evaluate the existing PHENIX IR HVAC system for adequate cooling of the new sPHENIX detector. 2. Design modifications or replacements, as required for air handlers, heaters, ductwork and refrigerant piping, etc. 3. Procure the necessary equipment to upgrade the existing HVAC temperature and humidity control system 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
Estimate Type (check all that apply):
| x | Work Complete
Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of HVAC components and materials based on existing PHENIX HVAC components which are similar to those needed for sPHENIX. The existing IR HVAC equipment is mostly adequate for sPHENIX needs and will be repurposed for sPHENIX. Some rework of the existing system is anticipated as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of HVAC equipment as indicated in the ""Dictionary Definition: section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $35000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.03: IR HVAC Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Cooling Water
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-23
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
IR Electronics Cooling Water Distribution System Work Package |  |  |  | 2.04.02.04 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX IR Electronics Cooling Water Distribution equipment. Work Statement: This work package includes the following tasks: 1 Evaluate the existing PHENIX Electronics Cooling Water System to adequately cool the sPHENIX detector. 2. Design modifications or replacements, as required for pumps, supply & return piping and heat exchangers. 3. Procure the necessary equipment to upgrade the existing temperature, pressure and flow control system. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Material and labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX Electronics Cooling System.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of pumps, heat exchangers, piping and controls as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01. (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $65000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.04: IR Electronics Cooling Water Distribution System Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Facility Safety
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
IR/AH Safety Subsystems Components Work Package |  |  |  | 2.04.02.05 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of the off-detector/carriage safety subsystems including in related SMCS, ODH, Fire, Smoke and Radiation safety systems. (Note On-detector/carriage safety subsystems are covered in work package WBS 2.04.01.05.) Work Statement: This work package includes the following tasks: 1 Design the individual Off Detector "Safety Monitor and Control Systems" (SMCS) to protect the sPHENIX subsystems from faults. 2. Design the new ODH detection system for personnel protection from a magnet quench. 2. Procure the necessary equipment to upgrade the existing On-Detector SMCS control system and new ODH system. 3. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX Off-Detector/Carriage Safety Subsystems.
Details of the Base Estimate (explanation of the Work)
Labor and material estimates are for analyses, design and procurement of the sPHENIX Off-Detector Safety Subsystems.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $32000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.05: IR/AH Safety Subsystems Components Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Assembly Hall
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Assembly Hall Modifications |  |  |  | 2.04.02.06 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of Assembly Hall generic equipment/infrastructure required to support the sPHENIX upgrade. (Note IR infrastructure, detector specific equipment and services, tooling, fixtures and services specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07, WBS 2.05, WBS 3.01 and 3.02 and the other work packages in WBS 2.09 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Analyze Assembly Hall Requirements 2. Create Assembly Hall modifications Schematic Design and Specification Control Documents 3. Review Assembly Hall modifications for Design/Safety; adress action items 4. Prepare Assembly Hall modifications Procurement Package(s) 5. Evaluate & Process Assembly Hall modifications Bids 6. Procure & Deliver Assembly Hall modifications (leadtime and fabrication included) 7. PerformAssembly Hall modifications Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05.
Estimate Type (check all that apply):
| x | Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of Assembly Hall components and materials based on existing PHENIX AH components which are similar to those needed for sPHENIX. The existing Assembly Hall equipment is mostly adequate for sPHENIX needs and will be repurposed for sPHENIX. Some rework of the existing infrastructure is anticipated as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of Assembly Hall equipment as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $10000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.02.06: Assembly Hall Modifications |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## Milestones
WBS Milestone # | WBS Milestone Title | Milestone Date | Notes/LINKS
S337700 | Design/Safety Reviews Complete, Magnet Cryo, Electrical & Control Structural Support in IR Components Released for Production
S338200 | Magnet cryo, electrical and control structural support components Ready for Installation
S338900 | Design/Safety Reviews Complete, Beampipe/Vacuum components Released for Production
S339400 | Beampipe/Vacuum components Ready for Installation
S340000 | Design/Safety Reviews Complete, IR HVAC Components Released for Production
S340500 | IR HVAC components Ready for Installation
S341100 | Design/Safety Reviews Complete, IR Electronics Cooling Water Distribution System Components Released for Production
S341600 | IR Electronics Cooling Water Distribution System Components Ready for Installation
S342200 | Design/Safety Reviews Complete, IR/AH Safety Subsystems Components Released for Production
S342700 | IR/AH Safety Subsystems Components Ready for Installation
S343300 | Design/Safety Reviews Complete, Assembly Hall Modifications Components Released for Production
Return to Navigation Sheet

## Reviews by Work Package
WBS # | WBS Title (Work Package) | WBS Title (Review) | NOTES/LINKS
2.04.02.01 | Magnet Cryo, Electrical & Control Structural Support in IR
S337500 |  | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety
2.04.02.02 | Beampipe/Vacuum Work Package
S338700 S338710 |  | Review Beampipe/Vacuum Design/Safety
2.04.02.03 | IR HVAC Work Package
S339800 |  | Review IR HVAC Design/Safety
2.04.02.04 | IR Electronics Cooling Water Distribution System Work Package
S340900 |  | Review IR Electronics cooling water System Design/Safety
2.04.02.05 | IR/AH Safety Subsystems Components Work Package
S342000 |  | Review IR/AH Safety Subsystems Design/Safety
2.04.02.06 | Assembly Hall Modifications
S343100 |  | Review Assembly Hall Modifications Design/Safety
Return to Navigation Sheet

## Procurement $ by Work Package
Work Package WBS # | Work Package WBS Title | Work Package Procurements (Total) (includes purchased parts, Central Shops fabricated parts, contract labor. Does not include BNL labor other than Central Shops fabrication.) | NOTES/LINKS
2.04.02.01 | Magnet Cryo, Electrical & Control Structural Support in IR | 50000
2.04.02.02 | Beampipe/Vacuum Work Package | 50000
2.04.02.03 | IR HVAC Work Package | 35000
2.04.02.04 | IR Electronics Cooling Water Distribution System Work Package | 65000
2.04.02.05 | IR/AH Safety Subsystems Components Work Package | 32000
2.04.02.06 | Assembly Hall Modifications | 10000
| Total for CA 2.04.02 | 242000 | Note: unburdened costs
Return to Navigation Sheet

## Facility Support Cntrl Account
Return to Navigation Page
WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.04.02 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Facility Support Systems |  |  |  |  | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty | Control account 1.9.2 Bottoms Up Composite estimate uncertainty (%)
| Task |  |  | hrs | hrs | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
2.04.02 | Facility Support Systems | Technical Scope: WBS 2.04.02 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Magnet Cryo, Electrical & Control Structural Support in IR 2. Beampipe/Vacuum 3. IR HVAC 4. IR Electronics Cooling Water Distribution System 5. IR/AH Safety Subsystems Components 6. Assembly Hall Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 6 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below). | [35 empty] | 242000 | [12 empty] | 0 | 6682.5 | 231963.2 | 79478 | 51579.6 | 0 | 0 | 369703.3 | 462129.125 | 318550 | 25% | 31.63%
2.04.02.01 | Magnet Cryo, Electrical & Control Structural Support in IR | [36 empty] | 50000 | [12 empty] | 0 | 0 | 38382.4 | 15571.2 | 7785.6 | 0 | 0 | 61739.2 | 77174 | 62500
S337300 /S337310 | Create Cryo Routing in IR Layout Drawings | Technical Scope: Evaluate and model the system requiremenrts for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 0 | 0 | 0 | 0 | 56 | 32 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 40 | 0 | 0 | 0 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 56 | 24 | 40 | 0 | 0 | 0 | 0 | 5840.8 | 1946.4 | 3244 | 0 | 0 | 11031.2 | 13789 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | Technical Scope: Create Structural Support assembly drawings for Cryo Structural supports in the IR Work Statement: Make appropriate detail drawings for Cryo Structural Supports. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | Technical Scope: Review the Cryo structural supports design/safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 0 | 0 | 0 | 1158.8 | 1448.5 | 0
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | Technical Scope: Address action items from the design and safety reviews. Work Statement: Evaluate committee action items and address appropriately. | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 324.4 | 0 | 0 | 0 | 1993.2 | 2491.5 | 0
S337700 | Design/Safety Reviews Complete, Magnet Cryo, Electrical & Control Structural Support in IR Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946.4 | 0 | 0 | 0 | 1946.4 | 2433 | 0
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | Technical Scope: Prepare the procurement package for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | Technical Scope: Evaluate the bid documents for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S338000 /S337200 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fabrication included) | Technical Scope: Procure and deliver components to the IR. Work Statement: Track and manage the procurement of all components for this item. | 80 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | . | 0 | 64 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 128 | 64 | 0 | 0 | 0 | 0 | 0 | 13350.4 | 5190.4 | 0 | 0 | 0 | 18540.8 | 23176 | 62500
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | Technical Scope: Perform inspection/acceptance tests for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 648.8 | 0 | 0 | 2317.6 | 2897 | 0
S338200 | Magnet cryo, electrical and control structural support components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.02.02 | Beampipe/Vacuum Work Package | [36 empty] | 50000 | [12 empty] | 0 | 2430 | 29204 | 17517.6 | 3244 | 0 | 0 | 52395.6 | 65494.5 | 62500
S338400 /S338410 | Create Beampipe/Vacuum Layout | Technical Scope: Evaluate and model the system requiremenrts for the Beampipe/Vacuum Layout in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 16 | 0 | 16 | 0 | 48 | 32 | 0 | 16 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 16 | 48 | 32 | 0 | 0 | 0 | 0 | 1944 | 5006.4 | 2595.2 | 0 | 0 | 0 | 9545.6 | 11932 | 0
S338500 | Create Beampipe/Vacuum Envelope Drawing | Technical Scope: Create Beampipe/Vacuum Envelope Drawings for the IR. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum envelope. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1622 | 0 | 0 | 0 | 1622 | 2027.5 | 0
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | Technical Scope: Create Beampipe/Vacuum subassembly and detail Drawings. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum subassemblies. | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 3244 | 0 | 0 | 0 | 3244 | 4055 | 0
S338700 S338710 | Review Beampipe/Vacuum Design/Safety | Technical Scope: Review Beampipe/Vacuum Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 4 | 0 | 4 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 486 | 834.4 | 324.4 | 0 | 0 | 0 | 1644.8 | 2056 | 0
S338800 S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews | Technical Scope: Address Action Items from Beampipe/Vacuum Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S338900 | Design/Safety Reviews Complete, Beampipe/Vacuum components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S339010 /S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation | Technical Scope: Technical Scope: Prepare the procurement package for the Beampipe/Vacuum Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S339100 /S339110 | Evaluate & Process Beampipe/Vacuum Components Bids | Technical Scope: Evaluate & Process Beampipe/Vacuum Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S339200 /S338300 /s339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Beampipe/Vacuum Components to the IR. Work Statement: Track and manage the procurement of all components for this item. | 80 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% | Beampipe copmponent design is too early to make detailed estimate. Based on similar beampipe sections at PHENIX and assuming the Be beampipe will be used, $50K is a reasonable estimate. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 128 | 64 | 0 | 0 | 0 | 0 | 0 | 13350.4 | 5190.4 | 0 | 0 | 0 | 18540.8 | 23176 | 62500
s339300 /S339310 | Perform Beampipe/vacuum Acceptance | Technical Scope: Perform Beampipe/vacuum inspection and acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 3244 | 0 | 0 | 5561.6 | 6952 | 0
S339400 | Beampipe/Vacuum components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.02.03 | IR HVAC Work Package | [36 empty] | 35000 | [12 empty] | 0 | 0 | 29204 | 10705.2 | 3244 | 0 | 0 | 43153.2 | 53941.5 | 43750
S339600 | Model IR HVAC Thermal Requirements | Technical Scope: Model IR HVAC Thermal Requirementsls in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | Technical Scope: Create IR HVAC Layout/schematic drawings & Design specifications . Work Statement: Make appropriate detail drawings for the IR HVAC System. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S339800 | Review IR HVAC Design/Safety | Technical Scope: Review IR HVAC Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 0 | 0 | 0 | 1158.8 | 1448.5 | 0
S339900 | Address Action Items froml IR HVAC Design & Safety Reviews | Technical Scope: Address Action Items from IR HVAC Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S340000 | Design/Safety Reviews Complete, IR HVAC Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the procurement package for the IR HVAC Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S340200 | Evaluate & Process IR HVACComponents Bids | Technical Scope: Evaluate & Process IR HVAC Components Bids. Work Statement: Evaluate endor bids, select vendor, place contract with vendor. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S340300 /S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR HVAC Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 25% | 25% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $35K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 96 | 48 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 3892.8 | 0 | 0 | 0 | 13905.6 | 17382 | 43750
S340400 | Perform IR HVAC Components Acceptance | Technical Scope: Perform IR HVAC Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 3244 | 0 | 0 | 5561.6 | 6952 | 0
S340500 | IR HVAC components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.02.04 | IR Electronics Cooling Water Distribution System Work Package | [36 empty] | 65000 | [12 empty] | 0 | 3888 | 42554.4 | 13949.2 | 4217.2 | 0 | 0 | 64608.8 | 80761 | 91000
s340700 /s340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements | Technical Scope: Model IR Electronics Cooling Water Distribution Thermal Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 | 0 | 32 | 0 | 160 | 160 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 160 | 32 | 32 | 0 | 0 | 0 | 3888 | 16688 | 2595.2 | 2595.2 | 0 | 0 | 25766.4 | 32208 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | Technical Scope: Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Documents Work Statement: Make appropriate detail drawings for the Electronics Cooling Water System. | 40 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 64 | 32 | 0 | 0 | 0 | 0 | 0 | 6675.2 | 2595.2 | 0 | 0 | 0 | 9270.4 | 11588 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | Technical Scope: Review IR Electronics cooling water System Design/Safety criteria Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | Technical Scope: Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S341100 | Design/Safety Reviews Complete, IR Electronics Cooling Water Distribution System Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the IR Electronics Cooling Water Distribution System Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 2595.2 | 0 | 0 | 0 | 5932.8 | 7416 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | Technical Scope: Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S341400 /S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR Electronics Cooling Water Distribution Components to the IR Work Statement: Track and manage the procurement of all components for this item. | 50 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 25% | 40% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $65K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M45 | 0 | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 8344 | 3244 | 0 | 0 | 0 | 11588 | 14485 | 91000
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | Technical Scope: Perform IR Electronics Cooling Water Distribution System Components Acceptance tests Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 20 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 1622 | 0 | 0 | 2780.8 | 3476 | 0
S341600 | IR Electronics Cooling Water Distribution System Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.02.05 | IR/AH Safety Subsystems Components Work Package | [36 empty] | 32000 | [12 empty] | 0 | 364.5 | 45057.6 | 11354 | 14273.6 | 0 | 0 | 71049.7 | 88812.125 | 44800
S341800 /S341810 | Analyze IR/AH Safety Subsystems Requirements | Technical Scope: Analyze Off Detector/Carriage Safety Subsystems Requirements.Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 3 | 0 | 3 | 0 | 96 | 96 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 3 | 96 | 24 | 48 | 0 | 0 | 0 | 364.5 | 10012.8 | 1946.4 | 3892.8 | 0 | 0 | 16216.5 | 20270.625 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for Off-Detector/Carriage Safety Subsystems Work Statement: Make appropriate detail drawings for Off Detector/Carriage Safety Subsystems. | 30 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 60 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 4866 | 0 | 0 | 0 | 14878.8 | 18598.5 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | Technical Scope: Review Off Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from Off Detector/Carriage Safety Subsystems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S342200 | Design/Safety Reviews Complete, IR/AH Safety Subsystems Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare Off Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | Technical Scope: Evaluate & Process Off Detector/Carriage Safety Subsystems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S342500 /S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Off Detector/Carriage Safety Subsystems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.. | 60 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | $25K for new ODH System needed for Cryo system: ROM estimate. All other off-detector safety systems to be repurposed $7K estimated to effect repurposing. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 0 | 48 | 0 | 0 | 0 | 0 | 10012.8 | 0 | 3892.8 | 0 | 0 | 13905.6 | 17382 | 44800
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | Technical Scope: Perform Off Detector/Carriage Safety Subsystems Components Acceptanc tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 80 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 80 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 6488 | 0 | 0 | 8805.6 | 11007 | 0
S342700 | IR/AH Safety Subsystems Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.02.06 | Assembly Hall Modifications | [36 empty] | 10000 | [12 empty] | 0 | 0 | 47560.8 | 10380.8 | 18815.2 | 0 | 0 | 76756.8 | 95946 | 14000
S342900 | Analyze Assembly Hall Modification Requirements | Technical Scope: Analyze Assembly Hall Modification Requirements Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 120 | 24 | 48 | 0 | 0 | 0 | 0 | 12516 | 1946.4 | 3892.8 | 0 | 0 | 18355.2 | 22944 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Assembly Hall Modifications Schematic Design and Specification Control Documents Work Statement: Make appropriate detail drawings for Assembly Hall Modifications. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 24 | 0 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 8 | 24 | 0 | 0 | 0 | 0 | 5006.4 | 648.8 | 1946.4 | 0 | 0 | 7601.6 | 9502 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | Technical Scope: Review Assembly Hall Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | Technical Scope: Address Action Items from Assembly Hall Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S343300 | Design/Safety Reviews Complete, Assembly Hall Modifications Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | Technical Scope: Prepare Assembly Hall Modifications Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | Technical Scope: Evaluate & Process Assembly Hall Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S342800 /S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 90 | 0 | 0 | 0 | 0 | 0 | 144 | 144 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% | No real modifications needed except to support assembly operations. Estimate $10K for minor modifications. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 144 | 24 | 48 | 0 | 0 | 0 | 0 | 15019.2 | 1946.4 | 3892.8 | 0 | 0 | 20858.4 | 26073 | 14000
S343700 | Perform Assembly Hall Modifications Components Acceptance | Technical Scope:Perform Assembly Hall Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
S343800 | Assembly Hall Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Administrator ADMIN1 PO | Scientist | Scientist |  |  | Engineer | Engineer/Professional |  |  |  | Designer | Designer/Drafter | [5 empty] | Technician | Technicians | [8 empty] | Trade | Bargaining Unit Trades |  |  |  |  | Student (unpaid)
[6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech Mech TECH3 PO D | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3
|  |  |  | Hours | Hours | Scientist | Scientist | Scientist | Hours |  |  |  |  | Hours | [6 empty] | Hours | [9 empty] | Hours | [5 empty] | Hours
|  | Resource Summary for Facility Support Systems, Safety Systems and Non-IR Infrastructure in Hours by Resource Type |  | 0 | 55 | 0 | 55 | 0 | 2224 | 2184 | 0 | 40 | 0 | 980 | 232 | 0 | 0 | 748 | 0 | 0 | 636 | 0 | 8 | 0 | 436 | 128 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | checksum for hours | 3895

## Cryo Support Work Package
Return to Navigation Page
WBS # | 2.04.02.01 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Magnet Cryo, Electrical & Control Structural Support in IR | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S337300 /S337310 | Create Cryo Routing in IR Layout Drawings | Technical Scope: Evaluate and model the system requiremenrts for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 0 |  | 0 | 0 | 0 | 56 | 32 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 40 | 0 | 0 | 0 | 24 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 56 | 24 | 40 | 0 | 0 | 0 | 0 | 5840.8 | 1946.4 | 3244 | 0 | 0 | 11031.2 | 13789 | 0
S337400 | Create Cryo Structural Support in IR Detail & Assembly Drawings | Technical Scope: Create Structural Support assembly drawings for Cryo Structural supports in the IR Work Statement: Make appropriate detail drawings for Cryo Structural Supports. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S337500 | Review Magnet Cryo, Electrical & Control Structural Support in IR Design/Safety | Technical Scope: Review the Cryo structural supports design/safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 0 | 0 | 0 | 1158.8 | 1448.5 | 0
S337600 | Address Action Items from Cryo Structural Support in IR Detail Design & Safety Reviews | Technical Scope: Address action items from the design and safety reviews. Work Statement: Evaluate committee action items and address appropriately. | 5 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 324.4 | 0 | 0 | 0 | 1993.2 | 2491.5 | 0
S337700 | Design/Safety Reviews Complete, Magnet Cryo, Electrical & Control Structural Support in IR Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1946.4 | 0 | 0 | 0 | 1946.4 | 2433 | 0
S337800 | Prepare Magnet Cryo, Electrical & Control Structural Support in IR Components Procurement Package(s) | Technical Scope: Prepare the procurement package for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S337900 | Evaluate & Process Magnet Cryo, Electrical & Control Structural Support in IR Components Bids | Technical Scope: Evaluate the bid documents for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S338000 /S337200 | Procure & Deliver Magnet Cryo, Electrical & Control Structural Support in IR Components (leadtime and fabrication included) | Technical Scope: Procure and deliver components to the IR. Work Statement: Track and manage the procurement of all components for this item. | 80 | 0 | 0 |  | 0 | 0 | 0 | 128 | 128 | 0 | . | 0 | 64 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 128 | 64 | 0 | 0 | 0 | 0 | 0 | 13350.4 | 5190.4 | 0 | 0 | 0 | 18540.8 | 23176 | 62500
S338100 | Perform Magnet Cryo, Electrical & Control Structural Support in IR Components Acceptance | Technical Scope: Perform inspection/acceptance tests for the Cryo, Electrical & Control structural supports in the IR. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 648.8 | 0 | 0 | 2317.6 | 2897 | 0
S338200 | Magnet cryo, electrical and control structural support components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 61739.2 | 77174 | 62500 | 50000 | 25% | 25%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 0 | 368 | 168 | 96 | 0 | 0 | 0 | 0 | 38382.4 | 15571.2 | 7785.6 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Beampipe_Vac Work Package
Return to Navigation Page
WBS # | 2.04.02.02 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Beampipe/Vacuum Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S338400 /S338410 | Create Beampipe/Vacuum Layout | Technical Scope: Evaluate and model the system requiremenrts for the Beampipe/Vacuum Layout in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 16 |  | 0 | 16 | 0 | 48 | 32 | 0 | 16 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 16 | 48 | 32 | 0 | 0 | 0 | 0 | 1944 | 5006.4 | 2595.2 | 0 | 0 | 0 | 9545.6 | 11932 | 0
S338500 | Create Beampipe/Vacuum Envelope Drawing | Technical Scope: Create Beampipe/Vacuum Envelope Drawings for the IR. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum envelope. | 10 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1622 | 0 | 0 | 0 | 1622 | 2027.5 | 0
S338600 | Create Beampipe/Vacuum subassembly and detail Drawings | Technical Scope: Create Beampipe/Vacuum subassembly and detail Drawings. Work Statement: Make appropriate detail drawings for the Beampipe/Vacuum subassemblies. | 20 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 3244 | 0 | 0 | 0 | 3244 | 4055 | 0
S338700 S338710 | Review Beampipe/Vacuum Design/Safety | Technical Scope: Review Beampipe/Vacuum Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 4 |  | 0 | 4 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 486 | 834.4 | 324.4 | 0 | 0 | 0 | 1644.8 | 2056 | 0
S338800 S338810 | Address Action Items from Beampipe/Vacuum Design & Safety Reviews | Technical Scope: Address Action Items from Beampipe/Vacuum Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S338900 | Design/Safety Reviews Complete, Beampipe/Vacuum components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S339010 /S339000 | Prepare Beampipe/Vacuum Components Procurement Package(s) Preparation | Technical Scope: Technical Scope: Prepare the procurement package for the Beampipe/Vacuum Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S339100 /S339110 | Evaluate & Process Beampipe/Vacuum Components Bids | Technical Scope: Evaluate & Process Beampipe/Vacuum Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S339200 /S338300 /s339210 | Procure & Deliver Beampipe/Vacuum Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Beampipe/Vacuum Components to the IR. Work Statement: Track and manage the procurement of all components for this item. | 80 | 0 | 0 |  | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% | Beampipe copmponent design is too early to make detailed estimate. Based on similar beampipe sections at PHENIX and assuming the Be beampipe will be used, $50K is a reasonable estimate. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 128 | 64 | 0 | 0 | 0 | 0 | 0 | 13350.4 | 5190.4 | 0 | 0 | 0 | 18540.8 | 23176 | 62500
s339300 /S339310 | Perform Beampipe/vacuum Acceptance | Technical Scope: Perform Beampipe/vacuum inspection and acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 3244 | 0 | 0 | 5561.6 | 6952 | 0
S339400 | Beampipe/Vacuum components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 52395.6 | 65494.5 | 62500 | 50000 | 25% | 25%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 20 | 280 | 216 | 40 | 0 | 0 | 0 | 2430 | 29204 | 17517.6 | 3244 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## IR HVAC Work Package
Return to Navigation Page
WBS # | 2.04.02.03 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| IR HVAC Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S339600 | Model IR HVAC Thermal Requirements | Technical Scope: Model IR HVAC Thermal Requirementsls in the IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S339700 | Create IR HVAC Layout/schematic drawings & Design specification control documents | Technical Scope: Create IR HVAC Layout/schematic drawings & Design specifications . Work Statement: Make appropriate detail drawings for the IR HVAC System. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S339800 | Review IR HVAC Design/Safety | Technical Scope: Review IR HVAC Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 0 | 0 | 0 | 1158.8 | 1448.5 | 0
S339900 | Address Action Items froml IR HVAC Design & Safety Reviews | Technical Scope: Address Action Items from IR HVAC Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S340000 | Design/Safety Reviews Complete, IR HVAC Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S340100 | Prepare IR HVAC Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the procurement package for the IR HVAC Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S340200 | Evaluate & Process IR HVACComponents Bids | Technical Scope: Evaluate & Process IR HVAC Components Bids. Work Statement: Evaluate endor bids, select vendor, place contract with vendor. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S340300 /S339500 | Procure & Deliver IR HVAC Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR HVAC Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 |  | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 25% | 25% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $35K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 96 | 48 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 3892.8 | 0 | 0 | 0 | 13905.6 | 17382 | 43750
S340400 | Perform IR HVAC Components Acceptance | Technical Scope: Perform IR HVAC Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 3244 | 0 | 0 | 5561.6 | 6952 | 0
S340500 | IR HVAC components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 43153.2 | 53941.5 | 43750 | 35000 | 25% | 25%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 0 | 280 | 132 | 40 | 0 | 0 | 0 | 0 | 29204 | 10705.2 | 3244 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Cooling Water Work Package
Return to Navigation Page
WBS # | 2.04.02.04 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| IR Electronics Cooling Water Distribution System Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
s340700 /s340710 | Model IR Electronics Cooling Water Distribution Thermal Requirements | Technical Scope: Model IR Electronics Cooling Water Distribution Thermal Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 |  | 0 | 32 | 0 | 160 | 160 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 160 | 32 | 32 | 0 | 0 | 0 | 3888 | 16688 | 2595.2 | 2595.2 | 0 | 0 | 25766.4 | 32208 | 0
S340800 | Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Control Documents | Technical Scope: Create IR Electronics Cooling Water Distribution Layout/Schematic Drawings & Design Specification Documents Work Statement: Make appropriate detail drawings for the Electronics Cooling Water System. | 40 | 0 | 0 |  | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 64 | 32 | 0 | 0 | 0 | 0 | 0 | 6675.2 | 2595.2 | 0 | 0 | 0 | 9270.4 | 11588 | 0
S340900 | Review IR Electronics cooling water System Design/Safety | Technical Scope: Review IR Electronics cooling water System Design/Safety criteria Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S341000 | Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews | Technical Scope: Address Action Items from IR Electronics Cooling Water Distribution Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S341100 | Design/Safety Reviews Complete, IR Electronics Cooling Water Distribution System Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S341200 | Prepare IR Electronics Cooling Water Distribution System Components Procurement Package(s) | Technical Scope: Technical Scope: Prepare the IR Electronics Cooling Water Distribution System Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 2595.2 | 0 | 0 | 0 | 5932.8 | 7416 | 0
S341300 | Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids | Technical Scope: Evaluate & Process IR Electronics Cooling Water Distribution System Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 0 | 0 | 0 | 4635.2 | 5794 | 0
S341400 /S340600 | Procure & Deliver IR Electronics Cooling Water Distribution Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver IR Electronics Cooling Water Distribution Components to the IR Work Statement: Track and manage the procurement of all components for this item. | 50 | 0 | 0 |  | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 25% | 40% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $65K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M45 | 0 | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 8344 | 3244 | 0 | 0 | 0 | 11588 | 14485 | 91000
S341500 | Perform IR Electronics Cooling Water Distribution System Components Acceptance | Technical Scope: Perform IR Electronics Cooling Water Distribution System Components Acceptance tests Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 20 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 1622 | 0 | 0 | 2780.8 | 3476 | 0
S341600 | IR Electronics Cooling Water Distribution System Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 64608.8 | 80761 | 91000 | 65000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 32 | 408 | 172 | 52 | 0 | 0 | 0 | 3888 | 42554.4 | 13949.2 | 4217.2 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Facility Safety Work Package
Return to Navigation Page
WBS # | 2.04.02.05 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| IR/AH Safety Subsystems Components Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S341800 /S341810 | Analyze IR/AH Safety Subsystems Requirements | Technical Scope: Analyze Off Detector/Carriage Safety Subsystems Requirements.Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 3 |  | 0 | 3 | 0 | 96 | 96 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 3 | 96 | 24 | 48 | 0 | 0 | 0 | 364.5 | 10012.8 | 1946.4 | 3892.8 | 0 | 0 | 16216.5 | 20270.625 | 0
S341900 | Create Schematic Design and Specification Control Documents for IR/AH Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for Off-Detector/Carriage Safety Subsystems Work Statement: Make appropriate detail drawings for Off Detector/Carriage Safety Subsystems. | 30 | 0 | 0 |  | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 60 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 4866 | 0 | 0 | 0 | 14878.8 | 18598.5 | 0
S342000 | Review IR/AH Safety Subsystems Design/Safety | Technical Scope: Review Off Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S342100 | Address Action Items from IR/AH Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from Off Detector/Carriage Safety Subsystems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S342200 | Design/Safety Reviews Complete, IR/AH Safety Subsystems Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S342300 | Prepare IR/AH Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare Off Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S342400 | Evaluate & Process IR/AH Safety Subsystems Components Bids | Technical Scope: Evaluate & Process Off Detector/Carriage Safety Subsystems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S342500 /S341700 | Procure & Deliver IR/AH Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Off Detector/Carriage Safety Subsystems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.. | 60 | 0 | 0 |  | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | $25K for new ODH System needed for Cryo system: ROM estimate. All other off-detector safety systems to be repurposed $7K estimated to effect repurposing. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 0 | 48 | 0 | 0 | 0 | 0 | 10012.8 | 0 | 3892.8 | 0 | 0 | 13905.6 | 17382 | 44800
S342600 | Perform IR/AH Safety Subsystems Components Acceptance | Technical Scope: Perform Off Detector/Carriage Safety Subsystems Components Acceptanc tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 80 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 80 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 6488 | 0 | 0 | 8805.6 | 11007 | 0
S342700 | IR/AH Safety Subsystems Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 71049.7 | 88812.125 | 44800 | 32000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 3 | 432 | 140 | 176 | 0 | 0 | 0 | 364.5 | 45057.6 | 11354 | 14273.6 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Assembly Hall Work Package
Return to Navigation Page
WBS # | 2.04.02.06 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Assembly Hall Modifications | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S342900 | Analyze Assembly Hall Modification Requirements | Technical Scope: Analyze Assembly Hall Modification Requirements Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 |  | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 120 | 24 | 48 | 0 | 0 | 0 | 0 | 12516 | 1946.4 | 3892.8 | 0 | 0 | 18355.2 | 22944 | 0
S343000 | Create Assembly Hall Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Assembly Hall Modifications Schematic Design and Specification Control Documents Work Statement: Make appropriate detail drawings for Assembly Hall Modifications. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 24 | 0 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 8 | 24 | 0 | 0 | 0 | 0 | 5006.4 | 648.8 | 1946.4 | 0 | 0 | 7601.6 | 9502 | 0
S343100 | Review Assembly Hall Modifications Design/Safety | Technical Scope: Review Assembly Hall Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S343200 | Address Action Items from Assembly Hall Modifications Design & Safety Reviews | Technical Scope: Address Action Items from Assembly Hall Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S343300 | Design/Safety Reviews Complete, Assembly Hall Modifications Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S343400 | Prepare Assembly Hall Modifications Components Procurement Package(s) | Technical Scope: Prepare Assembly Hall Modifications Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S343500 | Evaluate & Process Assembly Hall Modifications Components Bids | Technical Scope: Evaluate & Process Assembly Hall Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 10845.6 | 13557 | 0
S342800 /S343600 | Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Assembly Hall Modifications Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 90 | 0 | 0 |  | 0 | 0 | 0 | 144 | 144 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% | No real modifications needed except to support assembly operations. Estimate $10K for minor modifications. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 144 | 24 | 48 | 0 | 0 | 0 | 0 | 15019.2 | 1946.4 | 3892.8 | 0 | 0 | 20858.4 | 26073 | 14000
S343700 | Perform Assembly Hall Modifications Components Acceptance | Technical Scope:Perform Assembly Hall Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
S343800 | Assembly Hall Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hours | hours | hours | hours | hours | hours | hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 76756.8 | 95946 | 14000 | 10000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 0 | 456 | 128 | 232 | 0 | 0 | 0 | 0 | 47560.8 | 10380.8 | 18815.2 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Risk Codes
TABLE 1: Labor risk codes
Code | Type of Estimate | estimate uncertainty % | Description
L1 | Actual | 0% | Actual costs incurred on activities completed to date.
L2 | Level of Effort Tasks | 0%-20% | Support type activities that must be done to support other work activities or the entire project effort, where estimated effort is based on the duration of the activities it is supporting.
L3 | Advanced | 10%-25% | Based on experience with documented identical or nearly identical work. Development of activities, resource requirements, and schedule constraints are highly mature. Technical requirements are very straightforward to achieve.
L4 | Preliminary | 25%-40% | Based on direct experience with similar work. Development of activities, resource requirements, and schedule constraints are defined as preliminary (beyond conceptual) design level. Technical requirements are achievable and with some precedent.
L5 | Conceptual | 40%-60% | Based on expert judgment using some experience as a reference. Development of activities, resource requirements, and schedule constraints are defined at a conceptual level. Technical requirements are moderately challenging.
L6 | Pre-conceptual | 60%-80% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints are defined at a pre-conceptual level. Technical requirements are moderately challenging.
L7 | Rough Estimate | 80%-100% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints is largely incomplete. Technical requirements are challenging.
L8 | Beyond state of the art | > 100% | No experience available for reference. Activities, resource requirements, and schedule constraints are completely undeveloped. Technical requirements are beyond state of the art.
TABLE 2: Material risk codes
Code | Type of Estimate | estimate uncertainty % | Description
M1 | Existing Purchase order | 0% | Items have been completed or obligated. (Note: Contact Change Orders are considered a Risk and should not be included )
M2 | Procurement for LOE/Oversight work | 0%-20% | M&S items such as travel, software purchases and upgrades, computers, etc. estimated to support LOE efforts and other work activities.
M3 | Advanced | 10%-25% | Items for which there is a catalog price or recent vendor quote based on a completed or nearly completed design or an existing design with little or no modifications and for which the costs are documented.
M4 | Preliminary | 25%-40% | Items that can be readily estimated from a reasonably detailed but not completed design; items adapted from existing designs but with moderate modifications, which have documented costs from past projects. A recent vendor survey (e.g., budgetary quote, vendor RFI response) based on a preliminary design belongs here.
M5 | Conceptual | 40%-60% | Items with a documented conceptual level of design; items adapted from existing designs but with extensive modifications, which have documented costs from past projects.
M6 | Pre-conceptual - Common work | 60%-80% | Items that do not have a documented conceptual design, but do have documented costs from past projects. Use of this estimate type indicates little confidence in the estimate. Its use should be minimized when completing the final estimate.
M7 | Pre-conceptual - Uncommon work | 80%-100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Its use should be minimized when completing the final estimate.
M8 | Beyond state of the art | > 100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Technical requirements are beyond the state of the art.
Return to Navigation Page