## Navigation
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  |  | L2 WBS Number/Name |  | L3 Project Name (Control Account) |  | L3 WBS Number
sPHENIX Integration and Installation (click to see WBS structure for this Subsystem) |  |  | 2.05 Integration & Installation |  | Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation (click here for Control Account BoE summary) |  | 2.05.01
Instructions: How to use this document
|  | Work Package Name |  | WBS Number |  | Basis of Estimate Link
|  | Subsystem Interface & Integration Plan |  | 2.05.01 |  | Go To BoE
|  | Infrastructure Installation |  | 2.05.02 |  | Go To BoE
|  | Cradle Carriage Integration/Installation |  | 2.05.03 |  | Go To BoE
|  | sPHENIX SC Magnet Installation |  | 2.05.05 |  | Go To BoE
|  | Outer HCal Integration/Installation |  | 2.05.04 |  | Go To BoE
|  | Inner HCal Integration/Installation |  | 2.05.06 |  | Go To BoE
|  | EMCal Integration/Installation |  | 2.05.07 |  | Go To BoE
|  | TPC Integration/Installation |  | 2.05.08 |  | Go To BoE
|  | INTT Integration/Installation |  | 2.05.09 |  | Go To BoE
|  | MVTX Integration/Installation |  | 2.05.10 |  | Go To BoE
|  | Min Bias Integration/Installation |  | 2.05.11 |  | Go To BoE
|  | sPHENIX Full Detector Installation |  | 2.05.12 |  | Go To BoE
WBS Dictionary for 2.05 Installation and Integration
Description of this Control Account:
Technical Scope: WBS 2.05.01.13 is the Control Account for Project Management costs associated with Integration and Installation. Work Statement: This Control Account encompasses the efforts of the Integration and Installation level 2 manager to manage this subsystem in accordance with the BNL and DOE requirements, including collecting and analyzing management performance data for this subsystem, reporting the data as appropriate and generally assuring that this subsystem meets cost and schedule estimates, and if the subsystem management performance strays from the baseline, implementing appropriate actions to restore performance to the baseline.
Document Control
Version |  | Date | Author(s)
1 |  | 2017-05-19 | D. Lynch
2 |  | 2017-07-27 | D. Lynch
3 |  | 2017-08-03 | D. Lynch
4 |  | 2018-02-13 | D. Lynch | Updated WBS numbering and aligned estimate with P6
5 |  | 2018-02-16 | D.Lynch | updated labor estimates from FTE-days to hours
6 |  | 2018-11-27 | D.Lynch | Updated WBS numbering from 2.10 to 2.05

## Sheet1 (hidden)
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  |  | L2 WBS Number/Name |  | L3 Project Name (Control Account) |  | L3 WBS Number
sPHENIX Integration and Installation (click to see WBS structure for this Subsystem) |  |  | 1.10 Integration & Installation |  | Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation (click here for Control Account BoE summary) |  | 2.05.01
Instructions: How to use this document
|  | Work Package Name |  | WBS Number |  | Basis of Estimate Link
|  | Subsystem Interface & Integration Plan |  | 2.05.01 |  | Go To BoE
|  | Infrastructure Installation |  | 2.05.02 |  | Go To BoE
|  | Cradle Carriage Integration/Installation |  | 2.05.03 |  | Go To BoE
|  | sPHENIX SC Magnet Installation |  | 2.05.05 |  | Go To BoE
|  | Outer HCal Integration/Installation |  | 2.05.04 |  | Go To BoE
|  | Inner HCal Integration/Installation |  | 2.05.06 |  | Go To BoE
|  | EMCal Integration/Installation |  | 2.05.07 |  | Go To BoE
|  | TPC Integration/Installation |  | 2.05.08 |  | Go To BoE
|  | INTT Integration/Installation |  | 2.05.09 |  | Go To BoE
|  | MVTX Integration/Installation |  | 2.05.10 |  | Go To BoE
|  | Min Bias Integration/Installation |  | 2.05.11 |  | Go To BoE
|  | sPHENIX Full Detector Installation |  | 2.05.12 |  | Go To BoE
WBS Dictionary for 1.10 Installation and Integration
Description of this Control Account:
Technical Scope: WBS 2.05.01.13 is the Control Account for Project Management costs associated with Integration and Installation. Work Statement: This Control Account encompasses the efforts of the Integration and Installation level 2 manager to manage this subsystem in accordance with the BNL and DOE requirements, including collecting and analyzing management performance data for this subsystem, reporting the data as appropriate and generally assuring that this subsystem meets cost and schedule estimates, and if the subsystem management performance strays from the baseline, implementing appropriate actions to restore performance to the baseline.
Document Control
Version |  | Date | Author(s)
1 |  | 2017-05-19 | D. Lynch
2 |  | 2017-07-27 | D. Lynch
3 |  | (in progress) | D. Lynch

## Int & Inst Structure
Return to Navigation Page
| Subsystems | 2.05: sPHENIX Installation and Integration
| Control Accounts |  | 2.05.01: Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation
| Work Packages |  |  | 2.05.01: Subsystem Interface & Integration Plan
2.05.02: Infrastructure Installation
2.05.03: Cradle Carriage Integration/Installation
2.05.04: Outer HCal Integration/Installation
2.05.05: sPHENIX SC Magnet Installation
2.05.06: Inner HCal Integration/Installation
2.05.07: EMCal Integration/Installation
2.05.08: TPC Integration/Installation
2.05.09: INTT Integration/Installation
2.05.10: MVTX Integration/Installation
2.05.11: Min Bias Integration/Installation
2.05.12: sPHENIX Full Detector Installation
2.05.01.13: Integration and Installation Project Management and Oversight

## Int & Inst Dictionary
WBS 2.05 Integration and Installation Dictionary
Return to Navigation Page
WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.05 | WBS Item Definition
Integration and Installation
2.05.01 | Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation | Technical Scope: WBS 2.05.01 is the Control Account for all scientific, engineering and technical staff efforts to plan, execute and supervise all aspects of the assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics for the sPHENIX MIE (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02) and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This Control Account encompasses the planning for and all of the actual installation and commissioning of these components will take place at the sPHENIX experiment complex at building 1008. There are 12 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook.
2.05.01 | Subsystem Interface & Integration Plan | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to plan and supervise all aspects of the final assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02), and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This work package includes the preparation, creation and review of the following written and controlled documents: 1. Subsystem Interface & Integration Plan - Plan to describe and define all interfaces between WBS subsystems., including detector mechanical interfaces, electrical intefaces, conduits and cable routing management, space allocation, cooling (water and air), detector cryogenic, inerting, drying, etc. gas supply routing and interfaces. 2. Subsystem Initial and Final Envelope Drawings - Drawings to globally and locally (for each detector subsystem) define space allocation for detector subsystems, infrastructure, support services and potential future additions. 3. Cable and Services Management Plans - Overall plan for routing electrical and optical, power, signal, control and monitoring cables between detectors to control racks, front end modules, patch panels, data acquisition, etc. 4. Survey Plan - Overall plan for alignment and positioning of overall detector relative to nominal beam orbit, individual detector subsystems to the overall detector, and internal alignment and positioining of detector subsystem internal components to the subsystem overall alignment. After review of each of the items in this work package, satisfaction of all action items coming out of the reviews corresponds to successful completion of the work package.
S344300 | Create Subsystem Interface & Integration Plan | Technical Scope: Preparation of an Interface and Integration Plan. Work Statement: Gather information about all sPHENIX subsystems (dimensions, tolerances required services, environmental requirements, etc.) and create a unified plan to integrate all of the subsystems into the single sPHENIX experiment.
S344400 | Create Subsystem Initial Envelope Drawings | Technical Scope: Creation of initial envelope drawings for all subsystems. Work Statement: prepare drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Iterate drawings to reolve conflicts between subsystems.
S344500 | Create Subsystem Outline/Interface Drawings | Technical Scope: Creation of final envelope drawings for all subsystems. Work Statement: Finalize drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Freeze envelopes and interfaces at final design.
S344600 | Create Cable Management Plan | Technical Scope: Create Cable Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing and supporting canl;es/fibers and related services for all sPHENI detectors.
S344700 | Create Services Management Plan | Technical Scope: Create Servces Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing cooling, gas, etc between source and distribution panels and from there to detector electronics, control racks, front end modules, etc. (does not include cryogenics - see magnet for Cryo services)
S344800 | Create Survey Plan | Technical Scope: Create Survey plan for all detector subsystems. Work Statement: Prepare an overall plan for aligning each of the sPHENIX subsystems into the total experiment, preserving the dimensional alignments and performance requirements . Plan will determine how achieving this alignment will be implemented in the subsystems design and how this alignment will be erified and documented by RHIC surveyors.
S345000 | Review Integration and Installation Plan Design/Safety | Technical scope: Preparation for and execution of review for Engineering and safety review of Integration and Installation Plan. Work Statement: gather documentation describing the design and analyses of the integration and installation of all sPHENIX subsystems. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management.
S345100 | Review Cable Management Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Cable management Plan Plan. Work Statement: gather documentation describing the design and analyses of the cable management plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management.
S345200 | Review Survey Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Surey Plan Plan. Work Statement: gather documentation describing the design and analyses of thesurvey plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management.
S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey Plans) Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from subsystem Interface Integrationand Installation, cable management and survey plans engineering and safety reviews. Work Statement: receive action items from reviewers, evaluate action items implement changes, modifications to plans to appropriately satisfy each action item.
| Design/Safety Reviews Complete, Ready to Begin Installation | milestone
2.05.02 | Infrastructure Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install Infrastructure components and equipment in support of the sPHENIX detectors at 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.04: sPHENIX Infrastructure, and/or the specific detector subsystems (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific Infrastructure installation tasks detailed in this work package are: 1. Line electric power distribution installation 2. Magnet cryogenic and electrical supply services structural support and cable/cryo fluids lines management installation. 3. Beampipe/vacuum equipment installation 4. IR HVAC equipment installation 5. On-detector and off-detector safety subsystems installation 6. Detector support services systems installations (signal, power and monitoring cable and fiber, services management and structural support, etc.) 7. Electronics racks installation (including patch panels) 8. Gas and cooling systemequipment and services installation. (including source, distribution monitoring and control systems) 9. Detector access and work platforms installation. 10. Non-IR infrastructure installation. (Including gas pad, gas mixing house, control room, rackroom, assembly areas and offices components and equipment)
S346000 / S346100 | Install Line Electric Power Distribution | Technical Scope: All tasks related to the installation of Line electric power distribution for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S346500 / S346510 | Install Cryogenics Supply Structural Suport | Technical Scope: All tasks related to the installation of cryo supply structural support (including power and control cables) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S346300 / S346310 | Install Beampipe/Vacuum | Technical Scope: All tasks related to the installation of beam/vacuum components and support structures) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S345500 | Install IR HVAC | Technical Scope: All tasks related to the installation of IR/HVAC components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S347600 / S347700 | Install IR Electronics Cooling Water | Technical Scope: All tasks related to the installation of electronics cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S345700 / S345800 | Install On Detector and Off Detector Safety Subsystems | Technical Scope: All tasks related to the installation of On-detector and Off-detector components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S346900 | Install Detector Support Services Systems | Technical Scope: All tasks related to the installation of Detector support services components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S347100 / S347200 | Install Electronics Racks | Technical Scope: All tasks related to the installation of electronic racks and related generic equipment components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S3437400 | Install Gas and Cooling System Services | Technical Scope: All tasks related to the installation of gas and cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
S3346700 / S346710 | Install Non-IR Infrastructure | Technical Scope: All tasks related to the installation of non-IR infrastructure components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure.
2.05.03 | Cradle Carriage Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install cradle carriage components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.03: sPHENIX Infrastructure, and more specifically in WBS 2.03 (see WBS 2.03 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Cradle Carriage Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures 3. Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation 4. Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/Address action Items 5. Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports (These components procurement, fabrication, pre-assembly, acceptance testing and delivery to 1008 AH covered in WBS 2.03 work packages) 6. Assemble HCal cradle onto base 7. Install magnet mounting feet 8. Install platforms & access 9. Install Pole Tips Although these tasks are included in a single work package, these tasks are interlaced with installation tasks for the various detector subsystems that this carriage cradle supports, directly or indirectly. See the BOE's for WBS 2.05.01.04 through 2.05.01.12 for details on these related installation work packages and see the Installation and Integration MS Project file for linkage between these work packages
S347900 / S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of cradle carriage Integration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation.
S348000 / S348010 / S348100 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX Cradle/carriage. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items.
S348200 / S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation | Technical Scope: Create a written integration /installation procedure for the assembly of the cradle carriage in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX cradle carriage.
S348300 / S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX cradle carriage assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX cradle carriage and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required.
S348400 / S348810 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from cradle carriage Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S348500 | Design/Safety Reviews Complete, Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Ready for service | milestone
S348600 | Ready to Assemble Cradle Carriage in AH | milestone
S348700 / S348710 / S348800 | Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports | Technical scope: Assembly and installation of cradle base. Work Statement: Using work plan/permit, tooling and fixtures, installthe cradle carriage roller system, base plate and relevant alignment provisions.
S348900 / S348910 / S349000 | Assemble HCal cradle onto base | Technical scope: Installation/assembly of cradle onto base Work Statement: Using work plan/permit, tooling and fixtures, install the cradle onto the carriage base plate and relevant alignment provisions.
S349100 / S349200 | Install magnet mounting feet | Technical scope: Installation of magnet mounting feet onto the HCal sectors installed on carriage cradles. (Note the installation of the Outer HCal sectors is described in WBS 2.05.01.04 The Magnet is installed before the upper HCal sectors are installed (see WBS 2.05.01.05 for Magnet installation details). Work Statement: Using work plan/permit, tooling and fixtures, install the magnet mounting feet and relevant alignment provisions onto the HCal sectors.
S349300 / S349310 / S349400 | Install platforms & access | Technical scope: Installation of platforms and access onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the work platforms, access and related components onto the cradle base.
S349500 / S349510 / S349600 | Install Pole Tips | Technical scope: Installation of end caps/pole tips onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the end caps/pole tips and related components onto the cradle base.
2.05.04 | Outer HCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Outer Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, the reviews of these analyses and the assembly and testing of Outer HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Outer HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures 3. Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification and address action items 5. Transport Assembled Outer HCal Sectors to AH (Partial Shipment) (procurement, fabrication, assembly, testing and delivery to BNL of Outer HCal sectors and services covered in WBS 1.4 work packages) 6. Install Partial Outer HCal for SC Magnet Install (NOTE: at this point in the installation, the sPHENIX superconducting solenoid magnet must be installed. Refer to WBS # 2.05.01.05 for info on that work package) 7. Transport Remainder of Outer Hcal Sectors to AH 8. Install Remainder of Outer HCal Sectors 9. Align/Survey Outer HCal to SC Magnet Centerline 10. Install Outer HCal Cables and Services 11. Review Outer HCal for Operational Readiness (ORR)/ address action items 12. Commission Outer HCal
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Outer HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Outer HCal sectors during assembly. The design of those tools is covered in WBS 1.04, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated, and the design of the installation tools will need to be modified from the assembly handling tools to include provision for fine adjustment of orientation to allow the sectors to be installed in 32 different orientations.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Outer HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding, and sector assembly spreader tools for installing the Outer HCal sectors and services.
S349900 / S350000 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Outer HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Sc Magnet assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Outer HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Outer HCal and its services (e.g. critical lift calculations, etc.)
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Outer HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Outer HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S350400 | Design/Safety Reviews Complete, Outer HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S350500 | Outer HCal Sectors Ready for Installation | milestone
S350600 / S350700 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) | Technical scope: Transport first 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage.
S350800 / S350900 | Install Partial Outer HCal for SC Magnet Install | Technical scope: Install lower 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure.After these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package)
S351000 / S351100 | Transport Remainder of Outer Hcal Sectors to AH | Technical scope: After the sPHENIX SC Magnet is be installed (see 1.10.2.4 for SC Magnet installation work package), transport remaining 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage.
S351200 / S351300 | Install Remainder of Outer HCal Sectors | Technical scope: Install upper 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure. before these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package)
S351400 / S351410 / S351500 | Align/Survey Outer HCal to SC Magnet Centerline | Technical scope: Align all Outer HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Outer HCal and the cradle carriage, align the Outer HCal to to the nominal IP and beam RHIC axis in accordance with the Outer HCal installation procedure and work permit.
S351600 / S351700 | Install Outer HCal Cables and Services | Technical scope: Install all Outer HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Outer HCal services onto the sPHENIX cradle carriage.
S351800 | Review Outer HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Outer HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Outer HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S351900 | Address Action Items from Outer Hcal ORR | Technical scope: evaluation and implementation of recommendations from Outer HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S352000 / S352100 / S352200 | Commission Outer HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Outer HCal. Work Statement: Perform operational checks on HCal operational and control equipment, . Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.05 | sPHENIX SC Magnet Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Superconducting Solenoid Magnet components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed (including cryogenic delivery, current supply to the magnet control and monitoring of the magnet and magnet equipment safety systems such as quench protection), the design, procurement and acceptance of such equipment, reviews of these analyses, modification of the BABAR magnet to accomodate the sPHENIX detector design and magnet performance/quality testing are not in the scope of this work package but rather are part of sPHENIX WBS 2.02: sPHENIX Magnet and WBS 2.04 Infrastructure (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures 2. Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures 3. Prepare SC Magnet Integration/Installation Procedures 4. Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/ Address Action Items 5. Transport SC Magnet and services from 912 to AH (procurement, fabrication, assembly, testing and delivery to BNL of Magnet, Magnet modifications and services covered in WBS 2.02 work packages) 6. Install SC Magnet on Cradle Carriage 7. Align/Survey SC Magnet to Cradle Carriage 8. Prep SC Magnet for Run (Cryo) 9. Prep SC Magnet for Run (Electric) 10. Review SC Magnet for Operational Readiness (ORR)/Address Action Items
S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures | Technical Scope: All tasks related to the design of SC Magnet Integeration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation.
S352400 / S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX SC Magnet. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items.
S352600 | Prepare SC Magnet Integration/Installation Procedures | Technical Scope: Create a written integration /installation procedure for the assembly of the SC Magnet in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX SC Magnet.
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX SC Magnet and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required.
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from SC Magnet Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S352900 | Design/Safety Reviews Complete, sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S353000 | Ready to Install SC Magnet | milestone
S353100 / S353110 / S353200 | Transport SC Magnet from 912 to AH | Technical scope: Transportation of SC Magnet from 912 to 1008 AH by BNL riggers. Work Statement: In accordance with work plan/permit, tooling and fixtures, transport the SC Magnet from 912 to 1008, taking care to handle the Magnet and its services with appropriate care.
S353300 / S353310 / S353400 | Install SC Magnet on cradle carriage | Technical scope: Installation of SC Magnet onto lower half of Outer HCal previously mounted to cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, install the SC Magnet onto the cradle carriage.
S353500 / S353510 / S353600 | Align/Survey SC Magnet to cradle carriage | Technical scope: Alignment of SC Magnet with respect to nominal IP and beam axis related via the cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, and the SC Magnet Alignment specifications, align the SC Magnet to the nominal IP and beam RHIC axis with the assistance of BNL sureyors.
S353700 / S353710 / S353800 | Prep SC Magnet for Run (Cryo) | Technical scope: Preparation/Installation and commissioning of Cryo system for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Cryo techs. CAD Cryo tech efforts and all cryo equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD cryo technicians in preparing the cryo serices for the SC Magnet.
s353900 / S353910 / S354000 | Prep SC Magnet for Run (Electric) | Technical scope: Preparation/Installation and commissioning of electrical power, monitoring and safety systems for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Electrical techs and engineers. CAD electrical tech efforts and all electrical equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD electrical technicians in preparing the electrical serices for the SC Magnet.
S354100 / S354110 | Review SC Magnet for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the SC Magnet and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Magnet will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S354200 / S354210 | Address Action Items from SC Magnet ORR | Technical scope: evaluation and implementation of recommendations from SC Magnet ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
2.05.06 | Inner HCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Inner Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Inner HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Inner HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures 3. Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/address action items 5. Transport assembled Inner HCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of Inner HCal sectors, services and assembly end rings covered in WBS 1.04 work packages) 6. Install Inner HCal assembly Insertion Fixture 7. Install Inner HCal assembly on Insertion Fixture 8. Install 1st Inner HCal Support Ring 9. Install Inner HCal 10. Install 2nd Inner HCal Support Ring 11. Align/Survey Inner HCal to SC Magnet Centerline 12. Install Inner HCal Cables and Services 13. Review Inner HCal for Operational Readiness (ORR)/adderess action items 14. Commission Inner HCal
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Inner HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Inner HCal sectors during assembly. The design of those tools is covered in WBS 1.4, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Inner HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing the Inner HCal sectors into an integrated Inner HCal detector then installing this detector inside the SC Magnet and for installing Inner HCal services.
S354500 / S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Inner HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Outer HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Inner HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Inner HCal and its services (e.g. critical lift calculations, etc.)
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Inner HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Inner HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S355000 | Design/Safety Reviews Complete, Inner HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S355100 | Inner HCal Sectors Ready for Installation | milestone
S355200 / S355300 | Transport assembled Inner HCal Sectors to AH | Technical scope: Transport all 32 Inner HCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all Inner HCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full Inner HCal assembly.
S355400 / S355500 | Install Inner HCal assembly Insertion Fixture | Technical scope: Install the Inner HCal insertion fixture in the sPHENIX Assembly Hall (AH). Work Statement: sPHENIX technicans assemble the Inner HCal insertion fixture in the sPHENIX AH next to the sPHENIX cradle carriage (which by the time the Inner HCal is ready for insertion will have all of the Outer HCal and SC Magnet fully installed) in accordance with the Inner HCal installation procedure and work permit.
S355600 / S355700 | Install Inner HCal assembly on Insertion Fixture | Technical scope: Install all 32 Inner HCal sectors into full Inner HCal detector on the Inner HCal insertion fixture in the sPHENIX Assembly Hall. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install all 32 Inner HCal sectors between the Inner HCal assembly rings on the Inner HCal insertion fixture in accordance with the Inner HCal installation procedure and work permit.
S355800 / S355900 | Install 1st Inner HCal Support Ring | Technical scope: Install first (south side) Inner HCal support ring. Work Statement: sPHENIX technicans install the south Inner HCal support ring and align it appropriately with the sPHENIX SC Magnet in accordance with the Inner HCal installation procedure and work permit.
S356000 / S356100 | Install Inner HCal | Technical scope: Install the 32 Inner HCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the Inner HCal insertion fixture, install the Inner HCal assembly into the sPHENIX SC Magnet and attach the end ring on the south side to the south Inner HCal support ring, in accordance with the Inner HCal installation procedure and work permit.
S356200 / S356300 | Install 2nd Inner HCal Support Ring | Technical scope:Install first (north side) Inner HCal support ring. Work Statement: sPHENIX technicans install the north Inner HCal support ring and attach to the north side Inner HCal end ring. Attach the support ring to the outer HCal in accordance with the Inner HCal installation procedure and work permit.
S356400 / S356410 / S356500 | Align/Survey Inner HCal to SC Magnet Centerline | Technical scope: Align all Inner HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Inner HCal support rings, align the Inner HCal to the SC Magnet in accordance with the Inner HCal installation procedure and work permit.
S356600 / S356700 | Install Inner HCal Cables and Services | Technical scope: Install all Inner HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Inner HCal services onto the sPHENIX cradle carriage.
S356800 | Review Inner HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Inner HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Inner HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S356900 | Address Action Items from Inner Hcal ORR | Technical scope: evaluation and implementation of recommendations from Inner HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S357000 / S257100 / S357200 | Commission Inner HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Inner HCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.07 | EMCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Electromagnetic Calorimeter (EMCal) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of EMCal detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of EMCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.03: sPHENIX Electromagnetic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design EMCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures 3. PrepareEMCal Integration/Installation Tooling/Fixtures Procedures 4. Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled EMCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of EMCal sectors and services covered in WBS 1.03 work packages) 6. Install EMCal Sectors 7. Align/Survey EMCal to SC Magnet Centerline 8. Install EMCal Cables and Services 9. Review EMCal for Operational Readiness (ORR); address action items 10. Commission EMCall
S357400 | Design EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of EMCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of EMCal sectors during assembly. The design of those tools is covered in WBS 1.03, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for EMCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing this detector inside the SC Magnet onto rails attached to the Inner HCal and for installing EMCal services.
S357500 / S357600 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of EMCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S357700 | PrepareEMCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the EMCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the EMCal and its services.
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX EMCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from EMCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S358000 | Design/Safety Reviews Complete, EMCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S358100 | EMCal Sectors Ready for Installation | milestone
S358200 / S358300 | Transport Assembled EMCal Sectors to AH | Technical scope: Transport all 64 EMCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all EMCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full EMCal assembly.
S358400 / S358500 | Install EMCal Sectors | Technical scope: Install the 64 EMCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the EMCal sector insertion fixture, install the EMCal sectors, one at a time, south sectors then north sector with one south and one north sector mated to each of the Inner HCal sectors, into the sPHENIX SC Magnet and attach to the mated Inner HCal sector by the bearing rails, in accordance with the EMCal installation procedure and work permit.
S358600 / S358610 / S358700 | Align/Survey EMCal to SC Magnet Centerline | Technical scope: Align all EMCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the EMCal support rings, align the EMCal to the SC Magnet in accordance with the EMCal installation procedure and work permit.
S358800 / S358900 | Install EMCal Cables and Services | Technical scope: Install all EMCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all EMCal services onto the sPHENIX cradle carriage.
S359000 | Review EMCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the EMCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the EMCal will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S359100 | Address Action Items from EMCal ORR | Technical scope: evaluation and implementation of recommendations from EMCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S359200 / S359300 / S359400 | Commission EMCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the EMCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.08 | TPC Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Time Projection Chamber (TPC) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of TPC detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of TPC performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.02: sPHENIX Time Projection Chamber. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design TPC Integration/Installation Tooling/Fixtures 2. Fabricate/Procure TPC Integration/Installation Tooling/Fixtures 3. Prepare TPC Integration/Installation Tooling/Fixtures Procedures 4. Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled TPC Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of TPV components and services covered in WBS 1.02 work packages) 6. Install TPC Support 7. Install TPC (Mechanical) 8. Align/Survey TPC to SC Magnet Centerline 9. Install TPC Cables and Services 10. Review TPC for Operational Readiness (ORR); address action items 11. Commission TPC
S359600 | Design TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of TPC Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of TPC sectors during assembly. The design of those tools is covered in WBS 1.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for TPC Lifting and insertion/positioning fixtures for installing this detector inside the SC Magnet and for installing TPC services.
S359700 / S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of TPC Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal and EMCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the TPC detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the TPC and its services .
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX TPC and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from TPC Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S360200 | Design/Safety Reviews Complete, TPC Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S360300 | TPC Ready for Installation | milestone
S360400 / S360410 / S360500 | Transport Assembled TPC Sections to AH | Technical scope: Transport TPC detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all TPC components to 1008 AH.
S360700 / S360800 | Install TPC Support | Technical scope: Install the TPC detector permanent structural support and alignment components into the SC Magnet and any temporary support equipment (e.g. scaffolding, temporary Work Statement: sPHENIX technicans, using the TPC custom and generic tooling, install the TPC permanent structural support components in accordance with the TPC installation procedure and work permit.
S360900 / S361000 | Install TPC (Mechanical) | Technical scope: Install the TPC detector assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the TPC detector insertion fixture, install the TPC detector, in accordance with the TPC installation procedure and work permit.
S361100 / S361110 / S361200 | Align/Survey TPC to SC Magnet Centerline | Technical scope: Align all TPC sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the TPC permanent support structure, align the TPC to the SC Magnet in accordance with the TPC installation procedure and work permit.
S361300 / S361400 | Install TPC Cables and Services | Technical scope: Install all TPC services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all TPC services onto the sPHENIX cradle carriage.
S361500 | Review TPC for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the TPC and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the TPC will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S361600 | Address Action Items from TPC ORR | Technical scope: evaluation and implementation of recommendations from TPC ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S361700 / S361800 / S361900 | Commission TPC | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the TPC. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.09 | INTT Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Intermediate Silicon Strip Tracker (INTT) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of INTT detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of INTT performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.01: sPHENIX Intermediate Silcon Strip Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design INTT Integration/Installation Tooling/Fixtures 2. Fabricate/Procure INTT Integration/Installation Tooling/Fixtures 3. Prepare INTT Integration/Installation Tooling/Fixtures Procedures 4. Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled INTT Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of INTT components and services covered in WBS 3.11 work packages) 6. Install INTT Support 7. Install INTT (mechanical) 8. Align/Survey INTT to SC Magnet Centerline 9. Install INTT Cables and Services 10. Review INTT for Operational Readiness (ORR); address action items from INTT ORR 11. Commission INTT
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 0
S362100 / S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of INTT Integration and Installation tooling components for sPHENIX. (Note: see next task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the INTT detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the INTT and its services .
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX INTT and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from INTT Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S362600 | Design/Safety Reviews Complete, INTT Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S362700 | INTT Ready for Installation | milestone
S362800 / S362900 | Transport Assembled INTT Sections to AH | Technical scope: Transport INTT detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all INTT components to 1008 AH.
S363000 / S363100 | Install INTT Support | Technical scope: Install the INTT detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector structural supports, in accordance with the INTT installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports.
S363200 / S363300 | Install INTT (mechanical) | Technical scope: Install the INTT detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector, in accordance with the INTT installation procedure and work permit.
S363400 / S363410 / S363500 | Align/Survey INTT to SC Magnet Centerline | Technical scope: Align all INTT sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the INTT permanent support structure, align the INTT to the SC Magnet in accordance with the INTT installation procedure and work permit.
363600 / S363700 | Install INTT Cables and Services | Technical scope: Install all INTT services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all INTT services onto the sPHENIX cradle carriage.
S363800 | Review INTT for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the INTT and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the INTT will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S363900 | Address Action Items from INTT ORR | Technical scope: evaluation and implementation of recommendations from INTT ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S364000 / S364100 / S364200 | Commission INTT | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the INTT. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.10 | MVTX Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Monolithic Active Pixel Vertex Detector (MVTX) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of MVTX detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of MVTX performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.02: sPHENIX Monolithic Active Pixel Vertex Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design MVTX Integration/Installation Tooling/Fixtures 2. Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures 3. Prepare MVTX Integration/Installation Tooling/Fixtures Procedures 4. Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled MVTX Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of MVTX components and services covered in WBS 3.02 work packages) 6. Install MVTX Support 7. Install MVTX (mechanical) 8. Align/Survey MVTX to SC Magnet Centerline 9. Install MVTX Cables and Services 10. Review MVTX for Operational Readiness (ORR); address action items from MVTX ORR 11. Commission MVTX
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of MVTX Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of MVTX sectors during assembly. The design of those tools is covered in WBS 3.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for MVTX Lifting and insertion/positioning fixtures for installing this detector inside the TPC and the magnet and for installing MVTX services.
S364400 / S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of MVTX Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the MVTX detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the MVTX and its services .
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX MVTX and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from MVTX Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S364900 | Design/Safety Reviews Complete, MVTX Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S365000 | MVTX Ready for Installation | milestone
S365300 / S365400 | Transport Assembled MVTX Sections to AH | Technical scope: Transport MVTX detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all MVTX components to 1008 AH.
S365500 / S365600 | Install MVTX Support | Technical scope: Install the MVTX detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector structural supports, in accordance with the MVTX installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports.
2.05.01.10.10 | Install MVTX (mechanical) | Technical scope: Install the MVTX detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector, in accordance with the MVTX installation procedure and work permit.
S366700 / S366710 / S366800 | Align/Survey MVTX to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit.
S366900 / S367000 | Install MVTX Remaining Cables and Services | Technical scope: Install all MVTX services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all MVTX services onto the sPHENIX cradle carriage.
S367100 / S367200 | Review MVTX for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the MVTX and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the MVTX will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S367300 / S367400 | Address Action Items from MVTX ORR | Technical scope: evaluation and implementation of recommendations from MVTX ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S367500 / S367600 | Commission MVTX | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the MVTX. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.11 | Min Bias Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Minimum Bias Tracker (Min Bias) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of Min Bias detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Min Bias performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.07: sPHENIX Minimum Bias tracker. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Min Bias Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures 3. Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures 4. Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled Min Bias Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of Min Bias components and services covered in WBS 1.07 work packages) 6. Install Min Bias Support 7. Install Min Bias (mechanical) 8. Align/Survey Min Bias to SC Magnet Centerline 9. Install Min Bias Cables and Services 10. Review Min Bias for Operational Readiness (ORR); address action items from Min Bias ORR 11. Commission Min Bias
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Min Bias Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Min Bias sectors during assembly. The design of those tools is covered in WBS 1.07. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Min Bias Lifting and insertion/positioning fixtures for installing this detector inside the SCMagnet and for installing Min Bias services.
S367800 / S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Min Bias Integration and Installation tooling components for sPHENIX. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements.
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Min Bias detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Min Bias and its services .
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Min Bias and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary.
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Min Bias Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S368300 | Design/Safety Reviews Complete, Min Bias Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone
S368400 | Min Bias Ready for Installation | milestone
S368500 / S368600 | Transport Assembled Min Bias Sections to AH | Technical scope: Transport Min Bias detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all Min Bias components to 1008 AH.
S368700 / S368800 | Install Min Bias Support | Technical scope: Install the Min Bias detector assembly structural support into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector structural supports, in accordance with the Min Bias installation procedure and work permit.
S368900 / S369000 | Install Min Bias (mechanical) | Technical scope: Install the Min Bias detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector, in accordance with the Min Bias installation procedure and work permit.
S369100 / S369110 / S369200 | Align/Survey Min Bias to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit.
S369300 / S369400 | Install Min Bias Cables and Services | Technical scope: Install all Min Bias services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Min Bias services onto the sPHENIX cradle carriage.
S269500 | Review Min Bias for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S269600 | Address Action Items from Min Bias ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S369700 / S369800 / S369900 | Commission Min Bias | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Min Bias. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
2.05.12 | sPHENIX Full Detector Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts tomove the sPHENIX support carriage qwith the larger detector components mostly installed align the carrtiage ctradle to the beam line, then, after all of the inner detecors not previously installed are installed, commission the full detectro and make it ready for sPHENIX run 1. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Move Full sPHENIX to IR 2. Align Full sPHENIX to Nominal Beamline and IP 3. Perform Full System Commissioning 4. Review the Full sPHENIX Detector for Operational Readiness (ORR)/Address action items
S370000 / S370100 | Move Full sPHENIX to IR | Technical Scope: All efforts related to the relocation of the partially assembled sPHENIX experimetal equipment, mounted on the sPHENIX cradle carriage from the assembly hall (AH) to the interaction region (IR). The Calorimeter detectors (Outer and Inner detector, and the TPC tracker), the SC Magnet and all of its on-carriage support services, the end caps/pole tips and all on carriage work platforms and related access components will be fully installed, aligned and partially commissioned at this point. The INTT, MVTX and MBD subsystems (detectors and support ing services/equipment) will be installed, aligned and commissioned after the carriage is moved to the IR. Work Statement: gather Move the carriage from the AH to the IR. sPHENIX technicians will perform this task using existing hydraulic rams (repurposed from PHENIX hydraulic system used to drive carriages in and out of the IR.
S370200 / S370210 / S370300 | Align Full sPHENIX to Nominal Beamline and IP | Technical scope: Align the cradle carriage with its partial complement of subsystems to the nominal RHIC beamline and the sPHENIX interaction Point (IP). Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the cradle carriage align cradle carriage with the nominal RHIC beam path and the sPHENIX IP in accordance with the integration/installation plan/procedure and work permit.
S370400 | sPHENIX Installation Complete (MIE) | milestone
#REF! | Full System Commissioning (MIE + INTT + MVTX) | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of all sPHENIX MIE subsystems as a fully integrated system. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation.
S370600 | Full sPHENIX Detector Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management.
S370700 | Address Action Items from Full sPHENIX Detector ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item.
S370800 | All Design/Safety/Readiness Reviews Complete, sPHENIX Ready for Operations | milestone
2.05.01.13 | Integration and Installation Management | Technical Scope: WBS 2.05.01.13 is the Control Account for Project Management costs associated with Integration and Installation. Work Statement: This Control Account encompasses the efforts of the Integration and Installation level 2 manager to manage this subsystem in accordance with the BNL and DOE requirements, including collecting and analyzing management performance data for this subsystem, reporting the data as appropriate and generally assuring that this subsystem meets cost and schedule estimates, and if the subsystem management performance strays from the baseline, implementing appropriate actions to restore performance to the baseline.

## BoE for Int & Inst Tasks
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) | [5 empty] | Date of Est: | 2017-03-19
[10 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  |  | WBS number: | [5 empty] | Control Account
Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation |  |  |  |  | 2.05.01 | [5 empty] | TBD
WBS Dictionary Definition:
Technical Scope: WBS 2.05.01 is the Control Account for all scientific, engineering and technical staff efforts to plan, execute and supervise all aspects of the assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics for the sPHENIX MIE (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02) and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This Control Account encompasses the planning for and all of the actual installation and commissioning of these components will take place at the sPHENIX experiment complex at building 1008. There are 12 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook.
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
All supporting documents are provided or linked to in this workbook. This page refers to the control account and links to the summary information for all of the work packages that comprise this control account. The summary page for this control account which links to each of the work packages can be accessed by clicking here. This will take you to the labor and materioal sumaary sheet for this control account.
Assumptions Used in Developing Estimate
1. Materials for unique installation tooling and suplies used in installation only. Tools used in assembly of subsystems are included in the subsystem estimate, even if they are re-used here. (Note tools used in the assembly of the carriage cradle are included here). More detailed explanation of this are provided with provided in the BoE's for the individual work packages. 2. Labor estimates are for installation and testing performed after installation of the subsystems. Testing of assembled modules prior to installation is the responsibility of the subsystem. (see individual work packages for more detailed explanation). 3. Chillers, Gas system source, distribution, and other services are covered by the Infrastructure control acounts (see WBS 2.03 amd 2.04) or the individual detector subsystems or the Magnet subsystem. More detailed explanation for this division of responsibility is provided in the Infrastructure WBS. 4. Where approprate, re-purposing of PHENIX equipment is used to reduce labor and material costs. This is indicated where assumed in the individual work packages.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning for installation and the details of integrating all of the subsystems and the design of tools, fixtures and procedures for installing infrastructure and detector subsystems. 2. Assembly and installation of the carriage cradle, all of the infrastructure support equipment, and all of the services used by the detector and ancilliary subsystems. 3. Testing and commissioning of all subsystems afterinstalled and integrated into the sPHENIX detector.
Cost Summary
| WBS # |  | Work Package Description |  |  |  | Material Cost for this Work Package
| 2.05.01 |  | Subsystem Interface & Integration Plan |  |  |  | 0
| 2.05.02 |  | Infrastructure Installation |  |  |  | 5000
| 2.05.03 |  | Cradle Carriage Integration/Installation |  |  |  | 52500
| 2.05.05 |  | sPHENIX SC Magnet Installation |  |  |  | 43500
| 2.05.04 |  | Outer HCal Integration/Installation |  |  |  | 63500
| 2.05.06 |  | Inner HCal Integration/Installation |  |  |  | 84500
| 2.05.07 |  | EMCal Integration/Installation |  |  |  | 32500
| 2.05.08 |  | TPC Integration/Installation |  |  |  | 33000
| 2.05.09 |  | INTT Integration/Installation |  |  |  | 33000
| 2.05.10 |  | MVTX Integration/Installation |  |  |  | 32500
| 2.05.11 |  | Min Bias Integration/Installation |  |  |  | 13000
| 2.05.12 |  | sPHENIX Full Detector Installation |  |  |  | 2000
|  |  | Total Unburdened Material Cost for CA # 2.05.2 = |  |  |  |  | 395000
Labor Summary
| Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
| FTE-hrs | FTE-hrs | FTE-hrs | FTE-hrs | FTE-hrs | FTE-hrs | FTE-hrs
| 0 | 23696 | 51696 | 24248 | 107752 | 34144 | 78400
estimate uncertainty
Estimates for the labor and material described in this Control account are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in each work package. The overall material estimate uncertainty for this control account is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual work packages. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work packages' labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.01: Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation Control Account | [6 empty] | Labor estimate uncertainty: | 25%
[8 empty] | Material estimate uncertainty: | 36.42%

## BoE for Int & Inst Plans
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-20
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS Number: |  |  |  | Control Account Number
Subsystem Interface & Integration Plan |  |  |  | 2.05.01 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to plan and supervise all aspects of the final assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02), and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This work package includes the preparation, creation and review of the following written and controlled documents: 1. Subsystem Interface & Integration Plan - Plan to describe and define all interfaces between WBS subsystems., including detector mechanical interfaces, electrical intefaces, conduits and cable routing management, space allocation, cooling (water and air), detector cryogenic, inerting, drying, etc. gas supply routing and interfaces. 2. Subsystem Initial and Final Envelope Drawings - Drawings to globally and locally (for each detector subsystem) define space allocation for detector subsystems, infrastructure, support services and potential future additions. 3. Cable and Services Management Plans - Overall plan for routing electrical and optical, power, signal, control and monitoring cables between detectors to control racks, front end modules, patch panels, data acquisition, etc. 4. Survey Plan - Overall plan for alignment and positioning of overall detector relative to nominal beam orbit, individual detector subsystems to the overall detector, and internal alignment and positioining of detector subsystem internal components to the subsystem overall alignment. After review of each of the items in this work package, satisfaction of all action items coming out of the reviews corresponds to successful completion of the work package.
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Detector subsystems and Infrastructure subsystem will supply information on requirements in a timely fashion. 2. The Integration plans include only external alignment and stability of the detector subsystems. Design of internal support structure for detectors and internal alignment are the responsibility of the subsystem. 3. Design and analyses for chillers, cooling and gas system sources, distribution, and other services are covered by the Infrastructure control acounts (see WBS 2.03 and 2.04) or the individual detector subsystems or the Magnet subsystem. More detailed explanation for this division of responsibility is provided in the Infrastructure WBS. 4. This work package describes the requirements, goals and concepts for integrating and installing the detector subsystems and ancillary subsytems. Actual design of the structures and equipment to achieve these requirements are the responsibility of the detector subsystems and/or the infrastructure subsytem (see WBS 2.03 and 2.04 for more details)
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor cost estimate for the labor involved in planning for installation and the details of integrating all of the subsystems into the sPHENIX experiment, including: 1. Planning for the integration of the subsystems defined by sPHENIX WBS#'s 1.02 thru 1.7, 2.02 thru 2.04, 3.01 and 3.02, documentation of this plan and review of these plans. 2. Envelope definition and the efforts to prepare a drawing defining global envelope dimensions for the sPHENIX experiment and individual drawings defining the envelopes for each of the sPHENIX component subsystems. 3. Cable and services management and survey plans as an overall concept for routing electrical and optical, power, signal, control and monitoring cables between detectors to control racks, front end modules, patch panels, data acquisition, etc. The implementation of these plans and the analyses, design and procurement of all hardware required to implement these plans are the responsibility of the infrastrcture and detector subsystems. (See the individual subsystem estimates for details.) Note: there are no material costs associated with this work package.
Cost Summary
There are no material costs associated with this work package. The labor estimate can be found in the associated work package for this BoE.
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is re-evaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.01: Subsystem Interface & Integration Plan |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 0%

## BoE for Infra Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Infrastructure Installation |  |  |  | 2.05.02 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install Infrastructure components and equipment in support of the sPHENIX detectors at 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.04: sPHENIX Infrastructure, and/or the specific detector subsystems (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific Infrastructure installation tasks detailed in this work package are: 1. Line electric power distribution installation 2. Magnet cryogenic and electrical supply services structural support and cable/cryo fluids lines management installation. 3. Beampipe/vacuum equipment installation 4. IR HVAC equipment installation 5. On-detector and off-detector safety subsystems installation 6. Detector support services systems installations (signal, power and monitoring cable and fiber, services management and structural support, etc.) 7. Electronics racks installation (including patch panels) 8. Gas and cooling systemequipment and services installation. (including source, distribution monitoring and control systems) 9. Detector access and work platforms installation. 10. Non-IR infrastructure installation. (Including gas pad, gas mixing house, control room, rackroom, assembly areas and offices components and equipment)
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Detector subsystems and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the infrastructure items listed above in the "Dictionary Definition" section. 2. For equipment/components repurposed from items salvaged from the PHENIX removal and repurposing (R&R) efforts, only the labor required to repurpose the equipment is considered. 3. Infrastructure installation will commence as early as possible after (a) the infrastructure components/equipment has been provided by the infrastructure WBS, (b) PHENIX R&R has been completed and (c) CD2 authorization has been received for the sPHENIX MIE. 4. This work package describes the requirements, goals and concepts for integrating and installing the infrastructure components and equipment detector subsystems and ancillary subsytems. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the infrastructure subsytem (see WBS 2.04 for more details)."
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required for installation of components and equipment of sPHENIX infrastructure as indicated in the "Dictionary Definition" section above. - Currently there is a good deal of infrastructure already in place and/or aailable from the sPHENIX R&R efforts, and this is taken into account in this estimate. - All labor and material estimates are the result of engineering judgements based on similar requirements for infrastructure in similar projects (e.g. PHENIX, and recent PHENIX detectors.) - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link inthe above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $5000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.02: Infrastructure Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Cradle Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Cradle Carriage Integration/Installation |  |  |  | 2.05.03 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install cradle carriage components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.03: sPHENIX Infrastructure, and more specifically in WBS 2.03 (see WBS 2.03 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Cradle Carriage Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures 3. Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation 4. Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/Address action Items 5. Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports (These components procurement, fabrication, pre-assembly, acceptance testing and delivery to 1008 AH covered in WBS 2.03 work packages) 6. Assemble HCal cradle onto base 7. Install magnet mounting feet 8. Install platforms & access 9. Install Pole Tips Although these tasks are included in a single work package, these tasks are interlaced with installation tasks for the various detector subsystems that this carriage cradle supports, directly or indirectly. See the BOE's for WBS 2.05.01.04 through 2.05.01.12 for details on these related installation work packages and see the Installation and Integration MS Project file for linkage between these work packages
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Detector subsystems and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the Cradle Carriage items listed above in the "Dictionary Definition" section. 2. For equipment/components repurposed from items salvaged from the PHENIX removal and repurposing (R&R) efforts, only the labor required to repurpose the equipment is considered. 3. Cradle Carriage installation will commence as early as possible after (a) the Cradle carriage components/equipment have been provided by the infrastructure WBS, (b) PHENIX R&R has been completed and (c) CD2 authorization has been received for the sPHENIX MIE. 4. This work package describes the requirements, goals and concepts for integrating and installing the Cradle carriage components and equipment detector subsystems and ancillary subsytems. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the infrastructure subsytem (see WBS 2.03 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required for installation of components and equipment of sPHENIX cradle carriage as indicated in the "Dictionary Definition" section above. - Currently there is a good deal of infrastructure already in place and/or available from the sPHENIX R&R efforts, and this is taken into account in this estimate. - All labor and material estimates are the result of engineering judgements based on similar requirements for infrastructure in similar projects (e.g. PHENIX, and recent PHENIX detectors.) - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $52500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.03: Cradle Carriage Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 36.43%

## BoE for Outer HCal Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Outer HCal Integration/Installation |  |  |  | 2.05.04 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Outer Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, the reviews of these analyses and the assembly and testing of Outer HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Outer HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures 3. Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification and address action items 5. Transport Assembled Outer HCal Sectors to AH (Partial Shipment) (procurement, fabrication, assembly, testing and delivery to BNL of Outer HCal sectors and services covered in WBS 1.4 work packages) 6. Install Partial Outer HCal for SC Magnet Install (NOTE: at this point in the installation, the sPHENIX superconducting solenoid magnet must be installed. Refer to WBS # 2.05.01.05 for info on that work package) 7. Transport Remainder of Outer Hcal Sectors to AH 8. Install Remainder of Outer HCal Sectors 9. Align/Survey Outer HCal to SC Magnet Centerline 10. Install Outer HCal Cables and Services 11. Review Outer HCal for Operational Readiness (ORR)/ address action items 12. Commission Outer HCal
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX Outer HCal subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX Outer HCal in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX Outer HCal installation will commence as early as possible after (a) the sPHENIX Outer HCal components/equipment have been provided by the HCal WBS, (b) PHENIX R&R has been completed, (c) CD2 authorization has been received for the sPHENIX MIE and (d) cradle carriage has been assembled/installed to the point where the Outer HCal is to be mounted. 3. The SC Solenoid Magnet will be installed after the lower half of the Outer HCal sectors hae been installed. The remaining Outer HCal sectors, Outer HCal serices and Outer HCal Commissioing tasks will be acomplished after the Magnet is mechanically installed, but before Magnet services are installed. 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX Outer HCal components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the HCal subsytem (see WBS 1.04 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for installation of components and equipment of the sPHENIX Outer HCal as indicated in the "Dictionary Definition" section above. (Note: the Outer HCal components will be 32 fully assembled and tested sectors and assembly splice plates as defined in WBS 1.04) - The basic installation concept for the installation of the Outer HCal is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing large detector components, specifically large machined steel components with high precision alignment requirements, in similar projects. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX Outer HCal installation tasks as indicated in the "Dictionary Definition" section above. The labor and materials estimate for this work package can be found in this work book with the "Supporting Documents" link above.
Total unburdened material cost for this work package = $63500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.04: Outer HCal Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 39.17%

## BoE for Magnet Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
sPHENIX SC Magnet Installation |  |  |  | 2.05.05 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Superconducting Solenoid Magnet components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed (including cryogenic delivery, current supply to the magnet control and monitoring of the magnet and magnet equipment safety systems such as quench protection), the design, procurement and acceptance of such equipment, reviews of these analyses, modification of the BABAR magnet to accomodate the sPHENIX detector design and magnet performance/quality testing are not in the scope of this work package but rather are part of sPHENIX WBS 2.02: sPHENIX Magnet and WBS 2.04 Infrastructure (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures 2. Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures 3. Prepare SC Magnet Integration/Installation Procedures 4. Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/ Address Action Items 5. Transport SC Magnet and services from 912 to AH (procurement, fabrication, assembly, testing and delivery to BNL of Magnet, Magnet modifications and services covered in WBS 2.02 work packages) 6. Install SC Magnet on Cradle Carriage 7. Align/Survey SC Magnet to Cradle Carriage 8. Prep SC Magnet for Run (Cryo) 9. Prep SC Magnet for Run (Electric) 10. Review SC Magnet for Operational Readiness (ORR)/Address Action Items
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. sPHENIX Superconducting Solenoid Magnet subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX Superconducting Solenoid Magnet items listed above in the "Dictionary Definition" section. 2. For equipment/components repurposed from items salvaged from the PHENIX removal and repurposing (R&R) efforts, only the labor required to repurpose the equipment is considered. 3. sPHENIX Superconducting Solenoid Magnet installation will commence as early as possible after (a) the sPHENIX Superconducting Solenoid Magnet components/equipment have been provided by the Magnet WBS, (b) PHENIX R&R has been completed, (c) CD2 authorization has been received for the sPHENIX MIE and (d) cradle carriage has been assembled/installed to the point where the Magnet is mounted. 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX Superconducting Solenoid Magnet components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the Magnet subsytem (see WBS 2.02 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required for installation of components and equipment of sPHENIX Superconducting Solenoid Magnet as indicated in the "Dictionary Definition" section above. - Currently there is a good deal of infrastructure already in place and/or available from the sPHENIX R&R efforts, and this is taken into account in this estimate. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing large detector components, specifically superconducting magnets, in similar projects. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX Superconducting Solenoid Magnet installation tasks as indicated in the "Dictionary Definition" section above. The labor and materials estimate for this work package can be found in this work book with the "Supporting Documents" link above.
Total unburdened material cost for this work package = $43500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.05: sPHENIX SC Magnet Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 22.99%

## BoE for Inner HCal Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Inner HCal Integration/Installation |  |  |  | 2.05.06 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Inner Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Inner HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Inner HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures 3. Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/address action items 5. Transport assembled Inner HCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of Inner HCal sectors, services and assembly end rings covered in WBS 1.04 work packages) 6. Install Inner HCal assembly Insertion Fixture 7. Install Inner HCal assembly on Insertion Fixture 8. Install 1st Inner HCal Support Ring 9. Install Inner HCal 10. Install 2nd Inner HCal Support Ring 11. Align/Survey Inner HCal to SC Magnet Centerline 12. Install Inner HCal Cables and Services 13. Review Inner HCal for Operational Readiness (ORR)/adderess action items 14. Commission Inner HCal
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX Inner HCal subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX Inner HCal in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX Outer HCal installation will commence as early as possible after (a) the sPHENIX Inner HCal components/equipment have been provided by the HCal WBS, (b) CD2 authorization has been received for the sPHENIX MIE and (c) Outer HCal has been assembled/installed (which also indicates that the SC Magnet has been installed). 3. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX Inner HCal components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the HCal subsytem (see WBS 1.04 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for assembly and installation of components and equipment of the sPHENIX Inner HCal as indicated in the "Dictionary Definition" section above. (Note: the Inner HCal components will be 32 fully assembled and tested sectors and assembly end rings as defined in WBS 1.04) - The basic assembly and installation concept for the installation of the Inner HCal is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing large detector components, specifically large machined stainless steel components with high precision alignment requirements, in similar projects. - Material for this work package is limited to hardware and assembly/installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX Inner HCal installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $84500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.06: Inner HCal Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 39.05%

## BoE for EMCal Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
EMCal Integration/Installation |  |  |  | 2.05.07 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Electromagnetic Calorimeter (EMCal) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of EMCal detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of EMCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.03: sPHENIX Electromagnetic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design EMCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures 3. PrepareEMCal Integration/Installation Tooling/Fixtures Procedures 4. Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled EMCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of EMCal sectors and services covered in WBS 1.03 work packages) 6. Install EMCal Sectors 7. Align/Survey EMCal to SC Magnet Centerline 8. Install EMCal Cables and Services 9. Review EMCal for Operational Readiness (ORR); address action items 10. Commission EMCall
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX EMCal subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX EMCal in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX EMCal installation will commence as early as possible after the sPHENIX Inner HCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed). 3. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX EMCal components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the EMCal subsytem (see WBS 1.03 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for the installation of components and equipment of the sPHENIX EMCal as indicated in the "Dictionary Definition" section above. (Note: the EMCal components will be 64 fully assembled and tested sectors as defined in WBS 1.03) - The basic assembly and installation concept for the installation of the EMCal is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing large detector components, specifically large machined stainless steel components with high precision alignment requirements, in similar projects. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX EMCal installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $32500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.07: EMCal Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 38.85%

## BoE for TPC Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
TPC Integration/Installation |  |  |  | 2.05.08 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Time Projection Chamber (TPC) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of TPC detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of TPC performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.02: sPHENIX Time Projection Chamber. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design TPC Integration/Installation Tooling/Fixtures 2. Fabricate/Procure TPC Integration/Installation Tooling/Fixtures 3. Prepare TPC Integration/Installation Tooling/Fixtures Procedures 4. Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled TPC Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of TPV components and services covered in WBS 1.02 work packages) 6. Install TPC Support 7. Install TPC (Mechanical) 8. Align/Survey TPC to SC Magnet Centerline 9. Install TPC Cables and Services 10. Review TPC for Operational Readiness (ORR); address action items 11. Commission TPC
Return to Navigation Page
Estimate Type (check all that apply):
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX TPC subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX TPC in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX TPC installation will commence as early as possible after (a) the sPHENIX Inner HCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed) and (b) all EMCal sectors have beeen installed. 3. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX TPC components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the TPC subsytem (see WBS 1.02 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for the installation of components and equipment of the sPHENIX TPC as indicated in the "Dictionary Definition" section above. - The basic assembly and installation concept for the installation of the TPC is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing similar detector components, specifically delicate gas filled drift chamber components with high precision alignment requirements, in similar projects. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX TPC installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $33000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.08: TPC Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 38.64%

## BoE for INTT Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
INTT Integration/Installation |  |  |  | 2.05.09 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Intermediate Silicon Strip Tracker (INTT) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of INTT detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of INTT performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.01: sPHENIX Intermediate Silcon Strip Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design INTT Integration/Installation Tooling/Fixtures 2. Fabricate/Procure INTT Integration/Installation Tooling/Fixtures 3. Prepare INTT Integration/Installation Tooling/Fixtures Procedures 4. Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled INTT Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of INTT components and services covered in WBS 3.11 work packages) 6. Install INTT Support 7. Install INTT (mechanical) 8. Align/Survey INTT to SC Magnet Centerline 9. Install INTT Cables and Services 10. Review INTT for Operational Readiness (ORR); address action items from INTT ORR 11. Commission INTT
Return to Navigation Page
Estimate Type (check all that apply):
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX INTT subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX INTT in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX INTT installation will commence as early as possible after (a) the sPHENIX Inner HCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed), (b) all EMCal sectors have beeen installed (c) the TPC will already have been installed. 3. The INTT will be installed concurrently with the MVTX on a common support structure but with independent services. (Note: it is planned to be possible to install either the INTT or the MVTX alone, but installing the other detector subsystem will require removal of the installed subsystem and reinstalling both on the common support structure.) 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX INTT components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the INTT subsytem (see WBS 3.01 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for the installation of components and equipment of the sPHENIX INTT as indicated in the "Dictionary Definition" section above. - The basic assembly and installation concept for the installation of the INTT is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing similar detector components, specifically precision aligned silicon tracking detectors, in similar projects, and particularly relying on design concepts for the ALICE ITS MAPS detectors. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX INTT installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $33000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.09: INTT Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 38.26%

## BoE for MVTX Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
MVTX Integration/Installation |  |  |  | 2.05.10 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Monolithic Active Pixel Vertex Detector (MVTX) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of MVTX detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of MVTX performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.02: sPHENIX Monolithic Active Pixel Vertex Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design MVTX Integration/Installation Tooling/Fixtures 2. Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures 3. Prepare MVTX Integration/Installation Tooling/Fixtures Procedures 4. Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled MVTX Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of MVTX components and services covered in WBS 3.02 work packages) 6. Install MVTX Support 7. Install MVTX (mechanical) 8. Align/Survey MVTX to SC Magnet Centerline 9. Install MVTX Cables and Services 10. Review MVTX for Operational Readiness (ORR); address action items from MVTX ORR 11. Commission MVTX
Return to Navigation Page
Estimate Type (check all that apply):
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX MVTX subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX MVTX in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX MVTX installation will commence as early as possible after (a) the sPHENIX Inner HCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed), (b) all EMCal sectors have beeen installed (c) the TPC will already have been installed. 3. The MVTX will be installed concurrently with the INTT on a common support structure but with independent services. (Note: it is planned to be possible to install either the MVTX or the INTT alone, but installing the other detector subsystem will require removal of the installed subsystem and reinstalling both on the common support structure.) 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX MVTX components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the MVTX subsytem (see WBS 3.02 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for the installation of components and equipment of the sPHENIX MVTX as indicated in the "Dictionary Definition" section above. - The basic assembly and installation concept for the installation of the MVTX is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing similar detector components, specifically precision aligned silicon tracking detectors, in similar projects, and particularly relying on design concepts for the ALICE ITS MAPS detectors. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above "Suporting Documents" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX MVTX installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $32500
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.10: MVTX Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 38.46%

## BoE for MBD Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Min Bias Integration/Installation |  |  |  | 2.05.11 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Minimum Bias Tracker (Min Bias) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of Min Bias detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Min Bias performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.07: sPHENIX Minimum Bias tracker. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Min Bias Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures 3. Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures 4. Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled Min Bias Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of Min Bias components and services covered in WBS 1.07 work packages) 6. Install Min Bias Support 7. Install Min Bias (mechanical) 8. Align/Survey Min Bias to SC Magnet Centerline 9. Install Min Bias Cables and Services 10. Review Min Bias for Operational Readiness (ORR); address action items from Min Bias ORR 11. Commission Min Bias
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX Min Bias subsystem and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX Min Bias in accordance with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX Min Bias installation will commence as early as possible after (a) the sPHENIX Inner HCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed), (b) all EMCal sectors have beeen installed (c) the TPC will already have been installed. 3. The Min Bias is largely a repurposing of the PHENIX BBC detectors, and, as such, the support services and support structure required for the Min Bias is relatiely well understood. 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX Min Bias components and equipment. Actual design, approval and procurement of the components and equipment to be installed is the responsibility of the Min Bias subsytem (see WBS 1.07 for more details).
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for the installation of components and equipment of the sPHENIX Min Bias as indicated in the "Dictionary Definition" section above. - The basic assembly and installation concept for the installation of the Min Bias is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for installing similar detector components, specifically precision aligned silicon tracking detectors, in similar projects, and particularly relying on design concepts for the ALICE ITS MAPS detectors. - Material for this work package is limited to hardware and installation specific tooling and fixtures. Use the link in the above ""Suporting Documents"" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX Min Bias installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $13000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.11: Min Bias Integration/Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 35.58%

## BoE for Full Detector Inst
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-27
[7 empty] | Prepared By: | D. Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
sPHENIX Full Detector Installation |  |  |  | 2.05.12 |  |  |  | TBD
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts tomove the sPHENIX support carriage qwith the larger detector components mostly installed align the carrtiage ctradle to the beam line, then, after all of the inner detecors not previously installed are installed, commission the full detectro and make it ready for sPHENIX run 1. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Move Full sPHENIX to IR 2. Align Full sPHENIX to Nominal Beamline and IP 3. Perform Full System Commissioning 4. Review the Full sPHENIX Detector for Operational Readiness (ORR)/Address action items
Return to Navigation Page
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. The sPHENIX detexctor subsystems system and Infrastructure subsystem will supply all equipment to be installed. This work package covers material procurements for hardware, special tools and fixtures required only for installation of the sPHENIX full system with the tasks listed above in the "Dictionary Definition" section. 2. sPHENIX full system installation will commence as early as possible after (a) the sPHENIX EMCal has been assembled/installed (which also indicates that the Outer Hcal and SC Magnet have been installed), (b) all EMCal sectors have beeen installed (c) the TPC will already have been installed. 4. This work package describes the requirements, goals and concepts for integrating and installing the sPHENIX full system components and equipment. Actual design, approval and procurement of the components and equipment to be installed is also included in this work pacjkage.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for required tools, fixtures and related equipment as required for thefinal integration and installation of components and equipment used in the final assembly and commissioning of the full sPHENIX detector system as indicated in the "Dictionary Definition" section above. - The fianl assembly, installationand commissioning concept for thefull sPHENIX detector is fairly well developed, and design of actual equipment is in progress. - All labor and material estimates are the result of engineering judgements based on similar requirements for final assembly/installation and commissioning of similar detector systems and in particular experience with the PHENIX detector system. Use the link in the above ""Suporting Documents"" section to see details of the labor and material estimates for this work package.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for the sPHENIX Min Bias installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $2000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.05.12: sPHENIX Full Detector Installation |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | -37.5%

## Milestones
WBS Milestone # | WBS Milestone Title | Milestone Date | Notes/LINKS
Return to Navigation Page
Design/Safety Reviews Complete, Ready to Begin Installation
S348500 | Design/Safety Reviews Complete, Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Ready for service
S348600 | Ready to Assemble Cradle Carriage in AH
S350400 | Design/Safety Reviews Complete, Outer HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S350500 | Outer HCal Sectors Ready for Installation
S352900 | Design/Safety Reviews Complete, sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S353000 | Ready to Install SC Magnet
S355000 | Design/Safety Reviews Complete, Inner HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S355100 | Inner HCal Sectors Ready for Installation
S358000 | Design/Safety Reviews Complete, EMCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S358100 | EMCal Sectors Ready for Installation
S360200 | Design/Safety Reviews Complete, TPC Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S360300 | TPC Ready for Installation
S362600 | Design/Safety Reviews Complete, INTT Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S362700 | INTT Ready for Installation
S364900 | Design/Safety Reviews Complete, MVTX Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S365000 | MVTX Ready for Installation
S368300 | Design/Safety Reviews Complete, Min Bias Integration/Installation Tooling/Fixtures/Procedures Ready for Service
S368400 | Min Bias Ready for Installation
S370400 | sPHENIX Installation Complete (MIE)
S370800 | All Design/Safety/Readiness Reviews Complete, sPHENIX Ready for Operations

## Reviews by Work Package
WBS # | WBS Title (Work Package) | WBS Title (Review) | NOTES/LINKS
Return to Navigation Page
2.05.01 | Subsystem Interface & Integration Plan
S345000 |  | Review Integration and Installation Plan Design/Safety
S345100 |  | Review Cable Management Plan
S345200 |  | Review Survey Plan
2.05.03 | Cradle Carriage Integration/Installation
S348300 / S348310 |  | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
2.05.04 | Outer HCal Integration/Installation
S350200 |  | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S351800 |  | Review Outer HCal for Operational Readiness (ORR)
2.05.05 | sPHENIX SC Magnet Installation
S352700 |  | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S354100 / S354110 |  | Review SC Magnet for Operational Readiness (ORR)
2.05.06 | Inner HCal Integration/Installation
S354800 |  | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S356800 |  | Review Inner HCal for Operational Readiness (ORR)
2.05.07 | EMCal Integration/Installation
S357800 |  | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S359000 |  | Review EMCal for Operational Readiness (ORR)
2.05.08 | TPC Integration/Installation
S360000 |  | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S361500 |  | Review TPC for Operational Readiness (ORR)
2.05.09 | INTT Integration/Installation
S362400 |  | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S363800 |  | Review INTT for Operational Readiness (ORR)
2.05.10 | MVTX Integration/Installation
S364700 |  | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S367100 / S367200 |  | Review MVTX for Operational Readiness (ORR)
2.05.11 | Min Bias Integration/Installation
S368100 |  | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification
S269500 |  | Review Min Bias for Operational Readiness (ORR)
2.05.12 | sPHENIX Full Detector Installation
S370600 |  | Full sPHENIX Detector Operational Readiness (ORR)

## Procurement $ by Work Package
Work Package WBS # | Work Package WBS Title | Work Package Procurements (Total) (includes purchased parts, Central Shops fabricated parts, contract labor. Does not include BNL labor other than Central Shops fabrication.) | NOTES/LINKS
Return to Navigation Page
2.05.01 | Subsystem Interface & Integration Plan | 0
2.05.02 | Infrastructure Installation | 5000
2.05.03 | Cradle Carriage Integration/Installation | 52500
2.05.04 | Outer HCal Integration/Installation | 63500
2.05.05 | sPHENIX SC Magnet Installation | 43500
2.05.06 | Inner HCal Integration/Installation | 84500
2.05.07 | EMCal Integration/Installation | 32500
2.05.08 | TPC Integration/Installation | 33000
2.05.09 | INTT Integration/Installation | 33000
2.05.10 | MVTX Integration/Installation | 32500
2.05.11 | Min Bias Integration/Installation | 13000
2.05.12 | sPHENIX Full Detector Installation | 2000
|  | Total Procurements Cost 2017 dollars, [no overhead or estimate uncertainty added] for the WBS #2.05.01: Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation Control Account | 395000

## Int & Inst Control Account
Return to Navigation Page
| WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.05.01 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
|  | Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation |  |  |  |  | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty | Control account 2.05.2 Bottoms Up Composite estimate uncertainty (%)
[5 empty] | hrs | hrs | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
| 2.05.01 | Integration Documentation, Technical Coordination, Installation Tooling and Fixtures and Subsystem Installation | Technical Scope: WBS 2.05.01 is the Control Account for all scientific, engineering and technical staff efforts to plan, execute and supervise all aspects of the assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics for the sPHENIX MIE (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02) and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This Control Account encompasses the planning for and all of the actual installation and commissioning of these components will take place at the sPHENIX experiment complex at building 1008. There are 12 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. | [35 empty] | 395000 | [12 empty] | 0 | 359883 | 670649 | 244516.5 | 1089740.7 | 484375.32 | 0 | 2849164.52 | 3561455.65 | 538875 | 25% | 36.42%
| 2.05.01 | Subsystem Interface & Integration Plan | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to plan and supervise all aspects of the final assembly, integration and installation of the sPHENIX infrastructure components (defined by WBS 2.03 and 2.04), completed and tested detector subsystem modules and electronics (defined by WBS 1.02 though 1.07), sPHENIX superconducting solenoid magnet (defined by WBS 2.02), and parallel detector projects to be installed in sPHENIX (defined by WBS 3.01 and 3.02). Work Statement: This work package includes the preparation, creation and review of the following written and controlled documents: 1. Subsystem Interface & Integration Plan - Plan to describe and define all interfaces between WBS subsystems., including detector mechanical interfaces, electrical intefaces, conduits and cable routing management, space allocation, cooling (water and air), detector cryogenic, inerting, drying, etc. gas supply routing and interfaces. 2. Subsystem Initial and Final Envelope Drawings - Drawings to globally and locally (for each detector subsystem) define space allocation for detector subsystems, infrastructure, support services and potential future additions. 3. Cable and Services Management Plans - Overall plan for routing electrical and optical, power, signal, control and monitoring cables between detectors to control racks, front end modules, patch panels, data acquisition, etc. 4. Survey Plan - Overall plan for alignment and positioning of overall detector relative to nominal beam orbit, individual detector subsystems to the overall detector, and internal alignment and positioining of detector subsystem internal components to the subsystem overall alignment. After review of each of the items in this work package, satisfaction of all action items coming out of the reviews corresponds to successful completion of the work package. | [35 empty] | 0 | [12 empty] | 0 | 2430 | 40677 | 26763 | 6812.4 | 0 | 0 | 76682.4 | 95853 | 0
| S344300 | Create Subsystem Interface & Integration Plan | Technical Scope: Preparation of an Interface and Integration Plan. Work Statement: Gather information about all sPHENIX subsystems (dimensions, tolerances required services, environmental requirements, etc.) and create a unified plan to integrate all of the subsystems into the single sPHENIX experiment. | 160 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 8344 | 12976 | 0 | 0 | 0 | 21320 | 26650 | 0
| S344400 | Create Subsystem Initial Envelope Drawings | Technical Scope: Creation of initial envelope drawings for all subsystems. Work Statement: prepare drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Iterate drawings to reolve conflicts between subsystems. | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S344500 | Create Subsystem Outline/Interface Drawings | Technical Scope: Creation of final envelope drawings for all subsystems. Work Statement: Finalize drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Freeze envelopes and interfaces at final design. | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S344600 | Create Cable Management Plan | Technical Scope: Create Cable Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing and supporting canl;es/fibers and related services for all sPHENI detectors. | 20 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 40 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0 | 0 | 12516 | 3244 | 0 | 0 | 0 | 15760 | 19700 | 0
| S344700 | Create Services Management Plan | Technical Scope: Create Servces Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing cooling, gas, etc between source and distribution panels and from there to detector electronics, control racks, front end modules, etc. (does not include cryogenics - see magnet for Cryo services) | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 32 | 0 | 0 | 0 | 0 | 8344 | 3244 | 2595.2 | 0 | 0 | 14183.2 | 17729 | 0
| S344800 | Create Survey Plan | Technical Scope: Create Survey plan for all detector subsystems. Work Statement: Prepare an overall plan for aligning each of the sPHENIX subsystems into the total experiment, preserving the dimensional alignments and performance requirements . Plan will determine how achieving this alignment will be implemented in the subsystems design and how this alignment will be erified and documented by RHIC surveyors. | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 40 | 32 | 0 | 0 | 0 | 0 | 4172 | 3244 | 2595.2 | 0 | 0 | 10011.2 | 12514 | 0
| S345000 | Review Integration and Installation Plan Design/Safety | Technical scope: Preparation for and execution of review for Engineering and safety review of Integration and Installation Plan. Work Statement: gather documentation describing the design and analyses of the integration and installation of all sPHENIX subsystems. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. | 20 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 2430 | 2086 | 1622 | 0 | 0 | 0 | 6138 | 7672.5 | 0
| S345100 | Review Cable Management Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Cable management Plan Plan. Work Statement: gather documentation describing the design and analyses of the cable management plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management. | 10 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 20 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 3129 | 811 | 0 | 0 | 0 | 3940 | 4925 | 0
| S345200 | Review Survey Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Surey Plan Plan. Work Statement: gather documentation describing the design and analyses of thesurvey plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management. | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 1043 | 811 | 811 | 0 | 0 | 2665 | 3331.25 | 0
| S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey Plans) Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from subsystem Interface Integrationand Installation, cable management and survey plans engineering and safety reviews. Work Statement: receive action items from reviewers, evaluate action items implement changes, modifications to plans to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 1043 | 811 | 811 | 0 | 0 | 2665 | 3331.25 | 0
|  | Design/Safety Reviews Complete, Ready to Begin Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2.05.02 | Infrastructure Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install Infrastructure components and equipment in support of the sPHENIX detectors at 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.04: sPHENIX Infrastructure, and/or the specific detector subsystems (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific Infrastructure installation tasks detailed in this work package are: 1. Line electric power distribution installation 2. Magnet cryogenic and electrical supply services structural support and cable/cryo fluids lines management installation. 3. Beampipe/vacuum equipment installation 4. IR HVAC equipment installation 5. On-detector and off-detector safety subsystems installation 6. Detector support services systems installations (signal, power and monitoring cable and fiber, services management and structural support, etc.) 7. Electronics racks installation (including patch panels) 8. Gas and cooling systemequipment and services installation. (including source, distribution monitoring and control systems) 9. Detector access and work platforms installation. 10. Non-IR infrastructure installation. (Including gas pad, gas mixing house, control room, rackroom, assembly areas and offices components and equipment) | [35 empty] | 5000 | [12 empty] | 0 | 0 | 139762 | 25303.2 | 275740 | 106226.64 | 0 | 547031.84 | 683789.8 | 6250
| S346000 / S346100 | Install Line Electric Power Distribution | Technical Scope: All tasks related to the installation of Line electric power distribution for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 0 | 0 | 240 | 0 | 0 | 0 | 8344 | 0 | 0 | 27237.6 | 0 | 35581.6 | 44477 | 625
| S346500 / S346510 | Install Cryogenics Supply Structural Suport | Technical Scope: All tasks related to the installation of cryo supply structural support (including power and control cables) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 160 | 80 | 0 | 80 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 160 | 16 | 160 | 160 | 0 | 0 | 0 | 16688 | 1297.6 | 12976 | 18158.4 | 0 | 49120 | 61400 | 625
| S346300 / S346310 | Install Beampipe/Vacuum | Technical Scope: All tasks related to the installation of beam/vacuum components and support structures) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 100 | 80 | 0 | 20 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 100 | 16 | 120 | 0 | 0 | 0 | 0 | 10430 | 1297.6 | 9732 | 0 | 0 | 21459.6 | 26824.5 | 625
| S345500 | Install IR HVAC | Technical Scope: All tasks related to the installation of IR/HVAC components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 32 | 32 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 40 | 0 | 40 | 64 | 0 | 0 | 0 | 4172 | 0 | 3244 | 7263.36 | 0 | 14679.36 | 18349.2 | 625
| S347600 / S347700 | Install IR Electronics Cooling Water | Technical Scope: All tasks related to the installation of electronics cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 112 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 40 | 16 | 160 | 112 | 0 | 0 | 0 | 4172 | 1297.6 | 12976 | 12710.88 | 0 | 31156.48 | 38945.6 | 625
| S345700 / S345800 | Install On Detector and Off Detector Safety Subsystems | Technical Scope: All tasks related to the installation of On-detector and Off-detector components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 40 | 40 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 0 | 200 | 0 | 0 | 0 | 0 | 8344 | 0 | 16220 | 0 | 0 | 24564 | 30705 | 625
| S346900 | Install Detector Support Services Systems | Technical Scope: All tasks related to the installation of Detector support services components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 400 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 32 | 400 | 200 | 0 | 0 | 0 | 8344 | 2595.2 | 32440 | 22698 | 0 | 66077.2 | 82596.5 | 625
| S347100 / S347200 | Install Electronics Racks | Technical Scope: All tasks related to the installation of electronic racks and related generic equipment components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 60 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 240 | 240 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 1120 | 560 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 480 | 96 | 1120 | 0 | 0 | 0 | 0 | 50064 | 7785.6 | 90832 | 0 | 0 | 148681.6 | 185852 | 625
| S3437400 | Install Gas and Cooling System Services | Technical Scope: All tasks related to the installation of gas and cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 60 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 120 | 96 | 720 | 0 | 0 | 0 | 0 | 12516 | 7785.6 | 58392 | 0 | 0 | 78693.6 | 98367 | 625
| S3346700 / S346710 | Install Non-IR Infrastructure | Technical Scope: All tasks related to the installation of non-IR infrastructure components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 80 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 480 | 160 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 80 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 160 | 40 | 480 | 160 | 0 | 0 | 0 | 16688 | 3244 | 38928 | 18158.4 | 0 | 77018.4 | 96273 | 625
| 2.05.03 | Cradle Carriage Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install cradle carriage components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are not in the scope of this work package and control account but rather are part of sPHENIX WBS 2.03: sPHENIX Infrastructure, and more specifically in WBS 2.03 (see WBS 2.03 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Cradle Carriage Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures 3. Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation 4. Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/Address action Items 5. Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports (These components procurement, fabrication, pre-assembly, acceptance testing and delivery to 1008 AH covered in WBS 2.03 work packages) 6. Assemble HCal cradle onto base 7. Install magnet mounting feet 8. Install platforms & access 9. Install Pole Tips Although these tasks are included in a single work package, these tasks are interlaced with installation tasks for the various detector subsystems that this carriage cradle supports, directly or indirectly. See the BOE's for WBS 2.05.01.04 through 2.05.01.12 for details on these related installation work packages and see the Installation and Integration MS Project file for linkage between these work packages | [35 empty] | 52500 | [12 empty] | 0 | 0 | 62997.2 | 34873 | 83046.4 | 29053.44 | 0 | 209970.04 | 262462.55 | 71625
| S347900 / S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of cradle carriage Integration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation. | 40 | 0 | 0 | 0 | 0 | 0 | 100 | 80 | 0 | 20 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 100 | 160 | 0 | 0 | 0 | 0 | 0 | 10430 | 12976 | 0 | 0 | 0 | 23406 | 29257.5 | 0
| S348000 / S348010 / S348100 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX Cradle/carriage. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items. | 120 | 0 | 0 | 0 | 0 | 0 | 240 | 192 | 0 | 48 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the cradle carriage is fairly well set, but the details need to be established/M5 | 0 | 0 | 240 | 160 | 0 | 0 | 0 | 0 | 0 | 25032 | 12976 | 0 | 0 | 0 | 38008 | 47510 | 56000
| S348200 / S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation | Technical Scope: Create a written integration /installation procedure for the assembly of the cradle carriage in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX cradle carriage. | 30 | 0 | 0 | 0 | 0 | 0 | 78 | 30 | 0 | 48 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 78 | 30 | 0 | 0 | 0 | 0 | 0 | 8135.4 | 2433 | 0 | 0 | 0 | 10568.4 | 13210.5 | 0
| S348300 / S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX cradle carriage assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX cradle carriage and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
| S348400 / S348810 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from cradle carriage Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
| S348500 | Design/Safety Reviews Complete, Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Ready for service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S348600 | Ready to Assemble Cradle Carriage in AH | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S348700 / S348710 / S348800 | Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports | Technical scope: Assembly and installation of cradle base. Work Statement: Using work plan/permit, tooling and fixtures, installthe cradle carriage roller system, base plate and relevant alignment provisions. | 20 | 0 | 0 | 0 | 0 | 0 | 48 | 32 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 2500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 16 | 480 | 160 | 0 | 0 | 0 | 5006.4 | 1297.6 | 38928 | 18158.4 | 0 | 63390.4 | 79238 | 3125
| S348900 / S348910 / S349000 | Assemble HCal cradle onto base | Technical scope: Installation/assembly of cradle onto base Work Statement: Using work plan/permit, tooling and fixtures, install the cradle onto the carriage base plate and relevant alignment provisions. | 20 | 0 | 0 | 0 | 0 | 0 | 48 | 32 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 16 | 80 | 64 | 0 | 0 | 0 | 5006.4 | 1297.6 | 6488 | 7263.36 | 0 | 20055.36 | 25069.2 | 3750
| S349100 / S349200 | Install magnet mounting feet | Technical scope: Installation of magnet mounting feet onto the HCal sectors installed on carriage cradles. (Note the installation of the Outer HCal sectors is described in WBS 2.05.01.04 The Magnet is installed before the upper HCal sectors are installed (see WBS 2.05.01.05 for Magnet installation details). Work Statement: Using work plan/permit, tooling and fixtures, install the magnet mounting feet and relevant alignment provisions onto the HCal sectors. | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 10 | 8 | 160 | 0 | 0 | 0 | 0 | 1043 | 648.8 | 12976 | 0 | 0 | 14667.8 | 18334.75 | 3750
| S349300 / S349310 / S349400 | Install platforms & access | Technical scope: Installation of platforms and access onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the work platforms, access and related components onto the cradle base. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 240 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 19464 | 0 | 0 | 24099.2 | 30124 | 1250
| S349500 / S349510 / S349600 | Install Pole Tips | Technical scope: Installation of end caps/pole tips onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the end caps/pole tips and related components onto the cradle base. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 8 | 64 | 32 | 0 | 0 | 0 | 1668.8 | 648.8 | 5190.4 | 3631.68 | 0 | 11139.68 | 13924.6 | 3750
| 2.05.04 | Outer HCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Outer Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, the reviews of these analyses and the assembly and testing of Outer HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Outer HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures 3. Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification and address action items 5. Transport Assembled Outer HCal Sectors to AH (Partial Shipment) (procurement, fabrication, assembly, testing and delivery to BNL of Outer HCal sectors and services covered in WBS 1.4 work packages) 6. Install Partial Outer HCal for SC Magnet Install (NOTE: at this point in the installation, the sPHENIX superconducting solenoid magnet must be installed. Refer to WBS # 2.05.01.05 for info on that work package) 7. Transport Remainder of Outer Hcal Sectors to AH 8. Install Remainder of Outer HCal Sectors 9. Align/Survey Outer HCal to SC Magnet Centerline 10. Install Outer HCal Cables and Services 11. Review Outer HCal for Operational Readiness (ORR)/ address action items 12. Commission Outer HCal | [35 empty] | 63500 | [12 empty] | 0 | 19440 | 59033.8 | 25952 | 192693.6 | 125292.96 | 0 | 422412.36 | 528015.45 | 88375
| S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Outer HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Outer HCal sectors during assembly. The design of those tools is covered in WBS 1.04, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated, and the design of the installation tools will need to be modified from the assembly handling tools to include provision for fine adjustment of orientation to allow the sectors to be installed in 32 different orientations.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Outer HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding, and sector assembly spreader tools for installing the Outer HCal sectors and services. | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | Design completed by HCAl subsystem | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 24 | 0 | 0 | 0 | 0 | 3129 | 4866 | 1946.4 | 0 | 0 | 9941.4 | 12426.75 | 0
| S349900 / S350000 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Outer HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Sc Magnet assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the Outer HCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, alignment fixtures and scaffolding/M5 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 3892.8 | 3892.8 | 0 | 0 | 12792 | 15990 | 84000
| S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Outer HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Outer HCal and its services (e.g. critical lift calculations, etc.) | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 16 | 16 | 0 | 0 | 0 | 0 | 4172 | 1297.6 | 1297.6 | 0 | 0 | 6767.2 | 8459 | 0
| S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Outer HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Outer HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S350400 | Design/Safety Reviews Complete, Outer HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S350500 | Outer HCal Sectors Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S350600 / S350700 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) | Technical scope: Transport first 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 256 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 128 | 256 | 0 | 0 | 0 | 834.4 | 648.8 | 10380.8 | 29053.44 | 0 | 40917.44 | 51146.8 | 625
| S350800 / S350900 | Install Partial Outer HCal for SC Magnet Install | Technical scope: Install lower 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure.After these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package) | 60 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 64 | 0 | 192 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 48 | 512 | 256 | 0 | 0 | 0 | 6675.2 | 3892.8 | 41523.2 | 29053.44 | 0 | 81144.64 | 101430.8 | 625
| S351000 / S351100 | Transport Remainder of Outer Hcal Sectors to AH | Technical scope: After the sPHENIX SC Magnet is be installed (see 1.10.2.4 for SC Magnet installation work package), transport remaining 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 256 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 128 | 256 | 0 | 0 | 0 | 834.4 | 648.8 | 10380.8 | 29053.44 | 0 | 40917.44 | 51146.8 | 625
| S351200 / S351300 | Install Remainder of Outer HCal Sectors | Technical scope: Install upper 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure. before these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package) | 20 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 64 | 0 | 192 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 256 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 29053.44 | 0 | 82442.24 | 103052.8 | 625
| S351400 / S351410 / S351500 | Align/Survey Outer HCal to SC Magnet Centerline | Technical scope: Align all Outer HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Outer HCal and the cradle carriage, align the Outer HCal to to the nominal IP and beam RHIC axis in accordance with the Outer HCal installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 4 | 80 | 80 | 0 | 0 | 0 | 0 | 324.4 | 6488 | 9079.2 | 0 | 15891.6 | 19864.5 | 625
| S351600 / S351700 | Install Outer HCal Cables and Services | Technical scope: Install all Outer HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Outer HCal services onto the sPHENIX cradle carriage. | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 80 | 0 | 240 | 0 | 0 | 0 | 0 | 8344 | 0 | 19464 | 0 | 0 | 27808 | 34760 | 625
| S351800 | Review Outer HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Outer HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Outer HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S351900 | Address Action Items from Outer Hcal ORR | Technical scope: evaluation and implementation of recommendations from Outer HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 20% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S352000 / S352100 / S352200 | Commission Outer HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Outer HCal. Work Statement: Perform operational checks on HCal operational and control equipment, . Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 160 | 0 | 160 | 0 | 192 | 0 | 0 | 32 | 160 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 640 | 320 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task. All costs for test equipment and supplies in support of commissioing efforts are supplied by the subsystem./M1 | 0 | 160 | 192 | 32 | 640 | 0 | 640 | 0 | 19440 | 20025.6 | 2595.2 | 51904 | 0 | 0 | 93964.8 | 117456 | 625
| 2.05.05 | sPHENIX SC Magnet Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Superconducting Solenoid Magnet components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the components and equipment needed (including cryogenic delivery, current supply to the magnet control and monitoring of the magnet and magnet equipment safety systems such as quench protection), the design, procurement and acceptance of such equipment, reviews of these analyses, modification of the BABAR magnet to accomodate the sPHENIX detector design and magnet performance/quality testing are not in the scope of this work package but rather are part of sPHENIX WBS 2.02: sPHENIX Magnet and WBS 2.04 Infrastructure (see WBS 2.04 BoE's for more detailed description of its scope). Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures 2. Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures 3. Prepare SC Magnet Integration/Installation Procedures 4. Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/ Address Action Items 5. Transport SC Magnet and services from 912 to AH (procurement, fabrication, assembly, testing and delivery to BNL of Magnet, Magnet modifications and services covered in WBS 2.02 work packages) 6. Install SC Magnet on Cradle Carriage 7. Align/Survey SC Magnet to Cradle Carriage 8. Prep SC Magnet for Run (Cryo) 9. Prep SC Magnet for Run (Electric) 10. Review SC Magnet for Operational Readiness (ORR)/Address Action Items | [35 empty] | 43500 | [12 empty] | 0 | 0 | 42345.8 | 12165 | 98942 | 21790.08 | 0 | 175242.88 | 219053.6 | 53500
| S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures | Technical Scope: All tasks related to the design of SC Magnet Integeration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation. | 30 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 180 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 180 | 60 | 24 | 0 | 0 | 0 | 0 | 18774 | 4866 | 1946.4 | 0 | 0 | 25586.4 | 31983 | 0
| S352400 / S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX SC Magnet. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items. | 60 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the superconducting magnet is fairly well set, but the details need to be established/M4 | 0 | 0 | 30 | 10 | 10 | 0 | 0 | 0 | 0 | 3129 | 811 | 811 | 0 | 0 | 4751 | 5938.75 | 37500
| S352600 | Prepare SC Magnet Integration/Installation Procedures | Technical Scope: Create a written integration /installation procedure for the assembly of the SC Magnet in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX SC Magnet. | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 2086 | 811 | 0 | 0 | 0 | 2897 | 3621.25 | 0
| S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX SC Magnet and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from SC Magnet Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S352900 | Design/Safety Reviews Complete, sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S353000 | Ready to Install SC Magnet | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S353100 / S353110 / S353200 | Transport SC Magnet from 912 to AH | Technical scope: Transportation of SC Magnet from 912 to 1008 AH by BNL riggers. Work Statement: In accordance with work plan/permit, tooling and fixtures, transport the SC Magnet from 912 to 1008, taking care to handle the Magnet and its services with appropriate care. | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 1500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 4 | 32 | 64 | 0 | 0 | 0 | 3337.6 | 324.4 | 2595.2 | 7263.36 | 0 | 13520.56 | 16900.7 | 1875
| S353300 / S353310 / S353400 | Install SC Magnet on cradle carriage | Technical scope: Installation of SC Magnet onto lower half of Outer HCal previously mounted to cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, install the SC Magnet onto the cradle carriage. | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 1500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 2 | 32 | 64 | 0 | 0 | 0 | 3337.6 | 162.2 | 2595.2 | 7263.36 | 0 | 13358.36 | 16697.95 | 1875
| S353500 / S353510 / S353600 | Align/Survey SC Magnet to cradle carriage | Technical scope: Alignment of SC Magnet with respect to nominal IP and beam axis related via the cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, and the SC Magnet Alignment specifications, align the SC Magnet to the nominal IP and beam RHIC axis with the assistance of BNL sureyors. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 80 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 3500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 416 | 64 | 0 | 0 | 0 | 0 | 0 | 33737.6 | 7263.36 | 0 | 41000.96 | 51251.2 | 4375
| S353700 / S353710 / S353800 | Prep SC Magnet for Run (Cryo) | Technical scope: Preparation/Installation and commissioning of Cryo system for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Cryo techs. CAD Cryo tech efforts and all cryo equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD cryo technicians in preparing the cryo serices for the SC Magnet. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 336 | 16 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 336 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 27249.6 | 0 | 0 | 31884.8 | 39856 | 4375
| s353900 / S353910 / S354000 | Prep SC Magnet for Run (Electric) | Technical scope: Preparation/Installation and commissioning of electrical power, monitoring and safety systems for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Electrical techs and engineers. CAD electrical tech efforts and all electrical equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD electrical technicians in preparing the electrical serices for the SC Magnet. | 20 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 320 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 25952 | 0 | 0 | 30587.2 | 38234 | 3500
| S354100 / S354110 | Review SC Magnet for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the SC Magnet and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Magnet will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 10 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 811 | 0 | 0 | 3128.6 | 3910.75 | 0
| S354200 / S354210 | Address Action Items from SC Magnet ORR | Technical scope: evaluation and implementation of recommendations from SC Magnet ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 24 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1946.4 | 0 | 0 | 4264 | 5330 | 0
| 2.05.06 | Inner HCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to assemble and install the sPHENIX Inner Hadronic Calorimeter (Outer HCal) sectors in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of outer HCal detector structural and components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Inner HCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.04: sPHENIX Hadronic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Inner HCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures 3. Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures 4. Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification/address action items 5. Transport assembled Inner HCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of Inner HCal sectors, services and assembly end rings covered in WBS 1.04 work packages) 6. Install Inner HCal assembly Insertion Fixture 7. Install Inner HCal assembly on Insertion Fixture 8. Install 1st Inner HCal Support Ring 9. Install Inner HCal 10. Install 2nd Inner HCal Support Ring 11. Align/Survey Inner HCal to SC Magnet Centerline 12. Install Inner HCal Cables and Services 13. Review Inner HCal for Operational Readiness (ORR)/adderess action items 14. Commission Inner HCal | [35 empty] | 84500 | [12 empty] | 0 | 38880 | 68420.8 | 26438.6 | 110944.8 | 27237.6 | 0 | 271921.8 | 339902.25 | 117500
| S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Inner HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Inner HCal sectors during assembly. The design of those tools is covered in WBS 1.4, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Inner HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing the Inner HCal sectors into an integrated Inner HCal detector then installing this detector inside the SC Magnet and for installing Inner HCal services. | 40 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 120 | 0 | 0 | 0 | 0 | 0 | 6258 | 9732 | 0 | 0 | 0 | 15990 | 19987.5 | 0
| S354500 / S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Inner HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Outer HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the Inner HCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0 | 0 | 12516 | 3244 | 0 | 0 | 0 | 15760 | 19700 | 112000
| S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Inner HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Inner HCal and its services (e.g. critical lift calculations, etc.) | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 8344 | 3244 | 0 | 0 | 0 | 11588 | 14485 | 0
| S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Inner HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Inner HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S355000 | Design/Safety Reviews Complete, Inner HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S355100 | Inner HCal Sectors Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S355200 / S355300 | Transport assembled Inner HCal Sectors to AH | Technical scope: Transport all 32 Inner HCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all Inner HCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full Inner HCal assembly. | 20 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 16 | 120 | 160 | 0 | 0 | 0 | 1668.8 | 1297.6 | 9732 | 18158.4 | 0 | 30856.8 | 38571 | 625
| S355400 / S355500 | Install Inner HCal assembly Insertion Fixture | Technical scope: Install the Inner HCal insertion fixture in the sPHENIX Assembly Hall (AH). Work Statement: sPHENIX technicans assemble the Inner HCal insertion fixture in the sPHENIX AH next to the sPHENIX cradle carriage (which by the time the Inner HCal is ready for insertion will have all of the Outer HCal and SC Magnet fully installed) in accordance with the Inner HCal installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 4 | 4 | 80 | 0 | 0 | 0 | 0 | 417.2 | 324.4 | 6488 | 0 | 0 | 7229.6 | 9037 | 625
| S355600 / S355700 | Install Inner HCal assembly on Insertion Fixture | Technical scope: Install all 32 Inner HCal sectors into full Inner HCal detector on the Inner HCal insertion fixture in the sPHENIX Assembly Hall. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install all 32 Inner HCal sectors between the Inner HCal assembly rings on the Inner HCal insertion fixture in accordance with the Inner HCal installation procedure and work permit. | 16 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 0 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 0 | 0 | 53388.8 | 66736 | 625
| S355800 / S355900 | Install 1st Inner HCal Support Ring | Technical scope: Install first (south side) Inner HCal support ring. Work Statement: sPHENIX technicans install the south Inner HCal support ring and align it appropriately with the sPHENIX SC Magnet in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
| S356000 / S356100 | Install Inner HCal | Technical scope: Install the 32 Inner HCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the Inner HCal insertion fixture, install the Inner HCal assembly into the sPHENIX SC Magnet and attach the end ring on the south side to the south Inner HCal support ring, in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
| S356200 / S356300 | Install 2nd Inner HCal Support Ring | Technical scope:Install first (north side) Inner HCal support ring. Work Statement: sPHENIX technicans install the north Inner HCal support ring and attach to the north side Inner HCal end ring. Attach the support ring to the outer HCal in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
| S356400 / S356410 / S356500 | Align/Survey Inner HCal to SC Magnet Centerline | Technical scope: Align all Inner HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Inner HCal support rings, align the Inner HCal to the SC Magnet in accordance with the Inner HCal installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 4 | 80 | 80 | 0 | 0 | 0 | 0 | 324.4 | 6488 | 9079.2 | 0 | 15891.6 | 19864.5 | 625
| S356600 / S356700 | Install Inner HCal Cables and Services | Technical scope: Install all Inner HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Inner HCal services onto the sPHENIX cradle carriage. | 20 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 80 | 0 | 240 | 0 | 0 | 0 | 0 | 8344 | 0 | 19464 | 0 | 0 | 27808 | 34760 | 625
| S356800 | Review Inner HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Inner HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Inner HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
| S356900 | Address Action Items from Inner Hcal ORR | Technical scope: evaluation and implementation of recommendations from Inner HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
| S357000 / S257100 / S357200 | Commission Inner HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Inner HCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 320 | 0 | 320 | 0 | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 32 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task. All costs for test equipment and supplies in support of commissioing efforts are supplied by the subsystem./M1 | 0 | 320 | 160 | 0 | 192 | 0 | 640 | 0 | 38880 | 16688 | 0 | 15571.2 | 0 | 0 | 71139.2 | 88924 | 500
| 2.05.07 | EMCal Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Electromagnetic Calorimeter (EMCal) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of EMCal detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of EMCal sectors are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.03: sPHENIX Electromagnetic Calorimeter. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design EMCal Integration/Installation Tooling/Fixtures 2. Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures 3. PrepareEMCal Integration/Installation Tooling/Fixtures Procedures 4. Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled EMCal Sectors to AH (procurement, fabrication, assembly, testing and delivery to BNL of EMCal sectors and services covered in WBS 1.03 work packages) 6. Install EMCal Sectors 7. Align/Survey EMCal to SC Magnet Centerline 8. Install EMCal Cables and Services 9. Review EMCal for Operational Readiness (ORR); address action items 10. Commission EMCall | [35 empty] | 32500 | [12 empty] | 0 | 49329 | 45266.2 | 24411.1 | 87506.9 | 59014.8 | 0 | 265528 | 331910 | 45125
| S357400 | Design EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of EMCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of EMCal sectors during assembly. The design of those tools is covered in WBS 1.03, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for EMCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing this detector inside the SC Magnet onto rails attached to the Inner HCal and for installing EMCal services. | 60 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 26 | 0 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 26 | 53 | 21 | 0 | 0 | 0 | 0 | 2711.8 | 4298.3 | 1703.1 | 0 | 0 | 8713.2 | 10891.5 | 0
| S357500 / S357600 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of EMCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the EMCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 120 | 40 | 48 | 0 | 0 | 0 | 0 | 12516 | 3244 | 3892.8 | 0 | 0 | 19652.8 | 24566 | 42000
| S357700 | PrepareEMCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the EMCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the EMCal and its services. | 10 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 8 | 0 | 0 | 0 | 0 | 8344 | 3244 | 648.8 | 0 | 0 | 12236.8 | 15296 | 0
| S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX EMCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from EMCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S358000 | Design/Safety Reviews Complete, EMCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S358100 | EMCal Sectors Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S358200 / S358300 | Transport Assembled EMCal Sectors to AH | Technical scope: Transport all 64 EMCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all EMCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full EMCal assembly. | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 64 | 120 | 0 | 0 | 0 | 0 | 0 | 5190.4 | 13618.8 | 0 | 18809.2 | 23511.5 | 625
| S358400 / S358500 | Install EMCal Sectors | Technical scope: Install the 64 EMCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the EMCal sector insertion fixture, install the EMCal sectors, one at a time, south sectors then north sector with one south and one north sector mated to each of the Inner HCal sectors, into the sPHENIX SC Magnet and attach to the mated Inner HCal sector by the bearing rails, in accordance with the EMCal installation procedure and work permit. | 16 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 0 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 0 | 0 | 53388.8 | 66736 | 625
| S358600 / S358610 / S358700 | Align/Survey EMCal to SC Magnet Centerline | Technical scope: Align all EMCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the EMCal support rings, align the EMCal to the SC Magnet in accordance with the EMCal installation procedure and work permit. | 7 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 20 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 6 | 0 | 0 | 74 | 80 | 0 | 0 | 729 | 0 | 0 | 6001.4 | 9079.2 | 0 | 15809.6 | 19762 | 625
| S358800 / S358900 | Install EMCal Cables and Services | Technical scope: Install all EMCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all EMCal services onto the sPHENIX cradle carriage. | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 224 | 64 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 32 | 224 | 320 | 0 | 0 | 0 | 3337.6 | 2595.2 | 18166.4 | 36316.8 | 0 | 60416 | 75520 | 625
| S359000 | Review EMCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the EMCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the EMCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S359100 | Address Action Items from EMCal ORR | Technical scope: evaluation and implementation of recommendations from EMCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S359200 / S359300 / S359400 | Commission EMCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the EMCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 625
| 2.05.08 | TPC Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Time Projection Chamber (TPC) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of TPC detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of TPC performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.02: sPHENIX Time Projection Chamber. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design TPC Integration/Installation Tooling/Fixtures 2. Fabricate/Procure TPC Integration/Installation Tooling/Fixtures 3. Prepare TPC Integration/Installation Tooling/Fixtures Procedures 4. Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled TPC Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of TPV components and services covered in WBS 1.02 work packages) 6. Install TPC Support 7. Install TPC (Mechanical) 8. Align/Survey TPC to SC Magnet Centerline 9. Install TPC Cables and Services 10. Review TPC for Operational Readiness (ORR); address action items 11. Commission TPC | [35 empty] | 33000 | [12 empty] | 0 | 48600 | 39634 | 20437.2 | 51579.6 | 36316.8 | 0 | 196567.6 | 245709.5 | 45750
| S359600 | Design TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of TPC Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of TPC sectors during assembly. The design of those tools is covered in WBS 1.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for TPC Lifting and insertion/positioning fixtures for installing this detector inside the SC Magnet and for installing TPC services. | 60 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 100 | 100 | 72 | 0 | 0 | 0 | 0 | 10430 | 8110 | 5839.2 | 0 | 0 | 24379.2 | 30474 | 0
| S359700 / S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of TPC Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal and EMCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 90 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the TPC is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 6258 | 1622 | 0 | 0 | 0 | 7880 | 9850 | 42000
| S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the TPC detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the TPC and its services . | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 8 | 0 | 0 | 0 | 0 | 4172 | 1622 | 648.8 | 0 | 0 | 6442.8 | 8053.5 | 0
| S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX TPC and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from TPC Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S360200 | Design/Safety Reviews Complete, TPC Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S360300 | TPC Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S360400 / S360410 / S360500 | Transport Assembled TPC Sections to AH | Technical scope: Transport TPC detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all TPC components to 1008 AH. | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 0 | 32 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 2595.2 | 0 | 0 | 4264 | 5330 | 625
| S360700 / S360800 | Install TPC Support | Technical scope: Install the TPC detector permanent structural support and alignment components into the SC Magnet and any temporary support equipment (e.g. scaffolding, temporary Work Statement: sPHENIX technicans, using the TPC custom and generic tooling, install the TPC permanent structural support components in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Includes labor to open pole tip doors | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 16 | 76 | 0 | 0 | 0 | 0 | 834.4 | 1297.6 | 6163.6 | 0 | 0 | 8295.6 | 10369.5 | 625
| S360900 / S361000 | Install TPC (Mechanical) | Technical scope: Install the TPC detector assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the TPC detector insertion fixture, install the TPC detector, in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 4 | 16 | 60 | 0 | 0 | 0 | 0 | 417.2 | 1297.6 | 4866 | 0 | 0 | 6580.8 | 8226 | 625
| S361100 / S361110 / S361200 | Align/Survey TPC to SC Magnet Centerline | Technical scope: Align all TPC sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the TPC permanent support structure, align the TPC to the SC Magnet in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
| S361300 / S361400 | Install TPC Cables and Services | Technical scope: Install all TPC services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all TPC services onto the sPHENIX cradle carriage. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 180 | 60 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 24 | 24 | 180 | 240 | 0 | 0 | 0 | 2503.2 | 1946.4 | 14598 | 27237.6 | 0 | 46285.2 | 57856.5 | 625
| S361500 | Review TPC for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the TPC and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the TPC will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 1297.6 | 0 | 0 | 2966.4 | 3708 | 0
| S361600 | Address Action Items from TPC ORR | Technical scope: evaluation and implementation of recommendations from TPC ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 1297.6 | 0 | 0 | 2966.4 | 3708 | 0
| S361700 / S361800 / S361900 | Commission TPC | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the TPC. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 625
| 2.05.09 | INTT Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Intermediate Silicon Strip Tracker (INTT) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of INTT detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of INTT performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.01: sPHENIX Intermediate Silcon Strip Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design INTT Integration/Installation Tooling/Fixtures 2. Fabricate/Procure INTT Integration/Installation Tooling/Fixtures 3. Prepare INTT Integration/Installation Tooling/Fixtures Procedures 4. Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled INTT Components to AH (procurement, fabrication, assembly, testing and delivery to BNL of INTT components and services covered in WBS 3.11 work packages) 6. Install INTT Support 7. Install INTT (mechanical) 8. Align/Survey INTT to SC Magnet Centerline 9. Install INTT Cables and Services 10. Review INTT for Operational Readiness (ORR); address action items from INTT ORR 11. Commission INTT | [35 empty] | 33000 | [12 empty] | 0 | 48600 | 32750.2 | 17842 | 48011.2 | 36316.8 | 0 | 183520.2 | 229400.25 | 45625
| S362000 | Design INTT Integration/Installation Tooling/Fixtures | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 0 | 0 | 0 | 0 | 0 | 3129 | 4866 | 0 | 0 | 0 | 7995 | 9993.75 | 0
| S362100 / S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of INTT Integration and Installation tooling components for sPHENIX. (Note: see next task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the INTT is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 6258 | 1622 | 0 | 0 | 0 | 7880 | 9850 | 42000
| S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the INTT detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the INTT and its services . | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 4172 | 1622 | 0 | 0 | 0 | 5794 | 7242.5 | 0
| S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX INTT and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from INTT Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S362600 | Design/Safety Reviews Complete, INTT Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S362700 | INTT Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S362800 / S362900 | Transport Assembled INTT Sections to AH | Technical scope: Transport INTT detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all INTT components to 1008 AH. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 24 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1946.4 | 0 | 0 | 3429.6 | 4287 | 625
| S363000 / S363100 | Install INTT Support | Technical scope: Install the INTT detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector structural supports, in accordance with the INTT installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
| S363200 / S363300 | Install INTT (mechanical) | Technical scope: Install the INTT detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector, in accordance with the INTT installation procedure and work permit. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
| S363400 / S363410 / S363500 | Align/Survey INTT to SC Magnet Centerline | Technical scope: Align all INTT sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the INTT permanent support structure, align the INTT to the SC Magnet in accordance with the INTT installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
| 363600 / S363700 | Install INTT Cables and Services | Technical scope: Install all INTT services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all INTT services onto the sPHENIX cradle carriage. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 240 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 24 | 240 | 240 | 0 | 0 | 0 | 5006.4 | 1946.4 | 19464 | 27237.6 | 0 | 53654.4 | 67068 | 625
| S363800 | Review INTT for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the INTT and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the INTT will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S363900 | Address Action Items from INTT ORR | Technical scope: evaluation and implementation of recommendations from INTT ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S364000 / S364100 / S364200 | Commission INTT | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the INTT. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
| 2.05.10 | MVTX Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Monolithic Active Pixel Vertex Detector (MVTX) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of MVTX detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of MVTX performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 3.02: sPHENIX Monolithic Active Pixel Vertex Detector. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design MVTX Integration/Installation Tooling/Fixtures 2. Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures 3. Prepare MVTX Integration/Installation Tooling/Fixtures Procedures 4. Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled MVTX Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of MVTX components and services covered in WBS 3.02 work packages) 6. Install MVTX Support 7. Install MVTX (mechanical) 8. Align/Survey MVTX to SC Magnet Centerline 9. Install MVTX Cables and Services 10. Review MVTX for Operational Readiness (ORR); address action items from MVTX ORR 11. Commission MVTX | [35 empty] | 32500 | [12 empty] | 0 | 65124 | 27743.8 | 14435.8 | 58392 | 9079.2 | 0 | 174774.8 | 218468.5 | 45000
| S364300 | Design MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of MVTX Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of MVTX sectors during assembly. The design of those tools is covered in WBS 3.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for MVTX Lifting and insertion/positioning fixtures for installing this detector inside the TPC and the magnet and for installing MVTX services. | 60 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 0 | 0 | 0 | 0 | 0 | 3129 | 4866 | 0 | 0 | 0 | 7995 | 9993.75 | 0
| S364400 / S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of MVTX Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the MVTX is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 20 | 0 | 0 | 0 | 0 | 6258 | 1622 | 1622 | 0 | 0 | 9502 | 11877.5 | 42000
| S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the MVTX detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the MVTX and its services . | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 4172 | 811 | 0 | 0 | 0 | 4983 | 6228.75 | 0
| S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX MVTX and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from MVTX Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S364900 | Design/Safety Reviews Complete, MVTX Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S365000 | MVTX Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S365300 / S365400 | Transport Assembled MVTX Sections to AH | Technical scope: Transport MVTX detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all MVTX components to 1008 AH. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 0 | 32 | 0 | 0 | 0 | 0 | 834.4 | 0 | 2595.2 | 0 | 0 | 3429.6 | 4287 | 625
| S365500 / S365600 | Install MVTX Support | Technical scope: Install the MVTX detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector structural supports, in accordance with the MVTX installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
| 2.05.01.10.10 | Install MVTX (mechanical) | Technical scope: Install the MVTX detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector, in accordance with the MVTX installation procedure and work permit. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 80 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 6488 | 0 | 0 | 7971.2 | 9964 | 0
| S366700 / S366710 / S366800 | Align/Survey MVTX to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | Craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
| S366900 / S367000 | Install MVTX Remaining Cables and Services | Technical scope: Install all MVTX services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all MVTX services onto the sPHENIX cradle carriage. | 30 | 0 | 72 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Includes all hours added from LBNL estimates | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 72 | 0 | 0 | 320 | 0 | 0 | 0 | 8748 | 0 | 0 | 25952 | 0 | 0 | 34700 | 43375 | 625
| S367100 / S367200 | Review MVTX for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the MVTX and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the MVTX will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 32 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 32 | 8 | 8 | 16 | 0 | 0 | 0 | 3888 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 6668.8 | 8336 | 0
| S367300 / S367400 | Address Action Items from MVTX ORR | Technical scope: evaluation and implementation of recommendations from MVTX ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 32 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 32 | 8 | 8 | 16 | 0 | 0 | 0 | 3888 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 6668.8 | 8336 | 0
| S367500 / S367600 | Commission MVTX | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the MVTX. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 500 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 840 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
2.05.11 | 2.05.11 | Min Bias Integration/Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts to install the sPHENIX Minimum Bias Tracker (Min Bias) components in the sPHENIX Assembly Hall (AH) at Building 1008. The analyses required to determine the design of Min Bias detector structural components and equipment needed, the design, procurement and acceptance of such equipment, reviews of these analyses and the assembly and testing of Min Bias performance are not in the scope of this work package and control account but rather are part of sPHENIX WBS 1.07: sPHENIX Minimum Bias tracker. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Design Min Bias Integration/Installation Tooling/Fixtures 2. Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures 3. Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures 4. Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification; address action items 5. Transport Assembled Min Bias Sections to AH (procurement, fabrication, assembly, testing and delivery to BNL of Min Bias components and services covered in WBS 1.07 work packages) 6. Install Min Bias Support 7. Install Min Bias (mechanical) 8. Align/Survey Min Bias to SC Magnet Centerline 9. Install Min Bias Cables and Services 10. Review Min Bias for Operational Readiness (ORR); address action items from Min Bias ORR 11. Commission Min Bias | [35 empty] | 13000 | [12 empty] | 0 | 48600 | 28161 | 14598 | 35846.2 | 29507.4 | 0 | 156712.6 | 195890.75 | 17625
| S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Min Bias Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Min Bias sectors during assembly. The design of those tools is covered in WBS 1.07. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Min Bias Lifting and insertion/positioning fixtures for installing this detector inside the SCMagnet and for installing Min Bias services. | 60 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 30 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2433 | 0 | 0 | 0 | 4101.8 | 5127.25 | 0
| S367800 / S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Min Bias Integration and Installation tooling components for sPHENIX. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the MinBias is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 30 | 10 | 10 | 0 | 0 | 0 | 0 | 3129 | 811 | 811 | 0 | 0 | 4751 | 5938.75 | 14000
| S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Min Bias detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Min Bias and its services . | 10 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 4172 | 1622 | 0 | 0 | 0 | 5794 | 7242.5 | 0
| S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Min Bias and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Min Bias Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
| S368300 | Design/Safety Reviews Complete, Min Bias Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S368400 | Min Bias Ready for Installation | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S368500 / S368600 | Transport Assembled Min Bias Sections to AH | Technical scope: Transport Min Bias detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all Min Bias components to 1008 AH. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 625
| S368700 / S368800 | Install Min Bias Support | Technical scope: Install the Min Bias detector assembly structural support into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector structural supports, in accordance with the Min Bias installation procedure and work permit. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 625
| S368900 / S369000 | Install Min Bias (mechanical) | Technical scope: Install the Min Bias detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector, in accordance with the Min Bias installation procedure and work permit. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 625
| S369100 / S369110 / S369200 | Align/Survey Min Bias to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 32 | 20 | 0 | 0 | 0 | 0 | 0 | 2595.2 | 2269.8 | 0 | 4865 | 6081.25 | 625
| S369300 / S369400 | Install Min Bias Cables and Services | Technical scope: Install all Min Bias services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Min Bias services onto the sPHENIX cradle carriage. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 240 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 24 | 240 | 240 | 0 | 0 | 0 | 5006.4 | 1946.4 | 19464 | 27237.6 | 0 | 53654.4 | 67068 | 625
| S269500 | Review Min Bias for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S269600 | Address Action Items from Min Bias ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
| S369700 / S369800 / S369900 | Commission Min Bias | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Min Bias. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
| 2.05.12 | sPHENIX Full Detector Installation | Technical Scope: This work package includes all scientific, engineering and technical staff efforts tomove the sPHENIX support carriage qwith the larger detector components mostly installed align the carrtiage ctradle to the beam line, then, after all of the inner detecors not previously installed are installed, commission the full detectro and make it ready for sPHENIX run 1. Work Statement: The specific assembly and installation tasks detailed in this work package are: 1. Move Full sPHENIX to IR 2. Align Full sPHENIX to Nominal Beamline and IP 3. Perform Full System Commissioning 4. Review the Full sPHENIX Detector for Operational Readiness (ORR)/Address action items | [35 empty] | 2000 | [12 empty] | 0 | 38880 | 83857.2 | 1297.6 | 40225.6 | 4539.6 | 0 | 168800 | 211000 | 2500
| S370000 / S370100 | Move Full sPHENIX to IR | Technical Scope: All efforts related to the relocation of the partially assembled sPHENIX experimetal equipment, mounted on the sPHENIX cradle carriage from the assembly hall (AH) to the interaction region (IR). The Calorimeter detectors (Outer and Inner detector, and the TPC tracker), the SC Magnet and all of its on-carriage support services, the end caps/pole tips and all on carriage work platforms and related access components will be fully installed, aligned and partially commissioned at this point. The INTT, MVTX and MBD subsystems (detectors and support ing services/equipment) will be installed, aligned and commissioned after the carriage is moved to the IR. Work Statement: gather Move the carriage from the AH to the IR. sPHENIX technicians will perform this task using existing hydraulic rams (repurposed from PHENIX hydraulic system used to drive carriages in and out of the IR. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 160 | 96 | 24 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 160 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 12976 | 0 | 0 | 14459.2 | 18074 | 1250
| S370200 / S370210 / S370300 | Align Full sPHENIX to Nominal Beamline and IP | Technical scope: Align the cradle carriage with its partial complement of subsystems to the nominal RHIC beamline and the sPHENIX interaction Point (IP). Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the cradle carriage align cradle carriage with the nominal RHIC beam path and the sPHENIX IP in accordance with the integration/installation plan/procedure and work permit. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 16 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 1000 | 25% | 25% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 64 | 40 | 0 | 0 | 0 | 0 | 0 | 5190.4 | 4539.6 | 0 | 9730 | 12162.5 | 1250
| S370400 | sPHENIX Installation Complete (MIE) | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| #REF! | Full System Commissioning (MIE + INTT + MVTX) | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of all sPHENIX MIE subsystems as a fully integrated system. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 320 | 0 | 320 | 0 | 780 | 0 | 0 | 160 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 320 | 780 | 0 | 256 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S370600 | Full sPHENIX Detector Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 38880 | 81354 | 0 | 20761.6 | 0 | 0 | 140995.6 | 176244.5 | 0
| S370700 | Address Action Items from Full sPHENIX Detector ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S370800 | All Design/Safety/Readiness Reviews Complete, sPHENIX Ready for Operations | milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
|  |  | Resource Summary for Integration Documentation, Technical Coordination, Installation, Tooling, Fixtures and Subsystem Installation in Hours by Resource Type |  | Administrator ADMIN1 PO | Scientist | Scientist (hours) |  |  | Engineer | Engineer/Professional (hours) |  |  |  | Designer | Designer/Drafter (hours) | [5 empty] | Technician | Technicians (hours) | [8 empty] | Trade | Bargaining Unit Trades (hours) |  |  |  |  | Student (unpaid) | [5 empty] | Resource Summary for Integration Documentation, Technical Coordination, Installation, Tooling, Fixtures and Subsystem Installation in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
[7 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs
[5 empty] | hours | hours | Scientist | Scientist | Scientist | hours |  |  |  |  | hours | [6 empty] | hours | [9 empty] | hours | [5 empty] | hours | [6 empty] | 0 | 2962 | 6462 | 3031 | 13469 | 4268 | 9800
[5 empty] | 0 | 2962 | 6 | 2820 | 136 | 6462 | 754 | 0 | 3678 | 2030 | 3031 | 3015 | 16 | 0 | 0 | 0 | 0 | 13469 | 8325 | 3264 | 0 | 1347 | 409 | 80 | 40 | 0 | 0 | 4268 | 128 | 1672 | 2356 | 0 | 112 | 9800
0
[7 empty] | 0 | 4682
0
0
1968
0
[6 empty] | 39992 | 0
0
[6 empty] | -946 | 0
0
[6 empty] | -2502 | 3152
3036
[7 empty] | 8156 | 12838

## Int & Inst Plans Work Package
Return to Navigation Page
| WBS # | 2.05.01 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [7 empty] | Project Labor Cost by Resource Category
|  | Subsystem Interface & Integration Plan | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students |  | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
|  | TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs |  | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
| S344300 | Create Subsystem Interface & Integration Plan | Technical Scope: Preparation of an Interface and Integration Plan. Work Statement: Gather information about all sPHENIX subsystems (dimensions, tolerances required services, environmental requirements, etc.) and create a unified plan to integrate all of the subsystems into the single sPHENIX experiment. | 160 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 160 | 0 | 0 | 0 | Complete | 0 | 0 | 8344 | 12976 | 0 | 0 | 0 | 21320 | 26650 | 0
| S344400 | Create Subsystem Initial Envelope Drawings | Technical Scope: Creation of initial envelope drawings for all subsystems. Work Statement: prepare drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Iterate drawings to reolve conflicts between subsystems. | 40 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S344500 | Create Subsystem Outline/Interface Drawings | Technical Scope: Creation of final envelope drawings for all subsystems. Work Statement: Finalize drawings to globally define space allocation for all detector subsystems, infrastructure, support services and potential future additions, and individual outline/interface drawings for each detector subsystem. Freeze envelopes and interfaces at final design. | 20 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| S344600 | Create Cable Management Plan | Technical Scope: Create Cable Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing and supporting canl;es/fibers and related services for all sPHENI detectors. | 20 | 0 | 0 |  | 0 | 0 | 0 | 120 | 0 | 0 | 40 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 120 | 40 | 0 | 0 | 0 |  | 0 | 0 | 12516 | 3244 | 0 | 0 | 0 | 15760 | 19700 | 0
| S344700 | Create Services Management Plan | Technical Scope: Create Servces Management plan for all detector subsystems. Work Statement: Prepare an overall plan for routing cooling, gas, etc between source and distribution panels and from there to detector electronics, control racks, front end modules, etc. (does not include cryogenics - see magnet for Cryo services) | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 32 | 0 | 0 |  | 0 | 0 | 8344 | 3244 | 2595.2 | 0 | 0 | 14183.2 | 17729 | 0
| S344800 | Create Survey Plan | Technical Scope: Create Survey plan for all detector subsystems. Work Statement: Prepare an overall plan for aligning each of the sPHENIX subsystems into the total experiment, preserving the dimensional alignments and performance requirements . Plan will determine how achieving this alignment will be implemented in the subsystems design and how this alignment will be erified and documented by RHIC surveyors. | 20 | 0 | 0 |  | 0 | 0 | 0 | 40 |  | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 40 | 32 | 0 | 0 |  | 0 | 0 | 4172 | 3244 | 2595.2 | 0 | 0 | 10011.2 | 12514 | 0
| S344900 | Create Installation Plan | Technical Scope: Create overall Installation plan and sequence for sPHENIX | 20 | 0 | 0 |  | 0 | 0 | 0 | 200 | 0 | 0 | 200 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  |  |  | 0 | 0 | 200 | 40 | 0 | 0 | 0 |  | 0 | 0 |  | 3244 | 0 | 0 | 0 |  |  | 0
| S345000 | Review Integration and Installation Plan Design/Safety | Technical scope: Preparation for and execution of review for Engineering and safety review of Integration and Installation Plan. Work Statement: gather documentation describing the design and analyses of the integration and installation of all sPHENIX subsystems. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. | 20 | 0 | 20 |  | 0 | 20 | 0 | 20 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 20 | 20 | 20 | 0 | 0 | 0 |  | 0 | 2430 | 2086 | 1622 | 0 | 0 | 0 | 6138 | 7672.5 | 0
| S345100 | Review Cable Management Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Cable management Plan Plan. Work Statement: gather documentation describing the design and analyses of the cable management plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 20 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 10 | 0 | 0 | 0 |  | 0 | 0 | 3129 | 811 | 0 | 0 | 0 | 3940 | 4925 | 0
| S345200 | Review Survey Plan | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Surey Plan Plan. Work Statement: gather documentation describing the design and analyses of thesurvey plan for all sPHENIX subsystems. Prepare a presentation describing this plan. Present to a panel determined by sPHENIX engineering and management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 |  | 0 | 0 | 1043 | 811 | 811 | 0 | 0 | 2665 | 3331.25 | 0
20 | S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey Plans) Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from subsystem Interface Integrationand Installation, cable management and survey plans engineering and safety reviews. Work Statement: receive action items from reviewers, evaluate action items implement changes, modifications to plans to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0 |  | sPHENIX Engineers, Technicians and Designers; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 |  | 0 | 0 | 1043 | 811 | 811 | 0 | 0 | 2665 | 3331.25 | 0
|  | Design/Safety Reviews Complete, Ready to Begin Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[52 empty] | TOTAL HOURS | 824
| Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students |  | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[46 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs |  | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 76682.4 | 95853 | 0 | 0 | 25% | 0%
[21 empty] | Notes | [24 empty] | 0 | 20 | 510 | 210 | 84 | 0 | 0 |  | 0 | 2430 | 40677 | 30007 | 6812.4 | 0 | 0
There are no materials or supplies required for this work Package
Labor Estimate Details
| WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
| S344300 | Create Subsystem Interface & Integration Plan |  | 20
SCI3_PO
| S344400 | Create Subsystem Initial Envelope Drawings
| S344500 | Create Subsystem Outline/Interface Drawings
| S344600 | Create Cable Management Plan
| S344700 | Create Services Management Plan
| S344800 | Create Survey Plan
| S345000 | Review Integration and Installation Plan Design/Safety
| S345100 | Review Cable Management Plan
| S345200 | Review Survey Plan
| S345300 | Address Action Items from Subsystem Interface & Integration Plans (Interface, Integration, Cable Management and Survey Plans) Design & Safety Reviews
Design/Safety Reviews Complete, Ready to Begin Installation
Illustrations
Note: In some of the illustrations below and on other sheets in this documents older versions of the sPHENIX WBS numbering system is shown: the following table indicates the numbering system update:
| Old WBS | New WBS
| 2.08 | 2.02
| 2.0901 | 2.03.01
| 2.09.02 | 2.04.01
| 2.09.03 | 2.04.02
| 2.10 | 2.05
| 3.11 | 3.01
| 3.12 | 3.02

## Infra Inst Work Package
Return to Navigation Page
WBS # | 2.05.02 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Infrastructure Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S346000 / S346100 | Install Line Electric Power Distribution | Technical Scope: All tasks related to the installation of Line electric power distribution for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 0 | 0 | 240 | 0 | 0 | 0 | 8344 | 0 | 0 | 27237.6 | 0 | 35581.6 | 44477 | 625
S346500 / S346510 | Install Cryogenics Supply Structural Suport | Technical Scope: All tasks related to the installation of cryo supply structural support (including power and control cables) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 160 | 80 | 0 | 80 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 160 | 16 | 160 | 160 | 0 | 0 | 0 | 16688 | 1297.6 | 12976 | 18158.4 | 0 | 49120 | 61400 | 625
S346300 / S346310 | Install Beampipe/Vacuum | Technical Scope: All tasks related to the installation of beam/vacuum components and support structures) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 100 | 80 | 0 | 20 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 100 | 16 | 120 | 0 | 0 | 0 | 0 | 10430 | 1297.6 | 9732 | 0 | 0 | 21459.6 | 26824.5 | 625
S345500 | Install IR HVAC | Technical Scope: All tasks related to the installation of IR/HVAC components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 10 | 0 | 0 |  | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 32 | 32 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 40 | 0 | 40 | 64 | 0 | 0 | 0 | 4172 | 0 | 3244 | 7263.36 | 0 | 14679.36 | 18349.2 | 625
S347600 / S347700 | Install IR Electronics Cooling Water | Technical Scope: All tasks related to the installation of electronics cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 112 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 40 | 16 | 160 | 112 | 0 | 0 | 0 | 4172 | 1297.6 | 12976 | 12710.88 | 0 | 31156.48 | 38945.6 | 625
S345700 / S345800 | Install On Detector and Off Detector Safety Subsystems | Technical Scope: All tasks related to the installation of On-detector and Off-detector components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 40 | 40 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 0 | 200 | 0 | 0 | 0 | 0 | 8344 | 0 | 16220 | 0 | 0 | 24564 | 30705 | 625
S346900 | Install Detector Support Services Systems | Technical Scope: All tasks related to the installation of Detector support services components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 400 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 80 | 32 | 400 | 200 | 0 | 0 | 0 | 8344 | 2595.2 | 32440 | 22698 | 0 | 66077.2 | 82596.5 | 625
S347100 / S347200 | Install Electronics Racks | Technical Scope: All tasks related to the installation of electronic racks and related generic equipment components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 60 | 0 | 0 |  | 0 | 0 | 0 | 480 | 0 | 0 | 240 | 240 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 1120 | 560 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 480 | 96 | 1120 | 0 | 0 | 0 | 0 | 50064 | 7785.6 | 90832 | 0 | 0 | 148681.6 | 185852 | 625
S3437400 | Install Gas and Cooling System Services | Technical Scope: All tasks related to the installation of gas and cooling system components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 60 | 0 | 0 |  | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 120 | 96 | 720 | 0 | 0 | 0 | 0 | 12516 | 7785.6 | 58392 | 0 | 0 | 78693.6 | 98367 | 625
S3346700 / S346710 | Install Non-IR Infrastructure | Technical Scope: All tasks related to the installation of non-IR infrastructure components) for sPHENIX. Work Statement: gather all relevant equipment procured for this task, prepare procedure/work permit to define the installation steps. Assign personnel to perform all of steps in procedure. Evaluate performance of the work procedure. | 20 | 0 | 0 |  | 0 | 0 | 0 | 160 | 0 | 0 | 80 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 480 | 160 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 80 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | All Actual equipment costs are included in infrastructure (see WBS 1.9) | Based on experience with similar efforts/L4 | Allowance for assembly supplies. No special tooling expected./ M4 | 0 | 0 | 160 | 40 | 480 | 160 | 0 | 0 | 0 | 16688 | 3244 | 38928 | 18158.4 | 0 | 77018.4 | 96273 | 625
[50 empty] | TOTAL Hours | 5988
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 547031.84 | 683789.8 | 6250 | 5000 | 25% | 25%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 0 | 1340 | 312 | 3400 | 936 | 0 | 0 | 0 | 139762 | 25303.2 | 275740 | 106226.64 | 0
S346200 / S346210 | Install Line Electric Power Distribution | M&S Allowance |  |  | 2 |  | 500 | 1000
S346600 | Install Cryogenics Supply Structural Suport | M&S Allowance |  |  | 1 |  | 500 | 500
S346400 | Install Beampipe/Vacuum | M&S Allowance |  |  | 1 |  | 500 | 500
S345600 | Install IR HVAC | M&S Allowance |  |  | 1 |  | 500 | 500
S347800 / S347810 | Install IR Electronics Cooling Water | M&S Allowance |  |  | 2 |  | 500 | 1000
S345900 / S345910 | Install On Detector and Off Detector Safety Subsystems | M&S Allowance |  |  | 2 |  | 500 | 1000
S347000 | Install Detector Support Services Systems | M&S Allowance |  |  | 1 |  | 500 | 500
S347300 / S347310 | Install Electronics Racks | M&S Allowance |  |  | 2 |  | 500 | 1000
S347500 | Install Gas and Cooling System Services | M&S Allowance |  |  | 1 |  | 500 | 500
S346800 | Install Non-IR Infrastructure | M&S Allowance |  |  | 1 |  | 500 | 500
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations
(See relevant ICD'd for illustrations)

## Cradle Inst Work Package
Return to Navigation Page
WBS # | 2.05.03 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Cradle Carriage Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S347900 / S347910 | Design Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of cradle carriage Integration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation. | 40 | 0 | 0 |  | 0 | 0 | 0 | 100 | 80 | 0 | 20 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 100 | 160 | 0 | 0 | 0 | 0 | 0 | 10430 | 12976 | 0 | 0 | 0 | 23406 | 29257.5 | 0
S348000 / S348010 / S348100 | Fabricate/Procure Cradle Carriage Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX Cradle/carriage. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items. | 120 | 0 | 0 |  | 0 | 0 | 0 | 240 | 192 | 0 | 48 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the cradle carriage is fairly well set, but the details need to be established/M5 | 0 | 0 | 240 | 160 | 0 | 0 | 0 | 0 | 0 | 25032 | 12976 | 0 | 0 | 0 | 38008 | 47510 | 56000
S348200 / S348210 | Prepare Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Documentation | Technical Scope: Create a written integration /installation procedure for the assembly of the cradle carriage in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX cradle carriage. | 30 | 0 | 0 |  | 0 | 0 | 0 | 78 | 30 | 0 | 48 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 78 | 30 | 0 | 0 | 0 | 0 | 0 | 8135.4 | 2433 | 0 | 0 | 0 | 10568.4 | 13210.5 | 0
S348300 / S348310 | Review sPHENIX Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX cradle carriage assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX cradle carriage and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S348400 / S348810 | Address Action Items from Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from cradle carriage Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S348500 | Design/Safety Reviews Complete, Cradle Carriage Integration/Installation Tooling/Fixtures/Procedures Ready for service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S348600 | Ready to Assemble Cradle Carriage in AH | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S348700 / S348710 / S348800 | Assemble Cradle Carriage base, Cradle Carriage alignment and carriage roller supports | Technical scope: Assembly and installation of cradle base. Work Statement: Using work plan/permit, tooling and fixtures, installthe cradle carriage roller system, base plate and relevant alignment provisions. | 20 | 0 | 0 |  | 0 | 0 | 0 | 48 | 32 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 2500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 16 | 480 | 160 | 0 | 0 | 0 | 5006.4 | 1297.6 | 38928 | 18158.4 | 0 | 63390.4 | 79238 | 3125
S348900 / S348910 / S349000 | Assemble HCal cradle onto base | Technical scope: Installation/assembly of cradle onto base Work Statement: Using work plan/permit, tooling and fixtures, install the cradle onto the carriage base plate and relevant alignment provisions. | 20 | 0 | 0 |  | 0 | 0 | 0 | 48 | 32 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 16 | 80 | 64 | 0 | 0 | 0 | 5006.4 | 1297.6 | 6488 | 7263.36 | 0 | 20055.36 | 25069.2 | 3750
S349100 / S349200 | Install magnet mounting feet | Technical scope: Installation of magnet mounting feet onto the HCal sectors installed on carriage cradles. (Note the installation of the Outer HCal sectors is described in WBS 2.05.01.04 The Magnet is installed before the upper HCal sectors are installed (see WBS 2.05.01.05 for Magnet installation details). Work Statement: Using work plan/permit, tooling and fixtures, install the magnet mounting feet and relevant alignment provisions onto the HCal sectors. | 10 | 0 | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 10 | 8 | 160 | 0 | 0 | 0 | 0 | 1043 | 648.8 | 12976 | 0 | 0 | 14667.8 | 18334.75 | 3750
S349300 / S349310 / S349400 | Install platforms & access | Technical scope: Installation of platforms and access onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the work platforms, access and related components onto the cradle base. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 240 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 240 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 19464 | 0 | 0 | 24099.2 | 30124 | 1250
S349500 / S349510 / S349600 | Install Pole Tips | Technical scope: Installation of end caps/pole tips onto the cradle carriage assembly. Work Statement: Using work plan/permit, tooling and fixtures, install the end caps/pole tips and related components onto the cradle base. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 0 | 0 | 3000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 8 | 64 | 32 | 0 | 0 | 0 | 1668.8 | 648.8 | 5190.4 | 3631.68 | 0 | 11139.68 | 13924.6 | 3750
[38 empty] | TOTAL Materials | 52500 | [10 empty] | TOTAL Hours | 2314
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 209970.04 | 262462.55 | 71625 | 52500 | 25% | 36.43%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 0 | 604 | 430 | 1024 | 256 | 0 | 0 | 0 | 62997.2 | 34873 | 83046.4 | 29053.44 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## Outer HCal Inst Work Package
Return to Navigation Page
WBS # | 2.05.04 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Outer HCal Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S349800 | Design Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Outer HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Outer HCal sectors during assembly. The design of those tools is covered in WBS 1.04, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated, and the design of the installation tools will need to be modified from the assembly handling tools to include provision for fine adjustment of orientation to allow the sectors to be installed in 32 different orientations.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Outer HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding, and sector assembly spreader tools for installing the Outer HCal sectors and services. | 30 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | Design completed by HCAl subsystem | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 24 | 0 | 0 | 0 | 0 | 3129 | 4866 | 1946.4 | 0 | 0 | 9941.4 | 12426.75 | 0
S349900 / S350000 | Fabricate/Procure Outer HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Outer HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Sc Magnet assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the Outer HCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, alignment fixtures and scaffolding/M5 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 5006.4 | 3892.8 | 3892.8 | 0 | 0 | 12792 | 15990 | 84000
S350100 | Prepare Outer HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Outer HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Outer HCal and its services (e.g. critical lift calculations, etc.) | 20 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 16 | 16 | 0 | 0 | 0 | 0 | 4172 | 1297.6 | 1297.6 | 0 | 0 | 6767.2 | 8459 | 0
S350200 | Review Outer HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Outer HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S350300 | Address Action Items from Outer Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Outer HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S350400 | Design/Safety Reviews Complete, Outer HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S350500 | Outer HCal Sectors Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S350600 / S350700 | Transport Assembled Outer HCal Sectors to AH (Partial Shipment) | Technical scope: Transport first 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 |  | 0 | 256 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 128 | 256 | 0 | 0 | 0 | 834.4 | 648.8 | 10380.8 | 29053.44 | 0 | 40917.44 | 51146.8 | 625
S350800 / S350900 | Install Partial Outer HCal for SC Magnet Install | Technical scope: Install lower 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure.After these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package) | 60 | 0 | 0 |  | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 64 | 0 | 192 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 48 | 512 | 256 | 0 | 0 | 0 | 6675.2 | 3892.8 | 41523.2 | 29053.44 | 0 | 81144.64 | 101430.8 | 625
S351000 / S351100 | Transport Remainder of Outer Hcal Sectors to AH | Technical scope: After the sPHENIX SC Magnet is be installed (see 1.10.2.4 for SC Magnet installation work package), transport remaining 16 Outer HCal sectors from their sector assembly site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move 16 Outer HCal sectors to 1008 AH, in groups of 4 for Installation onto the sPHENIX cradle carriage. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 0 | 0 | 256 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 128 | 256 | 0 | 0 | 0 | 834.4 | 648.8 | 10380.8 | 29053.44 | 0 | 40917.44 | 51146.8 | 625
S351200 / S351300 | Install Remainder of Outer HCal Sectors | Technical scope: Install upper 16 Outer HCal sectors onto cradle carriage. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install 16 Outer HCal sectors onto the sPHENIX cradle carriage, in groups of 4 at a time in accordance with the Outer HCal work permit and installation procedure. before these 16 sectors are installed, the sPHENIX SC Magnet will be installed (see 1.10.2.4 for SC Magnet installation work package) | 20 | 0 | 0 |  | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 64 | 0 | 192 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 256 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 29053.44 | 0 | 82442.24 | 103052.8 | 625
S351400 / S351410 / S351500 | Align/Survey Outer HCal to SC Magnet Centerline | Technical scope: Align all Outer HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Outer HCal and the cradle carriage, align the Outer HCal to to the nominal IP and beam RHIC axis in accordance with the Outer HCal installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 |  | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 4 | 80 | 80 | 0 | 0 | 0 | 0 | 324.4 | 6488 | 9079.2 | 0 | 15891.6 | 19864.5 | 625
S351600 / S351700 | Install Outer HCal Cables and Services | Technical scope: Install all Outer HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Outer HCal services onto the sPHENIX cradle carriage. | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 80 | 0 | 240 | 0 | 0 | 0 | 0 | 8344 | 0 | 19464 | 0 | 0 | 27808 | 34760 | 625
S351800 | Review Outer HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Outer HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Outer HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Outer HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S351900 | Address Action Items from Outer Hcal ORR | Technical scope: evaluation and implementation of recommendations from Outer HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 20% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S352000 / S352100 / S352200 | Commission Outer HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Outer HCal. Work Statement: Perform operational checks on HCal operational and control equipment, . Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 160 |  | 0 | 160 | 0 | 192 | 0 | 0 | 32 | 160 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 640 | 320 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task. All costs for test equipment and supplies in support of commissioing efforts are supplied by the subsystem./M1 | 0 | 160 | 192 | 32 | 640 | 0 | 640 | 0 | 19440 | 20025.6 | 2595.2 | 51904 | 0 | 0 | 93964.8 | 117456 | 625
[38 empty] | TOTAL Materials | 63500 | [10 empty] | TOTAL Hours | 5166
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 422412.36 | 528015.45 | 88375 | 63500 | 25% | 39.17%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 160 | 566 | 320 | 2376 | 1104 | 640 | 0 | 19440 | 59033.8 | 25952 | 192693.6 | 125292.96 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## Magnet Inst Work Package
Return to Navigation Page
WBS # | 2.05.05 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| sPHENIX SC Magnet Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S352300 | Design SC Magnet Integration/Installation Tooling/Fixtures/Procedures | Technical Scope: All tasks related to the design of SC Magnet Integeration and Installation tooling components for sPHENIX. Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation. | 30 | 0 | 0 |  | 0 | 0 | 0 | 180 | 0 | 0 | 180 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 180 | 60 | 24 | 0 | 0 | 0 | 0 | 18774 | 4866 | 1946.4 | 0 | 0 | 25586.4 | 31983 | 0
S352400 / S352500 | Fabricate/Procure SC Magnet Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication/procurement of integration/installation of sPHENIX SC Magnet. Work Statement: gather all relevant procurement documentation, submit to procurement, track and manage the procurement receive and inspect/accept procured items. | 60 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the superconducting magnet is fairly well set, but the details need to be established/M4 | 0 | 0 | 30 | 10 | 10 | 0 | 0 | 0 | 0 | 3129 | 811 | 811 | 0 | 0 | 4751 | 5938.75 | 37500
S352600 | Prepare SC Magnet Integration/Installation Procedures | Technical Scope: Create a written integration /installation procedure for the assembly of the SC Magnet in the sPHENIX AH. Work Statement: Prepare an overall plan/work permit for installing all components of the sPHENIX SC Magnet. | 10 | 0 | 0 |  | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 2086 | 811 | 0 | 0 | 0 | 2897 | 3621.25 | 0
S352700 | Review sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX SC Magnet and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S352800 | Address Action Items from SC Magnet Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from SC Magnet Installation plans engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S352900 | Design/Safety Reviews Complete, sPHENIX SC Magnet Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S353000 | Ready to Install SC Magnet | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S353100 / S353110 / S353200 | Transport SC Magnet from 912 to AH | Technical scope: Transportation of SC Magnet from 912 to 1008 AH by BNL riggers. Work Statement: In accordance with work plan/permit, tooling and fixtures, transport the SC Magnet from 912 to 1008, taking care to handle the Magnet and its services with appropriate care. | 2 | 0 | 0 |  | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 1500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 4 | 32 | 64 | 0 | 0 | 0 | 3337.6 | 324.4 | 2595.2 | 7263.36 | 0 | 13520.56 | 16900.7 | 1875
S353300 / S353310 / S353400 | Install SC Magnet on cradle carriage | Technical scope: Installation of SC Magnet onto lower half of Outer HCal previously mounted to cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, install the SC Magnet onto the cradle carriage. | 2 | 0 | 0 |  | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 1500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 2 | 32 | 64 | 0 | 0 | 0 | 3337.6 | 162.2 | 2595.2 | 7263.36 | 0 | 13358.36 | 16697.95 | 1875
S353500 / S353510 / S353600 | Align/Survey SC Magnet to cradle carriage | Technical scope: Alignment of SC Magnet with respect to nominal IP and beam axis related via the cradle carriage. Work Statement: In accordance with work plan/permit, tooling and fixtures, and the SC Magnet Alignment specifications, align the SC Magnet to the nominal IP and beam RHIC axis with the assistance of BNL sureyors. | 10 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 80 | 0 | 0 | 336 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 0 | 0 | 3500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 416 | 64 | 0 | 0 | 0 | 0 | 0 | 33737.6 | 7263.36 | 0 | 41000.96 | 51251.2 | 4375
S353700 / S353710 / S353800 | Prep SC Magnet for Run (Cryo) | Technical scope: Preparation/Installation and commissioning of Cryo system for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Cryo techs. CAD Cryo tech efforts and all cryo equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD cryo technicians in preparing the cryo serices for the SC Magnet. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 336 | 16 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 336 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 27249.6 | 0 | 0 | 31884.8 | 39856 | 4375
s353900 / S353910 / S354000 | Prep SC Magnet for Run (Electric) | Technical scope: Preparation/Installation and commissioning of electrical power, monitoring and safety systems for SC Magnet. Scope includes sPHENIX technicians efforts to assist CAD Electrical techs and engineers. CAD electrical tech efforts and all electrical equipment, components, fixtures and tools are not part of this work package (see WBS 2.02 and WBS 2.04) Work Statement: Provide mechanical technician support as necessary to assist CAD electrical technicians in preparing the electrical serices for the SC Magnet. | 20 | 0 | 0 |  | 0 | 0 | 0 | 32 | 16 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 16 | 320 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 25952 | 0 | 0 | 30587.2 | 38234 | 3500
S354100 / S354110 | Review SC Magnet for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX SC Magnet assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the SC Magnet and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Magnet will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 10 | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 10 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 811 | 0 | 0 | 3128.6 | 3910.75 | 0
S354200 / S354210 | Address Action Items from SC Magnet ORR | Technical scope: evaluation and implementation of recommendations from SC Magnet ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 24 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1946.4 | 0 | 0 | 4264 | 5330 | 0
[38 empty] | TOTAL Materials | 43500 | [10 empty] | TOTAL Hours | 1968
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 175242.88 | 219053.6 | 53500 | 43500 | 25% | 22.99%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 0 | 406 | 150 | 1220 | 192 | 0 | 0 | 0 | 42345.8 | 12165 | 98942 | 21790.08 | 0
1968
-6
1962
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## Inner HCal Inst Work Package
Return to Navigation Page
WBS # | 2.05.06 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Inner HCal Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S354400 | Design Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Inner HCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Inner HCal sectors during assembly. The design of those tools is covered in WBS 1.4, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Inner HCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing the Inner HCal sectors into an integrated Inner HCal detector then installing this detector inside the SC Magnet and for installing Inner HCal services. | 40 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 120 | 0 | 0 | 0 | 0 | 0 | 6258 | 9732 | 0 | 0 | 0 | 15990 | 19987.5 | 0
S354500 / S354600 | Fabricate/Procure Inner HCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Inner HCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Outer HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the Inner HCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 120 | 40 | 0 | 0 | 0 | 0 | 0 | 12516 | 3244 | 0 | 0 | 0 | 15760 | 19700 | 112000
S354700 | Prepare Inner HCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Inner HCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Inner HCal and its services (e.g. critical lift calculations, etc.) | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 8344 | 3244 | 0 | 0 | 0 | 11588 | 14485 | 0
S354800 | Review Inner HCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Inner HCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S354900 | Address Action Items from Inner Hcal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Inner HCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S355000 | Design/Safety Reviews Complete, Inner HCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S355100 | Inner HCal Sectors Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S355200 / S355300 | Transport assembled Inner HCal Sectors to AH | Technical scope: Transport all 32 Inner HCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all Inner HCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full Inner HCal assembly. | 20 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 16 | 120 | 160 | 0 | 0 | 0 | 1668.8 | 1297.6 | 9732 | 18158.4 | 0 | 30856.8 | 38571 | 625
S355400 / S355500 | Install Inner HCal assembly Insertion Fixture | Technical scope: Install the Inner HCal insertion fixture in the sPHENIX Assembly Hall (AH). Work Statement: sPHENIX technicans assemble the Inner HCal insertion fixture in the sPHENIX AH next to the sPHENIX cradle carriage (which by the time the Inner HCal is ready for insertion will have all of the Outer HCal and SC Magnet fully installed) in accordance with the Inner HCal installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 4 | 4 | 80 | 0 | 0 | 0 | 0 | 417.2 | 324.4 | 6488 | 0 | 0 | 7229.6 | 9037 | 625
S355600 / S355700 | Install Inner HCal assembly on Insertion Fixture | Technical scope: Install all 32 Inner HCal sectors into full Inner HCal detector on the Inner HCal insertion fixture in the sPHENIX Assembly Hall. Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling and lifting tools install all 32 Inner HCal sectors between the Inner HCal assembly rings on the Inner HCal insertion fixture in accordance with the Inner HCal installation procedure and work permit. | 16 | 0 | 0 |  | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 0 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 0 | 0 | 53388.8 | 66736 | 625
S355800 / S355900 | Install 1st Inner HCal Support Ring | Technical scope: Install first (south side) Inner HCal support ring. Work Statement: sPHENIX technicans install the south Inner HCal support ring and align it appropriately with the sPHENIX SC Magnet in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
S356000 / S356100 | Install Inner HCal | Technical scope: Install the 32 Inner HCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the Inner HCal insertion fixture, install the Inner HCal assembly into the sPHENIX SC Magnet and attach the end ring on the south side to the south Inner HCal support ring, in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
S356200 / S356300 | Install 2nd Inner HCal Support Ring | Technical scope:Install first (north side) Inner HCal support ring. Work Statement: sPHENIX technicans install the north Inner HCal support ring and attach to the north side Inner HCal end ring. Attach the support ring to the outer HCal in accordance with the Inner HCal installation procedure and work permit. | 2 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 2 | 32 | 0 | 0 | 0 | 0 | 834.4 | 162.2 | 2595.2 | 0 | 0 | 3591.8 | 4489.75 | 625
S356400 / S356410 / S356500 | Align/Survey Inner HCal to SC Magnet Centerline | Technical scope: Align all Inner HCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the Inner HCal support rings, align the Inner HCal to the SC Magnet in accordance with the Inner HCal installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 4 | 80 | 80 | 0 | 0 | 0 | 0 | 324.4 | 6488 | 9079.2 | 0 | 15891.6 | 19864.5 | 625
S356600 / S356700 | Install Inner HCal Cables and Services | Technical scope: Install all Inner HCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Inner HCal services onto the sPHENIX cradle carriage. | 20 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 80 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 80 | 0 | 240 | 0 | 0 | 0 | 0 | 8344 | 0 | 19464 | 0 | 0 | 27808 | 34760 | 625
S356800 | Review Inner HCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Inner HCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Inner HCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Inner HCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
S356900 | Address Action Items from Inner Hcal ORR | Technical scope: evaluation and implementation of recommendations from Inner HCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
S357000 / S257100 / S357200 | Commission Inner HCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Inner HCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 320 |  | 0 | 320 | 0 | 160 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 32 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | There is no additional material cost associated with this task. All costs for test equipment and supplies in support of commissioing efforts are supplied by the subsystem./M1 | 0 | 320 | 160 | 0 | 192 | 0 | 640 | 0 | 38880 | 16688 | 0 | 15571.2 | 0 | 0 | 71139.2 | 88924 | 500
[38 empty] | TOTAL Materials | 84500 | [10 empty] | TOTAL Hours | 3550 | [6 empty] | #VALUE!
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 271921.8 | 339902.25 | 117500 | 84500 | 25% | 39.05%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 320 | 656 | 326 | 1368 | 240 | 640 | 0 | 38880 | 68420.8 | 26438.6 | 110944.8 | 27237.6 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## EMCal Inst Work Package
Return to Navigation Page
WBS # | 2.05.07 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| EMCal Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S357400 | Design EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of EMCal Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of EMCal sectors during assembly. The design of those tools is covered in WBS 1.03, but since assembly of sectors will be going on in parallel with Installation, the tool requirements will need to be duplicated.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for EMCal Lifting and indexing fixtures and holding fixtures for modules, work platforms and scaffolding for installing this detector inside the SC Magnet onto rails attached to the Inner HCal and for installing EMCal services. | 60 | 0 | 0 |  | 0 | 0 | 0 | 26 | 0 | 0 | 26 | 0 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 26 | 53 | 21 | 0 | 0 | 0 | 0 | 2711.8 | 4298.3 | 1703.1 | 0 | 0 | 8713.2 | 10891.5 | 0
S357500 / S357600 | Fabricate/Procure EMCal Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of EMCal Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the EMCal is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 120 | 40 | 48 | 0 | 0 | 0 | 0 | 12516 | 3244 | 3892.8 | 0 | 0 | 19652.8 | 24566 | 42000
S357700 | PrepareEMCal Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the EMCal sector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the EMCal and its services. | 10 | 0 | 0 |  | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 80 | 40 | 8 | 0 | 0 | 0 | 0 | 8344 | 3244 | 648.8 | 0 | 0 | 12236.8 | 15296 | 0
S357800 | Review EMCal Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX EMCal and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S357900 | Address Action Items from EMCal Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from EMCal Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S358000 | Design/Safety Reviews Complete, EMCal Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S358100 | EMCal Sectors Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S358200 / S358300 | Transport Assembled EMCal Sectors to AH | Technical scope: Transport all 64 EMCal sectors from their sector assembly/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: BNL riggers and sPHENIX technicans using appropriate custom and standard handling tools move all EMCal sectors to 1008 AH. These may be performed as a series of moves of smaller quantities of sectors in parallel with installing these sectors into the full EMCal assembly. | 10 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 64 | 120 | 0 | 0 | 0 | 0 | 0 | 5190.4 | 13618.8 | 0 | 18809.2 | 23511.5 | 625
S358400 / S358500 | Install EMCal Sectors | Technical scope: Install the 64 EMCal sectors assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the EMCal sector insertion fixture, install the EMCal sectors, one at a time, south sectors then north sector with one south and one north sector mated to each of the Inner HCal sectors, into the sPHENIX SC Magnet and attach to the mated Inner HCal sector by the bearing rails, in accordance with the EMCal installation procedure and work permit. | 16 | 0 | 0 |  | 0 | 0 | 0 | 64 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 512 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 64 | 64 | 512 | 0 | 0 | 0 | 0 | 6675.2 | 5190.4 | 41523.2 | 0 | 0 | 53388.8 | 66736 | 625
S358600 / S358610 / S358700 | Align/Survey EMCal to SC Magnet Centerline | Technical scope: Align all EMCal sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the EMCal support rings, align the EMCal to the SC Magnet in accordance with the EMCal installation procedure and work permit. | 7 | 0 | 6 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 20 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors/ not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 6 | 0 | 0 | 74 | 80 | 0 | 0 | 729 | 0 | 0 | 6001.4 | 9079.2 | 0 | 15809.6 | 19762 | 625
S358800 / S358900 | Install EMCal Cables and Services | Technical scope: Install all EMCal services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all EMCal services onto the sPHENIX cradle carriage. | 40 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 224 | 64 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 32 | 32 | 224 | 320 | 0 | 0 | 0 | 3337.6 | 2595.2 | 18166.4 | 36316.8 | 0 | 60416 | 75520 | 625
S359000 | Review EMCal for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX EMCal assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the EMCal and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the EMCal will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S359100 | Address Action Items from EMCal ORR | Technical scope: evaluation and implementation of recommendations from EMCal ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S359200 / S359300 / S359400 | Commission EMCal | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the EMCal. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 |  | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 625
[38 empty] | TOTAL Materials | 32500 | [10 empty] | TOTAL Hours | 4340
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 265528 | 331910 | 45125 | 32500 | 25% | 38.85%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 406 | 434 | 301 | 1079 | 520 | 1600 | 0 | 49329 | 45266.2 | 24411.1 | 87506.9 | 59014.8 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## TPC Inst Work Package
Return to Navigation Page
WBS # | 2.05.08 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| TPC Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S359600 | Design TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of TPC Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of TPC sectors during assembly. The design of those tools is covered in WBS 1.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for TPC Lifting and insertion/positioning fixtures for installing this detector inside the SC Magnet and for installing TPC services. | 60 | 0 | 0 |  | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 100 | 100 | 72 | 0 | 0 | 0 | 0 | 10430 | 8110 | 5839.2 | 0 | 0 | 24379.2 | 30474 | 0
S359700 / S359800 | Fabricate/Procure TPC Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of TPC Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about Inner HCal and EMCal assembly tooling and fixtures.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 90 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the TPC is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 6258 | 1622 | 0 | 0 | 0 | 7880 | 9850 | 42000
S359900 | Prepare TPC Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the TPC detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the TPC and its services . | 10 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 8 | 0 | 0 | 0 | 0 | 4172 | 1622 | 648.8 | 0 | 0 | 6442.8 | 8053.5 | 0
S360000 | Review TPC Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX TPC and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S360100 | Address Action Items from TPC Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from TPC Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S360200 | Design/Safety Reviews Complete, TPC Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S360300 | TPC Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S360400 / S360410 / S360500 | Transport Assembled TPC Sections to AH | Technical scope: Transport TPC detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all TPC components to 1008 AH. | 5 | 0 | 0 |  | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 16 | 0 | 32 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 2595.2 | 0 | 0 | 4264 | 5330 | 625
S360600 | Open SC Magnet Pole Tip Doors |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 25% |  |  |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | [6 empty] | 0
S360700 / S360800 | Install TPC Support | Technical scope: Install the TPC detector permanent structural support and alignment components into the SC Magnet and any temporary support equipment (e.g. scaffolding, temporary Work Statement: sPHENIX technicans, using the TPC custom and generic tooling, install the TPC permanent structural support components in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Includes labor to open pole tip doors | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 16 | 76 | 0 | 0 | 0 | 0 | 834.4 | 1297.6 | 6163.6 | 0 | 0 | 8295.6 | 10369.5 | 625
S360900 / S361000 | Install TPC (Mechanical) | Technical scope: Install the TPC detector assembly into the SC Magnet. Work Statement: sPHENIX technicans, using the TPC detector insertion fixture, install the TPC detector, in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 4 | 16 | 60 | 0 | 0 | 0 | 0 | 417.2 | 1297.6 | 4866 | 0 | 0 | 6580.8 | 8226 | 625
S361100 / S361110 / S361200 | Align/Survey TPC to SC Magnet Centerline | Technical scope: Align all TPC sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the TPC permanent support structure, align the TPC to the SC Magnet in accordance with the TPC installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
S361300 / S361400 | Install TPC Cables and Services | Technical scope: Install all TPC services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all TPC services onto the sPHENIX cradle carriage. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 180 | 60 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 24 | 24 | 180 | 240 | 0 | 0 | 0 | 2503.2 | 1946.4 | 14598 | 27237.6 | 0 | 46285.2 | 57856.5 | 625
S361500 | Review TPC for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX TPC assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the TPC and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the TPC will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 1297.6 | 0 | 0 | 2966.4 | 3708 | 0
S361600 | Address Action Items from TPC ORR | Technical scope: evaluation and implementation of recommendations from TPC ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 1297.6 | 0 | 0 | 2966.4 | 3708 | 0
S361700 / S361800 / S361900 | Commission TPC | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the TPC. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 |  | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 625
[38 empty] | TOTAL Materials | 33000 | [10 empty] | TOTAL Hours | 3608
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 196567.6 | 245709.5 | 45750 | 33000 | 25% | 38.64%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 400 | 380 | 252 | 656 | 320 | 1600 | 0 | 48600 | 39634 | 20437.2 | 51579.6 | 36316.8 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## INTT Inst Work Package
Return to Navigation Page
WBS # | 2.05.09 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| INTT Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S362000 | Design INTT Integration/Installation Tooling/Fixtures | 0 | 60 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 0 | 0 | 0 | 0 | 0 | 3129 | 4866 | 0 | 0 | 0 | 7995 | 9993.75 | 0
S362100 / S362200 | Fabricate/Procure INTT Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of INTT Integration and Installation tooling components for sPHENIX. (Note: see next task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the INTT is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 6258 | 1622 | 0 | 0 | 0 | 7880 | 9850 | 42000
S362300 | Prepare INTT Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the INTT detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the INTT and its services . | 10 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 4172 | 1622 | 0 | 0 | 0 | 5794 | 7242.5 | 0
S362400 | Review INTT Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX INTT and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S362500 | Address Action Items from INTT Integration/Installation Tooling/Fixtures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from INTT Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S362600 | Design/Safety Reviews Complete, INTT Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S362700 | INTT Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S362800 / S362900 | Transport Assembled INTT Sections to AH | Technical scope: Transport INTT detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all INTT components to 1008 AH. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 24 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1946.4 | 0 | 0 | 3429.6 | 4287 | 625
S363000 / S363100 | Install INTT Support | Technical scope: Install the INTT detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector structural supports, in accordance with the INTT installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
S363200 / S363300 | Install INTT (mechanical) | Technical scope: Install the INTT detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the INTT detector, in accordance with the INTT installation procedure and work permit. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
S363400 / S363410 / S363500 | Align/Survey INTT to SC Magnet Centerline | Technical scope: Align all INTT sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the INTT permanent support structure, align the INTT to the SC Magnet in accordance with the INTT installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
363600 / S363700 | Install INTT Cables and Services | Technical scope: Install all INTT services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all INTT services onto the sPHENIX cradle carriage. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 240 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 24 | 240 | 240 | 0 | 0 | 0 | 5006.4 | 1946.4 | 19464 | 27237.6 | 0 | 53654.4 | 67068 | 625
S363800 | Review INTT for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX INTT assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the INTT and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the INTT will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S363900 | Address Action Items from INTT ORR | Technical scope: evaluation and implementation of recommendations from INTT ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S364000 / S364100 / S364200 | Commission INTT | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the INTT. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 |  | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
[38 empty] | TOTAL Materials | 33000 | [10 empty] | TOTAL Hours | 3446
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 183520.2 | 229400.25 | 45625 | 33000 | 25% | 38.26%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 400 | 314 | 220 | 592 | 320 | 1600 | 0 | 48600 | 32750.2 | 17842 | 48011.2 | 36316.8 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## MVTX Inst Work Package
Return to Navigation Page
WBS # | 2.05.10 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| MVTX Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S364300 | Design MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of MVTX Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of MVTX sectors during assembly. The design of those tools is covered in WBS 3.02. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for MVTX Lifting and insertion/positioning fixtures for installing this detector inside the TPC and the magnet and for installing MVTX services. | 60 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 30 | 60 | 0 | 0 | 0 | 0 | 0 | 3129 | 4866 | 0 | 0 | 0 | 7995 | 9993.75 | 0
S364400 / S364500 | Fabricate/Procure MVTX Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of MVTX Integration and Installation tooling components for sPHENIX. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports.) Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the MVTX is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 60 | 20 | 20 | 0 | 0 | 0 | 0 | 6258 | 1622 | 1622 | 0 | 0 | 9502 | 11877.5 | 42000
S364600 | Prepare MVTX Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the MVTX detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the MVTX and its services . | 10 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 4172 | 811 | 0 | 0 | 0 | 4983 | 6228.75 | 0
S364700 | Review MVTX Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX MVTX and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S364800 | Address Action Items from MVTX Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from MVTX Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S364900 | Design/Safety Reviews Complete, MVTX Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S365000 | MVTX Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S365300 / S365400 | Transport Assembled MVTX Sections to AH | Technical scope: Transport MVTX detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all MVTX components to 1008 AH. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 0 | 32 | 0 | 0 | 0 | 0 | 834.4 | 0 | 2595.2 | 0 | 0 | 3429.6 | 4287 | 625
S365500 / S365600 | Install MVTX Support | Technical scope: Install the MVTX detector assembly structural support components into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector structural supports, in accordance with the MVTX installation procedure and work permit. (Note: see previous task for related info about INTT assembly tooling and fixtures.) (Note: the MVTX and INTT will share a common support structure on which either on or both of the subsystems can be supported. For purposes of completenness this component will show up in both work packages for these detecors, until the structural support system for both subsystems is finalized. At this point one or the other but not both subsystems workpackages will assume the responsibility for the structural supports. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 60 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 4866 | 0 | 0 | 6349.2 | 7936.5 | 625
2.05.01.10.10 | Install MVTX (mechanical) | Technical scope: Install the MVTX detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the MVTX detector, in accordance with the MVTX installation procedure and work permit. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 80 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 6488 | 0 | 0 | 7971.2 | 9964 | 0
S366700 / S366710 / S366800 | Align/Survey MVTX to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 20 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 500 | 25% | 25% | Craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 6488 | 9079.2 | 0 | 15567.2 | 19459 | 625
S366900 / S367000 | Install MVTX Remaining Cables and Services | Technical scope: Install all MVTX services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all MVTX services onto the sPHENIX cradle carriage. | 30 | 0 | 72 |  | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% | Includes all hours added from LBNL estimates | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 72 | 0 | 0 | 320 | 0 | 0 | 0 | 8748 | 0 | 0 | 25952 | 0 | 0 | 34700 | 43375 | 625
S367100 / S367200 | Review MVTX for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX MVTX assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the MVTX and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the MVTX will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 32 |  | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 32 | 8 | 8 | 16 | 0 | 0 | 0 | 3888 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 6668.8 | 8336 | 0
S367300 / S367400 | Address Action Items from MVTX ORR | Technical scope: evaluation and implementation of recommendations from MVTX ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 32 |  | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 32 | 8 | 8 | 16 | 0 | 0 | 0 | 3888 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 6668.8 | 8336 | 0
S367500 / S367600 | Commission MVTX | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the MVTX. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 |  | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 840 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
[38 empty] | TOTAL Materials | 32500 | [10 empty] | TOTAL Hours | 2620 | There are another 896 hours in university and other national lab labor from the MVTX installation file
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 174774.8 | 218468.5 | 45000 | 32500 | 25% | 38.46%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 536 | 266 | 178 | 720 | 80 | 840 | 0 | 65124 | 27743.8 | 14435.8 | 58392 | 9079.2 | 0
There are another 896 hours in university and other national lab labor from the MVTX installation file
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## MBD Inst Work Package
Return to Navigation Page
WBS # | 2.05.11 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Min Bias Integration/Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S367700 | Design Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the design of Min Bias Integeration and Installation tooling components for sPHENIX. (Note: some similar tools may be also used for the handling of Min Bias sectors during assembly. The design of those tools is covered in WBS 1.07. Those tools will be reused and augmented by additional tools described in this work package.) Work Statement: gather all relevant information and analyze requirements, create drawings and other relevant documentation for Min Bias Lifting and insertion/positioning fixtures for installing this detector inside the SCMagnet and for installing Min Bias services. | 60 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 30 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2433 | 0 | 0 | 0 | 4101.8 | 5127.25 | 0
S367800 / S367900 | Fabricate/Procure Min Bias Integration/Installation Tooling/Fixtures | Technical Scope: All tasks related to the fabrication and procurement of Min Bias Integration and Installation tooling components for sPHENIX. Work Statement: Prepare fabrication/procurement documentation, initiate procurement with Central shops/Procurement Office, participate in vendor selection, track procurement through delivery, inspect/accept all relevant procurements. | 60 | 0 | 0 |  | 0 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The concept for tooling and fixtures required to assemble the MinBias is fairly well set, but the details need to be established. Included in this cost are lifting fixtures holding fixtures, assembly and alignment fixtures/M5 | 0 | 0 | 30 | 10 | 10 | 0 | 0 | 0 | 0 | 3129 | 811 | 811 | 0 | 0 | 4751 | 5938.75 | 14000
S368000 | Prepare Min Bias Integration/Installation Tooling/Fixtures Procedures | Technical Scope: Prepare written Installation procedure for all aspects of the Min Bias detector and services installation. Work Statement: Prepare an installation procedure detailing all steps, tooling and fixture requirements, safety precautions, illustrations as appropriate, work permit(s) and any other relevant documentation required for the installation of the Min Bias and its services . | 10 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 4172 | 1622 | 0 | 0 | 0 | 5794 | 7242.5 | 0
S368100 | Review Min Bias Integration/Installation Tooling/Fixtures/Procedures Safety/Certification | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Min Bias and all tooling and fixtures required for this plan. Prepare a presentation describing these plans. Present to a panel determined by sPHENIX engineering and management. submit tooling/fixtures to certification tests as required. Perform tooling and fixture certification tests as necessary. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S368200 | Address Action Items from Min Bias Integration/Installation Tooling/Fixtures/Procedures Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from Min Bias Installation engineering and safety reviews and tooling certification tests. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 648.8 | 0 | 0 | 2132 | 2665 | 0
S368300 | Design/Safety Reviews Complete, Min Bias Integration/Installation Tooling/Fixtures/Procedures Ready for Service | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S368400 | Min Bias Ready for Installation | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S368500 / S368600 | Transport Assembled Min Bias Sections to AH | Technical scope: Transport Min Bias detector and support components from their holding area/test site at BNL to the 1008 Assembly Hall (AH). Work Statement: sPHENIX technicans using appropriate custom and standard handling tools move all Min Bias components to 1008 AH. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 625
S368700 / S368800 | Install Min Bias Support | Technical scope: Install the Min Bias detector assembly structural support into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector structural supports, in accordance with the Min Bias installation procedure and work permit. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 625
S368900 / S369000 | Install Min Bias (mechanical) | Technical scope: Install the Min Bias detector assembly into the SC Magnet. Work Statement: sPHENIX technicans install the Min Bias detector, in accordance with the Min Bias installation procedure and work permit. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 625
S369100 / S369110 / S369200 | Align/Survey Min Bias to SC Magnet Centerline | Technical scope: Align all MVTX sectors to the SC Magnet. Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the MVTX permanent support structure, align the MVTX to the SC Magnet in accordance with the MVTX installation procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 8 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 500 | 25% | 25% | craft is surveyors not riggers | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. Note, the cable trays cables, strain relief etc. costs are covered under the infrastructure effort. These costs are for any aditional hardware needed during final installation that is otherwise unaccounted for. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 32 | 20 | 0 | 0 | 0 | 0 | 0 | 2595.2 | 2269.8 | 0 | 4865 | 6081.25 | 625
S369300 / S369400 | Install Min Bias Cables and Services | Technical scope: Install all Min Bias services (power, control and signal cables; cooling and gas supplies) onto cradle carriage. Work Statement: sPHENIX technicans using appropriate custom and standard tools install all Min Bias services onto the sPHENIX cradle carriage. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 240 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 500 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 48 | 24 | 240 | 240 | 0 | 0 | 0 | 5006.4 | 1946.4 | 19464 | 27237.6 | 0 | 53654.4 | 67068 | 625
S269500 | Review Min Bias for Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S269600 | Address Action Items from Min Bias ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S369700 / S369800 / S369900 | Commission Min Bias | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of the Min Bias. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 50 | 0 | 400 |  | 0 | 400 | 0 | 80 | 0 | 0 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 80 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 500 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 400 | 80 | 40 | 80 | 0 | 1600 | 0 | 48600 | 8344 | 3244 | 6488 | 0 | 0 | 66676 | 83345 | 500
[38 empty] | TOTAL Materials | 13000 | [10 empty] | TOTAL Hours | 3152
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 156712.6 | 195890.75 | 17625 | 13000 | 25% | 35.58%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 400 | 270 | 180 | 442 | 260 | 1600 | 0 | 48600 | 28161 | 14598 | 35846.2 | 29507.4 | 0
3152
219
3371
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## Full Detector Inst Work Package
Return to Navigation Page
WBS # | 2.05.12 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| sPHENIX Full Detector Installation | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S370000 / S370100 | Move Full sPHENIX to IR | Technical Scope: All efforts related to the relocation of the partially assembled sPHENIX experimetal equipment, mounted on the sPHENIX cradle carriage from the assembly hall (AH) to the interaction region (IR). The Calorimeter detectors (Outer and Inner detector, and the TPC tracker), the SC Magnet and all of its on-carriage support services, the end caps/pole tips and all on carriage work platforms and related access components will be fully installed, aligned and partially commissioned at this point. The INTT, MVTX and MBD subsystems (detectors and support ing services/equipment) will be installed, aligned and commissioned after the carriage is moved to the IR. Work Statement: gather Move the carriage from the AH to the IR. sPHENIX technicians will perform this task using existing hydraulic rams (repurposed from PHENIX hydraulic system used to drive carriages in and out of the IR. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 160 | 96 | 24 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 8 | 8 | 160 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 12976 | 0 | 0 | 14459.2 | 18074 | 1250
S370200 / S370210 / S370300 | Align Full sPHENIX to Nominal Beamline and IP | Technical scope: Align the cradle carriage with its partial complement of subsystems to the nominal RHIC beamline and the sPHENIX interaction Point (IP). Work Statement: sPHENIX technicans working with BNL surveyors using appropriate alignment tools and adjustment/alignment features built into the cradle carriage align cradle carriage with the nominal RHIC beam path and the sPHENIX IP in accordance with the integration/installation plan/procedure and work permit. | 5 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 16 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 1000 | 25% | 25% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | The costs indicated are for hardware costs associated with this task. This is fairly well understood from projects with similar scope and detail./M4 | 0 | 0 | 0 | 0 | 64 | 40 | 0 | 0 | 0 | 0 | 0 | 5190.4 | 4539.6 | 0 | 9730 | 12162.5 | 1250
S370400 | sPHENIX Installation Complete (MIE) | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S370400 | sPHENIX Installation Complete (MIE + INTT + MVTX) | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S370500 / S370510 | Full System Commissioning (MIE + INTT + MVTX) | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of all sPHENIX MIE subsystems as a fully integrated system. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 320 |  | 0 | 320 | 0 | 780 | 0 | 0 | 160 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 256 | 128 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 320 | 780 | 0 | 256 | 0 | 1280 | 0 | 38880 | 81354 | 0 | 20761.6 | 0 | 0 | 140995.6 | 176244.5 | 0
S370500 / S370510 | Full System Commissioning (MIE) | Technical scope: Perform operational tests to adjust, calibrate, debug and optimize the operation and performance of all sPHENIX subsystems (incuding MIE, INTT and MVTX) as a fully integrated system. Work Statement: Perform operational checks on HCal operational and control equipment. Make adjustments and calibrations as necessary to optimize detector performance. Make adjustments to operating procedures as necessary to assure smooth and reliable operation. | 40 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S370600 | Full sPHENIX Detector Operational Readiness (ORR) | Technical scope: preparation for and execution of review for Engineering and safety review of sPHENIX Min Bias assembly/Installation in the sPHENIX AH. Work Statement: Gather all documentation describing the installation of the Min Bias and all of its sevrices including any acceptance/performance testing performed and survey data. Prepare a presentation to demonstrate the adequacy of the installation demonstarting confidence that the Min Bias will perform successfully and safely. Present it to a committee designated by sPHENIX management. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 16 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 1297.6 | 0 | 0 | 3615.2 | 4519 | 0
S370700 | Address Action Items from Full sPHENIX Detector ORR | Technical scope: evaluation and implementation of recommendations from Min Bias ORR. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | The labor required for this task is reasonably similar to well understood tasks from PHENIX and other projects of similar scale/L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 16 | 32 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 2595.2 | 0 | 0 | 7230.4 | 9038 | 0
S370800 | All Design/Safety/Readiness Reviews Complete, sPHENIX Ready for Operations | milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[38 empty] | TOTAL Materials | 2000 | [10 empty] | TOTAL Hours | 3036
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Total Labor Costs for this work package by Resoutce Catgory | [6 empty] | 176030.4 | 220038 | 2500 | 4000 | 25% | -37.5%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 320 | 836 | 32 | 528 | 40 | 1280 | 0 | 38880 | 87194.8 | 2595.2 | 42820.8 | 4539.6 | 0
3036
-2004
1032
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
Illustrations

## Risk Codes
TABLE 1: Labor risk codes
Code | Type of Estimate | Contingency % | Description
L1 | Actual | 0% | Actual costs incurred on activities completed to date.
L2 | Level of Effort Tasks | 0%-20% | Support type activities that must be done to support other work activities or the entire project effort, where estimated effort is based on the duration of the activities it is supporting.
L3 | Advanced | 10%-25% | Based on experience with documented identical or nearly identical work. Development of activities, resource requirements, and schedule constraints are highly mature. Technical requirements are very straightforward to achieve.
L4 | Preliminary | 25%-40% | Based on direct experience with similar work. Development of activities, resource requirements, and schedule constraints are defined as preliminary (beyond conceptual) design level. Technical requirements are achievable and with some precedent.
L5 | Conceptual | 40%-60% | Based on expert judgment using some experience as a reference. Development of activities, resource requirements, and schedule constraints are defined at a conceptual level. Technical requirements are moderately challenging.
L6 | Pre-conceptual | 60%-80% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints are defined at a pre-conceptual level. Technical requirements are moderately challenging.
L7 | Rough Estimate | 80%-100% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints is largely incomplete. Technical requirements are challenging.
L8 | Beyond state of the art | > 100% | No experience available for reference. Activities, resource requirements, and schedule constraints are completely undeveloped. Technical requirements are beyond state of the art.
TABLE 2: Material risk codes
Code | Type of Estimate | Contingency % | Description
M1 | Existing Purchase order | 0% | Items have been completed or obligated. (Note: Contact Change Orders are considered a Risk and should not be included )
M2 | Procurement for LOE/Oversight work | 0%-20% | M&S items such as travel, software purchases and upgrades, computers, etc. estimated to support LOE efforts and other work activities.
M3 | Advanced | 10%-25% | Items for which there is a catalog price or recent vendor quote based on a completed or nearly completed design or an existing design with little or no modifications and for which the costs are documented.
M4 | Preliminary | 25%-40% | Items that can be readily estimated from a reasonably detailed but not completed design; items adapted from existing designs but with moderate modifications, which have documented costs from past projects. A recent vendor survey (e.g., budgetary quote, vendor RFI response) based on a preliminary design belongs here.
M5 | Conceptual | 40%-60% | Items with a documented conceptual level of design; items adapted from existing designs but with extensive modifications, which have documented costs from past projects.
M6 | Pre-conceptual - Common work | 60%-80% | Items that do not have a documented conceptual design, but do have documented costs from past projects. Use of this estimate type indicates little confidence in the estimate. Its use should be minimized when completing the final estimate.
M7 | Pre-conceptual - Uncommon work | 80%-100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Its use should be minimized when completing the final estimate.
M8 | Beyond state of the art | > 100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Technical requirements are beyond the state of the art.