## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number
Magnet |  | 2.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Magnet Management & Technical Oversight |  | 2.01.01 |  | Management & Oversight
| Safety Reviews, Cooldown & Power Tests |  |  | 2.02.01 | Management & Oversight
| Mechnical Transport & Reassembly |  | 2.02.02 |  | Magnet Transport & Assembly
| Cryogenic Systems |  | 2.02.03 |  | Cryogenic Systems
| Power Supply & Quench Detection Systems |  | 2.02.04 |  | Power Supply & Quench Detection
| Magnet Field Measurement |  | 2.02.05 |  | Magnet Field Measurement

## Management & Oversight
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2019-03-30
[5 empty] | Prepared By: | Kin Yip
[5 empty] | DocNo. (refer Rev. Log) | docdb link 63
Work Package Name: |  |  |  | WBS Number: |  | Control Account Number
Magnet Management & Technical Oversight |  |  |  | 2.01.01, 2.02.01
WBS Dictionary Definition:
Here we include the support work of the management (WBS 2.01.01), safety reviews prior to commissioning, and the commissioning of all the entire system at the end (WBS 2.02.01).
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Details of the Base Estimate (explanation of the Work)
Estimates are based on the experience in the last two years.
Cost Summary
(follow link for detailed summary)
Cost |  | 1115775.4
Contingency
Labor Contingency Rules Applied • L2 – based on the duration of the project activities that we're supporting (20%)

## Magnet Transport & Assembly
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2019-03-30
[5 empty] | Prepared By: | Kin Yip
[5 empty] | DocNo. (refer Rev. Log) | docdb link 63
Work Package Name: |  |  |  | WBS Number: |  | Control Account Number
Mechanical Disassembly, Transport Prep. And Reassembly of Valve Box |  |  |  | 2.02.02
WBS Dictionary Definition:
Please refer to the dictionary file in docdb link 55
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
This estimate assumes that the magnet may be safely supported from the two ends, and that supports along the full length of the magnet are not required.
Details of the Base Estimate (explanation of the Work)
This BOE covers the cost of construction of the components to be used to adjust the position of the magnet cryostat within the detector. Components may either be temporary tooling, to be replaced by adjustable thickness permanent components at the completion of alignment, or permanently mounted adjustable magnet / detector supports, depending on the interface requirements.
Cost Summary
(follow link for detailed summary)
Cost | 210443.4
Contingency
Material Contingency Rules Applied for transport tooling & parts • M7 – pre-conceptual uncommon work (100%) • No conceptual design has been completed to date. No similar work of this scale has previously been completed. Labor Contingency Rules Applied • L7 – rough estimate (100%) for transport tooling • L2 – rough estimate (20%) in general Comments: Start of magnet cryostat adjustment tooling design effort is linked to the completion of detector design.

## Cryogenic Systems
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2019-03-30
[5 empty] | Prepared By: | Kin Yip
[5 empty] | DocNo. (refer Rev. Log) | docdb link 63
Work Package Name: |  |  |  | WBS Number: |  | Control Account Number
Cryogenic Systems |  |  |  | 2.02.03
WBS Dictionary Definition:
Please refer to the dictionary file in docdb link 55
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Past Project Procurement List (Cryo) [https://docdb.sphenix.bnl.gov/0000/000063/003/Past%20Project%20Procument%20List%20%28Cryo%29.pdf]
Assumptions Used in Developing Estimate
This assumes a cryogenic system that is tapping and connected to the RHIC cryogenic system.
Details of the Base Estimate (explanation of the Work)
Based on past procurements of similar equipment, contract value PO and equipment description for the past projects (see the "past procurement list") and an engineering judgement of the breakdown between each subsystem of the procurement.
Cost Summary
(follow link for detailed summary)
Cost |  | 2629484.09
Contingency
Material Contingency Rules Applied • A material risk contingency at the level of M4 is recommended set at 30%. Labor Contingency Rules Applied • L4 -- The current labor estimates is based on engineering judgement with direct experience (30%)

## PS & Quench Detection
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2019-03-30
[5 empty] | Prepared By: | Kin Yip
[5 empty] | DocNo. (refer Rev. Log) | docdb link 63
Work Package Name: |  |  |  | WBS Number: |  | Control Account Number
Power Supply & Quench Detection Systems |  |  |  | 2.02.04
WBS Dictionary Definition:
Please refer to the dictionary file in docdb link 55
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
535 MCM+B77 cable = 12 cables x (50’ PS-WCB + 50’ WCB-Mag + 50’ Mag-DR + 50’ DR-WCB + 50’ WCB-PS) x $16/ft = $48k Lugs = 10 locations x 12 lugs/location x $25/lug = $3k Water Cooled Buss (WCB) Parts = $3k Cable Tray Parts = $4k Miscellaneous Parts = $2k Total = $60k
Assumptions Used in Developing Estimate
• Reusing existing PHENIX Magnet Water Cooled Buss (two pairs of WCB in parallel, with minor modifications) as the connection between 1008B and 1008-IR. • 12 each 535 MCM cables to carry the 4600 A magnet current.
Details of the Base Estimate (explanation of the Work)
This estimate is for materials for hook-up of the DC power from the Power Supply in 1008B to the Magnet in 1008-IR, including the hook-up to the Dump Resistor (which may be located in 1008B or 1008-IR).
Cost Summary
(follow link for detailed summary)
Cost |  | 189626
Contingency
Material Contingency Rules Applied • M4 • Engineering Estimate based on Similar Items Labor Contingency Rules Applied • L4 • Engineering Estimate based on Similar Items

## Magnet Field Measurement
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2019-03-30
[5 empty] | Prepared By: | Kin Yip
[5 empty] | DocNo. (refer Rev. Log) | docdb link 63
Work Package Name: |  |  |  | WBS Number: |  | Control Account Number
Magnet Field Measurement |  |  |  | 2.02.05
WBS Dictionary Definition:
Please refer to the dictionary file in docdb link 55
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Prices are based on current provider listings.
Details of the Base Estimate (explanation of the Work)
This BOE covers the cost of a basic field monitoring setup. The final field map will be generated by detailed computer simulations. The measurements taken by the probes will provide set points but mainly field stability monitoring.
Cost Summary
(follow link for detailed summary)
Cost |  | 134526.4
Contingency
Material Contingency Rules Applied • M3 – based on catalog price (20%) Labor Contingency Rules Applied • L3 – based on nearly identical work done before (20%)

## Management & Oversight-Details
WBS | Description | Hours | Resources | Material | Labor | Total | Status | Basis of Estimate | Total | Grand Total
2.01.01 | Magnet Management and Technical Oversight | 7456
2.01.01 | 2018 Magnet Project Management | 880 | SCI3 AD | 0 | 106216 | 106216 | Pending | Labor hourly rates | 106216 |  | Complete | Thesed are LOE pending duration of the SC Magnet work
2.01.01 | 2019 Magnet Project Management | 2000 | SCI3 AD | 0 | 241400 | 241400 | Pending | Labor hourly rates | 241400 |  |  | Includes general management, cruyogenics management, Power System management
2.01.01 | 2020 Magnet Project Management | 880 | SCI3 AD | 0 | 106216 | 106216 | Pending | Labor hourly rates | 106216 |  |  | All are supervisory over their respective area
2.01.01 | 2021 Magnet Project Management | 880 | SCI3 AD | 0 | 106216 | 106216 | Pending | Labor hourly rates | 106216
2.01.01 | 2022 Magnet Project Management | 880 | SCI3 AD | 0 | 106216 | 106216 | Pending | Labor hourly rates | 106216
2.01.01 | Cryogenics System Technical Review | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates | 1656.8 |  | Complete
2.01.01 | 2018 Cryo L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6 |  | Complete
2.01.01 | 2019 Cryo L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2020 Cryo L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2021 Cryo L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2022 Cryo L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2018 PS & Quench Protection L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6 |  | Complete
2.01.01 | 2019 PS & Quench Protection L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2020 PS & Quench Protection L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2021 PS & Quench Protection L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.01.01 | 2022 PS & Quench Protection L3 Project Management | 352 | PROF4 AD | 0 | 36449.6 | 36449.6 | Pending | Labor hourly rates | 36449.6
2.02.01 | Safety Reviews, Cooldown, Power Tests
2.02.01.01 | Safety Reviews | 112 | [6 empty] | 12420.8
2.02.01.01 | LESHC-PSSC Review Cryogenic Safety Review | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.01.01 | LESHC-PSSC Review Cryogenic Safety Review | 8 | PROF4 AM | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.01.01 | LESHC-PSSC Review Cryogenic Safety Review | 16 | SCI3 AD | 0 | 1931.2 | 1931.2 | Pending | Labor hourly rates
2.02.01.01 | LESHC Review Magnet overall system Safety Review | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.01.01 | LESHC Review Magnet overall system Safety Review | 8 | PROF4 AM | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.01.01 | LESHC Review Magnet overall system Safety Review | 16 | SCI3 AD | 0 | 1931.2 | 1931.2 | Pending | Labor hourly rates
2.02.01.01 | ASSRC REVIEW | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.01.01 | ASSRC REVIEW | 16 | SCI3 AD | 0 | 1931.2 | 1931.2 | Pending | Labor hourly rates
2.02.01.02 | Cooldown and Power Tests | 724 | [6 empty] | 70937.8
2.02.01.02 | Cooldown | 60 | PROF3 AD | 0 | 5349 | 5349 | Pending | Labor hourly rates
2.02.01.02 | Cooldown | 60 | PROF4 AD | 0 | 6213 | 6213 | Pending | Labor hourly rates
2.02.01.02 | Cooldown | 60 | TECH3 AD | 0 | 4839 | 4839 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Static Heat Load test | 8 | PROF3 AD | 0 | 713.2 | 713.2 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Static Heat Load test | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Static Heat Load test | 8 | TECH3 AD | 0 | 645.2 | 645.2 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Low power test | 20 | PROF3 AD | 0 | 1783 | 1783 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Low power test | 80 | PROF4 AD | 0 | 8284 | 8284 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Low power test | 80 | SCI3 AD | 0 | 9656 | 9656 | Pending | Labor hourly rates
2.02.01.02 | 4.5K Low power test | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.01.02 | 4.5K High Power Test | 20 | PROF3 AD | 0 | 1783 | 1783 | Pending | Labor hourly rates
2.02.01.02 | 4.5K High Power Test | 80 | PROF4 AD | 0 | 8284 | 8284 | Pending | Labor hourly rates
2.02.01.02 | 4.5K High Power Test | 80 | SCI3 AD | 0 | 9656 | 9656 | Pending | Labor hourly rates
2.02.01.02 | 4.5K High Power Test | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.01 | Total Cost | 10728 |  | 0 | 1115775.4 | 1115775.4 |  |  |  | 1115775.4

## Magnet Trans & Assembly-Details
WBS | Description | Hours | Resources | Material | Labor | Total | Status | Basis of Estimate | Total | Grand Total
2.02.02 | Magnet Transport & Assembly | 1936 |  | 44000
2.02.02 | Preliminary Engineering Transport Tooling and Misc. Parts | 60 | PROF4 AM | 0 | 6213 | 6213 | Pending | Labor hourly rates | 6213
2.02.02 | Preliminary Engineering Transport Tooling and Misc. Parts | 24 | TECH3 PO D | 0 | 1935.6 | 1935.6 | Pending | Labor hourly rates | 1935.6
2.02.02 | Preliminary Safety and Design Review | 10 | PROF4 AM | 0 | 1035.5 | 1035.5 | Pending | Labor hourly rates | 1035.5
2.02.02 | Preliminary Safety and Design Review | 4 | TECH3 PO D | 0 | 322.6 | 322.6 | Pending | Labor hourly rates | 322.6
2.02.02 | Final Design (Magnet Transport) | 160 | PROF4 AM | 0 | 16568 | 16568 | Pending | Labor hourly rates | 16568
2.02.02 | Final Design (Magnet Transport) | 160 | TECH3 PO D | 0 | 12904 | 12904 | Pending | Labor hourly rates | 12904
2.02.02 | Final Design Review (Magnet Transport) | 20 | PROF4 AM | 0 | 2071 | 2071 | Pending | Labor hourly rates | 2071
2.02.02 | Final Design Review (Magnet Transport) | 10 | TECH3 PO D | 0 | 806.5 | 806.5 | Pending | Labor hourly rates | 806.5
2.02.02 | Procure Parts (for disassembly, transport & reassembly) | 80 | PROF4 AM | 40000 | 8284 | 48284 | Pending | Experience | 48284
2.02.02 | Procure Parts (for disassembly, transport & reassembly) | 80 | TECH3 PO D | 0 | 6452 | 6452 | Pending | Experience | 6452
2.02.02 | Assemble and Prepare Parts (Magnet Transport) | 16 | PROF4 AM | 0 | 1656.8 | 1656.8 | Pending | Experience | 1656.8
2.02.02 | Assemble and Prepare Parts (Magnet Transport) | 160 | TECH3 AM | 2000 | 12904 | 14904 | Pending | Experience | 14904
2.02.02 | Assemble and Prepare Parts (Magnet Transport) | 8 | TECH3 PO D | 0 | 645.2 | 645.2 | Pending | Experience | 645.2
2.02.02 | Disassemble Valve Box | 32 | PROF4 AM | 0 | 3313.6 | 3313.6 | Pending | Experience | 3313.6
2.02.02 | Disassemble Valve Box | 320 | TECH3 AM | 2000 | 25808 | 27808 | Pending | Experience | 27808
2.02.02 | Prepare for Coil Shipment - Shipping Constraints and Tooling | 16 | PROF4 AM | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates | 1656.8
2.02.02 | Prepare for Coil Shipment - Shipping Constraints and Tooling | 160 | TECH3 AM | 0 | 12904 | 12904 | Pending | Labor hourly rates | 12904
2.02.02 | Reinstall Valve Box | 40 | PROF4 AM | 0 | 4142 | 4142 | Pending | Labor hourly rates | 4142
2.02.02 | Reinstall Valve Box | 400 | TECH3 AM | 0 | 32260 | 32260 | Pending | Labor hourly rates | 32260
2.02.02 | Readjust Coil and Remove Shipping Tooling | 16 | PROF4 AM | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates | 1656.8
2.02.02 | Readjust Coil and Remove Shipping Tooling | 160 | TECH3 AM | 0 | 12904 | 12904 | Pending | Labor hourly rates | 12904
2.02.02 | Total Cost | 1936 |  | 44000 | 166443.4 | 210443.4 |  |  |  | 210443.4

## Cryogenic Systems - Details
WBS | Description | Hours | Resources | Material | Labor | Total | Status | Basis of Estimate | Total | Grand Total
2.02.03.01.01 | Engineering and Design | 703 | [6 empty] | 66646.85
2.02.03.01.01 | (RHIC Interface …) Cryo Process Design | 180 | PROF3 AD | 0 | 16047 | 16047 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) Cryo Process Design | 180 | PROF4 AD | 0 | 18639 | 18639 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) P&ID development&dwgs | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) ODH Analysis | 7 | PROF3 AD | 0 | 624.05 | 624.05 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) Mechanical Engeering Tasks | 96 | PROF3 AD | 0 | 8558.4 | 8558.4 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) SOW & Technical Specifications | 120 | PROF3 AD | 0 | 10698 | 10698 | Pending | Labor hourly rates
2.02.03.01.01 | (RHIC Interface …) SOW & Technical Specifications | 96 | PROF4 AD | 0 | 9940.8 | 9940.8 | Pending | Labor hourly rates
2.02.03.01.02 | Design/Drafting | 3264 | [6 empty] | 277113.6
2.02.03.01.02 | Helium Lines Routing from 1008B to IP8 hall and LN2 line routing from dewar to IP8 Hall. | 240 | PROF3 AD | 0 | 21396 | 21396 | Pending | Experience
2.02.03.01.02 | Helium Lines Routing from 1008B to IP8 hall and LN2 line routing from dewar to IP8 Hall. | 240 | TECH3 PO D | 0 | 19356 | 19356 | Pending | Experience
2.02.03.01.02 | RHIC interface valvebox and field joint layout at the interconnect where we tie into RHIC VJ lines and modeling of the particular RHIC interconnect | 480 | PROF3 AD | 0 | 42792 | 42792 | Pending | Experience
2.02.03.01.02 | RHIC interface valvebox and field joint layout at the interconnect where we tie into RHIC VJ lines and modeling of the particular RHIC interconnect | 480 | TECH3 PO D | 0 | 38712 | 38712 | Pending | Experience
2.02.03.01.02 | Transfer line system from 1008B to IP8 hall, detail layout | 192 | PROF3 AD | 0 | 17116.8 | 17116.8 | Pending | Experience
2.02.03.01.02 | Transfer line system from 1008B to IP8 hall, detail layout | 192 | TECH3 PO D | 0 | 15484.8 | 15484.8 | Pending | Experience
2.02.03.01.02 | (RHIC Interface …) Detailed dwg package for Procurement | 720 | PROF3 AD | 0 | 64188 | 64188 | Pending | Labor hourly rates
2.02.03.01.02 | (RHIC Interface …) Detailed dwg package for Procurement | 720 | TECH3 PO D | 0 | 58068 | 58068 | Pending | Labor hourly rates
2.02.03.01.03 | Procurement | 90 | [6 empty] | 9319.5
2.02.03.01.03 | (RHIC Interface …) Bid Prep and issue RFQ/RFP | 39 | PROF4 AD | 0 | 4038.45 | 4038.45 | Pending | Labor hourly rates
2.02.03.01.03 | (RHIC Interface …) Bid Prep and issue RFQ/RFP | 39 | PROF4 PO M | 0 | 4038.45 | 4038.45 | Pending | Labor hourly rates
2.02.03.01.03 | (RHIC Interface …) Bid period | 5 | PROF4 AD | 0 | 517.75 | 517.75 | Pending | Labor hourly rates
2.02.03.01.03 | (RHIC Interface …) Evaluate bids | 2 | PROF4 AD | 0 | 207.1 | 207.1 | Pending | Labor hourly rates
2.02.03.01.03 | (RHIC Interface …) Award Contract | 5 | PROF4 AD | 0 | 517.75 | 517.75 | Pending | Labor hourly rates
2.02.03.01.04.01 | Vendor Engineering and Design | 340 | [6 empty] | 611551.2
2.02.03.01.04.01 | (RHIC Interface …) Engineering | 72 | PROF3 AD | 0 | 6418.8 | 6418.8 | Pending | Labor hourly rates
2.02.03.01.04.01 | (RHIC Interface …) Engineering | 36 | PROF4 AD | 0 | 3727.8 | 3727.8 | Pending | Labor hourly rates
2.02.03.01.04.01 | (RHIC Interface …) Engineering | 54 | TECH3 PO D | 0 | 4355.1 | 4355.1 | Pending | Labor hourly rates
2.02.03.01.04.01 | (RHIC Interface …) Preliminary Design Review | 8 | PROF3 AD | 0 | 713.2 | 713.2 | Pending | Labor hourly rates
2.02.03.01.04.01 | (RHIC Interface …) Preliminary Design Review | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.01.04.01 | (RHIC Interface …) Detail dwg package | 24 | PROF3 AD | 110000 | 2139.6 | 112139.6 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Detail dwg package | 10 | PROF4 AD | 0 | 1035.5 | 1035.5 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Final Design Review | 16 | PROF3 AD | 220000 | 1426.4 | 221426.4 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Final Design Review | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Long lead items order | 8 | PROF3 AD | 200000 | 713.2 | 200713.2 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Long lead items order | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Drawings approvals | 40 | PROF3 AD | 50000 | 3566 | 53566 | Pending | Past Procurement
2.02.03.01.04.01 | (RHIC Interface …) Drawings approvals | 40 | PROF4 AD | 0 | 4142 | 4142 | Pending | Past Procurement
2.02.03.01.04.02 | Vendor Fabrication | 169 | [6 empty] | 536463.15
2.02.03.01.04.02 | (RHIC Interface …) Raw Material procurement | 8 | PROF4 AD | 200000 | 828.4 | 200828.4 | Pending | Past Procurement
2.02.03.01.04.02 | (RHIC Interface …) Main fabrication items | 72 | PROF3 AD | 0 | 6418.8 | 6418.8 | Pending | Labor hourly rates
2.02.03.01.04.02 | (RHIC Interface …) Main fabrication items | 72 | PROF4 AD | 0 | 7455.6 | 7455.6 | Pending | Labor hourly rates
2.02.03.01.04.02 | (RHIC Interface …) Final assemblies | 3 | PROF4 AD | 0 | 310.65 | 310.65 | Pending | Labor hourly rates
2.02.03.01.04.02 | (RHIC Interface …) BNL Holdpoint witness | 8 | PROF4 AD | 200000 | 828.4 | 200828.4 | Pending | Past Procurement
2.02.03.01.04.02 | (RHIC Interface …) Shipping | 6 | PROF4 AD | 120000 | 621.3 | 120621.3 | Pending | Past Procurement
2.02.03.01.05 | Delivery and receiving | 16 | [6 empty] | 1473.6
2.02.03.01.05 | (RHIC Interface …) Rigging/Truck Unloading | 8 | TECH3 AD | 0 | 645.2 | 645.2 | Pending | Labor hourly rates
2.02.03.01.05 | (RHIC Interface …) Inspection | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.01.06 | Installation | 800 | [6 empty] | 69572.8
2.02.03.01.06 | (RHIC Interface …) Rigging in place on piping supports | 20 | CRAFT3 | 0 | 2269.8 | 2269.8 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Rigging in place on piping supports | 20 | PROF3 AD | 0 | 1783 | 1783 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Rigging in place on piping supports | 20 | PROF4 AD | 0 | 2071 | 2071 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Rigging in place on piping supports | 20 | TECH3 AD | 0 | 1613 | 1613 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Field joint welding to RHIC Interconnect | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Field joint welding to RHIC Interconnect | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Field joint welding to RHIC Interconnect | 120 | TECH3 AD | 0 | 9678 | 9678 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Installation Cryo Mechanical MAGNET platform equipment | 12 | PROF3 AD | 0 | 1069.8 | 1069.8 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Installation Cryo Mechanical MAGNET platform equipment | 12 | PROF4 AD | 0 | 1242.6 | 1242.6 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Installation Cryo Mechanical MAGNET platform equipment | 240 | TECH3 AD | 0 | 19356 | 19356 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pressure. leak check and reliefs install equipment shakedown | 80 | PROF3 AD | 0 | 7132 | 7132 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pressure. leak check and reliefs install equipment shakedown | 80 | PROF4 AD | 0 | 8284 | 8284 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pressure. leak check and reliefs install equipment shakedown | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pump and purge | 4 | PROF3 AD | 0 | 356.6 | 356.6 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pump and purge | 4 | PROF4 AD | 0 | 414.2 | 414.2 | Pending | Labor hourly rates
2.02.03.01.06 | (RHIC Interface …) Final pump and purge | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.03.02.01 | Engineering and Design, LN2 supply transfer line system | 360 | [6 empty] | 34686
2.02.03.02.01 | Cryo Process Design | 48 | PROF3 AD | 0 | 4279.2 | 4279.2 | Pending | Labor hourly rates
2.02.03.02.01 | Cryo Process Design | 48 | PROF4 AD | 0 | 4970.4 | 4970.4 | Pending | Labor hourly rates
2.02.03.02.01 | P&ID development&dwgs | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.02.01 | P&ID development&dwgs | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.02.01 | Mechanical Engeering Tasks | 72 | PROF3 AD | 0 | 6418.8 | 6418.8 | Pending | Labor hourly rates
2.02.03.02.01 | Mechanical Engeering Tasks | 72 | PROF4 AD | 0 | 7455.6 | 7455.6 | Pending | Labor hourly rates
2.02.03.02.01 | SOW & Technical Specifications | 36 | PROF3 AD | 0 | 3209.4 | 3209.4 | Pending | Labor hourly rates
2.02.03.02.01 | SOW & Technical Specifications | 36 | PROF4 AD | 0 | 3727.8 | 3727.8 | Pending | Labor hourly rates
2.02.03.02.02 | Design/Drafting, LN2 supply transfer line system | 216 | [6 empty] | 20293.2
2.02.03.02.02 | LN2 supply transfer line detail layout | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.02.02 | LN2 supply transfer line detail layout | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.02.02 | Detailed dwg package for Procurement | 120 | PROF3 AD | 0 | 10698 | 10698 | Pending | Labor hourly rates
2.02.03.02.02 | Detailed dwg package for Procurement | 48 | PROF4 AD | 0 | 4970.4 | 4970.4 | Pending | Labor hourly rates
2.02.03.02.03 | Procurement, LN2 supply transfer line system | 80 | [6 empty] | 7765.6
2.02.03.02.03 | Bid Prep and qutoation: RFQ/RFP | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.02.03 | Bid Prep and qutoation: RFQ/RFP | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.02.03 | Evaluate bids | 12 | PROF3 AD | 0 | 1069.8 | 1069.8 | Pending | Labor hourly rates
2.02.03.02.03 | Evaluate bids | 12 | PROF4 AD | 0 | 1242.6 | 1242.6 | Pending | Labor hourly rates
2.02.03.02.03 | Award Contract | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.02.04.01 | Vendor Engineering and Design | 172 | [6 empty] | 139810.6
2.02.03.02.04.01 | (LN2 supply transfer line system) Kick off meeting | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.02.04.01 | (LN2 supply transfer line system) Engineering | 36 | PROF4 AD | 0 | 3727.8 | 3727.8 | Pending | Labor hourly rates
2.02.03.02.04.01 | (LN2 supply transfer line system) Preliminary Design Review | 8 | PROF4 AD | 22000 | 828.4 | 22828.4 | Pending | Experience
2.02.03.02.04.01 | (LN2 supply transfer line system) Detail dwg package | 48 | PROF4 AD | 0 | 4970.4 | 4970.4 | Pending | Labor hourly rates
2.02.03.02.04.01 | (LN2 supply transfer line system) Final Design Review | 8 | PROF4 AD | 50000 | 828.4 | 50828.4 | Pending | Experience
2.02.03.02.04.01 | (LN2 supply transfer line system) Long lead items order | 24 | PROF4 AD | 50000 | 2485.2 | 52485.2 | Pending | Experience
2.02.03.02.04.01 | (LN2 supply transfer line system) Drawings approvals | 40 | PROF4 AD | 0 | 4142 | 4142 | Pending | Labor hourly rates
2.02.03.02.04.02 | Vendor Fabrication | 100 | [6 empty] | 108355
2.02.03.02.04.02 | (LN2 supply transfer line system) Raw Material procurement | 36 | PROF4 AD | 50000 | 3727.8 | 53727.8 | Pending | Experience
2.02.03.02.04.02 | (LN2 supply transfer line system) Main fabrication items | 36 | PROF4 AD | 0 | 3727.8 | 3727.8 | Pending | Labor hourly rates
2.02.03.02.04.02 | (LN2 supply transfer line system) Final assemblies | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.02.04.02 | (LN2 supply transfer line system) BNL Holdpoint witness | 1 | PROF4 AD | 0 | 103.55 | 103.55 | Pending | Labor hourly rates
2.02.03.02.04.02 | (LN2 supply transfer line system) Shipping | 3 | PROF4 AD | 48000 | 310.65 | 48310.65 | Pending | Experience
2.02.03.02.05 | Delivery and receiving, LN2 supply transfer line system | 13 | [6 empty] | 1113.85
2.02.03.02.05 | Rigging/Truck Unloading | 5 | PROF3 AD | 0 | 445.75 | 445.75 | Pending | Experience
2.02.03.02.05 | Rigging/Truck Unloading | 7 | TECH3 AD | 0 | 564.55 | 564.55 | Pending | Experience
2.02.03.02.05 | Inspection | 1 | PROF4 AD | 0 | 103.55 | 103.55 | Pending | Experience
2.02.03.02.06 | Installation, LN2 supply transfer line system | 544 | [6 empty] | 61046.24
2.02.03.02.06 | Piping supports procure materials | 12 | PROF3 AD | 13000 | 1069.8 | 14069.8 | Pending | Experience
2.02.03.02.06 | Install piping supports | 80 | CRAFT3 | 0 | 9079.2 | 9079.2 | Pending | Labor hourly rates
2.02.03.02.06 | Install piping supports | 48 | PROF3 AD | 0 | 4279.2 | 4279.2 | Pending | Labor hourly rates
2.02.03.02.06 | Install piping supports | 128 | TECH3 AD | 0 | 10323.2 | 10323.2 | Pending | Labor hourly rates
2.02.03.02.06 | Rigging in place onto piping supports | 16 | CRAFT3 | 0 | 1815.84 | 1815.84 | Pending | Labor hourly rates
2.02.03.02.06 | Rigging in place onto piping supports | 16 | PROF3 AD | 0 | 1426.4 | 1426.4 | Pending | Labor hourly rates
2.02.03.02.06 | Rigging in place onto piping supports | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.03.02.06 | Install Instrumentation, reliefs and air supply to valves | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.02.06 | Install Instrumentation, reliefs and air supply to valves | 96 | TECH3 AD | 0 | 7742.4 | 7742.4 | Pending | Labor hourly rates
2.02.03.02.06 | Final pressure. leak check and equipment shakedown | 20 | PROF3 AD | 0 | 1783 | 1783 | Pending | Labor hourly rates
2.02.03.02.06 | Final pressure. leak check and equipment shakedown | 64 | TECH3 AD | 0 | 5161.6 | 5161.6 | Pending | Labor hourly rates
2.02.03.03.01 | Engineering and Design, Warm Piping System | 234 | [6 empty] | 22761.9
2.02.03.03.01 | Cryo Process Design | 48 | PROF3 AD | 0 | 4279.2 | 4279.2 | Pending | Labor hourly rates
2.02.03.03.01 | Cryo Process Design | 48 | PROF4 AD | 0 | 4970.4 | 4970.4 | Pending | Labor hourly rates
2.02.03.03.01 | P&ID development&dwgs | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.03.01 | P&ID development&dwgs | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Pending | Labor hourly rates
2.02.03.03.01 | Mechanical Engineering Tasks | 24 | PROF3 AD | 0 | 2139.6 | 2139.6 | Pending | Labor hourly rates
2.02.03.03.01 | Mechanical Engineering Tasks | 48 | PROF4 AD | 0 | 4970.4 | 4970.4 | Pending | Labor hourly rates
2.02.03.03.01 | Technical Specifications | 6 | PROF3 AD | 0 | 534.9 | 534.9 | Pending | Labor hourly rates
2.02.03.03.01 | Technical Specifications | 12 | PROF4 AD | 0 | 1242.6 | 1242.6 | Pending | Labor hourly rates
2.02.03.03.02.01 | Warm Piping tie in WR header | 132 | [6 empty] | 12286.2
2.02.03.03.02.01 | General Arrangement Layout | 80 | PROF3 AD | 0 | 7132 | 7132 | Pending | Labor hourly rates
2.02.03.03.02.01 | General Arrangement Layout | 20 | PROF4 AD | 0 | 2071 | 2071 | Pending | Labor hourly rates
2.02.03.03.02.01 | Detailed drawing package with weld map | 16 | PROF3 AD | 0 | 1426.4 | 1426.4 | Pending | Labor hourly rates
2.02.03.03.02.01 | Detailed drawing package with weld map | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.03.03.02.02 | Warm Piping tie in bldg 1010B compressor | 192 | [6 empty] | 17577.6
2.02.03.03.02.02 | General Arrangement Layout | 80 | PROF3 AD | 0 | 7132 | 7132 | Pending | Labor hourly rates
2.02.03.03.02.02 | General Arrangement Layout | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.03.03.02.02 | Detailed drawing package with weld map | 80 | PROF3 AD | 0 | 7132 | 7132 | Pending | Labor hourly rates
2.02.03.03.02.02 | Detailed drawing package with weld map | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.03.03.02.03 | GN2 Vent Line from platform coldbox | 144 | [6 empty] | 13183.2
2.02.03.03.02.03 | General Arrangement Layout | 40 | PROF3 AD | 0 | 3566 | 3566 | Pending | Labor hourly rates
2.02.03.03.02.03 | General Arrangement Layout | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.03.02.03 | Detailed drawing package with weld map | 80 | PROF3 AD | 0 | 7132 | 7132 | Pending | Labor hourly rates
2.02.03.03.02.03 | Detailed drawing package with weld map | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.03.03.02.04 | Warm Piping for summer 80K hold helium compressor loop | 231 | [6 empty] | 21155.25
2.02.03.03.02.04 | General Arrangement Layout | 64 | PROF3 AD | 0 | 5705.6 | 5705.6 | Pending | Labor hourly rates
2.02.03.03.02.04 | General Arrangement Layout | 13 | PROF4 AD | 0 | 1346.15 | 1346.15 | Pending | Labor hourly rates
2.02.03.03.02.04 | Detailed drawing package with weld map | 128 | PROF3 AD | 0 | 11411.2 | 11411.2 | Pending | Labor hourly rates
2.02.03.03.02.04 | Detailed drawing package with weld map | 26 | PROF4 AD | 0 | 2692.3 | 2692.3 | Pending | Labor hourly rates
2.02.03.03.03 | Procurement of materials, Warm Piping System | 228 | [6 empty] | 87572.6
2.02.03.03.03 | Reliefs | 72 | PROF3 AD | 8000 | 6418.8 | 14418.8 | Pending | Experience
2.02.03.03.03 | Reliefs | 72 | PROF4 AD | 0 | 7455.6 | 7455.6 | Pending | Experience
2.02.03.03.03 | Warm Valves | 36 | PROF4 AD | 15000 | 3727.8 | 18727.8 | Pending | Experience
2.02.03.03.03 | Piping and fittings | 24 | PROF4 AD | 32000 | 2485.2 | 34485.2 | Pending | Experience
2.02.03.03.03 | Piping supports | 24 | PROF4 AD | 10000 | 2485.2 | 12485.2 | Pending | Experience
2.02.03.03.04 | Installation, warm piping systems | 1148 | [6 empty] | 95136.2
2.02.03.03.04 | Phase 1: Welding of piping and install of piping supports | 144 | PROF3 AD | 0 | 12837.6 | 12837.6 | Pending | Labor hourly rates
2.02.03.03.04 | Phase 1: Welding of piping and install of piping supports | 360 | TECH3 AD | 0 | 29034 | 29034 | Pending | Labor hourly rates
2.02.03.03.04 | Phase 2: Welding of piping,vent lines and install of piping supports, after coldbox/magnet install | 72 | PROF3 AD | 0 | 6418.8 | 6418.8 | Pending | Labor hourly rates
2.02.03.03.04 | Phase 2: Welding of piping,vent lines and install of piping supports, after coldbox/magnet install | 360 | TECH3 AD | 0 | 29034 | 29034 | Pending | Labor hourly rates
2.02.03.03.04 | Pressure and leak check | 32 | PROF3 AD | 0 | 2852.8 | 2852.8 | Pending | Labor hourly rates
2.02.03.03.04 | Pressure and leak check | 32 | TECH3 AD | 0 | 2580.8 | 2580.8 | Pending | Labor hourly rates
2.02.03.03.04 | Install Instrumentation, reliefs and air supply to valves | 20 | PROF3 AD | 0 | 1783 | 1783 | Pending | Labor hourly rates
2.02.03.03.04 | Install Instrumentation, reliefs and air supply to valves | 64 | TECH3 AD | 0 | 5161.6 | 5161.6 | Pending | Labor hourly rates
2.02.03.03.04 | Final pressure. leak check and equipment shakedown | 32 | PROF3 AD | 0 | 2852.8 | 2852.8 | Pending | Labor hourly rates
2.02.03.03.04 | Final pressure. leak check and equipment shakedown | 32 | TECH3 AD | 0 | 2580.8 | 2580.8 | Pending | Labor hourly rates
2.02.03.04.01 | Engineering and Design | 504 | [6 empty] | 44823.6
2.02.03.04.01 | (Controls Hardware) Cryo instrument and equipment specifications | 120 | PROF3 AD | 0 | 10698 | 10698 | Pending | Labor hourly rates
2.02.03.04.01 | (Controls Hardware) Cryo instrument and equipment specifications | 120 | PROF4 AD | 0 | 12426 | 12426 | Pending | Labor hourly rates
2.02.03.04.01 | (Controls Hardware) Wire diagram dwgs | 128 | TECH3 AD | 0 | 10323.2 | 10323.2 | Pending | Labor hourly rates
2.02.03.04.01 | (Controls Hardware) Power distribution dwgs | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.03.04.01 | (Controls Hardware) I/O list table | 48 | PROF3 AD | 0 | 4279.2 | 4279.2 | Pending | Labor hourly rates
2.02.03.04.01 | (Controls Hardware) I/O list table | 48 | TECH3 AD | 0 | 3871.2 | 3871.2 | Pending | Labor hourly rates
2.02.03.04.02 | Procurement | 158 | [6 empty] | 140505.7
2.02.03.04.02 | (Controls Hardware) PLC I/O cards & expansion chassis | 15 | PROF3 AD | 7500 | 1337.25 | 8837.25 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Rack components | 4 | PROF3 AD | 6000 | 356.6 | 6356.6 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Lakeshore Temperature Controller/conditioners | 12 | PROF3 AD | 5000 | 1069.8 | 6069.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Lakeshore Temperature sensors | 12 | PROF3 AD | 22000 | 1069.8 | 23069.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) SC level probes | 12 | PROF3 AD | 3000 | 1069.8 | 4069.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) PresSure transmitters | 12 | PROF3 AD | 6400 | 1069.8 | 7469.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Flowmeters | 12 | PROF3 AD | 4600 | 1069.8 | 5669.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Vacuum gages and cables | 12 | PROF3 AD | 6000 | 1069.8 | 7069.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) 32 conductor cables, IP8 to 1008B racks | 12 | PROF3 AD | 16000 | 1069.8 | 17069.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) 8 conductor cables, IP8 to 1008B racks | 12 | PROF3 AD | 6200 | 1069.8 | 7269.8 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Heaters 480VAC | 14 | PROF3 AD | 17000 | 1248.1 | 18248.1 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Heater UL listed Control Panel | 14 | PROF3 AD | 18000 | 1248.1 | 19248.1 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Switch, 480 VAC | 5 | PROF3 AD | 1220 | 445.75 | 1665.75 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Network switch and Ethernet fiber drop | 5 | PROF3 AD | 3500 | 445.75 | 3945.75 | Pending | Experience
2.02.03.04.02 | (Controls Hardware) Cable tray and supports | 5 | PROF3 AD | 4000 | 445.75 | 4445.75 | Pending | Experience
2.02.03.04.03 | Installation: Cryo controls hardware | 601 | [6 empty] | 50883.05
2.02.03.04.03 | Rack built/rebuilt | 48 | PROF3 AD | 0 | 4279.2 | 4279.2 | Pending | Labor hourly rates
2.02.03.04.03 | Rack built/rebuilt | 96 | TECH3 AD | 0 | 7742.4 | 7742.4 | Pending | Labor hourly rates
2.02.03.04.03 | Rack install | 4 | PROF3 AD | 0 | 356.6 | 356.6 | Pending | Labor hourly rates
2.02.03.04.03 | Rack install | 13 | TECH3 AD | 0 | 1048.45 | 1048.45 | Pending | Labor hourly rates
2.02.03.04.03 | Cable pulling | 52 | CRAFT3 | 0 | 5901.48 | 5901.48 | Pending | Labor hourly rates
2.02.03.04.03 | Cable pulling | 52 | TECH3 AD | 0 | 4193.8 | 4193.8 | Pending | Labor hourly rates
2.02.03.04.03 | Cable termination | 160 | TECH3 AD | 0 | 12904 | 12904 | Pending | Labor hourly rates
2.02.03.04.03 | Check out continuity | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.03.04.03 | Heater Control Panel Install | 16 | TECH3 AD | 0 | 1290.4 | 1290.4 | Pending | Labor hourly rates
2.02.03.04.03 | Heater 480VAC wiring | 8 | CRAFT3 | 0 | 907.92 | 907.92 | Pending | Labor hourly rates
2.02.03.04.03 | Heater I/O wiring, temp sensors | 16 | TECH3 AD | 0 | 1290.4 | 1290.4 | Pending | Labor hourly rates
2.02.03.04.03 | Wire up instruments and control valves | 96 | TECH3 AD | 0 | 7742.4 | 7742.4 | Pending | Labor hourly rates
2.02.03.05 | Cryo Controls Software | 1944 | [6 empty] | 178387.6
2.02.03.05 | Control Logic eng document revision by Cryo process engineering | 240 | PROF3 AD | 0 | 21396 | 21396 | Pending | Labor hourly rates
2.02.03.05 | Control Logic eng document revision by Cryo process engineering | 240 | PROF4 AD | 0 | 24852 | 24852 | Pending | Labor hourly rates
2.02.03.05 | Interface document definition for variables to MCR and sPHENIX controls | 8 | PROF3 AD | 0 | 713.2 | 713.2 | Pending | Labor hourly rates
2.02.03.05 | Interface document definition for variables to MCR and sPHENIX controls | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.05 | Built HMI operator screens | 576 | PROF3 AD | 0 | 51350.4 | 51350.4 | Pending | Labor hourly rates
2.02.03.05 | Built HMI operator screens | 72 | PROF4 AD | 0 | 7455.6 | 7455.6 | Pending | Labor hourly rates
2.02.03.05 | PLC programming | 576 | PROF3 AD | 0 | 51350.4 | 51350.4 | Pending | Labor hourly rates
2.02.03.05 | PLC programming | 72 | PROF4 AD | 0 | 7455.6 | 7455.6 | Pending | Labor hourly rates
2.02.03.05 | Live I/O check out and control logic test | 64 | PROF3 AD | 0 | 5705.6 | 5705.6 | Pending | Labor hourly rates
2.02.03.05 | Live I/O check out and control logic test | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.03.05 | Live I/O check out and control logic test | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.03 | Total Cost |  |  | 1524420 | 1105064.09 | 2629484.09 |  |  |  | 2629484.09
12383

## PS & Quench Detection - Details
WBS | Description | Hours | Resources | Material | Labor | Total | Status | Basis of Estimate | Total | Grand Total
2.02.04.01.01 | Design AC/DC Power Distribution | [7 empty] | 12426
2.02.04.01.01 | Design Cable Tray and Supports for Power and Signal Distribution | 120 | PROF4 AD | 0 | 12426 | 12426 | Pending | Labor hourly rates
2.02.04.01.02 | Procure PS System Connections | [7 empty] | 82534.8
2.02.04.01.02 | Order AC Power Distribution Parts | 8 | PROF4 AD | 3000 | 828.4 | 3828.4 | Pending | Experience
2.02.04.01.02 | Order PS and Quench Detector AC Power Cables and Interconnects | 8 | PROF4 AD | 3000 | 828.4 | 3828.4 | Pending | Experience
2.02.04.01.02 | Order PS, Magnet, Dump Resistor DC Cabling and Interconnects | 16 | PROF4 AD | 60000 | 1656.8 | 61656.8 | Pending | Experience
2.02.04.01.02 | Fabricate DC flags | 80 | CRAFT3 | 0 | 9079.2 | 9079.2 | Pending | Labor hourly rates
2.02.04.01.02 | Order Cable Tray and Supports | 40 | PROF4 AD | 0 | 4142 | 4142 | Pending | Labor hourly rates
2.02.04.01.03 | Install PS AC/DC Cabling | [7 empty] | 51422
2.02.04.01.03 | Install Cable Tray and Supports for Power and Signal Distribution | 160 | CRAFT3 | 0 | 18158.4 | 18158.4 | Pending | Labor hourly rates
2.02.04.01.03 | Install Cable Tray and Supports for Power and Signal Distribution | 40 | PROF4 AD | 0 | 4142 | 4142 | Pending | Labor hourly rates
2.02.04.01.03 | Pull & Terminate AC/DC Power Cables and Signal Cables | 32 | PROF4 AD | 0 | 3313.6 | 3313.6 | Pending | Labor hourly rates
2.02.04.01.03 | Pull & Terminate AC/DC Power Cables and Signal Cables | 320 | TECH3 AD | 0 | 25808 | 25808 | Pending | Labor hourly rates
2.02.04.02.01 | Install Power Supply | [7 empty] | 29017.52
2.02.04.02.01 | Move PS to location | 8 | CRAFT3 | 0 | 907.92 | 907.92 | Pending | Labor hourly rates
2.02.04.02.01 | Connect AC Power to PS | 20 | CRAFT3 | 0 | 2269.8 | 2269.8 | Pending | Labor hourly rates
2.02.04.02.01 | Connect AC Power to PS | 5 | PROF4 AD | 0 | 517.75 | 517.75 | Pending | Labor hourly rates
2.02.04.02.01 | Connect DC Cabling to PS, Dump Resistor, Magnet | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.04.02.01 | Connect DC Cabling to PS, Dump Resistor, Magnet | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.04.02.01 | Connect Signal Interconnections | 7 | PROF4 AD | 0 | 724.85 | 724.85 | Pending | Labor hourly rates
2.02.04.02.01 | Connect Signal Interconnections | 32 | TECH3 AD | 0 | 2580.8 | 2580.8 | Pending | Labor hourly rates
2.02.04.02.01 | Power Supply Testing | 80 | PROF4 AD | 0 | 8284 | 8284 | Pending | Labor hourly rates
2.02.04.02.01 | Power Supply Testing | 80 | TECH3 AD | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.04.03.02.01 | Install Quench Detector | [7 empty] | 14225.68
2.02.04.03.02.01 | Move Quench Detector to location | 8 | CRAFT3 | 0 | 907.92 | 907.92 | Pending | Labor hourly rates
2.02.04.03.02.01 | Connect AC Power to Quench Detector | 24 | CRAFT3 | 0 | 2723.76 | 2723.76 | Pending | Labor hourly rates
2.02.04.03.02.01 | Connect Signal Interconnections | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.04.03.02.01 | Quench Detector Testing | 40 | PROF4 AD | 0 | 4142 | 4142 | Pending | Labor hourly rates
2.02.04.03.02.01 | Quench Detector Testing | 40 | TECH3 AD | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.04 | Total Cost | 1296 |  | 66000 | 123626 | 189626 |  |  |  | 189626
2.02.04.01.01 | Design AC/DC Power Distribution
2.02.04.01.01 | Design PS AC and Quench Detector Power Distribution | 80 | PROF4 AD | 0 | 8284 | 8284 | Completed | Labor hourly rates
2.02.04.01.01 | Design PS AC Power Hook-up | 20 | PROF4 AD | 0 | 2071 | 2071 | Completed | Labor hourly rates
2.02.04.01.01 | Design Quench Detector AC Power Hook-up | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Completed | Labor hourly rates
2.02.04.01.01 | Design PS, Magnet, Dump Resistor DC Cabling | 40 | PROF4 AD | 0 | 4142 | 4142 | Completed | Labor hourly rates
2.02.04.02.01 | Install Power Supply
2.02.04.02.01 | Design Signal Interconnects | 40 | PROF4 AD | 0 | 4142 | 4142 | Completed | Labor hourly rates
2.02.04.03.01 | Design Quench Detector System Connections
2.02.04.03.01 | Design Quench Detector Signal Interconnections | 40 | PROF4 AD | 0 | 4142 | 4142 | Completed | Labor hourly rates
2.02.04.03.02 | Procure Quench Detector System Connections
2.02.04.03.02 | Order Quench Detector Signal Cables and Interconnects | 24 | PROF4 AD | 0 | 2485.2 | 2485.2 | Completed | Labor hourly rates
2.02.04.03.02 | Install Quench Detector Cabling | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Completed | Labor hourly rates
2.02.04.03.02 | Install Quench Detector Cabling | 40 | TECH3 AD | 0 | 3226 | 3226 | Completed | Labor hourly rates
| Completed | 308 | Total | 0 | 30977.4 | 30977.4

## Magnet Field Meas. - Details
WBS | Description | Hours | Resources | Material | Labor | Total | Status | Basis of Estimate | Total | Grand Total
2.02.05.01 | Magnet Field Measurements Engineering and Design, Field Studies and Stress Analysis | [7 empty] | 73949.4
2.02.05.01 | Setup a detailed 3D model of the coil, return yoke and internal calorimeters | 160 | SCI3 PO | 0 | 19312 | 19312 | Pending | Labor hourly rates
2.02.05.01 | Setup a detailed 3D model of the coil, return yoke and internal calorimeters | 48 | TECH3 PO D | 0 | 3871.2 | 3871.2 | Pending | Labor hourly rates
2.02.05.01 | Design mounts for NMR probes to monitor field | 8 | PROF4 AD | 0 | 828.4 | 828.4 | Pending | Labor hourly rates
2.02.05.01 | Design mounts for NMR probes to monitor field | 40 | TECH3 PO D | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.05.01 | Design readout for NMR probes to monitor field | 4 | PROF4 AD | 0 | 414.2 | 414.2 | Pending | Labor hourly rates
2.02.05.01 | Design readout for NMR probes to monitor field | 40 | TECH3 PO D | 0 | 3226 | 3226 | Pending | Labor hourly rates
2.02.05.01 | Perform Magnet Assembly Stress Analysis | 360 | PROF4 AD | 0 | 37278 | 37278 | Pending | Labor hourly rates
2.02.05.01 | Perform Magnet Assembly Stress Analysis | 48 | SCI3 PO | 0 | 5793.6 | 5793.6 | Pending | Labor hourly rates
2.02.05.02 | Magnet Field Measurements Equipment Purchase and Fabrication | [7 empty] | 42055
2.02.05.02 | Procure NMR probes | 10 | PROF4 PO E | 6000 | 1035.5 | 7035.5 | Pending | Experience
2.02.05.02 | Procure NMR probe readout parts | 10 | PROF4 PO E | 1000 | 1035.5 | 2035.5 | Pending | Experience
2.02.05.02 | Fabricate NMR probe readout parts | 16 | PROF4 PO E | 0 | 1656.8 | 1656.8 | Pending | Experience
2.02.05.02 | Fabricate NMR probe readout parts | 16 | SCI3 PO | 0 | 1931.2 | 1931.2 | Pending | Experience
2.02.05.02 | Fabricate NMR probe readout parts | 160 | TECH3 PO D | 0 | 12904 | 12904 | Pending | Experience
2.02.05.02 | Fabricate NMR probe mounts | 16 | PROF4 AD | 0 | 1656.8 | 1656.8 | Pending | Labor hourly rates
2.02.05.02 | Fabricate NMR probe mounts | 16 | SCI3 PO | 0 | 1931.2 | 1931.2 | Pending | Labor hourly rates
2.02.05.02 | Fabricate NMR probe mounts | 160 | TECH3 PO D | 0 | 12904 | 12904 | Pending | Labor hourly rates
2.02.05.03 | Magnet Field Measurements Installation and Test, Post-Test Field Studies and Stress Analysis | [7 empty] | 18522
2.02.05.03 | Run 3D field simulations and construct field and force maps | 40 | SCI3 AD | 0 | 4828 | 4828 | Pending | Labor hourly rates
2.02.05.03 | Run 3D field simulations and construct field and force maps | 40 | SCI3 PO | 0 | 4828 | 4828 | Pending | Labor hourly rates
2.02.05.03 | install NMR probes to monitor field | 4 | SCI3 AD | 0 | 482.8 | 482.8 | Pending | Labor hourly rates
2.02.05.03 | install NMR probes to monitor field | 16 | SCI3 PO | 0 | 1931.2 | 1931.2 | Pending | Labor hourly rates
2.02.05.03 | install NMR probes to monitor field | 80 | TECH3 PO M | 0 | 6452 | 6452 | Pending | Labor hourly rates
2.02.05 | Total Cost | 1292 |  | 7000 | 127526.4 | 134526.4 |  |  |  | 134526.4