## Navigation
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
sPHENIX Infrastructure |  |  | 2.04 |  | Detector Support Systems |  | 2.04.01
|  | Work Package Name |  | WBS Number |  | Basis of Estimate Link
|  | Line Electric Power Distribution Work Package |  | 2.04.01.01 |  | Go To BoE
|  | Detector Support Services Systems Components Work Package |  | 2.04.01.02 |  | Go To BoE
|  | Detector Electronics Racks and Rack generic support systems |  | 2.04.01.03 |  | Go To BoE
|  | Detector Gas and Cooling Services Systems |  | 2.04.01.04 |  | Go To BoE
|  | Detector Safety Subsystems Work Package |  | 2.04.01.05 |  | Go To BoE
|  | Gas Mixing House & Gas Pad Components Work Package |  | 2.04.01.06 |  | Go To BoE
|  | Rack Room Modifications Work Package |  | 2.04.01.07 |  | Go To BoE
|  | Control Room Work Package |  | 2.04.01.08 |  | Go To BoE
Description of this Control Account:
Technical Scope: WBS 2.04.01 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Line Electric Power Distribution 2. Detector Support Services Systems Components 3. Detector Electronics Racks and Rack generic support systems 4. Detector Gas and Cooling Services Systems 5. Detector Safety Subsystems 6. Gas Mixing House & Gas Pad Components 7. Rack Room Modifications 8. Control Room and Offices Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 8 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below).

## Infrastructure Structure
Return to Navigation Page
Subsystems | 2.03 and 2.04: Infrastructure
Control Accounts | 2.03.01: Detector Mechanical and Support System | 2.04.01: Detector Support Systems |  | 2.04.02: Facility Support Systems
Work Packages |  |  | 2.04.01.01: Line Electric Power Distribution Work Package
2.04.01.02: Detector Support Services Systems Components Work Package
2.04.01.03: Detector Electronics Racks and Rack generic support systems
2.04.01.04: Detector Gas and Cooling Services Systems
2.04.01.05: Detector Safety Subsystems Work Package
2.04.01.06: Gas Mixing House & Gas Pad Components Work Package
2.04.01.07: Rack Room Modifications Work Package
2.04.01.08: Control Room Work Package

## Detector Support Sys Dictionary
Return to Navigation Page
WBS 2.04.01: Detector Support Systems Dictionary
WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.04.01 | Task Description
Detector Support Systems
Task
2.04.01 | Detector Support Systems | Technical Scope: WBS 2.04.01 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Line Electric Power Distribution 2. Detector Support Services Systems Components 3. Detector Electronics Racks and Rack generic support systems 4. Detector Gas and Cooling Services Systems 5. Detector Safety Subsystems 6. Gas Mixing House & Gas Pad Components 7. Rack Room Modifications 8. Control Room and Offices Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 8 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below).
2.04.01.01 | Line Electric Power Distribution Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX line electrical requirements and distribution of line electricity to all subsystems. Electrical distribution within the subsystems and detector control, signal and monitoring electronics are outside of this scope. (see each subsystems work packages for such info) Work Statement: This work package includes the following tasks: 1. Evaluate the existing facility electric power distribution system at building 1008A to adequately supply sPHENIX Experimental Equipment. Perform a load flow and short circuit analysis starting from the 13.8KV/480V Substation 8A to the 480VAC Bus DP, through to the 208VAC Bus DPA and ending at the 208VAC distribution panels in the Intersection Region (IR). 2. Perform an ARC Flash calculation. 3. Modify the above system, as required, including but not limited to, transformers, circuit breakers, power quality instruments/equipment to facilitate remote monitoring & control, cables, and Transient Voltage Surge Suppression (TVSS). 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
S327400 | Evaluate Exiting Power Distribution System for Line Electric Power | Technical Scope: Evaluation of the existing power supplied to the PHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S327500 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power | Technical Scope: Evaluation of the specific requirements for sPHENIX detector subsystems line electric power. Work Statement: Gather all relevant information from subsystems.
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | Technical Scope: Evaluation of the normal, emergency and UPS loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S327700 | Calculate Power Transformer Requirements for Line Electric Power | Technical Scope: Evaluation of the Power Transformer loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation.
S327800 | Size Conductors for Line Electric Power | Technical Scope: Evaluation of the Line Electric Power conductors feeding the sPHENIX detector subsystems in the 1008 IR. Work Statement: Calculate the optimum size of conductors..
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power | Technical Scope: Design schematic drawings for the Line Electric Power Distribution System in the 1008 IR. Work Statement: Create appropriate One-line drawings to reflect the sPHENIX desired configuration.
S328000 | Review Line Electric Distribution Design/Safety | Technical Scope: Review the Line Electric Power Distribution System for sPHENIX detector subsystems in the 1008 IR. Work Statement: Prepare documents and presentations as appropriate for review by CAD electrical engineering.
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | Technical Scope: Evaluation of the action items from Safety Reviews for the Line Electric Power Distribution System. 1008 IR. Work Statement: Appropriately address all action items from review.
S328200 | Design/Safety Reviews Complete, Line Electric Power Distribution Released for Production | Milestone
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | Technical Scope: Develop the procurement packages for components in the Line Electric Distribution System. Work Statement: Gather all relevant information from existing PHENIX documentation.
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | Technical Scope: Evaluation of the Line Electric Power Distribution components Bid documents. Work Statement: Prepare bid documents for line electrical power components, Initiate procure,ent of components.
S328500 /S328600 /S328700 /S328800 /S328900 /S329000 /S329100 | Procure & Deliver Line Electric Power Distribution Components (leadtime and fabrication included) | Technical Scope: Procurement and delivery of Line Electric Power Distribution components. Work Statement: Monitor and manage procurement process for line electric components.
S329200 | Perform Line Electric Power Distribution Components Acceptance | Technical Scope: Performance of Acceptance Tests for the Line Electric Power Distribution System. Work Statement: receive, inspect and accept line electric components.
S329300 | Line Electric Power Distribution Components Ready for Installation | Milestone
2.04.01.02 | Detector Support Services Systems Components Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector support services including cable routing and management, fibers, cooling lines, routing and cable manangement of monitoring and control lines, etc., including cable trays, mounting hardware etc., dry air, N2 and shop air. Also included in this work package are signal lines (fiber/cable) between on carriage racks and rack room electronics. (Note cables and fibers from detectors to patch panels, detectors to on carriage racks and patch panels to rack room racks are not part of this work package. (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific cables/fibers) Work Statement: This work package includes the following tasks: 1. Analyze Design Detector Support Services Systems Requirements 2. Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems 3. Review Design Detector Support Services Systems Design/Safety, address action items 4. Prepare Detector Support Services Systems Components Procurement Package(s) 5. Evaluate & Process Detector Support Services Systems Components Bids 6. Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) 7. Perform Detector Support Services Systems Components Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S329400 | Analyze Design Detector Support Services Systems Requirements | Technical Scope: Analyze Design Detector Support Services Systems Requirements Work Statement: Gather all relevant information from existing PHENIX documentation.
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems. Work Statement: Make appropriate detail drawings for Design Detector Support Services.
S329600 | Review Design Detector Support Services Systems Design/Safety | Technical Scope:Review Design Detector Support Services Systems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Support Services Systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately.
S329800 | Design/Safety Reviews Complete, Detector Support Services Systems Components Released for Production | Milestone
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) | Technical Scope: Prepare Detector Support Services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S330000 | Evaluate & Process Detector Support Services Systems Components Bids | Technical Scope: Evaluate & Process Detector Support Services Systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S330100 /S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.
S330300 | Perform Detector Support Services Systems Components Acceptance | Technical Scope: Perform Detector Support Services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S330400 | Detector Support Services Systems Components Ready for Installation | Milestone
2.04.01.03 | Detector Electronics Racks and Rack generic support systems | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector on carriage racks and generic control safety power distribution. (Note electronics and custom equipment specifically designed for the subsytem is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Design individual electronics racks to house the electronics chassis for the sPHENIX detector subsystems. 2. Design the internal rack cooling systems consisting of water piping, heat exchangers and fan trays . 3. Design the internal rack Supervisory Control & Data Aquisition System (SCADA) including safety monitoring & alarms. 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
S330600 /S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements | Technical Scope : Analyze Detector Electronics Racks and Rack generic support systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems. Work Statement: Make appropriate detail drawings for Detector Electronics Racks.
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety | Technical Scope: Review Detector Electronics Racks and Rack generic support systems Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately.
S331000 | Design/Safety Reviews Complete, Detector Electronics Racks and Rack generic support systems Components Released for Production | Milestone
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | Technical Scope:Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | Technical Scope: Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S331300 | Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.
S331400 /S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | Technical Scope:Perform Detector Electronics Racks and Rack generic support systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S331600 | Detector Electronics Racks and Rack generic support systems Components Ready for Installation | Milestone
2.04.01.04 | Detector Gas and Cooling Services Systems | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector gas and cooling services including pipe/tube routing and off detector distribution panels, control and monitoring cables and cable management. (Note Generic cooling and gas services- e.g. dry air, dry N2- are included in this work package. Detector specific cooling mediums and gas and associated gas distribution racks and monitoring equipment -e.g. GMH computers- are not included in this work package. (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific cables/fibers) Work Statement: This work package includes the following tasks: 1. Analyze Detector Gas and Cooling Services Systems Requirements 2. Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems 3. Review Detector Gas and Cooling Services Systems Design/Safety; address action items 4. Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) 5. Evaluate & Process Detector Gas and Cooling Services Systems Components Bids 6. Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) 7. Perform Detector Gas and Cooling services Systems Components Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S331700 | Analyze Detector Gas and Cooling Services Systems Requirements | Technical Scope: Analyze Detector Gas and Cooling Services Systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S331800 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems | Technical Scope : Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems. Work Statement: Make appropriate detail drawings for Detector Gas and Cooling Systems.
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety | Technical Scope : Review Detector Gas and Cooling Services Systems Design/Safety citeria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S332000 | Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews | Technical Scope : Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S332100 | Design/Safety Reviews Complete, Detector Gas and Cooling services Systems Components Released for Production | Milestone
S332200 | Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) | Technical Scope : Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S332300 | Evaluate & Process Detector Gas and Cooling Services Systems Components Bids | Technical Scope : Evaluate & Process Detector Gas and Cooling Services Systems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S332400 /S332500 | Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) | Technical Scope : Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.
S332600 | Perform Detector Gas and Cooling services Systems Components Acceptance | Technical Scope : Perform Detector Gas and Cooling services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S332700 | Detector Gas and Cooling services Systems Components Ready for Installation | Milestone
2.04.01.05 | Detector Safety Subsystems Work Package | "Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector on carriage racks and generic control safety power distribution. (Note electronics and custom equipment specifically designed for the subsytem is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.2 through 1.07, 2.02 , 2.05 , 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Design individual electronics racks to house the electronics chassis for the sPHENIX detector subsystems. 2. Design the internal rack cooling systems consisting of water piping, heat exchangers and fan trays . 3. Design the internal rack Supervisory Control & Data Aquisition System (SCADA) including safety monitoring & alarms. 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.02)
S332800 | Analyze Detector Safety Subsystems Requirements | Technical Scope: Analyze On Detector/Carriage Safety Subsystems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for On-Detector/Carriage Safety Subsystems. Work Statement: Make appropriate detail drawings for On Detector/Carriage Safety Subsystems.
S333000 | Review Detector Safety Subsystems Design/Safety | Technical Scope: Review On Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from On Detector/Carriage Safety Subsystems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately.
S333200 | Design/Safety Reviews Complete, Detector Safety Subsystems Components Released for Production | Milestone
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare On Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components.
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | Technical Scope:Evaluate & Process On Detector/Carriage Safety Subsystems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S333500 /S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver On Detector/Carriage Safety Subsystems Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item.
S333700 | Perform Detector Safety Subsystems Components Acceptance | Technical Scope: Perform On Detector/Carriage Safety Subsystems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S333800 | Detector Safety Subsystems Components Ready for Installation | Milestone
2.04.01.06 | Gas Mixing House & Gas Pad Components Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of Gas Mixing House & Gas Pad Components required to support the sPHENIX upgrade. (Note Gas system supply, monitoring and distribution equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Analyze Gas Mixing House & Gas Pad Components Requirements 2. Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents 3. Review Gas Mixing House & Gas Pad Components Design/Safety; adress action items 4. Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) 5. Evaluate & Process Gas Mixing House & Gas Pad Components Bids 6. Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) 7. Perform Gas Mixing House & Gas Pad Components Acceptance 8. Gas Mixing House & Gas Pad Components Ready for Installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements | Technical Scope: Analyze Gas Mixing House & Gas Pad Components Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents | Technical Scope: Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Gas Mixing House & Gas Pad.
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety | Technical Scope: Review Gas Mixing House & Gas Pad Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | Technical Scope :Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S334300 | Design/Safety Reviews Complete, Gas Mixing House & Gas Pad Components Released for Production | Milestone
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) | Technical Scope:Prepare Gas Mixing House & Gas Pad Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components.
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids | Technical Scope: Evaluate & Process Gas Mixing House & Gas Pad Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S334600 /S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item.
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance | Technical Scope: Perform Gas Mixing House & Gas Pad Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S334900 | Gas Mixing House & Gas Pad Components Ready for Installation | Milestone
2.04.01.07 | Rack Room Modifications Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of rack room racks and generic rack room equipment required to support the sPHENIX upgrade. (Note electronics and custom equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1 Evaluate the PHENIX Rack Room at building 1008 to accommodate new electronics racks and components necessary to support the sPHENIX Experiment. 2. Design modifications or replacements, as required for the installation of equipment. 3. Procure the necessary equipment to upgrade the existing Rack Room. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S335000 | Analyze Rack Room Modifications Requirements | Technical Scope : Analyze Rack Room Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Rack Room Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Rack Room modifications.
S335200 | Review Rack Room Modifications Components Design/Safety | Technical Scope: Review Rack Room Modifications Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | Technical Scope:Address Action Items from Rack Room Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S335400 | Design/Safety Reviews Complete, Rack Room Modifications Components Released for Production | Milestone
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) | Technical Scope: Prepare Rack Room Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components.
S335600 | Evaluate & Process Rack Room Modifications Components Bids | Technical Scope: Evaluate & Process Rack Room Modifications Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S335700 /S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item.
S335900 | Perform Rack Room Modifications Components Acceptance | Technical Scope: Perform Rack Room Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S336000 | Rack Room Modifications Components Ready for Installation | Milestone
2.04.01.08 | Control Room Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of control room and office modifications required to support the sPHENIX upgrade. (Note custom control room and office equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1 Evaluate the PHENIX control room and offices at building 1008 to update furniture, computers, and related equipmentand components necessary to support the sPHENIX Experiment. 2. Design modifications or replacements, as required for the installation of equipment. 3. Procure the necessary equipment to upgrade the existing control room and offices. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
S336100 | Analyze Control Room Requirements | Technical Scope: Analyze Control Room and Offices Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation.
S336200 | Create Control Room Schematic Design and Specification Control Documents | Technical Scope :Create Control Room and Offices Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Control Room and Offices modifications.
S336300 | Review Control Room Design/Safety | Technical Scope: Review Control Room and Offices Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee.
S336400 | Address Action Items from Control Room Design & Safety Reviews | Technical Scope:Address Action Items from Control Room and Offices Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately.
S336500 | Design/Safety Reviews Complete, Control Room Components Released for Production | Milestone
S336600 | Prepare Control Room Components Procurement Package(s) | Technical Scope: Prepare Control Room and Offices Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components.
S336700 | Evaluate & Process Control Room Components Bids | Technical Scope:Evaluate & Process Control Room and Offices Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor.
S336800 /S336900 | Procure & Deliver Control Room Components (leadtime and fabrication included) | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item.
S337000 | Perform Control Room Components Acceptance | Technical Scope: Perform Control Room and Offices Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate.
S337100 | Control Room components Ready for Installation | Milestone

## BoE for Det Sup Systems
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  |  | Date of Est: | 2017-03-20
[9 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  |  | WBS number: |  |  |  |  | Control Account
Detector Support Systems |  |  |  |  | 2.04.01 |  |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: WBS 2.04.01 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Line Electric Power Distribution 2. Detector Support Services Systems Components 3. Detector Electronics Racks and Rack generic support systems 4. Detector Gas and Cooling Services Systems 5. Detector Safety Subsystems 6. Gas Mixing House & Gas Pad Components 7. Rack Room Modifications 8. Control Room and Offices Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 8 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below).
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material cost estimate for this control account)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX detector subsystems. 3. Chillers, Gas system source, distribution, and other services are covered by this control account (see WBS 2.04.01) or Control Account 2.04.02 (Facility Support Systems) or the individual detector subsystems or the Magnet subsystem. More detailed explanation for this division of responsibility is provided in the BoE's for the individual work packages under this control account. (see the navigation page to access the work package BoE's.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of infrastructure equipment and components as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
| WBS # |  | Work Package Description |  |  | Material Cost for this Work Package
| 2.04.01.01 |  | Line Electric Power Distribution Work Package |  |  | 50000
| 2.04.01.02 |  | Detector Support Services Systems Components Work Package |  |  | 32000
| 2.04.01.03 |  | Detector Electronics Racks and Rack generic support systems |  |  | 32000
| 2.04.01.04 |  | Detector Gas and Cooling Services Systems |  |  | 107000
| 2.04.01.05 |  | Detector Safety Subsystems Work Package |  |  | 12000
| 2.04.01.06 |  | Gas Mixing House & Gas Pad Components Work Package |  |  | 10000
| 2.04.01.07 |  | Rack Room Modifications Work Package |  |  | 20000
| 2.04.01.08 |  | Control Room Work Package |  |  | 50000
|  |  | Total Unburdened Material Cost for CA # 2.04.02 = |  |  |  | 313000
estimate uncertainty
Estimates for the labor and material described in this Control account are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in each work package. The overall material estimate uncertainty for this control account is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual work packages. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work packages' labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01: Detector Support Systems | [5 empty] | Labor estimate uncertainty: | 25%
[7 empty] | Material estimate uncertainty: | 37.6%

## BoE for Line Electric
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS Number: |  |  |  | Control Account Number
Line Electric Power Distribution Work Package |  |  |  | 2.04.01.01 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX line electrical requirements and distribution of line electricity to all subsystems. Electrical distribution within the subsystems and detector control, signal and monitoring electronics are outside of this scope. (see each subsystems work packages for such info) Work Statement: This work package includes the following tasks: 1. Evaluate the existing facility electric power distribution system at building 1008A to adequately supply sPHENIX Experimental Equipment. Perform a load flow and short circuit analysis starting from the 13.8KV/480V Substation 8A to the 480VAC Bus DP, through to the 208VAC Bus DPA and ending at the 208VAC distribution panels in the Intersection Region (IR). 2. Perform an ARC Flash calculation. 3. Modify the above system, as required, including but not limited to, transformers, circuit breakers, power quality instruments/equipment to facilitate remote monitoring & control, cables, and Transient Voltage Surge Suppression (TVSS). 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
Estimate Type (check all that apply):
| x | Work Complete
Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX line electrical power distribution system.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of line electrical distribution equipment and components as indicated in the "Dictionary Definition: section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $50000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.01: Line Electric Power Distribution Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 25%

## BoE for Services
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Detector Support Services Systems Components Work Package |  |  |  | 2.04.01.02 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector support services including cable routing and management, fibers, cooling lines, routing and cable manangement of monitoring and control lines, etc., including cable trays, mounting hardware etc., dry air, N2 and shop air. Also included in this work package are signal lines (fiber/cable) between on carriage racks and rack room electronics. (Note cables and fibers from detectors to patch panels, detectors to on carriage racks and patch panels to rack room racks are not part of this work package. (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific cables/fibers) Work Statement: This work package includes the following tasks: 1. Analyze Design Detector Support Services Systems Requirements 2. Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems 3. Review Design Detector Support Services Systems Design/Safety, address action items 4. Prepare Detector Support Services Systems Components Procurement Package(s) 5. Evaluate & Process Detector Support Services Systems Components Bids 6. Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) 7. Perform Detector Support Services Systems Components Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Material and labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX detector support services systems. Wherever possible PHENIX equipment will be repurposed to be used in this work package.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of the detector support services systems as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $32000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.02: Detector Support Services Systems Components Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for Racks
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-23
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Detector Electronics Racks and Rack generic support systems |  |  |  | 2.04.01.03 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector on carriage racks and generic control safety power distribution. (Note electronics and custom equipment specifically designed for the subsytem is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Design individual electronics racks to house the electronics chassis for the sPHENIX detector subsystems. 2. Design the internal rack cooling systems consisting of water piping, heat exchangers and fan trays . 3. Design the internal rack Supervisory Control & Data Aquisition System (SCADA) including safety monitoring & alarms. 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Material and labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX electronic racks and generic rack support systems Wherever possible PHENIX equipment will be repurposed to be used in this work package. As there are more PHENIX racks available, repurposing for this work package will be extensive.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of the electronics racks support systems as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $32000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.03: Detector Electronics Racks and Rack generic support systems |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for Gas & Cooling
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Detector Gas and Cooling Services Systems |  |  |  | 2.04.01.04 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of detector gas and cooling services including pipe/tube routing and off detector distribution panels, control and monitoring cables and cable management. (Note Generic cooling and gas services- e.g. dry air, dry N2- are included in this work package. Detector specific cooling mediums and gas and associated gas distribution racks and monitoring equipment -e.g. GMH computers- are not included in this work package. (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific cables/fibers) Work Statement: This work package includes the following tasks: 1. Analyze Detector Gas and Cooling Services Systems Requirements 2. Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems 3. Review Detector Gas and Cooling Services Systems Design/Safety; address action items 4. Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) 5. Evaluate & Process Detector Gas and Cooling Services Systems Components Bids 6. Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) 7. Perform Detector Gas and Cooling services Systems Components Acceptance NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
| x | Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Material and labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX detector gas and cooling systems services. Wherever possible PHENIX equipment will be repurposed to be used in this work package. As there are more PHENIX gas systems than sPHENIX, repurposing for this work package will be extensive.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of the detector gas and cooling systems services as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $107000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.04: Detector Gas and Cooling Services Systems |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for Det Safety
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-23
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Detector Safety Subsystems Work Package |  |  |  | 2.04.01.05 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of the on-detector/carriage safety subsystems including in rack smoke and leak detector systems and on carriage smoke and leak detection systems. (Note Off detector/carriage safety subsystems are covered in work package WBS 2.04.02.4.) Work Statement: This work package includes the following tasks: 1 Design the individual On Detector "Safety Monitor and Control Systems" (SMCS) to protect the sPHENIX subsystems from faults. 2. Procure the necessary equipment to upgrade the existing On-Detector SMCS control system 3. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials to support the sPHENIX On Detector/Carriage Safety Subsystems.
Details of the Base Estimate (explanation of the Work)
Labor and material estimates are for analyses, design and procurement of the sPHENIX On DetectorSafety Subsystems.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $12000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.05: Detector Safety Subsystems Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for GMH & Gas Pad
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Gas Mixing House & Gas Pad Components Work Package |  |  |  | 2.04.01.06 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of Gas Mixing House & Gas Pad Components required to support the sPHENIX upgrade. (Note Gas system supply, monitoring and distribution equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1. Analyze Gas Mixing House & Gas Pad Components Requirements 2. Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents 3. Review Gas Mixing House & Gas Pad Components Design/Safety; adress action items 4. Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) 5. Evaluate & Process Gas Mixing House & Gas Pad Components Bids 6. Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) 7. Perform Gas Mixing House & Gas Pad Components Acceptance 8. Gas Mixing House & Gas Pad Components Ready for Installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
| x | Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of Gas Mixing House (GMH) and Gas Pad components and materials based on existing PHENIX GMH and gas Pad components which are similar to those needed for sPHENIX. The existing GMH and Gas Pad equipment is mostly adequate for sPHENIX needs and will be repurposed for sPHENIX. Some rework of the existing system is anticipated as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of Rack Room equipment as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $10000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.06: Gas Mixing House & Gas Pad Components Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for Rack Room
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Rack Room Modifications Work Package |  |  |  | 2.04.01.07 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of rack room racks and generic rack room equipment required to support the sPHENIX upgrade. (Note electronics and custom equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1 Evaluate the PHENIX Rack Room at building 1008 to accommodate new electronics racks and components necessary to support the sPHENIX Experiment. 2. Design modifications or replacements, as required for the installation of equipment. 3. Procure the necessary equipment to upgrade the existing Rack Room. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of HVAC components and materials based on existing PHENIX rack room components which are similar to those needed for sPHENIX. The existing rack room equipment is mostly adequate for sPHENIX needs and will be repurposed for sPHENIX. Some rework of the existing system is anticipated as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of Rack Room equipment as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to new hardware components and equipment and modifications to existing hardware (repurposed from PHENIX R&R) as required to accomplish the tasks indicated in the "Dictionary Definition" section above. The labor and materials estimate for this work package can be found in this work book with the "Supporting Documents" link above.
estimate uncertainty
Estimates for the labor and material described in this work package are currently based on Engineering estimates and analyses of rack room concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in this work package. The overall material estimate uncertainty for this control account is determined by a weight averaged summation of the estimate uncertainties for the individual components. Labor estimate uncertainty for all labor is assumed at a constant 25%.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $20000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.07: Rack Room Modifications Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## BoE for Control Room
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-24
[7 empty] | Prepared By: | P. Giannotti
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  |  |  | Control Account
Control Room Work Package |  |  |  | 2.04.01.08 |  |  |  | TBD
Return to Navigation Sheet
WBS Dictionary Definition:
Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the specification and design of control room and office modifications required to support the sPHENIX upgrade. (Note custom control room and office equipment specifically designed for the subsytems is not part of this work package). (See the work packages associated with the individual subsystems, WBS 1.02 through 1.07 and WBS 2.02, 2.05, 3.01 and 3.02 for information on these specific items.) Work Statement: This work package includes the following tasks: 1 Evaluate the PHENIX control room and offices at building 1008 to update furniture, computers, and related equipmentand components necessary to support the sPHENIX Experiment. 2. Design modifications or replacements, as required for the installation of equipment. 3. Procure the necessary equipment to upgrade the existing control room and offices. 4. Deliver all components and equipment to sPHENIX complex at building 1008 for installation NOTE: - Installation of these components is not included here; that is part of WBS 2.05
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this Work Package)
Assumptions Used in Developing Estimate
Labor and material estimates are for analyses, design and procurement of control room and offices components and materials based on existing PHENIX control room and office components which are similar to those needed for sPHENIX. The existing control room and office equipment is mostly adequate for sPHENIX needs and will be repurposed for sPHENIX. Some rework/replacement/updating of the existing system is anticipated as reflected in the estimate.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of control room and offices equipment as indicated in the "Dictionary Definition" section above. 2. All labor for installation of these infrastructure components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to new components and equipment and modifications to existing equipment and furniture (repurposed from PHENIX R&R) as required to accomplish the tasks indicated in the "Dictionary Definition" section above. The labor and materials estimate for this work package can be found in this work book with the "Supporting Documents" link above.
estimate uncertainty
Estimates for the labor and material described in this work package are currently based on Engineering estimates and analyses of control room and offices concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in this work package. The overall material estimate uncertainty for this control account is determined by a weight averaged summation of the estimate uncertainties for the individual components. Labor estimate uncertainty for all labor is assumed at a constant 25%.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $50000
estimate uncertainty
Estimates for the labor and material described in this Work Package are currently based on Engineering estimates and analyses of infrastructure concepts based on evolving design of the individual subsystems. estimate uncertainty is assigned to each detail in the work package. The overall material estimate uncertainty for this work package is determined by a weight averaged summation ("bottoms up") of the estimate uncertainties for the individual labor tasks and material items. Labor estimate uncertainty for all labor is initially assumed at a constant 25%. As the work package's labor content becomes more well defined the individual labor estimate uncertainties for each task is reevaluated and the composite estimate uncertainty calculated as weight averaged in accordance with the total estimated (unburdened) labor cost for the task.
| Bottoms Up Composite Labor estimate uncertainty for WBS #2.04.01.08: Control Room Work Package |  |  |  | Labor estimate uncertainty: | 25%
[5 empty] | Material estimate uncertainty: | 40%

## Milestones
WBS Milestone # | WBS Milestone Title | Milestone Date | Notes/LINKS
S328200 | Design/Safety Reviews Complete, Line Electric Power Distribution Released for Production
S329300 | Line Electric Power Distribution Components Ready for Installation
S329800 | Design/Safety Reviews Complete, Detector Support Services Systems Components Released for Production
S330400 | Detector Support Services Systems Components Ready for Installation
S331000 | Design/Safety Reviews Complete, Detector Electronics Racks and Rack generic support systems Components Released for Production
S331600 | Detector Electronics Racks and Rack generic support systems Components Ready for Installation
S332100 | Design/Safety Reviews Complete, Detector Gas and Cooling services Systems Components Released for Production
S332700 | Detector Gas and Cooling services Systems Components Ready for Installation
S333200 | Design/Safety Reviews Complete, Detector Safety Subsystems Components Released for Production
S333800 | Detector Safety Subsystems Components Ready for Installation
S334300 | Design/Safety Reviews Complete, Gas Mixing House & Gas Pad Components Released for Production
S334900 | Gas Mixing House & Gas Pad Components Ready for Installation
S335400 | Design/Safety Reviews Complete, Rack Room Modifications Components Released for Production
S336000 | Rack Room Modifications Components Ready for Installation
S336500 | Design/Safety Reviews Complete, Control Room Components Released for Production
S337100 | Control Room components Ready for Installation
Return to Navigation Sheet

## Reviews by Work Package
WBS # | WBS Title (Work Package) | WBS Title (Review) | NOTES/LINKS
2.04.01.01 | Line Electric Power Distribution Work Package
S328000 |  | Review Line Electric Distribution Design/Safety
2.04.01.02 | Detector Support Services Systems Components Work Package
S329600 |  | Review Design Detector Support Services Systems Design/Safety
2.04.01.03 | Detector Electronics Racks and Rack generic support systems
S330800 |  | Review Detector Electronics Racks and Rack generic support systems Design/Safety
2.04.01.04 | Detector Gas and Cooling Services Systems
S331900 |  | Review Detector Gas and Cooling Services Systems Design/Safety
2.04.01.05 | Detector Safety Subsystems Work Package
S333000 |  | Review Detector Safety Subsystems Design/Safety
2.04.01.06 | Gas Mixing House & Gas Pad Components Work Package
S334100 |  | Review Gas Mixing House & Gas Pad Components Design/Safety
2.04.01.07 | Rack Room Modifications Work Package
S335200 |  | Review Rack Room Modifications Components Design/Safety
2.04.01.08 | Control Room Work Package
S336300 |  | Review Control Room Design/Safety
Return to Navigation Sheet

## Procurement $ by Work Package
Work Package WBS # | Work Package WBS Title | Work Package Procurements (Total) (includes purchased parts, Central Shops fabricated parts, contract labor. Does not include BNL labor other than Central Shops fabrication.) | NOTES/LINKS
2.04.01.01 | Line Electric Power Distribution Work Package | 50000
2.04.01.02 | Detector Support Services Systems Components Work Package | 32000
2.04.01.03 | Detector Electronics Racks and Rack generic support systems | 32000
2.04.01.04 | Detector Gas and Cooling Services Systems | 107000
2.04.01.05 | Detector Safety Subsystems Work Package | 12000
2.04.01.06 | Gas Mixing House & Gas Pad Components Work Package | 10000
2.04.01.07 | Rack Room Modifications Work Package | 20000
2.04.01.08 | Control Room Work Package | 50000
| Total for CA 2.04.02 | 313000 | Note: unburdened costs
Return to Navigation Sheet

## Det Sup Syst Control Account
Return to Navigation Page
WBS # (Activity ID) (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.04.01 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Detector Support Systems |  |  |  |  | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty | Control account 2.04.01 Bottoms Up Composite estimate uncertainty (%)
| Task |  |  | hrs | hrs | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
2.04.01 | Detector Support Systems | Technical Scope: WBS 2.04.01 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility support systems, safety systems and non-IR infrastructure including the following work packages: 1. Line Electric Power Distribution 2. Detector Support Services Systems Components 3. Detector Electronics Racks and Rack generic support systems 4. Detector Gas and Cooling Services Systems 5. Detector Safety Subsystems 6. Gas Mixing House & Gas Pad Components 7. Rack Room Modifications 8. Control Room and Offices Modifications Work Statement: The actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 and is covered in the sPHENIX 2.05.01 control account. There are 8 work packages included in this control account. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below). | [35 empty] | 313000 | [12 empty] | 0 | 28674 | 203385 | 132355.2 | 89210 | 0 | 0 | 453624.2 | 567030.25 | 430700 | 25% | 37.6%
2.04.01.01 | Line Electric Power Distribution Work Package | Technical Scope: This work package encompasses all scientific, engineering and technical staff efforts to plan and supervise all aspects of the sPHENIX line electrical requirements and distribution of line electricity to all subsystems. Electrical distribution within the subsystems and detector control, signal and monitoring electronics are outside of this scope. (see each subsystems work packages for such info) Work Statement: This work package includes the following tasks: 1. Evaluate the existing facility electric power distribution system at building 1008A to adequately supply sPHENIX Experimental Equipment. Perform a load flow and short circuit analysis starting from the 13.8KV/480V Substation 8A to the 480VAC Bus DP, through to the 208VAC Bus DPA and ending at the 208VAC distribution panels in the Intersection Region (IR). 2. Perform an ARC Flash calculation. 3. Modify the above system, as required, including but not limited to, transformers, circuit breakers, power quality instruments/equipment to facilitate remote monitoring & control, cables, and Transient Voltage Surge Suppression (TVSS). 4. Review the design 5. Procure equipment needed to implement this design. 6. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01) | [35 empty] | 50000 | [12 empty] | 0 | 0 | 22737.4 | 648.8 | 0 | 0 | 0 | 23386.2 | 29232.75 | 62500
S327400 | Evaluate Exiting Power Distribution System for Line Electric Power | Technical Scope: Evaluation of the existing power supplied to the PHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S327500 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power | Technical Scope: Evaluation of the specific requirements for sPHENIX detector subsystems line electric power. Work Statement: Gather all relevant information from subsystems. | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2086 | 0 | 0 | 0 | 0 | 2086 | 2607.5 | 0
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | Technical Scope: Evaluation of the normal, emergency and UPS loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 5 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1043 | 0 | 0 | 0 | 0 | 1043 | 1303.75 | 0
S327700 | Calculate Power Transformer Requirements for Line Electric Power | Technical Scope: Evaluation of the Power Transformer loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 0 | 0 | 0 | 1668.8 | 2086 | 0
S327800 | Size Conductors for Line Electric Power | Technical Scope: Evaluation of the Line Electric Power conductors feeding the sPHENIX detector subsystems in the 1008 IR. Work Statement: Calculate the optimum size of conductors.. | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power | Technical Scope: Design schematic drawings for the Line Electric Power Distribution System in the 1008 IR. Work Statement: Create appropriate One-line drawings to reflect the sPHENIX desired configuration. | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S328000 | Review Line Electric Distribution Design/Safety | Technical Scope: Review the Line Electric Power Distribution System for sPHENIX detector subsystems in the 1008 IR. Work Statement: Prepare documents and presentations as appropriate for review by CAD electrical engineering. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | Technical Scope: Evaluation of the action items from Safety Reviews for the Line Electric Power Distribution System. 1008 IR. Work Statement: Appropriately address all action items from review. | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S328200 | Design/Safety Reviews Complete, Line Electric Power Distribution Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | Technical Scope: Develop the procurement packages for components in the Line Electric Distribution System. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 6258 | 0 | 0 | 0 | 0 | 6258 | 7822.5 | 0
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | Technical Scope: Evaluation of the Line Electric Power Distribution components Bid documents. Work Statement: Prepare bid documents for line electrical power components, Initiate procure,ent of components. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 0 | 0 | 0 | 2503.2 | 3129 | 0
S328500 /S328600 /S328700 /S328800 /S328900 /S329000 /S329100 | Procure & Deliver Line Electric Power Distribution Components (leadtime and fabrication included) | Technical Scope: Procurement and delivery of Line Electric Power Distribution components. Work Statement: Monitor and manage procurement process for line electric components. | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 0 | 0 | 0 | 0 | 5006.4 | 6258 | 62500
S329200 | Perform Line Electric Power Distribution Components Acceptance | Technical Scope: Performance of Acceptance Tests for the Line Electric Power Distribution System. Work Statement: receive, inspect and accept line electric components. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S329300 | Line Electric Power Distribution Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.02 | Detector Support Services Systems Components Work Package | [36 empty] | 32000 | [12 empty] | 0 | 3888 | 17105.2 | 12651.6 | 4217.2 | 0 | 0 | 37862 | 47327.5 | 44800
S329400 | Analyze Design Detector Support Services Systems Requirements | Technical Scope: Analyze Design Detector Support Services Systems Requirements Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 | 0 | 32 | 0 | 40 | 0 | 0 | 40 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 40 | 32 | 32 | 0 | 0 | 0 | 3888 | 4172 | 2595.2 | 2595.2 | 0 | 0 | 13250.4 | 16563 | 0
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems. Work Statement: Make appropriate detail drawings for Design Detector Support Services. | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 2595.2 | 0 | 0 | 0 | 5932.8 | 7416 | 0
S329600 | Review Design Detector Support Services Systems Design/Safety | Technical Scope:Review Design Detector Support Services Systems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Support Services Systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S329800 | Design/Safety Reviews Complete, Detector Support Services Systems Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) | Technical Scope: Prepare Detector Support Services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S330000 | Evaluate & Process Detector Support Services Systems Components Bids | Technical Scope: Evaluate & Process Detector Support Services Systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S330100 /S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 50 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | Mostly reuse existing PHENIX support services systems. Expect about $4000 per subsystem new components =8 x $4000 . (cable trays, stands, piping, hardware etc, very prelimineary so use 40% estimate uncertainty on material. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 4172 | 3244 | 0 | 0 | 0 | 7416 | 9270 | 44800
S330300 | Perform Detector Support Services Systems Components Acceptance | Technical Scope: Perform Detector Support Services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 4 | 4 | 20 | 0 | 0 | 0 | 0 | 417.2 | 324.4 | 1622 | 0 | 0 | 2363.6 | 2954.5 | 0
S330400 | Detector Support Services Systems Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.03 | Detector Electronics Racks and Rack generic support systems | [36 empty] | 32000 | [12 empty] | 0 | 0 | 33376 | 43469.6 | 3244 | 0 | 0 | 80089.6 | 100112 | 44800
S330600 /S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements | Technical Scope : Analyze Detector Electronics Racks and Rack generic support systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems. Work Statement: Make appropriate detail drawings for Detector Electronics Racks. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 96 | 24 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 96 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 7785.6 | 0 | 0 | 0 | 12792 | 15990 | 0
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety | Technical Scope: Review Detector Electronics Racks and Rack generic support systems Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 32 | 8 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2595.2 | 0 | 0 | 0 | 4264 | 5330 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 32 | 8 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2595.2 | 0 | 0 | 0 | 4264 | 5330 | 0
S331000 | Design/Safety Reviews Complete, Detector Electronics Racks and Rack generic support systems Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | Technical Scope:Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 16 | 16 | 72 | 24 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 72 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 5839.2 | 0 | 0 | 0 | 9176.8 | 11471 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | Technical Scope: Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 60 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 48 | 48 | 144 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 144 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 11678.4 | 0 | 0 | 0 | 21691.2 | 27114 | 0
S331300 | Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 48 | 48 | 144 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | Mostly reuse existing PHENIX racks with internal hardware. Expect about $1000 per rack new components. Expect about 32 racks in IR (4 for Outer HCal, 4 for Inner HCal, 12 for EMCal, 2 each for TPC, MVTX, INTT and Min Bias and 4 additional general purpose) Reuse of existing racks and buckets and heat exchanges saves approx. $8500/rack ($1800 for rack, $3000 for heat exchangers, $1000 for bucket, $600 for fans, $1000 for fittings and hardware, $500 for smoke detector, $600 for leak detector) =$272,000 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 144 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 11678.4 | 0 | 0 | 0 | 21691.2 | 27114 | 44800
S331400 /S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | Technical Scope:Perform Detector Electronics Racks and Rack generic support systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 3244 | 0 | 0 | 6210.4 | 7763 | 0
S331600 | Detector Electronics Racks and Rack generic support systems Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.04 | Detector Gas and Cooling Services Systems | [36 empty] | 107000 | [12 empty] | 0 | 11664 | 56322 | 30818 | 13624.8 | 0 | 0 | 112428.8 | 140536 | 149800
S331700 | Analyze Detector Gas and Cooling Services Systems Requirements | Technical Scope: Analyze Detector Gas and Cooling Services Systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 120 | 0 | 96 | 0 | 96 | 0 | 240 | 0 | 0 | 240 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 96 | 240 | 96 | 96 | 0 | 0 | 0 | 11664 | 25032 | 7785.6 | 7785.6 | 0 | 0 | 52267.2 | 65334 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems | Technical Scope : Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems. Work Statement: Make appropriate detail drawings for Detector Gas and Cooling Systems. | 60 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 96 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 48 | 48 | 0 | 0 | 0 | 0 | 10012.8 | 3892.8 | 3892.8 | 0 | 0 | 17798.4 | 22248 | 0
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety | Technical Scope : Review Detector Gas and Cooling Services Systems Design/Safety citeria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 20 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 1622 | 648.8 | 0 | 0 | 3939.6 | 4924.5 | 0
S332000 | Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews | Technical Scope : Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 8 | 8 | 0 | 0 | 0 | 0 | 2086 | 648.8 | 648.8 | 0 | 0 | 3383.6 | 4229.5 | 0
S332100 | Design/Safety Reviews Complete, Detector Gas and Cooling services Systems Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S332200 | Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) | Technical Scope : Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 90 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 72 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 5839.2 | 0 | 0 | 0 | 9176.8 | 11471 | 0
S332300 | Evaluate & Process Detector Gas and Cooling Services Systems Components Bids | Technical Scope : Evaluate & Process Detector Gas and Cooling Services Systems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 0 | 0 | 0 | 4449.6 | 5562 | 0
S332400 /S332500 | Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) | Technical Scope : Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 120 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 96 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107000 | 25% | 40% | Outer HCal needs nothing, Iner HCal needs forced air, about $3000, TPC Needs liquid cooling and gas and laser, cooling ~$30,000, gas ~$8000, Laser, ~$2000 (use existing laser), INTT and MTX need cooling $30000 each and N2 $2000 each, Min Bias needs N2 $2000 Total = $107000, (Note some costs to be borne by subsystems. This to be ironed out by integration negotiations. May reduce this number) | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 7785.6 | 0 | 0 | 0 | 17798.4 | 22248 | 149800
S332600 | Perform Detector Gas and Cooling services Systems Components Acceptance | Technical Scope : Perform Detector Gas and Cooling services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 20 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 648.8 | 0 | 0 | 3615.2 | 4519 | 0
S332700 | Detector Gas and Cooling services Systems Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.05 | Detector Safety Subsystems Work Package | [36 empty] | 12000 | [12 empty] | 0 | 2916 | 22528.8 | 12002.8 | 4541.6 | 0 | 0 | 41989.2 | 52486.5 | 16800
S332800 | Analyze Detector Safety Subsystems Requirements | Technical Scope: Analyze On Detector/Carriage Safety Subsystems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 24 | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 24 | 48 | 24 | 48 | 0 | 0 | 0 | 2916 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 13761.6 | 17202 | 0
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for On-Detector/Carriage Safety Subsystems. Work Statement: Make appropriate detail drawings for On Detector/Carriage Safety Subsystems. | 30 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S333000 | Review Detector Safety Subsystems Design/Safety | Technical Scope: Review On Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from On Detector/Carriage Safety Subsystems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S333200 | Design/Safety Reviews Complete, Detector Safety Subsystems Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare On Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | Technical Scope:Evaluate & Process On Detector/Carriage Safety Subsystems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 0 | 0 | 0 | 4449.6 | 5562 | 0
S333500 /S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver On Detector/Carriage Safety Subsystems Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 25% | 40% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $12K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 3892.8 | 0 | 0 | 0 | 8899.2 | 11124 | 16800
S333700 | Perform Detector Safety Subsystems Components Acceptance | Technical Scope: Perform On Detector/Carriage Safety Subsystems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 648.8 | 0 | 0 | 1807.6 | 2259.5 | 0
S333800 | Detector Safety Subsystems Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.06 | Gas Mixing House & Gas Pad Components Work Package | [36 empty] | 10000 | [12 empty] | 0 | 0 | 23780.4 | 18490.8 | 28547.2 | 0 | 0 | 70818.4 | 88523 | 14000
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements | Technical Scope: Analyze Gas Mixing House & Gas Pad Components Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 24 | 48 | 0 | 0 | 0 | 0 | 6258 | 1946.4 | 3892.8 | 0 | 0 | 12097.2 | 15121.5 | 0
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents | Technical Scope: Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Gas Mixing House & Gas Pad. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 60 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 4866 | 3892.8 | 0 | 0 | 11262 | 14077.5 | 0
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety | Technical Scope: Review Gas Mixing House & Gas Pad Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | Technical Scope :Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S334300 | Design/Safety Reviews Complete, Gas Mixing House & Gas Pad Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) | Technical Scope:Prepare Gas Mixing House & Gas Pad Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 3892.8 | 0 | 0 | 8342.4 | 10428 | 0
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids | Technical Scope: Evaluate & Process Gas Mixing House & Gas Pad Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 3892.8 | 0 | 0 | 8342.4 | 10428 | 0
S334600 /S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 90 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 72 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 144 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% | No modifications identified yet. Subsystems to bear costs of gas monitoring and distribution racks, additional supporting infrastucture not yet identified not expected to exceed $10K | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 72 | 72 | 144 | 0 | 0 | 0 | 0 | 7509.6 | 5839.2 | 11678.4 | 0 | 0 | 25027.2 | 31284 | 14000
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance | Technical Scope: Perform Gas Mixing House & Gas Pad Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S334900 | Gas Mixing House & Gas Pad Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.07 | Rack Room Modifications Work Package | [36 empty] | 20000 | [12 empty] | 0 | 6804 | 18356.8 | 7461.2 | 22059.2 | 0 | 0 | 54681.2 | 68351.5 | 28000
S335000 | Analyze Rack Room Modifications Requirements | Technical Scope : Analyze Rack Room Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 0 | 0 | 32 | 32 | 0 | 32 | 0 | 0 | 0 | 0 | 64 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 32 | 32 | 64 | 0 | 0 | 0 | 3888 | 3337.6 | 2595.2 | 5190.4 | 0 | 0 | 15011.2 | 18764 | 0
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Rack Room Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Rack Room modifications. | 40 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | Technical Scope: Review Rack Room Modifications Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 972 | 834.4 | 0 | 0 | 0 | 0 | 1806.4 | 2258 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | Technical Scope:Address Action Items from Rack Room Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 16 | 16 | 0 | 0 | 0 | 972 | 834.4 | 1297.6 | 1297.6 | 0 | 0 | 4401.6 | 5502 | 0
S335400 | Design/Safety Reviews Complete, Rack Room Modifications Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) | Technical Scope: Prepare Rack Room Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 3892.8 | 0 | 0 | 6396 | 7995 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | Technical Scope: Evaluate & Process Rack Room Modifications Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 32 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 2595.2 | 0 | 0 | 4912.8 | 6141 | 0
S335700 /S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 96 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 25% | 40% | Most rack room equipment will be repurposed from PHENIX R&R. $20K seems like a good amount to cover any modifications or small additions needed. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 48 | 24 | 96 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 7785.6 | 0 | 0 | 14738.4 | 18423 | 28000
S335900 | Perform Rack Room Modifications Components Acceptance | Technical Scope: Perform Rack Room Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 4 | 16 | 0 | 0 | 0 | 972 | 834.4 | 324.4 | 1297.6 | 0 | 0 | 3428.4 | 4285.5 | 0
S336000 | Rack Room Modifications Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.04.01.08 | Control Room Work Package | [36 empty] | 50000 | [12 empty] | 0 | 3402 | 9178.4 | 6812.4 | 12976 | 0 | 0 | 32368.8 | 40461 | 70000
S336100 | Analyze Control Room Requirements | Technical Scope: Analyze Control Room and Offices Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 8 | 16 | 0 | 0 | 0 | 972 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 3752.8 | 4691 | 0
S336200 | Create Control Room Schematic Design and Specification Control Documents | Technical Scope :Create Control Room and Offices Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Control Room and Offices modifications. | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 417.2 | 648.8 | 0 | 0 | 0 | 1066 | 1332.5 | 0
S336300 | Review Control Room Design/Safety | Technical Scope: Review Control Room and Offices Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 486 | 417.2 | 0 | 0 | 0 | 0 | 903.2 | 1129 | 0
S336400 | Address Action Items from Control Room Design & Safety Reviews | Technical Scope:Address Action Items from Control Room and Offices Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 8 | 16 | 0 | 0 | 0 | 972 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 3752.8 | 4691 | 0
S336500 | Design/Safety Reviews Complete, Control Room Components Released for Production | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S336600 | Prepare Control Room Components Procurement Package(s) | Technical Scope: Prepare Control Room and Offices Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 3892.8 | 0 | 0 | 6396 | 7995 | 0
S336700 | Evaluate & Process Control Room Components Bids | Technical Scope:Evaluate & Process Control Room and Offices Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S336800 /S336900 | Procure & Deliver Control Room Components (leadtime and fabrication included) | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 30 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50000 | 25% | 40% | Most control room and office equipment will be to0 old to be repurposed from PHENIX R&R. $50K seems like a good amount to cover any new computers and monitors and needed furniture upgrades. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 24 | 48 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 3892.8 | 3892.8 | 0 | 0 | 10288.8 | 12861 | 70000
S337000 | Perform Control Room Components Acceptance | Technical Scope: Perform Control Room and Offices Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% | 0 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 4 | 16 | 0 | 0 | 0 | 972 | 834.4 | 324.4 | 1297.6 | 0 | 0 | 3428.4 | 4285.5 | 0
S337100 | Control Room components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Administrator ADMIN1 PO | Scientist | Scientist (hours) |  |  | Engineer | Engineer/Professional (hours) |  |  |  | Designer | Designer/Drafter (hours) | [5 empty] | Technician | Technicians (hours) | [8 empty] | Trade | Bargaining Unit Trades (hours) |  |  |  |  | Student (unpaid)
[6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3
|  |  |  | hours | hours | Scientist | Scientist | Scientist | hours |  |  |  |  | hours | [6 empty] | hours | [9 empty] | hours | [5 empty] | hours
|  | Resource Summary for Facility Support Systems, Safety Systems and Non-IR Infrastructure in Hours by Resource Type |  | 0 | 236 | 0 | 236 | 0 | 1950 | 0 | 0 | 1092 | 858 | 1632 | 1000 | 424 | 0 | 208 | 0 | 0 | 51140 | 680 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Checksum for hours | 5186

## Line Electric Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.01 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Line Electric Power Distribution Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S327400 | Evaluate Exiting Power Distribution System for Line Electric Power | Technical Scope: Evaluation of the existing power supplied to the PHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 20 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S327500 | Gather Design Requirements for All sPHENIX Subsystems for Line Electric Power | Technical Scope: Evaluation of the specific requirements for sPHENIX detector subsystems line electric power. Work Statement: Gather all relevant information from subsystems. | 10 | 0 | 0 |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2086 | 0 | 0 | 0 | 0 | 2086 | 2607.5 | 0
S327600 | Evaluate Normal, Emergency and UPS Load Requirements for Line Electric Power | Technical Scope: Evaluation of the normal, emergency and UPS loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 5 | 0 | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1043 | 0 | 0 | 0 | 0 | 1043 | 1303.75 | 0
S327700 | Calculate Power Transformer Requirements for Line Electric Power | Technical Scope: Evaluation of the Power Transformer loads for sPHENIX detector subsystems in the 1008 IR. Work Statement: Gather all relevant information from existing PHENIX documentation. | 8 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 0 | 0 | 0 | 0 | 1668.8 | 2086 | 0
S327800 | Size Conductors for Line Electric Power | Technical Scope: Evaluation of the Line Electric Power conductors feeding the sPHENIX detector subsystems in the 1008 IR. Work Statement: Calculate the optimum size of conductors.. | 4 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S327900 | Create Line Electric Distribution Design/Schematic Drawings for Line Electric Power | Technical Scope: Design schematic drawings for the Line Electric Power Distribution System in the 1008 IR. Work Statement: Create appropriate One-line drawings to reflect the sPHENIX desired configuration. | 4 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S328000 | Review Line Electric Distribution Design/Safety | Technical Scope: Review the Line Electric Power Distribution System for sPHENIX detector subsystems in the 1008 IR. Work Statement: Prepare documents and presentations as appropriate for review by CAD electrical engineering. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S328100 | Address Action Items from Line Electric Distribution Design & Safety Reviews | Technical Scope: Evaluation of the action items from Safety Reviews for the Line Electric Power Distribution System. 1008 IR. Work Statement: Appropriately address all action items from review. | 5 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S328200 | Design/Safety Reviews Complete, Line Electric Power Distribution Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S328550 | Prepare Line Electric Power Distribution Components Procurement Package(s) | Technical Scope: Develop the procurement packages for components in the Line Electric Distribution System. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 6258 | 0 | 0 | 0 | 0 | 6258 | 7822.5 | 0
S328850 | Evaluate & Process Line Electric Power Distribution Components Bid | Technical Scope: Evaluation of the Line Electric Power Distribution components Bid documents. Work Statement: Prepare bid documents for line electrical power components, Initiate procure,ent of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 0 | 0 | 0 | 2503.2 | 3129 | 0
S328500 /S328600 /S328700 /S328800 /S328900 /S329000 /S329100 | Procure & Deliver Line Electric Power Distribution Components (leadtime and fabrication included) | Technical Scope: Procurement and delivery of Line Electric Power Distribution components. Work Statement: Monitor and manage procurement process for line electric components. | 60 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 25% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly predictable based on similar previous projects. 25% estimate uncertainty is reasonable./M4 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 0 | 0 | 0 | 0 | 5006.4 | 6258 | 62500
S329200 | Perform Line Electric Power Distribution Components Acceptance | Technical Scope: Performance of Acceptance Tests for the Line Electric Power Distribution System. Work Statement: receive, inspect and accept line electric components. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 834.4 | 0 | 0 | 0 | 0 | 834.4 | 1043 | 0
S329300 | Line Electric Power Distribution Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details
[44 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 23386.2 | 29232.75 | 62500 | 50000 | 25% | 25%
[45 empty] | 0 | 0 | 218 | 8 | 0 | 0 | 0 | 0 | 0 | 22737.4 | 648.8 | 0 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Services Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.02 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Detector Support Services Systems Components Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S329400 | Analyze Design Detector Support Services Systems Requirements | Technical Scope: Analyze Design Detector Support Services Systems Requirements Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 |  | 0 | 32 | 0 | 40 | 0 | 0 | 40 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 40 | 32 | 32 | 0 | 0 | 0 | 3888 | 4172 | 2595.2 | 2595.2 | 0 | 0 | 13250.4 | 16563 | 0
S329500 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Design Detector Support Services Systems. Work Statement: Make appropriate detail drawings for Design Detector Support Services. | 40 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 2595.2 | 0 | 0 | 0 | 5932.8 | 7416 | 0
S329600 | Review Design Detector Support Services Systems Design/Safety | Technical Scope:Review Design Detector Support Services Systems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S329700 | Address Action Items from Detector Support Services Systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Support Services Systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S329800 | Design/Safety Reviews Complete, Detector Support Services Systems Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S329900 | Prepare Detector Support Services Systems Components Procurement Package(s) | Technical Scope: Prepare Detector Support Services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 20 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S330000 | Evaluate & Process Detector Support Services Systems Components Bids | Technical Scope: Evaluate & Process Detector Support Services Systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 0 | 0 | 0 | 2966.4 | 3708 | 0
S330100 /S330200 | Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Support Services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 50 | 0 | 0 |  | 0 | 0 | 0 | 40 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | Mostly reuse existing PHENIX support services systems. Expect about $4000 per subsystem new components =8 x $4000 . (cable trays, stands, piping, hardware etc, very prelimineary so use 40% estimate uncertainty on material. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 4172 | 3244 | 0 | 0 | 0 | 7416 | 9270 | 44800
S330300 | Perform Detector Support Services Systems Components Acceptance | Technical Scope: Perform Detector Support Services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 5 | 0 | 0 |  | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 4 | 4 | 20 | 0 | 0 | 0 | 0 | 417.2 | 324.4 | 1622 | 0 | 0 | 2363.6 | 2954.5 | 0
S330400 | Detector Support Services Systems Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 37862 | 47327.5 | 44800 | 32000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 32 | 164 | 156 | 52 | 0 | 0 | 0 | 3888 | 17105.2 | 12651.6 | 4217.2 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Racks Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.03 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Detector Electronics Racks and Rack generic support systems | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S330600 /S330600 | Analyze Detector Electronics Racks and Rack generic support systems Requirements | Technical Scope : Analyze Detector Electronics Racks and Rack generic support systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S330700 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems | Technical Scope: Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Electronics Racks and Rack generic support systems. Work Statement: Make appropriate detail drawings for Detector Electronics Racks. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 24 | 24 | 96 | 24 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 96 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 7785.6 | 0 | 0 | 0 | 12792 | 15990 | 0
S330800 | Review Detector Electronics Racks and Rack generic support systems Design/Safety | Technical Scope: Review Detector Electronics Racks and Rack generic support systems Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 32 | 8 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2595.2 | 0 | 0 | 0 | 4264 | 5330 | 0
S330900 | Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews | Technical Scope: Address Action Items from Detector Electronics Racks and Rack generic support systems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 32 | 8 | 8 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 32 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 2595.2 | 0 | 0 | 0 | 4264 | 5330 | 0
S331000 | Design/Safety Reviews Complete, Detector Electronics Racks and Rack generic support systems Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S331100 | Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) | Technical Scope:Prepare Detector Electronics Racks and Rack generic support systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 16 | 16 | 72 | 24 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 72 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 5839.2 | 0 | 0 | 0 | 9176.8 | 11471 | 0
S331200 | Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids | Technical Scope: Evaluate & Process Detector Electronics Racks and Rack generic support systems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 60 | 0 | 0 |  | 0 | 0 | 0 | 96 | 0 | 0 | 48 | 48 | 144 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 144 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 11678.4 | 0 | 0 | 0 | 21691.2 | 27114 | 0
S331300 | Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Detector Electronics Racks and Rack generic support systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 |  | 0 | 0 | 0 | 96 | 0 | 0 | 48 | 48 | 144 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32000 | 25% | 40% | Mostly reuse existing PHENIX racks with internal hardware. Expect about $1000 per rack new components. Expect about 32 racks in IR (4 for Outer HCal, 4 for Inner HCal, 12 for EMCal, 2 each for TPC, MVTX, INTT and Min Bias and 4 additional general purpose) Reuse of existing racks and buckets and heat exchanges saves approx. $8500/rack ($1800 for rack, $3000 for heat exchangers, $1000 for bucket, $600 for fans, $1000 for fittings and hardware, $500 for smoke detector, $600 for leak detector) =$272,000 | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 144 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 11678.4 | 0 | 0 | 0 | 21691.2 | 27114 | 44800
S331400 /S331500 | Perform Detector Electronics Racks and Rack generic support systems Components Acceptance | Technical Scope:Perform Detector Electronics Racks and Rack generic support systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 8 | 8 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 40 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 3244 | 0 | 0 | 6210.4 | 7763 | 0
S331600 | Detector Electronics Racks and Rack generic support systems Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 80089.6 | 100112 | 44800 | 32000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 0 | 320 | 536 | 40 | 0 | 0 | 0 | 0 | 33376 | 43469.6 | 3244 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Gas & Cooling Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.04 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Detector Gas and Cooling Services Systems | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S331700 | Analyze Detector Gas and Cooling Services Systems Requirements | Technical Scope: Analyze Detector Gas and Cooling Services Systems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 120 | 0 | 96 |  | 0 | 96 | 0 | 240 | 0 | 0 | 240 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 96 | 240 | 96 | 96 | 0 | 0 | 0 | 11664 | 25032 | 7785.6 | 7785.6 | 0 | 0 | 52267.2 | 65334 | 0
S331800 | Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems | Technical Scope : Create Layout/Schematic Drawings & Design, Specification Control Documents, Assembly & Detail Drawings for Detector Gas and Cooling Services Systems. Work Statement: Make appropriate detail drawings for Detector Gas and Cooling Systems. | 60 | 0 | 0 |  | 0 | 0 | 0 | 96 | 0 | 0 | 96 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 96 | 48 | 48 | 0 | 0 | 0 | 0 | 10012.8 | 3892.8 | 3892.8 | 0 | 0 | 17798.4 | 22248 | 0
S331900 | Review Detector Gas and Cooling Services Systems Design/Safety | Technical Scope : Review Detector Gas and Cooling Services Systems Design/Safety citeria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 20 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 1622 | 648.8 | 0 | 0 | 3939.6 | 4924.5 | 0
S332000 | Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews | Technical Scope : Address Action Items from Detector Gas and Cooling services Systems Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 20 | 0 | 0 | 20 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 20 | 8 | 8 | 0 | 0 | 0 | 0 | 2086 | 648.8 | 648.8 | 0 | 0 | 3383.6 | 4229.5 | 0
S332100 | Design/Safety Reviews Complete, Detector Gas and Cooling services Systems Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S332200 | Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) | Technical Scope : Prepare Detector Gas and Cooling services Systems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 90 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 32 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 72 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 5839.2 | 0 | 0 | 0 | 9176.8 | 11471 | 0
S332300 | Evaluate & Process Detector Gas and Cooling Services Systems Components Bids | Technical Scope : Evaluate & Process Detector Gas and Cooling Services Systems Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 0 | 0 | 0 | 4449.6 | 5562 | 0
S332400 /S332500 | Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) | Technical Scope : Procure & Deliver Detector Gas and Cooling services Systems Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 120 | 0 | 0 |  | 0 | 0 | 0 | 96 | 0 | 0 | 96 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107000 | 25% | 40% | Outer HCal needs nothing, Iner HCal needs forced air, about $3000, TPC Needs liquid cooling and gas and laser, cooling ~$30,000, gas ~$8000, Laser, ~$2000 (use existing laser), INTT and MTX need cooling $30000 each and N2 $2000 each, Min Bias needs N2 $2000 Total = $107000, (Note some costs to be borne by subsystems. This to be ironed out by integration negotiations. May reduce this number) | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 10012.8 | 7785.6 | 0 | 0 | 0 | 17798.4 | 22248 | 149800
S332600 | Perform Detector Gas and Cooling services Systems Components Acceptance | Technical Scope : Perform Detector Gas and Cooling services Systems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 20 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 16 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 1297.6 | 648.8 | 0 | 0 | 3615.2 | 4519 | 0
S332700 | Detector Gas and Cooling services Systems Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 112428.8 | 140536 | 149800 | 107000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 96 | 540 | 380 | 168 | 0 | 0 | 0 | 11664 | 56322 | 30818 | 13624.8 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Detector Safety Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.05 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Detector Safety Subsystems Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S332800 | Analyze Detector Safety Subsystems Requirements | Technical Scope: Analyze On Detector/Carriage Safety Subsystems Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 24 |  | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 24 | 48 | 24 | 48 | 0 | 0 | 0 | 2916 | 5006.4 | 1946.4 | 3892.8 | 0 | 0 | 13761.6 | 17202 | 0
S332900 | Create Schematic Design and Specification Control Documents for Detector Safety Subsystems | Technical Scope: Create Schematic Design and Specification Control Documents for On-Detector/Carriage Safety Subsystems. Work Statement: Make appropriate detail drawings for On Detector/Carriage Safety Subsystems. | 30 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 48 | 24 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 0 | 0 | 0 | 6952.8 | 8691 | 0
S333000 | Review Detector Safety Subsystems Design/Safety | Technical Scope: Review On Detector/Carriage Safety Subsystems Design/Safety Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S333100 | Address Action Items from Detector Safety Subsystems Design & Safety Reviews | Technical Scope: Address Action Items from On Detector/Carriage Safety Subsystems Design & Safety Reviews Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 0 | 0 | 0 | 2317.6 | 2897 | 0
S333200 | Design/Safety Reviews Complete, Detector Safety Subsystems Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S333300 | Prepare Detector Safety Subsystems Components Procurement Package(s) | Technical Scope: Prepare On Detector/Carriage Safety Subsystems Components Procurement Package(s) Work Statement: Prepare bid documents and initiate procurement of components. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S333400 | Evaluate & Process Detector Safety Subsystems Components Bids | Technical Scope:Evaluate & Process On Detector/Carriage Safety Subsystems Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 0 | 0 | 0 | 4449.6 | 5562 | 0
S333500 /S333600 | Procure & Deliver Detector Safety Subsystems Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver On Detector/Carriage Safety Subsystems Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 25% | 40% | Too early in design phase for a detailed cost analysis, but based on similar requirements in PHENIX and assuming repurposing of much of the equipment, $12K seems reasonable | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 3892.8 | 0 | 0 | 0 | 8899.2 | 11124 | 16800
S333700 | Perform Detector Safety Subsystems Components Acceptance | Technical Scope: Perform On Detector/Carriage Safety Subsystems Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 4 | 8 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 648.8 | 0 | 0 | 1807.6 | 2259.5 | 0
S333800 | Detector Safety Subsystems Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 41989.2 | 52486.5 | 16800 | 12000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 24 | 216 | 148 | 56 | 0 | 0 | 0 | 2916 | 22528.8 | 12002.8 | 4541.6 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## GMH & Gas Pad Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.06 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Gas Mixing House & Gas Pad Components Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S333900 | Analyze Gas Mixing House & Gas Pad Components Requirements | Technical Scope: Analyze Gas Mixing House & Gas Pad Components Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 30 | 0 | 0 |  | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 60 | 24 | 48 | 0 | 0 | 0 | 0 | 6258 | 1946.4 | 3892.8 | 0 | 0 | 12097.2 | 15121.5 | 0
S334000 | Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents | Technical Scope: Create Gas Mixing House & Gas Pad Components Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Gas Mixing House & Gas Pad. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 60 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 4866 | 3892.8 | 0 | 0 | 11262 | 14077.5 | 0
S334100 | Review Gas Mixing House & Gas Pad Components Design/Safety | Technical Scope: Review Gas Mixing House & Gas Pad Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S334200 | Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews | Technical Scope :Address Action Items from Gas Mixing House & Gas Pad Components Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 0 | 0 | 0 | 1483.2 | 1854 | 0
S334300 | Design/Safety Reviews Complete, Gas Mixing House & Gas Pad Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S334400 | Prepare Gas Mixing House & Gas Pad Components Procurement Package(s) | Technical Scope:Prepare Gas Mixing House & Gas Pad Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 3892.8 | 0 | 0 | 8342.4 | 10428 | 0
S334500 | Evaluate & Process Gas Mixing House & Gas Pad Components Bids | Technical Scope: Evaluate & Process Gas Mixing House & Gas Pad Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 24 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 1946.4 | 3892.8 | 0 | 0 | 8342.4 | 10428 | 0
S334600 /S334700 | Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Gas Mixing House & Gas Pad Components (leadtime and fabrication included) Work Statement: Track and manage the procurement of all components for this item. | 90 | 0 | 0 |  | 0 | 0 | 0 | 72 | 0 | 0 | 72 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 144 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 25% | 40% | No modifications identified yet. Subsystems to bear costs of gas monitoring and distribution racks, additional supporting infrastucture not yet identified not expected to exceed $10K | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 72 | 72 | 144 | 0 | 0 | 0 | 0 | 7509.6 | 5839.2 | 11678.4 | 0 | 0 | 25027.2 | 31284 | 14000
S334800 | Perform Gas Mixing House & Gas Pad Components Acceptance | Technical Scope: Perform Gas Mixing House & Gas Pad Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S334900 | Gas Mixing House & Gas Pad Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 70818.4 | 88523 | 14000 | 10000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 0 | 228 | 228 | 352 | 0 | 0 | 0 | 0 | 23780.4 | 18490.8 | 28547.2 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Rack Room Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.07 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Rack Room Modifications Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S335000 | Analyze Rack Room Modifications Requirements | Technical Scope : Analyze Rack Room Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 40 | 0 | 32 |  | 0 | 32 | 0 | 32 | 0 | 0 | 0 | 32 | 32 | 0 | 32 | 0 | 0 | 0 | 0 | 64 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 32 | 32 | 32 | 64 | 0 | 0 | 0 | 3888 | 3337.6 | 2595.2 | 5190.4 | 0 | 0 | 15011.2 | 18764 | 0
S335100 | Create Rack Room Modifications Schematic Design and Specification Control Documents | Technical Scope: Create Rack Room Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Rack Room modifications. | 40 | 0 | 0 |  | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 32 | 8 | 0 | 0 | 0 | 0 | 0 | 3337.6 | 648.8 | 0 | 0 | 0 | 3986.4 | 4983 | 0
S335200 | Review Rack Room Modifications Components Design/Safety | Technical Scope: Review Rack Room Modifications Components Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 972 | 834.4 | 0 | 0 | 0 | 0 | 1806.4 | 2258 | 0
S335300 | Address Action Items from Rack Room Modifications Design & Safety Reviews | Technical Scope:Address Action Items from Rack Room Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 16 | 16 | 0 | 0 | 0 | 972 | 834.4 | 1297.6 | 1297.6 | 0 | 0 | 4401.6 | 5502 | 0
S335400 | Design/Safety Reviews Complete, Rack Room Modifications Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S335500 | Prepare Rack Room Modifications Components Procurement Package(s) | Technical Scope: Prepare Rack Room Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 3892.8 | 0 | 0 | 6396 | 7995 | 0
S335600 | Evaluate & Process Rack Room Modifications Components Bids | Technical Scope: Evaluate & Process Rack Room Modifications Components Bids. Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 20 | 0 | 0 |  | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 16 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 16 | 8 | 32 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 2595.2 | 0 | 0 | 4912.8 | 6141 | 0
S335700 /S335800 | Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included) | Technical Scope: Procure & Deliver Rack Room Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 60 | 0 | 0 |  | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 48 | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 96 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 25% | 40% | Most rack room equipment will be repurposed from PHENIX R&R. $20K seems like a good amount to cover any modifications or small additions needed. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 48 | 24 | 96 | 0 | 0 | 0 | 0 | 5006.4 | 1946.4 | 7785.6 | 0 | 0 | 14738.4 | 18423 | 28000
S335900 | Perform Rack Room Modifications Components Acceptance | Technical Scope: Perform Rack Room Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 4 | 16 | 0 | 0 | 0 | 972 | 834.4 | 324.4 | 1297.6 | 0 | 0 | 3428.4 | 4285.5 | 0
S336000 | Rack Room Modifications Components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 54681.2 | 68351.5 | 28000 | 20000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 56 | 176 | 92 | 272 | 0 | 0 | 0 | 6804 | 18356.8 | 7461.2 | 22059.2 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Control Room Work Package
Return to Navigation Page
WBS # (Activity ID) | 2.04.01.08 | Task Description | Duration (d) | Administrator ADMIN1 PO | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Control Room Work Package | [5 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost | Total Labor cost with estimate uncertainty | Total Material Cost with estimate uncertainty
| TASK |  |  | hrs | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S336100 | Analyze Control Room Requirements | Technical Scope: Analyze Control Room and Offices Modifications Requirements. Work Statement: Gather all relevant information from existing PHENIX documentation. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 8 | 16 | 0 | 0 | 0 | 972 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 3752.8 | 4691 | 0
S336200 | Create Control Room Schematic Design and Specification Control Documents | Technical Scope :Create Control Room and Offices Modifications Schematic Design and Specification Control Documents. Work Statement: Make appropriate detail drawings for Control Room and Offices modifications. | 5 | 0 | 0 |  | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 417.2 | 648.8 | 0 | 0 | 0 | 1066 | 1332.5 | 0
S336300 | Review Control Room Design/Safety | Technical Scope: Review Control Room and Offices Modifications Design/Safety criteria. Work Statement: Prepare documents and presentations as appropriate for review by CAD Safety Committee. | 5 | 0 | 4 |  | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 486 | 417.2 | 0 | 0 | 0 | 0 | 903.2 | 1129 | 0
S336400 | Address Action Items from Control Room Design & Safety Reviews | Technical Scope:Address Action Items from Control Room and Offices Modifications Design & Safety Reviews. Work Statement: Evaluate committee action items and address appropriately. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 8 | 16 | 0 | 0 | 0 | 972 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 3752.8 | 4691 | 0
S336500 | Design/Safety Reviews Complete, Control Room Components Released for Production | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S336600 | Prepare Control Room Components Procurement Package(s) | Technical Scope: Prepare Control Room and Offices Modifications Components Procurement Package(s). Work Statement: Prepare bid documents and initiate procurement of components. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 24 | 0 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 0 | 3892.8 | 0 | 0 | 6396 | 7995 | 0
S336700 | Evaluate & Process Control Room Components Bids | Technical Scope:Evaluate & Process Control Room and Offices Modifications Components Bids Work Statement: Evaluate vendor bids, select vendor, place contract with vendor. | 10 | 0 | 0 |  | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 8 | 8 | 16 | 0 | 0 | 0 | 0 | 834.4 | 648.8 | 1297.6 | 0 | 0 | 2780.8 | 3476 | 0
S336800 /S336900 | Procure & Deliver Control Room Components (leadtime and fabrication included) | Procure & Deliver Control Room and Offices Modifications Components (leadtime and fabrication included). Work Statement: Track and manage the procurement of all components for this item. | 30 | 0 | 0 |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 24 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 48 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 25% | 40% | Most control room and office equipment will be to0 old to be repurposed from PHENIX R&R. $50K seems like a good amount to cover any new computers and monitors and needed furniture upgrades. | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Rough order of magnitude estimate, but the work is fairly early though based on similar previous projects. 40% estimate uncertainty is reasonable./M5 | 0 | 0 | 24 | 48 | 48 | 0 | 0 | 0 | 0 | 2503.2 | 3892.8 | 3892.8 | 0 | 0 | 10288.8 | 12861 | 70000
S337000 | Perform Control Room Components Acceptance | Technical Scope: Perform Control Room and Offices Modifications Components Acceptance tests. Work Statement: Receive, inspect and acceptance test all components for this item as appropriate. | 10 | 0 | 8 |  | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 16 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 8 | 8 | 4 | 16 | 0 | 0 | 0 | 972 | 834.4 | 324.4 | 1297.6 | 0 | 0 | 3428.4 | 4285.5 | 0
S337100 | Control Room components Ready for Installation | Milestone | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials and Supplies Details | [43 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
[45 empty] | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 32368.8 | 40461 | 70000 | 50000 | 25% | 40%
WBS | Description | Item | Vendor |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | [25 empty] | 0 | 28 | 88 | 84 | 160 | 0 | 0 | 0 | 3402 | 9178.4 | 6812.4 | 12976 | 0 | 0
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  | QTY | Qty (Repeats) | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s)

## Risk Codes
TABLE 1: Labor risk codes
Code | Type of Estimate | Contingency % | Description
L1 | Actual | 0% | Actual costs incurred on activities completed to date.
L2 | Level of Effort Tasks | 0%-20% | Support type activities that must be done to support other work activities or the entire project effort, where estimated effort is based on the duration of the activities it is supporting.
L3 | Advanced | 10%-25% | Based on experience with documented identical or nearly identical work. Development of activities, resource requirements, and schedule constraints are highly mature. Technical requirements are very straightforward to achieve.
L4 | Preliminary | 25%-40% | Based on direct experience with similar work. Development of activities, resource requirements, and schedule constraints are defined as preliminary (beyond conceptual) design level. Technical requirements are achievable and with some precedent.
L5 | Conceptual | 40%-60% | Based on expert judgment using some experience as a reference. Development of activities, resource requirements, and schedule constraints are defined at a conceptual level. Technical requirements are moderately challenging.
L6 | Pre-conceptual | 60%-80% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints are defined at a pre-conceptual level. Technical requirements are moderately challenging.
L7 | Rough Estimate | 80%-100% | Based on expert judgment without similar experience. Development of activities, resource requirements, and schedule constraints is largely incomplete. Technical requirements are challenging.
L8 | Beyond state of the art | > 100% | No experience available for reference. Activities, resource requirements, and schedule constraints are completely undeveloped. Technical requirements are beyond state of the art.
TABLE 2: Material risk codes
Code | Type of Estimate | Contingency % | Description
M1 | Existing Purchase order | 0% | Items have been completed or obligated. (Note: Contact Change Orders are considered a Risk and should not be included )
M2 | Procurement for LOE/Oversight work | 0%-20% | M&S items such as travel, software purchases and upgrades, computers, etc. estimated to support LOE efforts and other work activities.
M3 | Advanced | 10%-25% | Items for which there is a catalog price or recent vendor quote based on a completed or nearly completed design or an existing design with little or no modifications and for which the costs are documented.
M4 | Preliminary | 25%-40% | Items that can be readily estimated from a reasonably detailed but not completed design; items adapted from existing designs but with moderate modifications, which have documented costs from past projects. A recent vendor survey (e.g., budgetary quote, vendor RFI response) based on a preliminary design belongs here.
M5 | Conceptual | 40%-60% | Items with a documented conceptual level of design; items adapted from existing designs but with extensive modifications, which have documented costs from past projects.
M6 | Pre-conceptual - Common work | 60%-80% | Items that do not have a documented conceptual design, but do have documented costs from past projects. Use of this estimate type indicates little confidence in the estimate. Its use should be minimized when completing the final estimate.
M7 | Pre-conceptual - Uncommon work | 80%-100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Its use should be minimized when completing the final estimate.
M8 | Beyond state of the art | > 100% | Items that do not have a documented conceptual design, and have no documented costs from past projects. Technical requirements are beyond the state of the art.
Return to Navigation Page