## Risks
Risk Identification | [7 empty] | Primary Risk (Unmitigated Risk Assessment) | [9 empty] | Risk Handling Plan (Mitigations) |  |  |  | Residual Risk (Post- Mitigation Assessment)
Risk ID Number | RLS activity or next WBS | Lab | System | Sequence | Owner | Risk Title | IF/THEN | Likelihood of Impact (%) | Schedule Impact | Technical Impact | Cost Impact Estimate ($K) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score | Overall Impact Score | Risk Handling Plan (Mitigations) | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Risk Handling Method | Cost of Mitigations ($K) (Notes OK) | Residual Risk Likelihood of Impact (%) | Residual Schedule Impact | Residual Technical Impact | Low Cost Impact ($K) | Likely Cost Impact ($K) | High Cost Impact ($K) | Low Schedule Impact (Mos) | Likely Schedule Impact (Mos) | High Schedule Impact (Mos) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score (Calculated) | Overall Impact Score (Residual) | Management Assessment: Overall Impact (Over-Ride) | Expected Value ($K) | Average Expected Value ($K) | Basis of Impact Estimates How were cost and schedule ranges ( Columns Z through AE) developed? | Matrix Code Likelihood | Matrix Code Severity | Risk Burndown Notes | Risk Manager Quantitative Model Notes | Risk Manager Review Questions | Retired Risk Notes Date, Risks Realized, etc… | Notes
sPH_Mgmt_001 | 101022 | BNL | Management |  | Ed O'Brien | Departure of Key Personnel | If someone critical to the Project informs of his intention to leave sPHENIX, then a replacement needs to be found. | 10% | Moderate |  | 72 | 2 | 2 | 3 | 0 | 3.3333 | High | Closely work with sPHENIX collaboration and BNL management to identify and hire a replacement. | T: Someone critical to the Project informs of his intention to leave sPHENIX Dec 2018 Don Lynch retires; Jan 2019 Paul Giannotti retires; Feb 2019 Russ Feder replaces Don Lynch | Mitigate |  | 5% | Moderate |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 0 | Impact estimates were approved on Jan 31 2019 based on most recent project experience with fillig out vacancies. Cost impact is considered zero because of the savings during personnel replacement search. | Unlikely | Moderate | [5 empty] | #REF!
sPH_Mgmt_002 | 101022 | BNL | Management |  | Ed O'Brien | Safety incident | If safety incident resulting in serious injury and 'Stop Work' protocol initiated at BNL happens, then schedule delay may occur. | 5% | Low |  | 63 | 2 | 2 | 2 | 0 | 2.6667 | Moderate | Carefully plan all work in accordance with BNL SBMS. Include safety reviews and safety review recommendations implementation in sPHENIX resource loaded schedule. | T: Safety incident resulting in serious injury and 'Stop Work' protocol occurs at BNL | Mitigate |  | 2% | Low |  | 0 | 0 | 0 | 0.1 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 | Schedule delay will not have a cost impact because the project has 14 mo of float. | Unlikely | Low | [5 empty] | #REF!
sPH_Mgmt_003 | 101010 | BNL | Management |  | Ed O'Brien | Funding profile stretches | If funds are not available on time then procurements will be delayed, resulting in schedule delays and possibly cost increase. | 50% | Low |  | 500 | 3 | 4 | 2 | 0 | 6 | High | Work closely with the funding agency so any funding profile changes can be evaluated as early as possible and sPHENIX Project schedule optimally adjusted to match the new funding profile. Since the Project is internally funded through redirect, the mitigation also comes through good communication within BNL management to ensure success. | T: Funds not available on time | Mitigate |  | 30% | Low |  | 0 | 200 | 300 | 0 | 3 | 6 | 3 | 3 | 2 | 0 | 5 | High |  | 60 | 50 | Cost Impact was assessed for FY20 and FY21 spend profile (using the preliminary baseline), assuming one (likely) or two (worst) quarter funding delay. Further assumption was that delayed procurements would result in 10% cost increase. | Possible | High | [5 empty] | #REF!
sPH_Mgmt_004 | S101022 | BNL | Management |  | Ed O'Brien | University Contributed Labor for sPHENIX | If sPHENIX loses University contributing labor, then there will be a loss of progress on the specific detector to which the university was contributing labor and need to replace this effort either by recruiting another university to the tasks or hiring the needed skill sets. | 4% | Low |  | 3900 | 2 | 4 | 2 | 0 | 4 | High | Informing DOE-ONP about scale and duration of efforts planned by all the various universities on sPHENIX. Recruitment of other sPHENIX collaborating institutions if a given University cannot continue. Maintain contact with other NP/HEP groups capable of such work if a paid contract must be placed. Cost and schedule impacts will be reduced as individual work activities are completed. | T: Loss of a University contributing labor to the sPHENIX project | Mitigate |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019. Nine new risks (one per each participating University) replace this one. CAMs will own the respective University labor related risks. |  | #REF!
sPH_Mgmt_005 | 101022 | BNL | Management |  | Ed O'Brien | Schedule Delay | If Planned Early Completion moves out past Baseline Early Completion milestone, then Project L1 Milestone 'Early Project Completion' is not achieved | 30% | Low |  | 13 | 3 | 1 | 2 | 0 | 3 | Moderate | Reserve contingency throughout project for covering schedule delay. | After PD-2 approval monitor cost contingency using the baseline change control and schedule contingency using the RLS in P6. Reassess residual risk parameters monthly and approve any changes by the RMB. |  |  | 10% | Low |  | 0 | 0 | 46 | 0 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 1.5333 | We assume that there is a 10% chance of a month delay beyond 'Early Project Completion' milestone. The probability went down from 30% because of the project's success with prototypes. In case of such a delay we estimate the 'standing army' cost for the BNL contributed labor and supplies is 25, 872 per month. Estimated Resources: Scientist Managing 50% | Unlikely | Low | [5 empty] | #REF!
sPH_Mgmt_006 | 1.01 | BNL | Management |  | Ed O'Brien | Infrastructure support delayed | If an Infrastructure/Installation Milestone is delayed, then Project activities dependent on Infrastructure milestone are delayed | 5% | Low |  | 0 | 2 | 1 | 2 | 0 | 2 | Low | Develop a detailed resource loaded schedule with key milestones for Infrastructure support and closely monitor this schedule for risk triggers. |  |  |  | 0% | Low | [7 empty] | 0 | 0 | 2 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support. |  | #REF!
sPH_Mgmt_007 | 101022 | BNL | Management |  | Ed O'Brien | Major Vendor Failure | If an Infrastructure/Installation Milestone is delayed, then Project activities dependent on Infrastructure milestone are delayed | 5% | Low |  | 0 | 2 | 1 | 2 | 0 | 2 | Low | Develop a detailed resource loaded schedule with key milestones for Infrastructure support and closely monitor this schedule for risk triggers. | Measure risk exposure quarterly and update cost impact numbers accordingly. Monitor all procurements and placed contract deliveries to track trends. |  |  | 3% | Moderate |  | 1000 | 1000 | 1000 | 0 | 2 | 3 | 2 | 4 | 3 | 0 | 4.6667 | High |  | 30 | 30 |  | Unlikely | High |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support. |  | #REF!
sPH_TPC_001 | 112100 | BNL | TPC |  | Tom Hemmick | Performance failure of v2 prototype | If the v2 prototype fails, then there will need to be a v3 prototype added to the cycle. | 5% |  |  | 150 | 2 | 3 | 0 | 0 | 2 | Low | We will add a design cycle of a smaller device than the full sized field cage if the v1 prototype fails. We will proceed on v2 only after success of the small version. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019. This risk is retired since Field Cage v2 prototype production is in the RLS. |  | #REF!
sPH_TPC_002 | 112100 | BNL | TPC |  | Tom Hemmick | Success of v1 field cage prototype | Cost savings due to skipping the v2 step. No schedule impact since the v2 field cage is not on the critical path. | 50% | Negligible |  | 150 | 3 | 3 | 1 | 0 | 4 | High | This is an opportunity so no mitigation is required. |  |  |  | 50% | Negligible |  | -150 | -150 | -150 | -4 | -4 | -4 | 3 | 1 | 1 | 0 | 2 | Low |  | -75 | -75 | Cost and schedule impact are based on the RLS where V2 Field Cage prototype step would be unneccessary in case of V1 success. | Possible | Low | [5 empty] | #REF!
sPH_TPC_003 | 1.02 | BNL | TPC |  | Tom Hemmick | Failure or delay of CERN production | If factories wait upon GEM foil delivery and suffer schedule shifts, then the factory production of modules is critical path and will directly affect schedule. | 10% |  |  | 174 | 2 | 3 | 0 | 0 | 2 | Low | We will monitor carefully the success of CERN foil production and will hire a technician who will exclusively work on producing GEM foils for our Project. If delays still occur, we will seek a second vendor. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual | [5 empty] | #REF!
sPH_TPC_004 | 139000 | BNL | TPC |  | Tom Hemmick | SAMPA Chip 80 nsec development | If SAMPA chip modification to include 80 nsec option (by eliminating 320 nsec option) fails to work effectively, then the TPC will have to default to using the 160 nsec option which may effect rate capability, but not affect performance of the TPC using moderate rates. | 33% | Negligible |  | 180 | 3 | 3 | 1 | 0 | 4 | High | An additional design cycle shall be added. | Monitoring is done using monthly P6 status updates. |  |  | 5% | Low |  | 147 | 170 | 215 | 4 | 5 | 7 | 2 | 3 | 2 | 0 | 3.3333 | High |  | 8.5 | 8.8667 | Low cost, schedule impact: Very minor error was found for the full SAMPA chip. In this case, the design change can be done in 1-week or so. Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $22K for 1-month design workforce Activities to be recycled: S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) Likely cost, schedule impact: Some minor errors were found for the full SAMPA chip. In this case, the design change may take 1-month. Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $45K for 2-month design workforce. Activities to be recycled: S138900 (1 month out of this) S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) High cost, schedule impact: Major issues were found already at prototype chip which is before the full SAMPA chip. In this case, we should try to find the solution to the issues by prototype test (additional 1-month), implement in the full SAMPA chip design and go for the full SAMPA chip production. If the full SAMPA chip was not successful, we have to go for another thorough design cycle (2-month). Mandatory time for design adjustment in negotiation with the chip company is estimated as 1 month, followed by the chip production time of 3-months. $125K for chip production and $90K for 4-month design workforce. Activities to be recycled: S138600 (1 month out of this) S138900 (2 month out of this) S139600 (1 month out of this) S140200,S140300,S140400 ($125K out of this) | Unlikely | High | [5 empty] | #REF!
sPH_TPC_005 | 1.02 | BNL | TPC |  | Tom Hemmick | Currency fluctuation on TPC GEMs contract with CERN | If US to Swiss Franc exchange rate goes up, then cost to produce TPC GEMs at CERN goes up. | 10% |  |  | 174 | 2 | 3 | 0 | 0 | 2 | Low | Accept this risk since nothing can be done to mitigate it. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019. Currency fluctuations can go both ways and there is no reason to expect that Swiss franc will go up agaisnt the US dollar in near future. |  | #REF!
sPH_TPC_006 | 125500 | BNL | TPC |  | Tom Hemmick | Wayne State Students Unavailable (R1 Modules) | If student labor unavailable at Wayne State University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Wayne State students in December 2019 |  |  | 2% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 2.8533 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Unlikely | Negligible | [5 empty] | #REF!
sPH_TPC_007 | 129500 | BNL | TPC |  | Tom Hemmick | Vanderbilt Students Unavailable (R2 Modules) | If student labor unavailable at Vanderbilt University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Vanderbilt students in December 2019 |  |  | 2% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 2.8533 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Unlikely | Negligible | [5 empty] | #REF!
sPH_TPC_008 | 133700 | BNL | TPC |  | Tom Hemmick | Temple Students Unavailable (R3a Modules) | If student labor unavailable at Temple University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Temple students in December 2019 |  |  | 2% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 2.8533 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Unlikely | Negligible | [5 empty] | #REF!
sPH_TPC_009 | 134000 | BNL | TPC |  | Tom Hemmick | Weizmann Students Unavailable (R3b Modules) | If student labor unavailable at Weizmann University GEM factory, then this factory would need 1 technician for the 6 month duration of the module production. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of Weizmann students in December 2019 |  |  | 2% |  |  | 0 | 0 | 428 | 3 | 6 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 2.8533 | Best: move effort to another 'TPC' University Likely: add new University to the TPC group Worst: absorb the effort into BNL. 160 h from student to TECH3 PO M (4.7 stud/day) | Unlikely | Negligible | [5 empty] | #REF!
sPH_TPC_010 | 112900 | BNL | TPC |  | Tom Hemmick | SUNY Stony Brook Staff and/or Students Not Available (TPC) | If detector-scientist, engineering and/or student labor unavailable to prepare prototype and production TPC field cage, TPC mechanics, HV and gas system and to contribute to TPC laser and DAM, and to perform final TPC assembly and testing, then new staff would need to be hired at SUNY Stony Brook, leading to schedule delay, or a technician would have to be hired to replace student labor, leading to cost and schedule delay. | 15% | Negligible |  | 100 | 3 | 2 | 1 | 0 | 3 | Moderate | SUNY Stony Brook recruitment of professional and student staff as part of ongoing contract. Maintain contact with other NP/HEP groups with appropriately-skilled detector-scientists. Maintain contact with technicians if one must be hired on short notice to hold schedule in absence of students. Cost and schedule impacts will be reduced as individual work activities are completed. | Get a list of Stony Brook students in December 2019 |  |  | 2% |  |  | 0 | 0 | 14 | 3 | 6 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  | 0 | 0.093333 |  | Unlikely | Negligible | [5 empty] | #REF!
sPH_EMCal_001 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of W powder supplier | If there is a failure of the primary supplier of W powder (Tungsten Heavy Powder) to sign a contract and deliver the powder for the final block production at an affordable price, then | 50% |  |  | 332 | 3 | 4 | 0 | 0 | 4 | High | We have identified another supplier (Starck) that we feel can deliver powder that can meet our specs at roughly 2/3 the THP price. Preliminary tests of samples of their powder appear to have adequate density. Further tests are being planned to build and test a number blocks (~10) using their powder and measure their performance. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. UIUC placed 2 contracts with Starck in April 2018 and Oct 2019, got both delivered. |  | #REF!
sPH_EMCal_002 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of SciFi supplier | If there is a failure of fiber vendor to sign a contract or deliver fiber on time, then that will cause a delay in the schedule and result in higher cost for the fiber | 10% |  |  | 868 | 2 | 4 | 0 | 0 | 2.6667 | Moderate | There are only two vendors capable of supplying fibers that will meet our specs, Saint-Gobain and Kuraray. We have built and tested blocks made with fibers from both vendors. If the Saint-Gobain cannot deliver the fiber for the price they quoted and on the time scale we require, we would have to purchase the fiber from Kuraray and pay the higher price. The production of sectors 0-12 will test whether Saint-Gobain can deliver the fiber on time and within budget. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Jan 22 2019 (PO 359217) |  | #REF!
sPH_EMCal_003 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of primary production site for blocks (University of Illinois Urbana Champaign) | If UIUC decides to not fabricate the absorber blocks, then there will be a delay in EMCal schedule and a significant increase in labor resources required to build the blocks at BNL or another collaborating institution, unless the outside institution provides the labor as an in-kind contribution to sPHENIX. | 5% | Negligible |  | 300 | 2 | 4 | 1 | 0 | 3.3333 | High | Several Chinese institutions have recently joined sPHENIX which have expressed interest in contributing to the EMCAL project and have the capability to produce the blocks. There will be a meeting in China in April 2018 to discuss this. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 | Best case: move effort to another University, Likely: add new University. Worst: absorb the effort into BNL: 15,333 h to TECH3 PO M (includes escalation) | Not Residual | No Residual | [5 empty] | #REF!
sPH_EMCal_004 | 178100 | BNL | EMCal |  | Craig Woody | Delay of EMCal block production at UIUC due to component supplies or technical issues | If EMCal Block production rate is not on schedule, then there will be a delay in EMCal schedule. | 25% | Negligible |  | 50 | 3 | 2 | 1 | 0 | 3 | Moderate | Add shifts or additional production when supplies are available or technical issues are resolved. Schedule early purchase & delivery of W powder, fibers, screens, epoxy . Monthly labor rate at UIUC is $7500/sector. |  |  |  | 10% | Low |  | 0 | 0 | 0 | 0.2 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 |  | Unlikely | Low | [5 empty] | #REF!
sPH_EMCal_005 | 196500 | BNL | EMCal |  | Craig Woody | Delay of EMCal module production or sector assembly rate due to component supplies or technical issues | If EMCal module production/assembly rate is not on schedule, then there will be a delay in EMCal schedule. | 40% | Negligible |  | 30 | 3 | 2 | 1 | 0 | 3 | Moderate | Add shifts or additional production when supplies are available or technical issues are resolved. Store partially assembled sectors until they can be completed. Use planned sector storage time as float. Rate for hiring a job shopper is ~$30/hour. However, If we cannot find all the primary labor for the module and sector factories from the BNL labor pool, we would need to hire new technicians for roughly one year. This would be result in an additional cost of ~ $100K/technician/year. |  |  |  | 10% | Low |  | 0 | 0 | 0 | 0.2 | 0.5 | 1 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 |  | Unlikely | Low | [5 empty] | #REF!
sPH_EMCal_006 | 1.03 | BNL | EMCal |  | Craig Woody | EMCal Preproduction sectors do not meet production specs | If Preproduction EMCal sectors fail testing, then EMCal Sector components need replacements or/and assembly steps need rework. | 30% |  |  | 58 | 3 | 2 | 0 | 0 | 2 | Low | It is likely that during the assembly of the first sectors we will need to tune and modify our fixtures and procedures. By pre-assembling, before epoxying parts together we can minimize any irreversible errors. Some re-working and testing will likely be required as part of the production. If additional blocks are needed, they can be added to the end of the block production run. |  |  |  | 0% |  |  | 0 | 0 | 0 | 0.5 | 1 | 4 | 0 | 1 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Mar 22 2019. |  | #REF!
sPH_EMCal_007 | 174700 | BNL | EMCal |  | Craig Woody | Student Labor Productivity | If EMCal Block production is not on schedule, then there will be a delay in EMCal schedule and increased cost. | 15% | Low |  | 169 | 3 | 3 | 2 | 0 | 5 | High | Add an additional UIUC TECH3 to the fiber filling team (205h x $76/h x .75 = $24k) and to the block production team(50h/sector x 51 sectors x $76/h x 0.75 = $145k | Monitoring is done using monthly P6 status updates. |  |  | 5% | Low |  | 72 | 145 | 145 | 0.25 | 0.5 | 1.5 | 2 | 3 | 2 | 0 | 3.3333 | High |  | 7.25 | 6.0333 | Add an additional UIUC TECH3 to the fiber filling team (205h x $76/h x .75 = $24k) and to the block production team(50h/sector x 51 sectors x $76/h x 0.75 = $145k | Unlikely | High | [5 empty] | #REF!
sPH_EMCal_008 | 1.03 | BNL | EMCal |  | Craig Woody | Loss of Epoxy supplier | If current vendor stops producing the epoxy we have chosen, or we lose the manufacturer/vendor, or experience delivery delays, then we would have to find an alternative product, either from the same manufacturer or from another manufacturer, resulting in a schedule delay. | 10% |  |  | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible | An alternative epoxy would need to be tested to be sure that it infuses the tungsten powder and doesn't affect the fiber light output. $6k for 1 week of technician time plus cost of epoxy samples and test materials. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Feb 20 2019. Successful preproduction contract and more than one supplier identified. |  | #REF!
sPH_EMCal_009 | 172800 | BNL | EMCal |  | Craig Woody | UIUC students not available for EMCal Fiber Assemblies | If UIUC students are not available for fiber assemblies, then there will be a delay in EMCal schedule and increased cost. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 | Not Primary | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in late Spring 2019 |  |  | 2% | Negligible |  | 0 | 0 | 1222 | 3 | 6 | 6 | 2 | 1 | 1 | 0 | 1.3333 | Low |  | 0 | 8.1467 | Best: move effort to another University Likely: add new University Worst: absorb the effort into BNL. 15,333 h to TECH3 PO M (includes escalation) | Unlikely | Low | [5 empty] | #REF!
sPH_EMCal_010 | 178100 | BNL | EMCal |  | Craig Woody | UIUC students not available for EMCal Final Block Fabrication | If UIUC students are not available for block fabrication, then there will be a delay in EMCal schedule and increased cost. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 | Not Primary | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in February 2020 |  |  | 2% | Moderate |  | 0 | 0 | 639 | 3 | 6 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 4.26 | Best: move effort to another University Likely: add new University Worst: absorb the effort into BNL. 135h*52 to TECH3 PO M (includes escalation) | Unlikely | Moderate | [5 empty] | #REF!
sPH_EMCal_011 | 196500 | BNL | EMCal |  | Craig Woody | Loss of Students for Sector testing | If UIUC students are not available for sector assembly, then there will be a delay in EMCal schedule and increased cost. | 10% | Moderate |  | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate | Get a list of participating students from collaboration institutions at least 3 months before activity begins. | Get a list of students in late Spring 2020 |  |  | 2% | Moderate |  | 0 | 0 | 628 | 1 | 3 | 6 | 2 | 1 | 3 | 0 | 2.6667 | Moderate |  | 0 | 4.1867 |  | Unlikely | Moderate | [5 empty] | #REF!
sPH_HCal_001 | 208100 | BNL | HCal |  | John Lajoie | Loss of scintillating tile provider (Uniplast) | If Uniplast is unable to engage in or complete the production contract, then schedule delay in the procurement of the scintillating tiles, along with correspond delays in inner and outer HCAL assembly. | 10% | Moderate |  | 2380 | 2 | 4 | 3 | 0 | 4.6667 | High | Explore alternate scintillator vendors (FNAL, Eljen). Detailed risk analysis here: https://docdb.sphenix.bnl.gov/cgi-bin/private/ShowDocument?docid=111 | Monitor pre-production tiles deliveries and evaluate production procurement progress on a weekly schedule. |  |  | 10% | Moderate |  | 1190 | 2380 | 2380 | 6 | 12 | 12 | 2 | 4 | 3 | 0 | 4.6667 | High |  | 238 | 198.3333 | Details documented here: https://docdb.sphenix.bnl.gov/cgi-bin/private/ShowDocument?docid=111 | Unlikely | High | [5 empty] | #REF!
sPH_HCal_002 | 1.04 | BNL | HCal |  | John Lajoie | Some pre-production scintillating tiles do not meet production specifications. | If testing of pre-production outer HCAL scintillating tiles indicates that some fraction do not meet specifications, then then this may cause a delay in the full production to make up the loss. | 10% |  |  | 26 | 2 | 2 | 0 | 0 | 1.3333 | Low | Test scintillating tiles at supplier as part of production, and again upon receipt at BNL. This will catch any problems as quickly as possible so they can be remediated quickly as part of the pre-production. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Apr 3 2019. |  | #REF!
sPH_HCal_003 | 208400 | BNL | HCal |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal scin. tiles testing | If student labor is unavailable for HCal scintillating tile or HCal sector assembly and testing, then a technician would need to be hired to replace students. | 0% |  |  | 150 | 0 | 3 | 0 | 0 | 0 | Not Primary | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of students in Summer 2019. |  |  | 2% | Low |  | 0 | 0 | 109 | 1 | 2 | 2 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0.72667 | Best: ISU takes over Likely: add new OHCal University Worst: absorb the effort into BNL. 1300 h from Student to TECH3 PO M | Unlikely | Low | [5 empty] | #REF!
sPH_HCal_004 | 210000 | BNL | HCal |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal sector assembly and testing | If student labor is unavailable for HCal scintillating tile or HCal sector assembly and testing, then a technician would need to be hired to replace students. | 15% |  |  | 150 | 3 | 3 | 0 | 0 | 3 | Moderate | Identify activities with student labor 3 month before start to make sure students are available and committed to finish their work. Identify potential technician to hire if student labor becomes unavailable. | Get a list of students in late Spring 2020 |  |  | 2% | Low |  | 0 | 0 | 648 | 0 | 0 | 4 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 4.32 | Best: ISU takes over Likely: add new OHCal University Worst: absorb the effort into BNL. 1300 h from Student to TECH3 PO M | Unlikely | Low | [5 empty] | #REF!
sPH_CalEl_001 | S195200 | BNL | CalEl |  | Eric Mannel | Delay in SiPM Delivery | If OPC SiPM order is not placed on schedule or vendor is unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 15% |  |  | 11 | 3 | 1 | 0 | 0 | 1 | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | #REF!
sPH_CalEl_001_a | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in SiPM Delivery | If TEC SiPM order is not placed on schedule or vendor is unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 15% |  |  | 11 | 3 | 1 | 0 | 0 | 1 | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | #REF!
sPH_CalEl_002 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in testing of SiPMs | If SiPM Delivery not placed on schedule, vendor delay, or collab. institution unable to meet production schedule, then there will be a delay in assembly of HCal and EMCal SiPM daughter boards and a potential delay in HCal and EMCal module assembly. | 20% |  |  | 11 | 3 | 1 | 0 | 0 | 1 | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | #REF!
sPH_CalEl_003 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in Assembly of HCal Daughter boards, Preamps, Interface boards, LED Drivers | If Procurement of components for HCal and issuing of orders are late, then this will delay HCal module assembly and testing | 20% |  |  | 25 | 3 | 1 | 0 | 0 | 1 | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | #REF!
sPH_CalEl_004 | 1.05 | BNL | CalEl |  | Eric Mannel | Delay in assembly of EMCal Daughter boards, Preamps or Interface boards | If Procurement of components for EMCal and issuing of orders are late, then this will delay EMCal module assembly and testing | 20% |  |  | 25 | 3 | 1 | 0 | 0 | 1 | Negligible |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO ) |  | #REF!
sPH_CalEl_005 | 1.05 | BNL | CalEl |  | Eric Mannel | Foreign Procurement of SiPMs | If Change in procurement costs/delivery schedule, then SiPM procurement cost goes up. | 50% |  |  | 43 | 3 | 2 | 0 | 0 | 2 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed, foreign vendor uncertainty no longer applies. |  | #REF!
sPH_CalEl_006 | 1.05 | BNL | CalEl |  | Eric Mannel | Hamamatsu declines to bid/Alternative vendor | If Hamamatsu declines to bid, then | 10% |  |  | 100 | 2 | 2 | 0 | 0 | 1.3333 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed. |  | #REF!
sPH_CalEl_007 | 230200 | BNL | CalEl |  | Eric Mannel | U. Michigan Staff and/or Students Unavailable (Cal FEE/SiPM) | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | 15% |  |  | 100 | 3 | 2 | 0 | 0 | 2 | Low |  |  |  |  | 2% | Low |  | 0 | 0 | 107 | 1 | 2 | 2 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0.71333 |  | Unlikely | Low | [5 empty] | #REF!
sPH_CalEl_008 | 1.05.02.02 | BNL | CalEl |  | Eric Mannel | EMCal electronics component prices go up | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary | Measure current risk exposure. Anticipate major procurements using the RLS 6-month look-ahead. Identify and develop relationships with alternative vendors for major procurements. Reserve enough contingency to absorb cost increase. | Keep Project management informed of latest procurement trends and evaluate alternatives at least monthly. |  |  | 50% | Low |  | 161 | 161 | 161 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 5 | High |  | 80.5 | 80.5 |  | Possible | High | [5 empty] | #REF!
sPH_CalEl_009 | 1.05.02.04 | BNL | CalEl |  | Eric Mannel | EMCal electronics components procurement is late | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary |  |  |  |  | 10% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 |  | Unlikely | Low | [5 empty] | #REF!
sPH_CalEl_010 | 1.05.02.02 | BNL | CalEl |  | Eric Mannel | HCal electronics component prices go up | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary | Measure current risk exposure. Anticipate major procurements using the RLS 6-month look-ahead. Identify and develop relationships with alternative vendors for major procurements. Reserve enough contingency to absorb cost increase. | Keep Project management informed of latest procurement trends and evaluate alternatives at least monthly. |  |  | 50% | Low |  | 161 | 161 | 161 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 5 | High |  | 80.5 | 80.5 |  | Possible | High | [5 empty] | #REF!
sPH_CalEl_011 | 1.05.02.04 | BNL | CalEl |  | Eric Mannel | EMCal electronics components procurement is late | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary |  |  |  |  | 10% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 |  | Unlikely | Low | [5 empty] | #REF!
sPH_CalEl_012 | 1.05.02.03 | BNL | CalEl |  | Eric Mannel | Digitizer component prices go up | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary | Measure current risk exposure. Anticipate major procurements using the RLS 6-month look-ahead. Identify and develop relationships with alternative vendors for major procurements. Reserve enough contingency to absorb cost increase. | Keep Project management informed of latest procurement trends and evaluate alternatives at least monthly. |  |  | 50% | Low |  | 117 | 117 | 117 | 0 | 0 | 0 | 3 | 3 | 2 | 0 | 5 | High |  | 58.5 | 58.5 |  | Possible | High | [5 empty] | #REF!
sPH_CalEl_013 | 1.05.02.04 | BNL | CalEl |  | Eric Mannel | Digitizer components procurement is late | If student labor unavailable for SiPM testing and/or Calorimeter FEE board testing, then | [8 empty] | 0 | Not Primary |  |  |  |  | 10% | Low |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 2 | 0 | 2 | Low |  | 0 | 0 |  | Unlikely | Low | [5 empty] | #REF!
sPH_DAQ&Tr_001 | 257000 | BNL | DAQ&Trigger |  | Martin Purschke | DAQ Prototype does not meet specifications | If tests with the various prototype stages reveal problems, then DAQ prototype throughput and performance is below specifications | 10% |  |  | 10 | 2 | 1 | 0 | 0 | 0.66667 | Negligible | Acquire more or more expensive PCs |  |  |  | 5% |  |  | 10 | 35 | 74 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1.3333 | Low |  | 1.75 | 1.9833 |  | Unlikely | Low | [5 empty] | #REF!
sPH_DAQ&Tr_002 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Global Lvl1 expert not available | If we lose engineering expertise due to employees leaving, then adaptation of PHENIX GL1 runs into obstacles | 10% |  |  | 0 | 2 | 1 | 0 | 0 | 0.66667 | Negligible | Select different card, identify a different BNL engineer |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Jan 31 2019. Risk did not realize. The design is ready. |  | #REF!
sPH_DAQ&Tr_003 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Timing System technology still not finalized | If legacy systems using the obsolete GLink protocol need to be changed, then conversion/adaptation from GLINK problematic, or envisioned replacement board cannot be used | 40% |  |  | 0 | 3 | 1 | 0 | 0 | 1 | Negligible | Meet with experts to down select technology; select different card and/or re-engineer fiber interface |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Dec 17 2018. We have already procured the GL1 and GTM units that we believe are the final ones. |  | #REF!
sPH_DAQ&Tr_004 | 1.06 | BNL | DAQ&Trigger |  | Martin Purschke | Local LVL1 implementation runs into obstacles | If simulations reveal the failure of an envisioned algorithm, then performance of LLVL1 algorithms inadequate. Trigger latency too high. | 30% |  |  | 85 | 3 | 2 | 0 | 0 | 2 | Low | Prioritize Physics goals to decide which triggers to run or procure more hardware |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual |  |  |  | Retired Dec 17 2018. Full simulations of all trigger algorithms are now complete. Specific implementations in the firmware and latencies need to be measured. There are two rounds of prototype modules and firmware in the P6 schedule including specifically called out reviews after each stage. Handling any timing and algorithm issues is already accounted for in the official schedule. |  | #REF!
sPH_DAQ&Tr_005 | S258900 | BNL | DAQ&Trigger |  | Martin Purschke | TPC produces higher data rate than we can store | If the TPC or other subsystem cannot meet the envisioned data reduction specifications, then data volume, especially from the TPC, is too high | 30% |  |  | 100 | 3 | 2 | 0 | 0 | 2 | Low | Invest in more local storage, change compression algorithms |  |  |  | 30% |  |  | 50 | 100 | 150 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 2 | Low |  | 30 | 30 |  | Possible | Low | [5 empty] | #REF!
sPH_DAQ&Tr_006 | 1.06.02.04 | BNL | DAQ&Trigger |  | Martin Purschke | U Colorado Staff and/or Students unavailable (LL1 Trigger) | If engineering labor unavailable to write and test trigger firmware and/or assemble and test LL1 trigger system, then new professional staff would need to be hired at U. Colorado, leading to schedule delay, or an outside professional would have to be hired by U. Colorado to complete the work on time, leading to cost and schedule impact | 10% |  |  | 100 | 2 | 2 | 0 | 0 | 1.3333 | Low | U. Colorado recruitment of engineering and postdoctoral staff as part of ongoing contract. Maintain contact with other NP/HEP groups capable of such work if a paid contract must be placed. Cost and schedule impacts will be reduced as individual work activities are completed. |  |  |  | 2% |  |  | 388 | 388 | 388 | 3 | 3 | 3 | 2 | 4 | 0 | 0 | 2.6667 | Moderate |  | 7.76 | 7.76 |  | Unlikely | Moderate |  |  |  |  | Retired Dec 17 2018. Engineering for board design and initial firmware is handled at Nevis Laboratories. For longer term maintenance and algorithm updates in firmware, the U. Colorado group will have postdoctoral research scientists and graduate students for the task. The schedule includes time for transitioning between such scientists and students, and faculty at the U. Colorado will provide necessary continuity. | #REF!
sPH_MinBias_001 | S272700 | BNL | MinBias |  | Mickey Chiu | Failure of D/S Board Prototype | If the D/S Board does not meet specifications, then we need to redesign to more conservative design | 10% |  |  | 50 | 2 | 2 | 0 | 0 | 1.3333 | Low |  |  |  |  | 10% |  |  | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  |  |  |  | Unlikely | Negligible | [5 empty] | #REF!
sPH_MinBias_001 | 273500 273600 | BNL | MinBias |  | Mickey Chiu | Nevis Labor not available | If Nevis labor is not available, then there will be schedule delays. | 0% |  |  | 0 | 0 | 1 | 0 | 0 | 0 | Not Primary |  |  |  |  | 2% |  |  | 0 | 0 | 0 | 1 | 3 | 6 | 2 | 1 | 0 | 0 | 0.66667 | Negligible |  |  |  |  | Unlikely | Negligible | [5 empty] | #REF!
sPH_SC_Magnet_001 | 2.02 | BNL | SC Magnet |  | Roberto Than | Delay in sPHENIX support platform construction | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 | Negligible | Monitor platform construction and see if some construction can begin without platform |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  |  |  |  | Not Residual | Not Residual |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager. |  | #REF!
sPH_SC_Magnet_002 | 2.02 | BNL | SC Magnet |  | Roberto Than | Magnet temperature sensors too far to read | If one is unable to read existing magnet temperature sensors in the service building over 400 feet away, then the sensors are not read or monitored by the cryogenic control system | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 | Negligible | An instrumentation rack will need to be added to the sPHENIX platform to read the sensors. Alternatively, different equipment may be needed with added cost. |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | Not Residual |  |  |  |  | Not Residual | Not Residual | Jan 17 2019: prob. went from 55% to 10%. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  | #REF!
sPH_SC_Magnet_003 | 2.02 | BNL | SC Magnet |  | Roberto Than | Vendor Delay in fabrication (Cryogenic ) | If a delay in sPHENIX support platform construction occurs, then the installation of cryogenic components on platform can't start | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 | Negligible | Monitor platform construction and see if some construction can begin without platform |  |  |  | 5% | Low |  | 42 | 42 | 42 | 0 | 2 | 6 | 2 | 2 | 2 | 0 | 2.6667 | Moderate |  |  |  |  | Unlikely | Moderate |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager. |  | #REF!
sPH_SC_Magnet_004 | 2.02 | BNL | SC Magnet |  | Carl Schultheiss | Parts availability or fabrication (Quench Detector) | If one is unable to read existing magnet temperature sensors in the service building over 400 feet away, then the sensors are not read or monitored by the cryogenic control system | 15% |  |  | 5 | 3 | 1 | 0 | 0 | 1 | Negligible | An instrumentation rack will need to be added to the sPHENIX platform to read the sensors. Alternatively, different equipment may be needed with added cost. |  |  |  | 5% | Low |  | 27 | 27 | 27 | 0 | 2 | 6 | 2 | 2 | 2 | 0 | 2.6667 | Moderate |  |  |  |  | Unlikely | Moderate | Jan 17 2019: prob. went from 55% to 10%. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need. |  | #REF!
sPH_Carriage_Cradle_001 | 311350 | BNL | Carriage and Structural Components |  | J. Mills | Steel Prices rise beyond EU | If raw steel prices rise due to market changes then the budget for this subsystem will need to go up. | 25% | Negligible | [7 empty] | Negligible | Closely monitoring market trends in hopes of anticipating any major changes. May procure components earlier if possible. |  |  |  | 15% |  |  | 76 | 76 | 76 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 2 | Low |  |  |  | (Pole tips: 110) + (Carriage Cradle: 130) = 240 (tona). Weight X $/pound = $600,000. EU 40% = $240,000 15% of $840,000 = $126,000 | Possible | Low | [5 empty] | #REF!
sPH_Carriage_Cradle_002 | 316000 | BNL | Carriage and Structural Components |  | J. Mills | Existing Detector Support Rails Require Replacement | If the support rails are deemed unacceptable then the rails will need full replacement increasing this subsystem cost. | 50% | Low | [7 empty] | Negligible | Through engineering analysis we will try to modify the existing rails such that all loads can be safely supported without having to fully replace them. Minor reconfiguring of the cradle carriage design will also be explored. |  |  |  | 50% |  |  | 250 | 500 | 720 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 4 | High |  |  |  | Best case: encasing existing rails in concrete. Likely: using available solid plates and machining them. Worst: fully replacing tracks and support beams. | Possible | High | [5 empty] | #REF!
sPH_Infrastructure | 2.04 | BNL | Infrastructure |  | R. Pisani/J. Mills | Failure of a major piece of facility equipment | If there is a single component failure then replacement or repair of component will be necessary. | [10 empty] | CAD to inspect existing hi-risk components planned for use in sPHENIX in FY'19/FY'20. Maintenance/repair will be performed prior to start of operations/commisssioning. |  |  |  | 10% | Low |  | 7.5 | 20 | 132.5 | 1 | 3 | 6 | [5 empty] | Negligible | [11 empty] | #REF!
sPH_Infrastructure_01 | 2.04 | BNL | Infrastructure |  | P. Giannotti | CA-D engineers are not available for timely design efforts | If CA-D engineers are not available for timely design efforts, then there would be cascading delays to production, assembly and installation | 30% | Negligible |  | 0 | 3 | 1 | 1 | 0 | 2 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual | [5 empty] | #REF!
sPH_Infrastructure_02 | 2.04 | BNL | Infrastructure |  | P. Giannotti | Cradle and/or Pole Tips Fabrication delayed | If fabrication is delayed, then Cradle and/or Pole Tips are not available on time to commence assembly and installation | 10% | Negligible |  | 0 | 2 | 1 | 1 | 0 | 1.3333 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual | [5 empty] | #REF!
sPH_Integration_Installation_01 | 2.05 | BNL | Integration Installation |  | D. Lynch | Subsystem not ready for installation | If a subsystem on a Critical Path is not delivered on time for scheduled installation, then there will be delays in construction/installation of sPHENIX | 30% | Negligible |  | 0 | 3 | 1 | 1 | 0 | 2 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual | [5 empty] | #REF!
sPH_Integration_Installation_02 | 2.05 | BNL | Integration Installation |  | D. Lynch | Labor not available for installation | If Labor is not available for timely installation, then there will be delays in construction/installation of sPHENIX | 10% | Negligible |  | 20 | 2 | 1 | 1 | 0 | 1.3333 | Low |  |  |  |  | 0% | [8 empty] | 0 | 0 | 0 | 0 | 0 | No Residual |  | 0 | 0 |  | Not Residual | No Residual | [5 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
[7 empty] | ` | [40 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## CB_DATA_ (hidden)
#NAME?

## SelectionCriteria
Value | Score | Value | Score | Cost Threshold ($K) | Modifier | Score
High | 4 | Very Likely (>50%) | 4 | High | > | 225
Moderate | 3 | Possible (≤50%) | 3 | Moderate | <= | 225
Low | 2 | Unlikely (≤10%) | 2 | Low | <= | 100
Negligible | 1 | Rare (≤1%) | 1 | Negligible | <= | 25
Handling Methods | What does it mean? (Info Only)
Mitigate | Active Planning to Reduce Odds/Impact
Avoid | Project Plan is changed; Risk CAN'T occur, and is retired or deleted.
Accept | If risk happens, Impact will happen, No plan to reduce.
Transfer | 3rd Party bears impact of risk - WARNING: MOU or similar document in place!
Burndown Start Year (YY) | 19
NOTE: This Column alters Cost Score Thresholds.
NOTE: Altering values on this page may change or break scoring on the "Risks" Tab. Please do not alter without reviewing underlying formulas and conditional formatting!
The VALUE Column and Score are for REFERENCE ONLY, and are not used as selection criteria in the spreadsheet - Instead actual % values are directly entered into Likelihood columns, and are used in formula calculations.

## Retired Risks
Retired Risks
Risk ID Number | Project L3 or L4 WBS | Lab | System | Sequence | Owner | Risk Title | IF/THEN | Likelihood of Impact (%) | Schedule Impact | Technical Impact | Cost Impact Estimate ($K) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score | Overall Impact Score | Risk Handling Plan (Mitigations) | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Risk Handling Method | Cost of Mitigations ($K) (Notes OK) | Residual Risk Likelihood of Impact (%) | Residual Schedule Impact | Residual Technical Impact | Low Cost Impact ($K) | Likely Cost Impact ($K) | High Cost Impact ($K) | Low Schedule Impact (Mos) | Likely Schedule Impact (Mos) | High Schedule Impact (Mos) | Probability Score (1-4) | Cost Score (1-4) | Schedule Score (1-4) | Technical Score (1-4) | Overall Impact Score (Calculated) | Overall Impact Score (Residual) | Management Assessment: Overall Impact | Expected Value ($K) | Average Expected Value ($K) | Basis of Impact Estimates How were cost and schedule ranges ( Columns Z through AE) developed? | Risk Burndown Notes | Risk Manager Quantitative Model Notes | Risk Manager Review Questions | Retired Risk Notes Date, Risks Realized, etc… | Notes
sPH_Mgmt_001 |  |  |  |  | Ed O'Brien | Departure of Key Personnel | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Mgmt_002 |  |  |  |  | Ed O'Brien | Safety incident | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Mgmt_003 |  |  |  |  | Ed O'Brien | Funding profile stretches | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Mgmt_004 |  |  |  |  | Ed O'Brien | University Contributed Labor for sPHENIX | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. Nine new risks (one per each participating University) replace this one. CAMs will own the respective University labor related risks.
sPH_Mgmt_005 |  |  |  |  | Ed O'Brien | Schedule Delay | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Mgmt_006 |  |  |  |  | Ed O'Brien | Infrastructure support delayed | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. sPHENIX MIE does not include installation, so the installation-related risks will be tracked in sPHENIX Support.
sPH_TPC_001 |  |  |  |  | Tom Hemmick | Performance failure of v2 prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. This risk is retired since Field Cage v2 prototype production is in the RLS.
sPH_TPC_002 |  |  |  |  | Tom Hemmick | Success of v1 field cage prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_003 |  |  |  |  | Tom Hemmick | Failure or delay of CERN production | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_004 |  |  |  |  | Tom Hemmick | SAMPA Chip 80 nsec development | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_005 |  |  |  |  | Tom Hemmick | Currency fluctuation on TPC GEMs contract with CERN | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019. Currency fluctuations can go both ways and there is no reason to expect that Swiss franc will go up agaisnt the US dollar in near future.
sPH_TPC_006 |  |  |  |  | Tom Hemmick | Wayne State Students Unavailable (R1 Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_007 |  |  |  |  | Tom Hemmick | Vanderbilt Students Unavailable (R2 Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_008 |  |  |  |  | Tom Hemmick | Temple Students Unavailable (R3a Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_009 |  |  |  |  | Tom Hemmick | Weizmann Students Unavailable (R3b Modules) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_TPC_010 |  |  |  |  | Tom Hemmick | SUNY Stony Brook Staff and/or Students Not Available (TPC) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_001 |  |  |  |  | Craig Woody | Loss of W powder supplier | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. UIUC placed 2 contracts with Starck in April 2018 and Oct 2019, got both delivered.
sPH_EMCal_002 |  |  |  |  | Craig Woody | Loss of SciFi supplier | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Jan 22 2019 (PO 359217)
sPH_EMCal_003 |  |  |  |  | Craig Woody | Loss of primary production site for blocks (University of Illinois Urbana Champaign) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_004 |  |  |  |  | Craig Woody | Delay of EMCal block production at UIUC due to component supplies or technical issues | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_005 |  |  |  |  | Craig Woody | Delay of EMCal module production or sector assembly rate due to component supplies or technical issues | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_006 |  |  |  |  | Craig Woody | EMCal Preproduction sectors do not meet production specs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Mar 22 2019.
sPH_EMCal_007 |  |  |  |  | Craig Woody | Student Labor Productivity | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_008 |  |  |  |  | Craig Woody | Loss of Epoxy supplier | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Feb 20 2019. Successful preproduction contract and more than one supplier identified.
sPH_EMCal_009 |  |  |  |  | Craig Woody | UIUC students not available for EMCal Fiber Assemblies | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_010 |  |  |  |  | Craig Woody | UIUC students not available for EMCal Final Block Fabrication | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_EMCal_011 |  |  |  |  | Craig Woody | Loss of Students for Sector testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_HCal_001 |  |  |  |  | John Lajoie | Loss of scintillating tile provider (Uniplast) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_HCal_002 |  |  |  |  | John Lajoie | Some pre-production scintillating tiles do not meet production specifications. | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Apr 3 2019.
sPH_HCal_003 |  |  |  |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal scin. tiles testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_HCal_004 |  |  |  |  | John Lajoie | Georgia State U Staff and/or Students Not Available for HCal sector assembly and testing | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_CalEl_001 |  |  |  |  | Eric Mannel | Delay in SiPM Delivery | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_001_a |  |  |  |  | Eric Mannel | Delay in SiPM Delivery | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_002 |  |  |  |  | Eric Mannel | Delay in testing of SiPMs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_003 |  |  |  |  | Eric Mannel | Delay in Assembly of HCal Daughter boards, Preamps, Interface boards, LED Drivers | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_004 |  |  |  |  | Eric Mannel | Delay in assembly of EMCal Daughter boards, Preamps or Interface boards | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired on Jan 31 2019 Risk did not realize. Contract placed Sep 18 2018 (PO )
sPH_CalEl_005 |  |  |  |  | Eric Mannel | Foreign Procurement of SiPMs | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed, foreign vendor uncertainty no longer applies.
sPH_CalEl_006 |  |  |  |  | Eric Mannel | Hamamatsu declines to bid/Alternative vendor | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019 Risk did not realize. Order with Hamamatsu has been placed.
sPH_CalEl_007 |  |  |  |  | Eric Mannel | U. Michigan Staff and/or Students Unavailable (Cal FEE/SiPM) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_DAQ&Tr_001 |  |  |  |  | Martin Purschke | DAQ Prototype does not meet specifications | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_DAQ&Tr_002 |  |  |  |  | Martin Purschke | Global Lvl1 expert not available | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Jan 31 2019. Risk did not realize. The design is ready.
sPH_DAQ&Tr_003 |  |  |  |  | Martin Purschke | Timing System technology still not finalized | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Dec 17 2018. We have already procured the GL1 and GTM units that we believe are the final ones.
sPH_DAQ&Tr_004 |  |  |  |  | Martin Purschke | Local LVL1 implementation runs into obstacles | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Dec 17 2018. Full simulations of all trigger algorithms are now complete. Specific implementations in the firmware and latencies need to be measured. There are two rounds of prototype modules and firmware in the P6 schedule including specifically called out reviews after each stage. Handling any timing and algorithm issues is already accounted for in the official schedule.
sPH_DAQ&Tr_005 |  |  |  |  | Martin Purschke | TPC produces higher data rate than we can store | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_DAQ&Tr_006 |  |  |  |  | Martin Purschke | U Colorado Staff and/or Students unavailable (LL1 Trigger) | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_MinBias_001 |  |  |  |  | Mickey Chiu | Failure of D/S Board Prototype | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_MinBias_001 |  |  |  |  | Mickey Chiu | Nevis Labor not available | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_SC_Magnet_001 |  |  |  |  | Roberto Than | Delay in sPHENIX support platform construction | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Mar 28 2019. Risk did not realize. The support platform is in a different WBS and therefore the schedule will be monitored by a different L2 manager.
sPH_SC_Magnet_002 |  |  |  |  | Roberto Than | Magnet temperature sensors too far to read | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | Retired Mar 28 2019. Justification: We have obtained one original CLTS （Cryogenic Linear Temperature Sensor) from BaBar/Ansaldo card which changed resistance to 4 to 20 mA. We have tested it and it worked. We have then made copies of this card for as many channels as we need.
sPH_Infrastructure_01 |  |  |  |  | P. Giannotti | CA-D engineers are not available for timely design efforts | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Infrastructure_02 |  |  |  |  | P. Giannotti | Cradle and/or Pole Tips Fabrication delayed | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Integration_Installation_01 |  |  |  |  | D. Lynch | Subsystem not ready for installation | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
sPH_Integration_Installation_02 |  |  |  |  | D. Lynch | Labor not available for installation | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
0 |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
0 |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
0 |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
0 |  |  |  |  | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0 |  |  |  |  | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
[12 empty] | 0 | 0 | 0 | 0 | 0 | Negligible | [13 empty] | 0 | 0 | 0 | 0 | 0 | Negligible |  | 0 | 0
`

## RiskPresentation
Choose Row: | 5 |  | 20 | 55.86 | 19.29 | 15.29 | 17.14
|  | 18 | Risk ID | Title | System | Owner | Residual Impact
|  |  | sPH_Mgmt_003 | Funding profile stretches | Management | Ed O'Brien | High
|  | 18 | Risk Statement (If/Then): |  |  | Likelihood: | 30%
|  | 18 | If funds are not available on time then procurements will be delayed, resulting in schedule delays and possibly cost increase. |  |  | Cost Impact: | Moderate
|  | 18 |  |  |  | Schedule Impact: | Low
|  | 18 |  |  |  | Technical Impact:
|  | 18 | Risk Handling (Mitigations): |  |  | Cost Impacts ($K) |  | Schedule Impact (Months)
|  | 18 | Work closely with the funding agency so any funding profile changes can be evaluated as early as possible and sPHENIX Project schedule optimally adjusted to match the new funding profile. Since the Project is internally funded through redirect, the mitigation also comes through good communication within BNL management to ensure success. |  |  | Expected Value: | 60
|  | 18 |  |  |  | Average EV: | 50
|  | 18 |  |  |  | Low Cost: | 0 | Low: | 0
|  | 18 |  |  |  | Likely Cost: | 200 | Likely: | 3
|  | 18 |  |  |  | High Cost: | 300 | High: | 6
Basis of Impact Estimates (Cost & Sched.):
Cost Impact was assessed for FY20 and FY21 spend profile (using the preliminary baseline), assuming one (likely) or two (worst) quarter funding delay. Further assumption was that delayed procurements would result in 10% cost increase.
|  | 18 | Risk Handling Schedule ( Triggers, Milesones, Due Dates):
T: Funds not available on time
NOTE: In cell B1 above, enter the ROW from the "Risks" Tab to display a page for the selected risk.
Use caution altering any data other than cell B1 above, as it may break the summary.
If you add or remove columns from the "Risks" tab, you will need to manually update the corresponding formulas on THIS page.

## BASIC Counts
Impact | Pre-Mitigation | Post-Mitigation
High | 9 | 9
Moderate | 12 | 6
Low | 18 | 15
Negligible | 15 | 8
No Residual | 0 | 25
Residual Total |  | 38
|  |  | Severity of Impact ---------------------- Probability | Negligible | Low | Moderate | High
|  |  | Very Likely | 0 | 0 | 0 | 0
|  |  | Possible | 0 | 3 | 0 | 5
|  |  | Unlikely | 7 | 12 | 6 | 4
|  |  | Rare | 0 | 0 | 0 | 0
|  |  | Expected Value Total: | 527.76
|  |  | Averate Expected Value Total: | 512.87
NOTE: If columns are altered on the RISKS tab, this page may stop working.

## L2 slides
L2