## Overview
|  | Labor |  | Materials
1.03.01 | EMCal Block Production
1.03.01.01 | EMCAL Prototype V2.1 Block Production | 0 |  | 0
1.03.01.02 | EMCAL Pre-Prod Prototype Block Production (for Sector 0) | 1018 |  | 1080
1.03.01.02 | EMCAL Pre-Prod Prototype Block Production (for Sectors 1-12) | 5136 |  | 755649.65
1.03.01.03 | EMCAL Final Block Production (for Sectors 13-64) | 16783 |  | 1952353
| TOTAL Hours | 22937 | TOTAL Materials | 2709082.65

## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
EMCAL |  | 1.03 |  | EMCAL Block Production |  | 1.03.01
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| EMCal Prototype v2.1 Blocks |  | 1.03.01.01 |  | EMC Prototype v2.1 Blocks
| EMCAL pre-production (Blocks for Sector 0) |  | 1.03.01.02 |  | EMCAL Pre-Production Prototype Blocks, Sector 0
| EMCAL pre-production (Blocks for Sectors 1-12) |  | 1.03.01.02 |  | EMCAL Pre-Production Prototype Blocks, Sectors 1-12
| EMCAL Final Block Production (Blocks for Sectors 13-64) |  | 1.03.01.03 |  | EMCAL Final Block Production

## Prototype v2.1 SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-01-25
[7 empty] | Prepared By: | Anne Sickles, Caroline Riedl, Eric Thorsland
[7 empty] | DocNo. (refer Rev. Log) | 70 v16
Work Package Name: |  |  |  |  | WBS Number: |  |  | Control Account Number
EMCal Prototype v2.1 Block Production |  |  |  |  | 1.03.01.01
WBS Dictionary Definition:
Produce 16 Tungsten powder/epoxy/scintillating fiber "SPACAL" absorber blocks for v2.1 prototype
Estimate Type (check all that apply):
| x | Work Complete
| x | Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
Blocks will be produced according to modified design drawings 4/2017 Blocks will be produced using methods developed while producing blocks for v2 prototype
Details of the Base Estimate (explanation of the Work)
Cost Summary
[6 empty] | Labor | Materials
[6 empty] | total | total
|  | 1.3.1 | EMCal Block Production
|  | 1.3.1.1 | EMCAL Prototype V2.1 Block Production |  |  | 0 | 0
estimate uncertainty
commodity material costs (Ex: tungsten powder) may vary with market values.

## PreProd "Sector 0" SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-25
[8 empty] | Prepared By: | Anne Sickles
[8 empty] | DocNo. (refer Rev. Log) | 70 v16
Work Package Name: |  |  |  |  | WBS Number: |  |  |  | Control Account Number
EMCAL Module PreProduction Prototype Block Production |  |  |  |  | 1.03.01.02
WBS Dictionary Definition:
Produce 96 Tungsten powder/epoxy/scintillating fiber "SPACAL" absorber blocks for the Pre-Production prototype "Sector 0".
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
*The cost estimates are based on our experience producing blocks for the V2 prototype.
Details of the Base Estimate (explanation of the Work)
Materials
Labor
Cost Summary
(follow link for detailed summary)
[7 empty] | Labor | Materials
[7 empty] | total | total
|  | 1.3.1 | EMCal Block Production
|  | 1.3.1.2 | EMCAL pre-production sector 0 blocks production |  |  |  | 1018 | 1080
estimate uncertainty

## PreProd sector 1-12 SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-01-25
[7 empty] | Prepared By: | Anne Sickles
[7 empty] | DocNo. (refer Rev. Log) | 70 v16
Work Package Name: |  |  |  |  | WBS Number: |  |  | Control Account Number
EMCAL Module PreProduction Prototype Block Production |  |  |  |  | 1.3.1.2
WBS Dictionary Definition:
Produce tungsten SPACAL blocks for 12 full sectors (1152 blocks)
Estimate Type (check all that apply):
| x | Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
*The cost estimates are based on our experience producing blocks for the V2 prototype.
Details of the Base Estimate (explanation of the Work)
Materials
Labor
Cost Summary
[6 empty] | Labor | Materials
[6 empty] | total | total
|  | 1.03.01 | EMCal Block Production
|  | 1.03.01.02 | EMCAL pre-production sectors 1-12 blocks production |  |  | 5136 | 755649.65
estimate uncertainty

## Final Block Prod SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-25
[8 empty] | Prepared By: | Anne Sickles, Caroline Riedl, Eric Thorsland
[8 empty] | DocNo. (refer Rev. Log) | 70 v16
Work Package Name: |  |  |  |  | WBS Number: |  |  |  | Control Account Number
EMCAL Final Block Production |  |  |  |  | 1.3.1.3
WBS Dictionary Definition:
Produce 3744 Tungsten powder/epoxy/scintillating fiber "SPACAL" absorber blocks for the final sPHENIX EMCalorimeter Sectors 13-64. These remaining 52 de-scoped sectors will be built with block shapes 1-18, or 72 blocks per sector.
Estimate Type (check all that apply):
| x | Work Complete
| x | Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
*The cost estimates are based on our experience producing blocks for the V2 prototype. Block production will use similar methods, scaled up for larger production quantities.
Details of the Base Estimate (explanation of the Work)
Labor details
materials - Details
Cost Summary
[7 empty] | Labor | Materials
[7 empty] | total | total
|  | 1.3.1 | EMCal Block Production
|  | 1.3.1.3 | EMCAL Final Block Production |  |  |  | 16783 | 1952353
estimate uncertainty
Text

## V2.1 - MATERIALS-Details
WBS | Activity ID | Description | space req (ft^2) | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.03.01.01 |  | EMC Prototype v2.1 Blocks | [7 empty] | 0
1.03.01.01 | S156600 | Order screens |  | Etched metal plates | TechEtch http://www.tech-etch.com | 0 | delivered | quote & purchase | 0

## sector 0 MATERIALS-Details
WBS | Activity ID | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.01.02 |  | EMCAL PreProductionPrototype Block Production |  |  | 1080 |  |  | 1080
1.03.01.02.01 |  | Order Material for preproduction prototype Sector 0
1.03.01.02.01 | S157200 | Order & deliver W | Tungsten | Tungsten Heavy Powder http://www.tungstenheavypowder.com | 0 | complete | quote
1.03.01.02.01 | S157400 | Order & deliver fibers | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 0 | complete | quote
1.03.01.02.01 | S157600 | Order & deliver screens | Etched metal plates | TechEtch http://www.tech-etch.com | 0 | complete | quote
1.03.01.02.01 | S157800 | Order & deliver expoxy | Epoxy glue | Epoxy Technology http://www.epotek.com | 0 | complete | quote
1.03.01.02.01 | S157900 | Order & deliver mold parts | Sum: |  | 0 | complete
|  |  | Delrin plates | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Vacuum hose | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Fitings for vacuum | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Potting tools (various) | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Hardware [packs of 100] | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Silicone grease | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Vibrating tables | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Digital scales | McMaster-Car https://www.mcmaster.com/ | included in costs for final blocks |  | webpage |  | Complete
|  |  | Solo cups [cases of 1000] | Solo Cup http://www.solocup.com/ | 250 |  | webpage |  | Complete
|  |  | Stiring tools [boxes of 500] | McMaster-Car https://www.mcmaster.com/ | 250 |  | webpage |  | Complete
|  |  | Cleaning supplies | do-it-best hardware https://www.doitbest.com | 250 |  | webpage |  | Complete
|  |  | Gloves | Local MRL store room | 250 |  | catalog |  | Complete
|  |  | Safety gear | Local MRL store room | included in costs for final blocks |  | catalog |  | Complete
1.03.01.02.01 | S158100 | Set up factory for preproduction prototype Sector 0 | Sum: | 0 | 0
|  | (costs indicated are 25% of actual price | Fork truck | UIUC campus | included in costs for final blocks | delivered
|  | because items will be used also for projects other than sPHENIX) | Charger for fork truck | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  | Battery packages for fork truck | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  | Shelves | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  |  | tbd | included in costs for final blocks
1.03.01.02.03 |  | Pack and ship preproduction blocks to BNL Sector 0 | Shipping |  | 1080 |  | Estimate
| S159300 | Ship preproduction prototype blocks 1-12 for Sector 0 to BNL |  | UIUC contractor | 135 | complete | PO
| S159500 | Ship preproduction prototype blocks 13-24 for Sector 0 to BNL |  | UIUC contractor | 135 | complete | PO
| S159700 | Ship preproduction prototype blocks 25-36 for Sector 0 to BNL |  | UIUC contractor | 135 | complete | PO
| S159900 | Ship preproduction prototype blocks 37-48 for Sector 0 to BNL |  | UIUC contractor | 135 | complete | PO
| S160100 | Ship preproduction prototype blocks 49-60 for Sector 0 to BNL |  | UIUC contractor | 135 | complete | PO
| S160300 | Ship preproduction prototype blocks 61-72 for Sector 0 to BNL |  | UIUC contractor | 135 |  | PO
| S160500 | Ship preproduction prototype blocks 73-84 for Sector 0 to BNL |  | UIUC contractor | 135 |  | PO
| S160700 | Ship preproduction prototype blocks 85-96 for Sector 0 to BNL |  | UIUC contractor | 135 |  | PO

## sectors 1-12 MATERIALS-Details
WBS | Activity ID | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.01.02 |  | EMCAL PreProductionPrototype Block Production (- for Sectors 1-12 only) | [5 empty] | 755649.65
1.03.01.02.04 |  | Order Material for EMCal Block Preproduction |  |  | 742689.65
1.03.01.02.04 | S161600 | Order & deliver W sectors 1-3 | Tungsten powder | H.C.Starck | 73140 | delivered | quote
1.03.01.02.04 | S161700 | Order & deliver W sectors 4-12 | Tungsten powder | H.C.Starck | 219420
1.03.01.02.04 | S162800 | Order & deliver fibers batch 1 | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 115200 | delivered | quote |  | Completed prior to 10/1/2018
1.03.01.02.04 | S162900 | Order & deliver fibers batch 2 | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 115200 | delivered | quote |  | Completed prior to 10/1/2018
1.03.01.02.04 | S163000 | Order & deliver fibers batch 3 | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 96000 | delivered | quote
1.03.01.02.04 | S163100 | Order & deliver fibers batch 4 | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 57600 | delivered | quote
1.03.01.02.04 | S164000 | Order & deliver screens | Etched metal plates | TechEtch http://www.tech-etch.com | 221618 | ordered | quote--this buys screens for entire detector
1.03.01.02.04 | S164700 | Order & deliver expoxy | Epoxy glue | Epoxy Technology http://www.epotek.com | 39105 | quote | quote (scaled from full detector quote to 12 full sectors)
1.03.01.02.04 | S164800 | Order & deliver mold parts | Sum: |  | 5806.65
|  |  | Delrin plates | McMaster-Car https://www.mcmaster.com/ | 1336.5 |  | webpage
|  |  | Vacuum hose | McMaster-Car https://www.mcmaster.com/ | 122 |  | webpage
|  |  | Fitings for vacuum | McMaster-Car https://www.mcmaster.com/ | 1725 |  | webpage
|  |  | Potting tools (various) | McMaster-Car https://www.mcmaster.com/ | 56.25 |  | webpage
|  |  | Hardware [packs of 100] | McMaster-Car https://www.mcmaster.com/ | 77.9 |  | webpage
|  |  | Silicone grease | McMaster-Car https://www.mcmaster.com/ | 190 |  | webpage
|  |  | Vibrating tables | McMaster-Car https://www.mcmaster.com/ | 996 |  | webpage
|  |  | Digital scales | McMaster-Car https://www.mcmaster.com/ | 89 |  | webpage
|  |  | Solo cups [cases of 1000] | Solo Cup http://www.solocup.com/ | 272 |  | webpage
|  |  | Stiring tools [boxes of 500] | McMaster-Car https://www.mcmaster.com/ | 47 |  | webpage
|  |  | Cleaning supplies | do-it-best hardware https://www.doitbest.com | 375 |  | webpage
|  |  | Gloves | Local MRL store room | 286 |  | catalog
|  |  | Safety gear | Local MRL store room | 234 |  | catalog
1.03.01.02.04 | S165700 | Set up factory | Sum: | 0 | 30000
|  | (costs indicated are 25% of actual price | Fork truck | UIUC campus | included in costs for final blocks | delivered
|  | because items will be used also for projects other than sPHENIX) | Charger for fork truck | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  | Battery packages for fork truck | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  | Shelves | Bahrns Equipment http://www.bahrns.com | included in costs for final blocks | delivered
|  |  |  | tbd | included in costs for final blocks
1.03.01.02.06 |  | 12x ship 12 sectors to BNL | Shipping |  | 12960 |  | Estimate
1.03.01.02.06 | S167200 | Pack and ship EMCAL blocks for Prepro sector 1 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S167400 | Pack and ship EMCAL blocks for Prepro sector 2 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S167600 | Pack and ship EMCAL blocks for Prepro sector 3 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S167800 | Pack and ship EMCAL blocks for Prepro sector 4 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S168000 | Pack and ship EMCAL blocks for Prepro sector 5 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S168200 | Pack and ship EMCAL blocks for Prepro sector 6 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S168400 | Pack and ship EMCAL blocks for Prepro sector 7 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S168600 | Pack and ship EMCAL blocks for Prepro sector 8 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S168800 | Pack and ship EMCAL blocks for Prepro sector 9 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S169000 | Pack and ship EMCAL blocks for Prepro sector 10 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S169200 | Pack and ship EMCAL blocks for Prepro sector 11 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0
1.03.01.02.06 | S169400 | Pack and ship EMCAL blocks for Prepro sector 12 to BNL M&S |  |  | 1080 |  | PO for shipping sector 0

## Final Block Prod - MATERIALS
WBS | Activity ID | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.01.03 |  | EMCAL Final Block Production | [5 empty] | 1952353
1.03.01.03.01 |  | Order Material for EMCal Final Block Produciton |  |  | 1910233
1.03.01.03.01 | S170200 / S170210 | Order & deliver W (de-scoped sectors 13-64) | Tungsten | H.C.Starck | 950820 |  | quote
1.03.01.03.01 | S171000 - S171023 | Order & deliver fibers #1 | Optical fibers | Saint Gobain http://www.saint-gobain-northamerica.com | 840000 | ordered | quote
1.03.01.03.01 | S171800 | Order & deliver epoxy | Epoxy glue | Epoxy Technology http://www.epotek.com | 90653 |  | quote (scaled from full detector quote to 52 sectors at 77% acceptance
1.03.01.03.01 | S172500 | Order & deliver mold parts | Sum of mold costs: | subtotal | 26230
|  |  | Delrin plates | McMaster-Car https://www.mcmaster.com/ | 5792 |  | webpage
|  |  | Vacuum hose | McMaster-Car https://www.mcmaster.com/ | 528 |  | webpage
|  |  | Fitings for vacuum | McMaster-Car https://www.mcmaster.com/ | 7475 |  | webpage
|  |  | Potting tools (various) | McMaster-Car https://www.mcmaster.com/ | 243 |  | webpage
|  |  | Hardware [packs of 100] | McMaster-Car https://www.mcmaster.com/ | 338 |  | webpage
|  |  | Silicone grease | McMaster-Car https://www.mcmaster.com/ | 824 |  | webpage
|  |  | Vibrating tables | McMaster-Car https://www.mcmaster.com/ | 2988 |  | webpage
|  |  | Digital scales | McMaster-Car https://www.mcmaster.com/ | 3596 |  | webpage
|  |  | Solo cups [cases of 1000] | Solo Cup http://www.solocup.com/ | 362 |  | webpage
|  |  | Stiring tools [boxes of 500] | McMaster-Car https://www.mcmaster.com/ | 203 |  | webpage
|  |  | Cleaning supplies | do-it-best hardware https://www.doitbest.com | 1625 |  | webpage
|  |  | Gloves | Local MRL store room | 1240 |  | catalog
|  |  | Safety gear | Local MRL store room | 1016 |  | catalog
1.03.01.03.01 | S172700 | Set up factory for final blocks | Sum of factory set up: | subtotal | 2530
|  | (costs indicated are 25% of actual price | Fork truck | UIUC campus | 0 | delivered
|  | because items will be used also for projects other than sPHENIX) | Charger for fork truck | Bahrns Equipment http://www.bahrns.com | 0 | delivered
|  |  | Battery packages for fork truck | Bahrns Equipment http://www.bahrns.com | 0 | delivered
|  |  | Shelves | Bahrns Equipment http://www.bahrns.com | 0 | delivered
1.03.01.03.03 |  | 8x ship 8 block for 64 sectors to BNL | Shipping | tbd | 42120 |  | Estimate
1.03.01.03.03 | S178310 | Pack and ship final blocks for sectors 13-16 to BNL |  | note this is for 4 sectors only, others are for 8 sectors | 3240 |  | PO for sector 0
1.03.01.03.03 | S178410 | Pack and ship final blocks for sectors 17-24 to BNL |  |  | 6480 |  | PO for sector 0
1.03.01.03.03 | S178510 | Pack and ship final blocks for sectors 25-32 to BNL |  |  | 6480 |  | PO for sector 0
1.03.01.03.03 | S178610 | Pack and ship final blocks for sectors 33-40 to BNL |  |  | 6480 |  | PO for sector 0
1.03.01.03.03 | S178710 | Pack and ship final blocks for sectors 40-48 to BNL |  |  | 6480 |  | PO for sector 0
1.03.01.03.03 | S178810 | Pack and ship final blocks for sectors 49-56 to BNL |  |  | 6480 |  | PO for sector 0
1.03.01.03.03 | S178910 | Pack and ship final blocks for sectors 56-64 to BNL |  |  | 6480 |  | PO for sector 0

## EMC Block Prod-Labor -Details
WBS | Activity ID | Description | Item | duration (days) | Status | Basis of Estimate | Budgeted hours | Senior Tech [%] | Student [%] | Tech [%] | Senior Tech [h] | Student [h] | Techn [h]
1.03.01 |  | EMCal Block Production |  |  |  |  | 22937
1.03.01.01 |  | EMCAL Prototype V2.1 Module Production |  |  |  |  | 0
1.03.01.01 | S156600 | Order screens for v2.1 prototype |  | 25 | complete | past experience
1.03.01.01 | S156800 | Fabricate molds for v2.1 prototype |  | 20 | complete | past experience
1.03.01.01 | S156900 | Fabricate blocks for v2.1 prototype |  | 50 | complete | past experience
1.03.01.01 | S157000 | Ship v2.1 blocks to BNL |  | 5 | complete | past experience
1.03.01.02 |  | EMCAL Preproduction Prototype Block Production |  |  |  |  | 6154
|  | Preproduction Sector 0 |  |  |  |  | 1018
|  | Preproduciton Sectors 1-12 |  |  |  |  | 5136
1.03.01.02.01 |  | Order Material for preproduction prototype Sector 0 |  |  |  |  | 0
1.03.01.02.01 | S157100 | Order W powder preproduction prototype |  | 40 | complete
1.03.01.02.01 | S157300 | Order fibers preproduction prototype |  | 90 | complete
1.03.01.02.01 | S157500 | Order screens for preproduction prototype |  | 40 | complete
1.03.01.02.01 | S157700 | Order epoxy for preproduction prototype |  | 20 | complete
1.03.01.02.01 | S158000 | Order parts for molds for preproduction prototype |  | 20 | complete
1.03.01.02.01 | S158100 | Set up factory for preproduction prototype |  | 90 | complete | past experience
1.03.01.02.01 | S158200 | Prepare fiber assemblies for PPP Sector 0 |  |  | complete | past experience
1.03.01.02.02 |  | Fabricate blocks for preproduction prototype Sector 0 |  |  |  |  | 858 | 0.1 | 0.05 | 0.85 | 85.8 | 42.9 | 729.3
1.03.01.02.02 | S158300 | Fabricate blocks 1-12 for preproduction prototype Sector 0 |  | 5 | complete | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2 | Complete in FY2018
1.03.01.02.02 | S158400 | Fabricate blocks 13-24 for preproduction prototype Sector 0 FY18 |  |  | complete | past experience | 66 | 0.1 | 0.05 | 0.85 | 6.6 | 3.3 | 56.1 | Complete in FY2018
1.03.01.02.02 | S158500 | Fabricate blocks 13-24 for preproduction prototype Sector 0 FY19 |  | 5 |  | past experience | 66 | 0.1 | 0.05 | 0.85 | 6.6 | 3.3 | 56.1
1.03.01.02.02 | S158600 | Fabricate blocks 25-36 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
1.03.01.02.02 | S158700 | Fabricate blocks 37-48 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
1.03.01.02.02 | S158800 | Fabricate blocks 49-60 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
1.03.01.02.02 | S158900 | Fabricate blocks 61-72 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
1.03.01.02.02 | S159000 | Fabricate blocks 73- 84 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
1.03.01.02.02 | S159100 | Fabricate blocks 85-96 for preproduction prototype Sector 0 |  | 5 |  | past experience | 132 | 0.1 | 0.05 | 0.85 | 13.2 | 6.6 | 112.2
|  | 8 (weeks)x 2,916 |  | 8 (weeks) x 5 days | [6 empty] | 0 | 0 | 0
1.03.01.02.03 |  | Pack and ship preproduction blocks to BNL for Sector 0 |  |  |  |  | 160 |  |  |  | 0 | 0 | 0
1.03.01.02.03 | S159200 | Ship preproduction prototype blocks 1-12 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S159400 | Ship preproduction prototype blocks 13-24 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S159600 | Ship preproduction prototype blocks 25-36 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S159800 | Ship preproduction prototype blocks 37-48 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S160000 | Ship preproduction prototype blocks 49-60 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S160200 | Ship preproduction prototype blocks 61-72 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S160400 | Ship preproduction prototype blocks 73-84 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.03 | S160600 | Ship preproduction prototype blocks 85-96 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
[11 empty] | 0 | 0 | 0
1.03.01.02.04 |  | Order Material for prepro sector 1-12 blocks |  |  |  |  | 2880 |  |  |  | 0 | 0 | 0
1.03.01.02.04 | S161600 | Order W powder prepro sector 1-3 blocks |  | 20 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S161700 | Order W powder prepro sector 4-12 blocks |  | 20 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S162000 | Order fibers prepro sector 1-12 blocks |  | 90 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S163200 | Order screens for prepro sector 1-12 blocks |  | 40 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S164700 | Order epoxy for prepro sector 1-12 blocks |  | 20 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S164900 | Order parts for molds for prepro sector 1-12 blocks |  | 20 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S165700 | Set up factory for prepro sector 1-12 blocks |  | 90 | complete | [5 empty] | 0 | 0 | 0
1.03.01.02.04 | S165800 | Prepare fiber assemblies for prepro sector 1-12 blocks |  | 96 | in progress | past experience | 2880 | 0 | 1 | 0 | 0 | 2880 | 0
[11 empty] | 0 | 0 | 0
1.03.01.02.05 |  | Fabricate EMCal Prepro blocks Sectors 1-12 |  |  |  |  | 2016 |  |  |  | 0 | 0 | 0
1.03.01.02.05 | S165900 | Fabricate EMCAL Prepro blocks sector 1 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166000 | Fabricate EMCAL Prepro blocks sector 2 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166100 | Fabricate EMCAL Prepro blocks sector 3 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166200 | Fabricate EMCAL Prepro blocks sector 4 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166300 | Fabricate EMCAL Prepro blocks sector 5 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166400 | Fabricate EMCAL Prepro blocks sector 6 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166500 | Fabricate EMCAL Prepro blocks sector 7 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166600 | Fabricate EMCAL Prepro blocks sector 8 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166700 | Fabricate EMCAL Prepro blocks sector 9 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166800 | Fabricate EMCAL Prepro blocks sector 10 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S166900 | Fabricate EMCAL Prepro blocks sector 11 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
1.03.01.02.05 | S167000 | Fabricate EMCAL Prepro blocks sector 12 |  | 10 |  | past experience | 168 | 0.1 | 0.05 | 0.85 | 16.8 | 8.4 | 142.8
|  | 8 (weeks)x 2,916 |  | 8 (weeks) x 5 days | [6 empty] | 0 | 0 | 0
1.03.01.02.06 |  | Pack and ship prepro sector 1-12 blocks |  |  |  |  | 240 | 0.3 | 0 | 0.7 | 72 | 0 | 168
1.03.01.02.06 | S167100 | pack and ship prepro sector 1 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S167300 | pack and ship prepro sector 2 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S167500 | pack and ship prepro sector 3 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S167700 | pack and ship prepro sector 4 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S167900 | pack and ship prepro sector 5 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S168100 | pack and ship prepro sector 6 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S168300 | pack and ship prepro sector 7 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S168500 | pack and ship prepro sector 8 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S168700 | pack and ship prepro sector 9 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S168900 | pack and ship prepro sector 10 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S169100 | pack and ship prepro sector 11 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.02.06 | S169300 | pack and ship prepro sector 12 |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
[11 empty] | 0 | 0 | 0
1.03.01.03 |  | EMCAL Final Block Production |  |  |  |  | 16783
1.03.01.03.01 |  | Order Material for EMCal Final Block Production |  |  |  |  | 9497
1.03.01.03.01 | S169500 | Establish EMCal Final Blocks contract with UIUC |  |  |  |  | 10
1.03.01.03.01 | S169600 | Place bid for W powder for final blocks |  | 125 |  |  | 12 | 1 | 0 | 0 | 12 | 0 | 0
1.03.01.03.01 | S170400 | Procure EMCal Fibers for Final Blocks
1.03.01.03.01 | S171200 | Order & deliver epoxy for final blocks |  | 90 |  |  | 16 | 1 | 0 | 0 | 16 | 0 | 0
1.03.01.03.01 | S171900 | Order & deliver mold parts for final blocks |  | 90 | [6 empty] | 0 | 0 | 0
1.03.01.03.01 | S172600 | Set up factory for final blocks |  | 90 |  | past experience | 79 | 0.5 | 0 | 0.5 | 39.5 | 0 | 39.5
|  | Construction of storage shelves |  | #80%
|  | Re-arranging laboratory space |  | #20%
1.03.01.03.01 | S172800 | Prepare fiber assemblies (de-scoped sectors 13-64) |  | 487 |  | past experience | 9360 | 0 | 1 | 0 | 0 | 9360 | 0
|  | 3D fixture production: programming, printing, cleanup |  | #1%
|  | Cutting fibers |  | #10%
|  | Sorting & organizing fiber sets |  | #4%
|  | Actual mesh filling |  | #75%
|  | QA |  | #5%
|  | Preparation of fiber storage (containers and labeling) |  | #1%
|  | Transport to storage |  | #4%
1.03.01.03.01 | S172900 | Readiness and Safety Review for final block production |  | 8 |  |  | 20 | 1 | 0 | 0 | 20 | 0 | 0
1.03.01.03.02 |  | Fabricate final blocks |  |  |  |  | 7020
|  | Mold fabrication |  | 6% |  | XX% refers to overall
|  | Rough cutting |  | #15% |  | #% refers to subcategory
|  | Machine programming |  | #10%
|  | Machining |  | #50%
|  | Post-machine cleanup |  | #15%
|  | Mold assembly |  | #10%
|  | Powder filling |  | 22%
|  | Tungsten QA (weighing) |  | #20%
|  | Filling the mold |  | #70%
|  | QA mold postfill |  | #10%
|  | Potting (epoxy filling) |  | 50%
|  | Epoxy preparation & mixing |  | #10%
|  | Actual potting |  | #70%
|  | Mold removal |  | #10%
|  | QA post-potting (measuring dim's & check powder uniformity) |  | #10%
|  | Mold cleanup |  | 3%
|  | Wiping |  | #30%
|  | Removal of residual powder |  | #40%
|  | Re-assembly of mold |  | #30%
|  | Post-pot machining of blocks |  | 13%
|  | Rough machining (saw & mill) |  | #30%
|  | QA of rough machining |  | #10%
|  | Final machining (diamond) |  | #40%
|  | QA of final machining |  | #20%
|  | QA of optical block properties |  | 5%
|  | Storage of finished modules |  | 1%
1.03.01.03.02 | S173000 | Fabricate final blocks sector 13 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75 | Labor mix to be reviewed after Sectors 1-12
1.03.01.03.02 | S173100 | Fabricate final blocks sector 14 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173200 | Fabricate final blocks sector 15 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173300 | Fabricate final blocks sector 16 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173400 | Fabricate final blocks sector 17 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173500 | Fabricate final blocks sector 18 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173600 | Fabricate final blocks sector 19 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173700 | Fabricate final blocks sector 20 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173800 | Fabricate final blocks sector 21 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S173900 | Fabricate final blocks sector 22 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174000 | Fabricate final blocks sector 23 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174100 | Fabricate final blocks sector 24 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174200 | Fabricate final blocks sector 25 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174300 | Fabricate final blocks sector 26 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174400 | Fabricate final blocks sector 27 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174500 | Fabricate final blocks sector 28 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174600 | Fabricate final blocks sector 29 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174700 | Fabricate final blocks sector 30 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174800 | Fabricate final blocks sector 31 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S174900 | Fabricate final blocks sector 32 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175000 | Fabricate final blocks sector 33 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175100 | Fabricate final blocks sector 34 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175200 | Fabricate final blocks sector 35 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175300 | Fabricate final blocks sector 36 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175400 | Fabricate final blocks sector 37 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175500 | Fabricate final blocks sector 38 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175600 | Fabricate final blocks sector 39 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175700 | Fabricate final blocks sector 40 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175800 | Fabricate final blocks sector 41 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S175900 | Fabricate final blocks sector 42 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176000 | Fabricate final blocks sector 43 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176100 | Fabricate final blocks sector 44 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176200 | Fabricate final blocks sector 45 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176300 | Fabricate final blocks sector 46 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176400 | Fabricate final blocks sector 47 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176500 | Fabricate final blocks sector 48 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176600 | Fabricate final blocks sector 49 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176700 | Fabricate final blocks sector 50 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176800 | Fabricate final blocks sector 51 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S176900 | Fabricate final blocks sector 52 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177000 | Fabricate final blocks sector 53 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177100 | Fabricate final blocks sector 54 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177200 | Fabricate final blocks sector 55 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177300 | Fabricate final blocks sector 56 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177400 | Fabricate final blocks sector 57 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177500 | Fabricate final blocks sector 58 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177600 | Fabricate final blocks sector 59 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177700 | Fabricate final blocks sector 60 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177800 | Fabricate final blocks sector 61 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S177900 | Fabricate final blocks sector 62 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S178000 | Fabricate final blocks sector 63 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.02 | S178100 | Fabricate final blocks sector 64 |  | 6 |  | past experience | 135 | 0.1 | 0.05 | 0.85 | 13.5 | 6.75 | 114.75
1.03.01.03.03 |  | Pack and ship final blocks to BNL |  |  |  |  | 266
1.03.01.03.03 | S178300 | Pack and ship final blocks for sectors 13-16 to BNL |  | 5 |  | past experience | 20 | 0.3 | 0 | 0.7 | 6 | 0 | 14
1.03.01.03.03 | S178400 | Pack and ship final blocks for sectors 17-24 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7
1.03.01.03.03 | S178500 | Pack and ship final blocks for sectors 25-32 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7
1.03.01.03.03 | S178600 | Pack and ship final blocks for sectors 33-40 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7
1.03.01.03.03 | S178700 | Pack and ship final blocks for sectors 40-48 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7
1.03.01.03.03 | S178800 | Pack and ship final blocks for sectors 49-56 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7
1.03.01.03.03 | S178900 | Pack and ship final blocks for sectors 56-64 to BNL |  | 5 |  | past experience | 41 | 0.3 | 0 | 0.7 | 12.3 | 0 | 28.7

## Quotations
Quote for sectors 1-12 fiber | Quote for Sectors 13-64 fiber
We are investigating whether other potentially cheaper powders meet our needs.
We expect to have more information about that in Spring 2018.