## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Hadronic Calorimeter |  | 1.04 |  | Inner HCAL |  | 1.04.01
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Inner HCAL Support Structure & Support Rings |  | 1.04.01 |  | Inner HCAL Support Structure & Support Rings

## I HCAL Support Structure&Rings
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-04
[7 empty] | Prepared By: | John G. Lajoie
[7 empty] | DocNo. (refer Rev. Log) | 142 v3
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Inner HCAL Support Structure & Support Rings |  |  |  | 1.04.01
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO IDENTITY COMPONENTS FOR THE INNER HCAL SUPPORT STRUCTURE, DESIGN AND CONSTRUCT THE MECHANICAL ELEMENTS OF THE SUPPORT STRUCTURE. THIS SUPPORT STRUCTURE REPLACES THE INNER HCAL (DESCOPED) AND PROVIDES A SUPPORT FOR IN EMCAL. THIS ITEM ALSO CONTAINS ALL TASKS WHICH ARE REQUIRED TO DESIGN AND PROCURE THE INNER HCAL SUPPORT RINGS. THESE SUPPORT RINGS SUPPORT THE SUPPORT STRUCTURE AND EMC AND TRANSFER THE LOAD TO THE OUTER HCAL. WORK STATEMENT: PROVIDE INNER HADRONIC CALORIMETER SUPPORT STRUCTURE. PROVIDE INNER HADRONIC CALORIMETER SUPPORT RINGS.
Estimate Type (check all that apply):
| X | Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
Click for detailed summary
Guidelines Used in Developing Estimate
The primary cost element of the work package, the inner HCAL support structure, is costed based on a vendor bid/quote through Iowa State University for the original inner HCAL constructed from aluminum. FEA analysis has shown that this design, used as an uninstrumented frame, is sufficent to support the weight of the EMCAL. The inner HCAL sector mechanical design was highly advanced and a prototype had been constructed in SS310 stainless steel. This cost estimate was based on a highly evolved design of the inner HCAL mechanical structure. The uncertainty for this large item is therefore estimated at 20%. We consider this to be a highly conservative design for a support frame until such time as additional engineering can be completed. All labor in this work package (BNL engineering and design) are costed at current BNL rates with a 20% uncertainty. We justify the uncertainty based on the advanced state of the design and the engineers estimate of the work remaining. The inner HCAL support ring is based on an engineering estimate at with a 40% uncertainty. It is not anticipated that special lifting fixtures should be required.
Details of the Base Estimate (explanation of the Work)
This work item covers the design and manufacture of the support structure to replace the inner HCAL. In addition to the design and manufacture of the inner HCAL structures, this work item also includes the engineering design, review, FEA analysis, and manufacture of the "support rings" that will support the inner HCAL strutures when assembled.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
[5 empty] | Total | Labor Hours
[5 empty] | 978075 | 826
Uncertainty
Uncertainty is estimated at 40% for engineering estimates or for parts where a full design does not exist. Small orders for catalog items are assigned a 20% uncertainty. Engineering design time is assigned a 20% uncertainty based on past experience and the fact that each element includes rounds of review and time for additional redesign.

## Support Structure&Rings Details
Materials
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.04.01 |  | Inner HCAL Support Structure & Support Rings | [6 empty] | 978075
| S199300 | Manufacture Inner HCAL Support Structure | [5 empty] | 928075
|  |  | Manufacture Support Structure |  | 928075 | Pending | Budgetary Quotation
| S200000 | Manufacture Inner HCAL Support Rings | [5 empty] | 50000
|  |  | Manufacture Support Rings |  | 50000 | Pending | Conceptual Design
Labor
WBS |  | Description | Justification | Category | Hours | TOTAL
1.04.01 | S197800 | Design Inner HCAL Support Structure | Engineering Estimate | PROF | 32 | 112 | Complete
|  |  |  | TECH | 80
1.04.01 | S197900 | Internal Review of Inner HCAL Support Structure | Engineering Estimate | SCI | 16 | 48
|  |  |  | PROF | 16
|  |  |  | TECH | 16
1.04.01 | S198000 | Address Issues from Internal Review Support Structure | Engineering Estimate | SCI | 8 | 36
|  |  |  | PROF | 8
|  |  |  | TECH | 20
1.04.01 | S198200 | Manufacture Inner HCAL Support Structure - Provide Requirements to Procurement | Engineering Estimate | SCI | 14 | 74 | All hours combined onto activity S198200; 284 hours total
|  |  |  | PROF | 20
|  |  |  | TECH | 40
1.04.01 | S198800 | Manufacture Inner HCAL Support Structure - Prepare and Send Solicitation | Engineering Estimate | SCI | 7 | 83
|  |  |  | PROF | 28
|  |  |  | TECH | 48
1.04.01 | S199000 | Manufacture Inner HCAL Support Structure - Vendor Selection | Engineering Estimate | SCI | 7 | 127
|  |  |  | PROF | 40
|  |  |  | TECH | 80
1.04.01 | S198300 | Design Inner HCAL Support Rings -FY18 | Engineering Estimate | PROF | 8 | 22 | Complete
|  |  |  | TECH | 14
1.04.01 | S198400 | Design Inner HCAL Support Rings - FY20 | Engineering Estimate | PROF | 24 | 90
|  |  |  | TECH | 66
1.04.01 | S198500 | Internal Review of Inner HCAL Support Rings | Engineering Estimate | SCI | 16 | 48
|  |  |  | PROF | 16
|  |  |  | TECH | 16
1.04.01 | S198600 | Address Issues from Internal Review Support Rings | Engineering Estimate | SCI | 8 | 36
|  |  |  | PROF | 8
|  |  |  | TECH | 20
1.04.01 | S199400 | Manufacture Inner HCAL Support Rings - Provide Requirements to Purchasing | Engineering Estimate | SCI | 14 | 74 | All hours combined into activity S199400; 284 hours total
|  |  |  | PROF | 20
|  |  |  | TECH | 40
1.04.01 | S199500 | Manufacture Inner HCAL Support Rings - Prepare and Send Solicitation | Engineering Estimate | SCI | 7 | 83
|  |  |  | PROF | 28
|  |  |  | TECH | 48
1.04.01 | S199700 | Manufacture Inner HCAL Support Rings - Vendor Selection | Engineering Estimate | SCI | 7 | 127
|  |  |  | PROF | 40
|  |  |  | TECH | 80
|  | Grand Total |  |  | 826 | 826