## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Calorimeter Electronics |  | 1.05 |  | Calorimeter Digitzers |  | 1.05.03
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Calorimeter Digitizer: Preproduction |  | 1.05.03.01 |  | WBS 1.05.03.01 BoE
| Calorimeter Digitizer: Production |  | 1.05.03.02 |  | WBS 1.05.03.02 BoE
| Control Account |  | Description
| Calorimeter Digitizers |  | This Account covers the design and production of the preproduction and production electronics for the calorimeter digitzer system
Note on D17: Eric Mannel:

## WBS1.05.03.01BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-20
[7 empty] | Prepared By: | E.J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 146 v1
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Calorimeter Digitizer: Preproduction Prototype |  |  |  | 1.05.03.01
WBS Dictionary Definition:
This work package covers the final design, layout and fabrication for the 1/2-Crate preproduction protoype, and 7 Crate advanced preproduction digitizer systems needed for the sPHENIX EMCal and HCal detectors. The system consists of the Digitizer and XMIT modules, crate and crate controller and assoicated power supplies.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
System Cost
Guidelines Used in Developing Estimate
The following guidelines were used in the estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) For high value components (FPGAs, ADCs), budgetary estimates were obtained from vendors. 4) Design and production is considered a contractual aggreement with Columbia University, Nevis Labs and includes all labor. 5) Commercial vendors are assumed for all board fabrication and assembly. 5) Costs include a 10% loss due to yield in the assembly and testing stages. 4) Boards are tested prior to delivery to BNL and fully operational. 5) Installation in the sPHENIX IR is part of WBS 1.10
Details of the Base Estimate (explanation of the Work)
This work package covers the preproduction 1/2 Crate and 7 Crate design, layout and fabrication for the digitizers needed for the sPHENIX EMCal and HCal detectors.The design stage includes all design modifications as specified in the design change documents for the preproduction digitizer system. The layout stage includes all modifications to the layout files and producing the necessary design files needed for board fabrication, parts procurement and board assembly. Procurement includes obtaining all quotes, placing orders, tracking orders and receipt of items. Q/A testing covers the testing of individual components prior to deliver for installation. The type and number of modules produced in each stage is summarized in WBS1.5.3SystemCost table.
Cost Summary
|  | Task | Cost Basis |  | Cost
|  | 1/2 Crate Prototype Parts Procurement | Catalogue/Quote/Eng Estimate |  | 12345.4559
|  | 1/2 Crate Protoype Board Fabrication | Catalogue/Quote/Eng Estimate |  | 12500
|  | 1/2 Crate Board Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 50000
|  | 1/2 Crate Total Cost |  |  | 74845.4559 | Prices for 7-crate were in flux
At time of BOE; P6 values here
|  | 7 Crate Parts Procurement | Catalogue/Quote/Eng Estimate |  | 177359.259 | 155534
|  | 7 Crate Board Fabrication | Catalogue/Quote/Eng Estimate |  | 39371.387 | 34485
|  | 7 Crate Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 79858.183 | 69948
|  | 7 Crate Total Cost |  |  | 296588.829 | These are 12% lower than older BOE
Quoted to the left
Design Uncertainty
Parts Procurement and Board Fabrication: 25%
Board Assembly: 40%

## WBS1.05.03.02BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-20
[6 empty] | Prepared By: | E.J. Mannel
[6 empty] | DocNo. (refer Rev. Log) | 146 v1
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
Calorimeter Digitizers: Production |  |  |  | 1.05.03.02
WBS Dictionary Definition:
This work package covers the final design, layout and fabrication for the production digitizers needed for the sPHENIX EMCal and HCal detectors. The EMCal requires a total of 19584 channels, and the HCal requires a total of 1536 channels. The Digitizer System constists of the 64 channel ADC Digitizer boards, XMIT boards, Controller boards, Clock Masters Boards, Trigger Transmitter Modules, Crates, assoicated power supplies, and patch fibers from the digitzer crates to the local patch panel in the 1008 interaction region.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
System Costs
Guidelines Used in Developing Estimate
The following guidelines were used in the estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) For high value components (FPGAs, ADCs), budgetary estimates were obtained from vendors. 4) Design and production is planned as a contractual agreement with Columbia University, Nevis Labs and includes all labor. 5) Commercial vendors are assumed for all board fabrication and assembly. 6) Cost include a 10% loss due to yield in the assembly and testing stages. 7) No spares are included.
Details of the Base Estimate (explanation of the Work)
This work package covers the final design, layout and fabrication for the digitizers needed for the sPHENIX EMCal and HCal detectors.The design stage includes all design modifications as specified in the design change documents for the production digitizer system. The layout stage includes all modifications to the layout files and producing the necessary design files needed for board fabrication, parts procurement and board assembly. Procurement includes obtaining all quotes, placing orders, tracking orders and receipt of items. Q/A testing covers the testing of individual components prior to deliver for installation. The type and number of modules required is summarized in WBS1.05.03SystemCost table.
Cost Summary
|  | Task | Cost Basis |  | Cost
|  | Parts Procurement | Catalogue/Quote/Eng Estimate |  | 584602.7926
|  | Board Fabrication | Catalogue/Quote/Eng Estimate |  | 129048.843
|  | Board Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 199076.887
|  | Total Cost |  |  | 912728.5226
Design Uncertainty
Parts Procurement and Board Fabrication: 25%
Board Assembly and Testing: 40%

## 1.05.03.01Tasks
WBS: 1.05.03.01
Calorimeter Digitizer: Preproduction Prototype
Date: 28-Feb-2017
Last Revision: 31-March-2019
WBS | Activity ID | Task | Task Description | Duration (d) | Scientist | Engineer | Designer | Technician | Trades | Student | Materials and Supplies | %Design Uncertianty | Materials And Supplies + %Design Uncertainty | Risk Code |  | Notes
[5 empty] | Hours | Hours | Hours | Hours | Hours | Hours |  |  |  | Labor | Material
1.05.03.01 | S245500 | Review and write design change specifications for calorimeter digitizer system: 1/2-Crate Prototype | Review prototype design and specify all changes that need to be made to for the 1/2-crate prototype | 40 | [11 empty] | Completed
1.05.03.01 | S245600 | Design Digitzer ADC Boards: 1/2-Crate Prototype | Update schematic as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S245700 | Design Digitizer Controller Board: 1/2-Crate Prototype | Update schematic as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S245800 | Design Digitizer XMIT Board: 1/2-Crate Prototype | Update schematic as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S245900 | Design Digitizer Clock Master: 1/2-Crate Prototype | Update schematic as required based on design change requirements. | 60 | [11 empty] | Completed
1.05.03.01 | S246000 | Design Digitzer Crate: 1/2-Crate Prototype | Update schematic as required based on design change requirements. | 30 | [11 empty] | Completed
1.05.03.01 | S246100 | Layout Digitizer ADC Board: 1/2-Crate Prototype | Update layout as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S246200 | Layout Digitizer Controller Board: 1/2-Crate Prototype | Update layout as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S246300 | Layout Digitzer XMIT Board: 1/2-Crate Prototype | Update layout as required based on design change requirements. | 40 | [11 empty] | Completed
1.05.03.01 | S246400 | Layout Digitizer Clock Master: 1/2-Crate | Update layout as required based on design change requirements. | 151 | [11 empty] | Completed
1.05.03.01 | S246500 | Calorimeter Digitzer System Electrical Safety Review | Provide safety documentation as apprpriate for the 1/2 crate prototype | 10 | [9 empty] | L3 |  | Completed
1.05.03.01 | S246600 | Calorimeter Digitizer Safety Review Complete | Milestone | 0 | [9 empty] | L3 |  | Completed
1.05.03.01 | S246700 | Review Calorimeter Digitizer Safety Review Report | Review safety documentation and implement any changes that may be required for safety. | 15 | [11 empty] | Completed
1.05.03.01 | S246800 | Procure 1/2-Crate Digitizer - Provide Requirements to Procurement | This task covers the setting up of the procurement of components, printed circuit boards, assembly and testing for 7 digitizer boards, 6 Crate controllers (minimum lot order, new designr) and 4 Clock masters (Prototypes) for a 1/2 crate system test. Crates and XMIT boards are from previous prototype productions. | 5 | [11 empty] | Completed
1.05.03.01 | S246900 | Procure 1/2-Crate Digitizer - Prepare & Send Solicitation | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 5 | [11 empty] | Completed
1.05.03.01 | S247000 | Procure 1/2-Crate Digitizer - Vendor Responses | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 10 | [11 empty] | Completed
1.05.03.01 | S247100 | Procure 1/2-Crate Digitizer - Vendor Selection | This tasks covers the time to formalize the contract with Columbia University/Nevis Labs. | 5 | [11 empty] | Completed
1.05.03.01 | S247200 / S247300 | Procure 1/2-Crate Digitizer - Parts - Contract Award(s) | Milestone | 0 | [11 empty] | Completed
1.05.03.01 | S247500 / S247600 | Procure 1/2-Crate Digitizer - Contract/PO - Leadtime for Parts | This task covers the lead time for the parts order placement and delivery of all components needed for assembly | 25
1.05.03.01 | S247700 | Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Parts | This task covers the procurement of components for 7 digitizer boards, 6 Crate controllers (minimum lot order, new designr) and 4 Clock masters (Prototypes) for a 1/2 crate system test. Crates and XMIT boards are from previous prototype productions. | 5 | [6 empty] | 12345.4559 | 0.25 | 15497.8198 |  | M3
1.05.03.01 | S247800 / S247900 | Procure 1/2-Crate Digitizer - Contract/PO - Leadtime for Boards | This task covers the lead time for the printed circuit board order placement and delivery needed for assembly | 25 | [11 empty] | Completed
1.05.03.01 | S248000 | Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Boards | This task covers the full delivery and inspection of al delivered boards | 5 | [6 empty] | 12500 | 0.25 | 16150 |  | M3
1.05.03.01 | S248100 | Procure 1/2-Crate Digitizer - Contract/PO - Leadtime for Assembly & Tests | This task covers the lead time for assembly of boards using outside vendors and intitial testing of boards upon receipt. | 25
1.05.03.01 | S248200 | Procure 1/2-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | This task covers the assembly and testing of 7 digitizer boards, 6 Crate controllers (minimum lot order, new designr) and 4 Clock masters (Prototypes) for a 1/2 crate system test. Crates and XMIT boards are from previous prototype productions. | 5 | [6 empty] | 50000 | 0.4 | 53200 |  | M3
1.05.03.01 | S248300 | Calorimeter Digitizer 1/2-Crate Complete | Milestone | 0
1.05.03.01 | S248400 | Review and write design change specifications for calorimeter digitizer system: 7-Crate Production | Review prototype design and specify all changes that need to be made to for the 7-crate prototype | 5 |  | 28 | [7 empty] | L3
1.05.03.01 | S248500 | Preprod Design Digitzer ADC Boards: 7-Crate Production | Update schematic as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S248600 | Preprod Design Digitizer Controller Board: 7-Crate Production | Update schematic as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S248700 | Preprod Design Digitizer XMIT Board: 7-Crate Production | Update schematic as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S248800 | Preprod Design Digitizer Clock Master: 7-Crate | Update schematic as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S248900 | Preprod Design Digitzer Crate: 7-Crate Production | Update schematic as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S249000 | Preprod Layout Digitizer ADC Board: 7-Crate Production | Update layout as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S249100 | Preprod Layout Digitizer Controller Board: 7-Crate Production | Update layout as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S249200 | Preprod Layout Digitzer XMIT Board: 7-Crate Production | Update layout as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S249300 | Preprod Layout Digitizer Clock Master: 7-Crate | Update layout as required based on design change requirements. | 10 |  | 40 | [7 empty] | L3
1.05.03.01 | S249400 | Preprod Calorimeter Digitzer System Electrical Safety Review | This task cover the preperation of documentation for an electrical safety review of the Digitizer System | 10 |  | 40 | 40 | [6 empty] | L3
1.05.03.01 | S249500 | Preprod Calorimeter Digitizer Safety Review Complete | Milestone | 0
1.05.03.01 | S249600 | Preprod Review Calorimeter Digitizer Safety Review Report | This task covers reviewing the electrical safety review report and implementing any changes recommended. | 5 | 80 | 20 | 20 | [6 empty] | L3
1.05.03.01 | S249800 | Procure 7-Crate Digitizer - Provide Requirements to Procurement | This task covers producing all the documentation for the production of 7 digitizer boards, 6 Crate controllers (minimum lot order, new designr) and 4 Clock masters (Prototypes) for a 1/2 crate system test. Crates and XMIT boards are from previous prototype productions. | 5 |  | 65 | [7 empty] | L3
1.05.03.01 | S250000 | Procure 7-Crate Digitizer - Prepare & Send Solicitation | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 10
1.05.03.01 | S250200 | Procure 7-Crate Digitizer - Vendor Responses | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 20
1.05.03.01 | S250300 | Procure 7-Crate Digitizer - Vendor Selection | This tasks covers the time to formalize the contract with Columbia University/Nevis Labs. | 20
1.05.03.01 | S250400 / S250500 / S250600 | Procure 7-Crate Digitizer - Contract Award(s) | Milestone | 0
1.05.03.01 | S250700 | Procure 7-Crate Digitizer - Contract/PO - Leadtime for Parts | This task covers the lead time for the ording, and receiving of the parts needed for assembly of boards for 7 crates. | 55
1.05.03.01 | S250800 | Procure 7-Crate Digitizer - Contract/PO - Leadtime for Boards | This task covers the lead time for the ording, and receiving of the printed circuit boards needed for assembly of boards for 7 crates. | 55
1.05.03.01 | S250900 | Procure 7-Crate Digitizer - Contract/PO - Leadtime for Assembly & Tests | This task covers the lead time for the parts order placement and delivery of all components needed for assembly | 55 | [12 empty] | BOE Update needed
1.05.03.01 | S251000 | Procure 7-Crate Digitizer - Contract/PO - Delivery Acceptance for Parts | This task covers the lead time for the placement and delivery of all assembled boards for the 7 crate production. | 5 | [6 empty] | 177359.259 | 0.25 | 222114.8737 |  | M3 |  | 155534 | in P6
1.05.03.01 | S251100 | Procure 7-Crate Digitizer - Contract/PO - Delivery Acceptance for Boards | This task covers the receiving and Q/A testing of all the printed circuit boards for a 7 crate production | 5 | [6 empty] | 39371.387 | 0.25 | 49352.8337 |  | M3 |  | 34485 | in P6
1.05.03.01 | S251200 | Procure 7-Crate Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | This task covers the receiving and Q/A testing of all the assembled boards for a 7 crate production | 5 | [6 empty] | 79858.183 | 0.4 | 95001.4562 |  | M3 |  | 69948 | in P6
1.05.03.01 | S251300 | Preprod Calorimeter Digitizer 7-Crate Complete | Milestone | 0
1.5.3.1 |  | Total Cost: |  |  | 80 | 513 | 60 | 0 | 0 | 0 | 371434.2848 |  | 451316.9835
|  |  |  | TOTAL Hours | 653
`

## 1.05.03.02Tasks
WBS: 1.05.03.02
Calorimeter Digitizer: Production Prototype
Date: 28-Feb-2017
Last Revision: 31-March-2019
WBS | Activity ID | Task | Task Description | Duration (d) | Scientist | Engineer | Designer | Technician | Trades | Student | Materials and Supplies | %Design Uncertainty | Materials and Supplies + %Design Uncertainty | Risk Code |  | Notes
[5 empty] | Hours | Hours | Hours | Hours | Hours | Hours |  |  |  | Labor | Material
1.05.03.02 | S251400 | Production Readiness & Safety Review: Calorimeter Digitizers | Full system production readiness review | 5 | 40 | 80 | 40 | [6 empty] | L3
1.05.03.02 | S251500 | Calorimeter Digitizer Readiness & Safety Review Complete | Milestone | 0
1.05.03.02 | S251600 | Review Calorimeter Electronics Readiness & Safety Review Report | Review production readiness review and make any changes required. | 10 |  | 120 | 16 | [6 empty] | L3
1.05.03.02 | S251700 | Procure Production Digitizer - Provide Requirements to Procurement | Provide all the documenation required for a contract with Columbia University/Nevis Labs for the production of 23 crates of digitizer electronics | 20 | 120 | 16 |  | 24 | [5 empty] | L3
1.05.03.02 | S251800 | Procure Production Digitizer - Prepare & Send Solicitation | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 30
1.05.03.02 | S251900 | Procure Production Digitizer - Vendor Responses | This task covers the time required for the generation of an Statement of Work and contract with Columbia University/Nevis Labs. | 20
1.05.03.02 | S252000 | Procure Production Digitizer - Vendor Selection | This tasks covers the time to formalize the contract with Columbia University/Nevis Labs. | 40
1.05.03.02 | S252100 / S252200 / S252300 | Procure Production Digitizer - Contract Award(s) | Milestone | 0
1.05.03.02 | S252400 | Procure Production Digitizer - Contract/PO - Leadtime for Parts | This task cover the procurement for all the parts needed for 23 crates of digitizer electronics needed to complete the system for the EMCal and HCal detectors | 55
1.05.03.02 | S2527000 | Procure Production Digitizer - Contract/PO - Delivery Acceptance for Parts | This task covers the verification that all parts have been received that are required for board assembly | 5 | [6 empty] | 584602.7926 | 0.25 | 732119.6908 |  | M3
1.05.03.02 | S252500 | Procure Production Digitizer - Contract/PO - Leadtime for Boards | This task cover the procurement for all the printed circuit boards needed for 23 crates of digitizer electronics needed to complete the system for the EMCal and HCal detectors | 55
1.05.03.02 | S252800 | Procure Production Digitizer - Contract/PO - Delivery Acceptance for Boards | This task covers the verification that allPCBs have been received that are required for board assembly | 5 | [6 empty] | 129048.843 | 0.25 | 161766.4538 |  | M3
1.05.03.02 | S252600 | Procure Production Digitizer - Contract/PO - Leadtime for Assembly & Tests | This task cover the outside assembly and in house Q/A testing for all the printed circuit boards needed for 23 crates of digitizer electronics needed to complete the system for the EMCal and HCal detectors | 55
1.05.03.02 | S252900 | Procure Production Digitizer - Contract/PO - Delivery Acceptance for Assembly & Tests | This task covers the verification that all boards have been delivered and tested. | 5 | [6 empty] | 199076.887 | 0.4 | 248707.6418 |  | M4
1.05.03.02 | S253000 | Calorimeter Digitizer Production Complete | Milestone | 0
1.05.03.02 | S253100 | Calorimeter Electronics Complete | Milestone | 0
1.5.3.2 |  | Total Cost: |  |  | 160 | 216 | 56 | 24 | 0 | 0 | 912728.5226 |  | 1142593.7864
|  |  |  | TOTAL Hours | 456
`

## WBS1.05.03SystemCost
sPHENIX WBS 1.5.3: System Cost
Date: 02-Feb-2018
Last Revision: 12-April-2018
DESCRIPTION |  | MANUFACTURER | QUANT. | Cost Basis | Unit Cost | NRE | Total Cost | Total Cost + 10% | %Design Uncertainty | Total Cost + %Design Uncertainty | Notes:
1/2 Crate
| Digitizer ADC Board-Parts | Nevis | 7 | BOM: Catalog/Quote | 1354.8471 |  | 9483.9297 | 10432.3227 | 0.25 | 13040.4033
| Digitizer ADC Board-PC Board Fab | Nevis | 1 | BOM: Catalog/Quote | 5500 | 500 | 6000 | 6000 | 0.25 | 7500 | Lot charge for board fabrication
| Digitizer ADC Board-Assembly | Nevis | 1 | BOM: Catalog/Quote | 2150 | 850 | 3000 | 3000 | 0.4 | 4200 | Lot charge for board assembly
| Digitizer ADC Board Total | [5 empty] | 18483.9297 | 19432.3227 |  | 24740.4033
| Digitizer XMIT Board-Part | Nevis | 0 | BOM: Catalog/Quote | 192.035 |  | 0 | 0 | 0.25 | 0
| Digitizer XMIT Board-PC Board Fab | Nevis | 0 | BOM: Catalog/Quote | 308.61 | 500 | 0 | 0 | 0.25 | 0
| Digitizer XMIT Board-Assembly | Nevis | 0 | BOM: Catalog/Quote | 95 | 850 | 0 | 0 | 0.4 | 0
| Digitzer XMIT Board Total | [5 empty] | 0 | 0 |  | 0
| Digitizer Crate Controller-Parts | Nevis | 6 | BOM: Catalog/Quote | 223.202 |  | 1339.212 | 1473.1332 | 0.25 | 1841.4165
| Digitizer Crate Controller- PC Board Fab | Nevis | 6 | BOM: Catalog/Quote | 2500 | 500 | 3000 | 3000 | 0.25 | 3750 | Lot charge for board fabrication
| Digitizer Crate Controller-Assembly | Nevis | 6 | BOM: Catalog/Quote | 1650 | 850 | 2500 | 2500 | 0.4 | 3500 | Lot charge for board assembly
| Digitizer Crate Controller Total | [5 empty] | 6839.212 | 6973.1332 |  | 9091.4165
| Digitzer Clock Masters-Parts | Nevis | 4 | BOM: Catalog/Quote | 100 |  | 400 | 440 | 0.4 | 616
| Digitzer Clock Masters-PC Board Fab | Nevis | 4 | BOM: Catalog/Quote | 3500 |  | 3500 | 3500 | 0.4 | 4900 | Lot charge for board fabrication
| Digitzer Clock Masters-Assembly | Nevis | 4 | BOM: Catalog/Quote | 2500 |  | 2500 | 2500 | 0.4 | 3500 | Lot charge for board assembly
| Digitizer Clock Master Total | [5 empty] | 6400 | 6440 |  | 9016
| Total Material and Assembly Cost: | [5 empty] | 31723.1417 | 32845.4559 |  | 42847.8198
| Total Part Cost | [5 empty] | 11223.1417 | 12345.4559 |  | 15497.8198
| Total PC BoardFrabrication Costs | [5 empty] | 12500 | 12500 |  | 16150
| Total Board Assembly Cost | [5 empty] | 8000 | 8000 |  | 11200
| Production Fees | [5 empty] | 42000 | 42000 |  | 42000
| Total With Fees: 1/2 Crate Production | [5 empty] | 73723.1417 | 74845.4559 |  | 84847.8198
7 Crate Production
| Digitizer ADC Board-Parts | Nevis | 84 | BOM: Catalog/Quote | 1354.8471 |  | 113807.1564 | 125187.872 | 0.25 | 156484.8401
| Digitizer ADC Board-Fab | Nevis | 84 | BOM: Catalog/Quote | 256.88 |  | 21577.92 | 23735.712 | 0.25 | 29669.64
| Digitizer ADC Board-Assembly | Nevis | 84 | BOM: Catalog/Quote | 262.25 |  | 22029 | 24231.9 | 0.4 | 33924.66
| Digitizer ADC Board Total |  |  |  | 1873.9771 |  | 157414.0764 | 173155.484 |  | 220079.1401
| Digitizer XMIT Board-Part | Nevis | 28 | BOM: Catalog/Quote | 192.035 |  | 5376.9811 | 5914.6792 | 0.25 | 7393.349
| Digitizer XMIT Board-Fab | Nevis | 28 | BOM: Catalog/Quote | 308.61 |  | 8641.08 | 9505.188 | 0.25 | 11881.485
| Digitizer XMIT Board-Assembly | Nevis | 28 | BOM: Catalog/Quote | 95 |  | 2660 | 2926 | 0.4 | 4096.4
| Digitzer XMIT Board Total | [5 empty] | 16678.0611 | 18345.8672 |  | 23371.234
| Digitizer Crate Controller-Parts | Nevis | 7 | BOM: Catalog/Quote | 223.202 |  | 1562.414 | 1718.6554 | 0.25 | 2148.3193
| Digitizer Crate Controller-Fab | Nevis | 7 | BOM: Catalog/Quote | 87.1 |  | 609.7 | 670.67 | 0.25 | 838.3375
| Digitizer Crate Controller-Assembly | Nevis | 7 | BOM: Catalog/Quote | 376.79 |  | 2637.53 | 2901.283 | 0.4 | 4061.7962
| Digitizer Crate Controller Total | [5 empty] | 4809.644 | 5290.6084 |  | 7048.453
| Digitzer Clock Masters-Parts | Nevis | 2 | Engineering Estimate | 100 |  | 200 | 220 | 0.25 | 275
| Digitzer Clock Masters-Fab | Nevis | 2 | Engineering Estimate | 500 |  | 1000 | 1100 | 0.25 | 1375
| Digitzer Clock Masters-Assembly | Nevis | 2 | Engineering Estimate | 500 |  | 1000 | 1100 | 0.4 | 1540
| Digitizer Clock Master Total | [5 empty] | 2200 | 2420 |  | 3190
| Digitzer Trigger Interface-Parts | Nevis | 84 | Engineering Estimate | 30 |  | 2520 | 2772 | 0.4 | 3880.8
| Digitzer Trigger Interface-Fab | Nevis | 84 | Engineering Estimate | 10 |  | 840 | 924 | 0.4 | 1293.6
| Digitzer Trigger Interface-Assembly | Nevis | 84 | Engineering Estimate | 10 |  | 840 | 924 | 0.4 | 1293.6
| Digitizer Trigger InterfaceTotal | [5 empty] | 4200 | 4620 |  | 6468
| Digitizer Backplane-Parts | Nevis | 7 | BOM: Catalog/Quote | 474.07 |  | 3318.49 | 3650.339 | 0.25 | 4562.9237
| Digitizer Backplane-Fab | Nevis | 7 | BOM: Catalog/Quote | 387.6 |  | 2713.2 | 2984.52 | 0.25 | 3730.65
| Digitizer Backplane-Assembly | Nevis | 7 | BOM: Catalog/Quote | 640 |  | 4480 | 4928 | 0.4 | 6899.2
| Digitizer Backplane Total | [5 empty] | 10511.69 | 11562.859 |  | 15192.7738
| Digitizer JSEB2 Boards-Parts | Nevis | 7 | BOM: Catalog/Quote | 514.7598 |  | 3603.3185 | 3963.6503 | 0.25 | 4954.5629
| Digitizer JSEB2 Boards-Fab | Nevis | 7 | BOM: Catalog/Quote | 58.61 |  | 410.27 | 451.297 | 0.25 | 564.1213
| Digitizer JSEB2 Boards-Assembly | Nevis | 7 | BOM: Catalog/Quote | 110 |  | 770 | 847 | 0.4 | 1185.8
| Digitizer JSEB2 Boards Total | [5 empty] | 4783.5885 | 5261.9473 |  | 6704.4841
| Digitizer Crates | Nevis | 7 | BOM: Catalog/Quote | 1703 |  | 11921 | 13113.1 | 0.25 | 16391.375
| Total Material and Assembly Cost: | [5 empty] | 212518.06 | 233769.866 |  | 291977.4599
| Total Part Cost | [5 empty] | 142309.36 | 156540.296 |  | 196091.17
| Total Fabrication Costs | [5 empty] | 35792.17 | 39371.387 |  | 49352.8337
| Total Assembly Cost | [5 empty] | 34416.53 | 37858.183 |  | 53001.4562
| Production Fees | [5 empty] | 42000 | 42000 |  | 42000
| Production Total With Fees | [5 empty] | 254518.06 | 275769.866 |  | 340445.4599
| Power Systems (1 per rack) | VICOR | 2 |  | 7500 |  | 15000 | 16500 | 0.25 | 20625
| Fibers- Digitizer to Patch panel IR |  | 397 | Catalog | 9.89 |  | 3926.33 | 4318.963 | 0.25 | 5398.7038
| Total: Non-Nevis Production Costs | [5 empty] | 18926.33 | 20818.963 |  | 26023.7038
| Total System Cost: 7 Crate Production | [5 empty] | 273444.39 | 296588.829 |  | 366469.1637
Final Production
| Digitizer ADC Board-Parts | Nevis | 276 | BOM: Catalog/Quote | 1354.8471 |  | 373937.7996 | 411331.5796 | 0.25 | 514164.4745
| Digitizer ADC Board-Fab | Nevis | 276 | BOM: Catalog/Quote | 256.88 |  | 70898.88 | 77988.768 | 0.25 | 97485.96
| Digitizer ADC Board-Assembly | Nevis | 276 | BOM: Catalog/Quote | 262.25 |  | 72381 | 79619.1 | 0.4 | 111466.74
| Digitizer ADC Board Total |  |  |  | 1873.9771 |  | 517217.6796 | 568939.4476 |  | 723117.1745
| Digitizer XMIT Board-Part | Nevis | 92 | BOM: Catalog/Quote | 192.035 |  | 17667.2237 | 19433.946 | 0.25 | 24292.4326
| Digitizer XMIT Board-Fab | Nevis | 92 | BOM: Catalog/Quote | 308.61 |  | 28392.12 | 31231.332 | 0.25 | 39039.165
| Digitizer XMIT Board-Assembly | Nevis | 92 | BOM: Catalog/Quote | 95 |  | 8740 | 9614 | 0.4 | 13459.6
| Digitzer XMIT Board Total | [5 empty] | 54799.3437 | 60279.278 |  | 76791.1976
| Digitizer Crate Controller-Parts | Nevis | 23 | BOM: Catalog/Quote | 223.202 |  | 5133.646 | 5647.0106 | 0.25 | 7058.7633
| Digitizer Crate Controller-Fab | Nevis | 23 | BOM: Catalog/Quote | 87.1 |  | 2003.3 | 2203.63 | 0.25 | 2754.5375
| Digitizer Crate Controller-Assembly | Nevis | 23 | BOM: Catalog/Quote | 376.79 |  | 8666.17 | 9532.787 | 0.4 | 13345.9018
| Digitizer Crate Controller Total | [5 empty] | 15803.116 | 17383.4276 |  | 23159.2026
| Digitzer Clock Masters-Parts | Nevis | 6 | Engineering Estimate | 100 |  | 600 | 660 | 0.25 | 825
| Digitzer Clock Masters-Fab | Nevis | 6 | Engineering Estimate | 500 |  | 3000 | 3300 | 0.25 | 4125 | Lot charge for board fabrication
| Digitzer Clock Masters-Assembly | Nevis | 6 | Engineering Estimate | 500 |  | 3000 | 3300 | 0.4 | 4620 | Lot charge for board assembly
| Digitizer Clock Master Total | [5 empty] | 6600 | 7260 |  | 9570
| Digitzer Trigger Interface-Parts | Nevis | 276 | Engineering Estimate | 30 |  | 8280 | 9108 | 0.4 | 12751.2
| Digitzer Trigger Interface-Fab | Nevis | 276 | Engineering Estimate | 10 |  | 2760 | 3036 | 0.4 | 4250.4
| Digitzer Trigger Interface-Assembly | Nevis | 276 | Engineering Estimate | 10 |  | 2760 | 3036 | 0.4 | 4250.4
| Digitizer Trigger InterfaceTotal | [5 empty] | 13800 | 15180 |  | 21252
| Digitizer Backplaner-Parts | Nevis | 23 | BOM: Catalog/Quote | 474.07 |  | 10903.61 | 11993.971 | 0.25 | 14992.4638
| Digitizer Backplane-Fab | Nevis | 23 | BOM: Catalog/Quote | 387.6 |  | 8914.8 | 9806.28 | 0.25 | 12257.85
| Digitizer Backplane-Assembly | Nevis | 23 | BOM: Catalog/Quote | 640 |  | 14720 | 16192 | 0.4 | 22668.8
| Digitizer Backplane Total | [5 empty] | 34538.41 | 37992.251 |  | 49919.1138
| Digitizer JSEB2 Boards-Parts | Nevis | 23 | BOM: Catalog/Quote | 514.7598 |  | 11839.4749 | 13023.4224 | 0.25 | 16279.278
| Digitizer JSEB2 Boards-Fab | Nevis | 23 | BOM: Catalog/Quote | 58.61 |  | 1348.03 | 1482.833 | 0.25 | 1853.5413
| Digitizer JSEB2 Boards-Assembly | Nevis | 23 | BOM: Catalog/Quote | 110 |  | 2530 | 2783 | 0.4 | 3896.2
| Digitizer JSEB2 Boards Total | [5 empty] | 15717.5049 | 17289.2554 |  | 22029.0193
| Digitizer Crates-Parts | Nevis | 23 | BOM: Catalog/Quote | 1703 |  | 39169 | 43085.9 | 0.25 | 53857.375
| Total Material and Assembly Cost: | [5 empty] | 697645.0542 | 767409.5596 |  | 958443.0826
| Total Part Cost | [5 empty] | 467530.7542 | 514283.8296 |  | 644220.9871
| Total Fabrication Costs | [5 empty] | 117317.13 | 129048.843 |  | 161766.4538
| Total Assembly Cost | [5 empty] | 112797.17 | 124076.887 |  | 173707.6418
| Assembly Fees | [5 empty] | 75000 | 75000 |  | 75000
| Production Total With Fees | [5 empty] | 772645.0542 | 842409.5596 |  | 1054695.0826
| Power Systems (1 per rack) | VICOR | 8 |  | 7500 |  | 60000 | 66000 | 0.25 | 82500
| Fibers- Digitizer to Patch panel IR | FIBERTRONICS | 397 | Catalog | 9.89 |  | 3926.33 | 4318.963 | 0.25 | 5398.7038
| Total: Non-Nevis Production Costs | [5 empty] | 63926.33 | 70318.963 |  | 87898.7038
| Total System Cost: Final Production | [5 empty] | 836571.3842 | 912728.5226 |  | 1142593.7864

## DigitizerADCBoards
Sphenix WBS 1.5.2: Digitizer ADC Boards
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Unit Cost | Module Cost
PC BOARD | VIASYSTEMS | Sphenix_cal_ADC | 1 | 256.88 | 256.88
SETUP | VIASYSTEMS | Sphenix_cal_ADC | 1 | 500
ETEST | VIASYSTEMS | Sphenix_cal_ADC | 1 | 0 | 0
RESISTOR - 0402 - 100 OHM - 0.1% | SUSUMU | RG1005P-101-B-T5 | 128 | 0.01 | 1.28
RESISTOR - 0402 - 1K OHM - 0.1% | PANASONIC | ERA-2AEB102X | 128 | 0.01 | 1.28
RESISTOR - 0402 - RB - 6.49K OHM - 0.1% | PANASONIC | ERA-2AEB6491X | 128 | 0.055 | 7.04
RESISTOR - 0402 - RF - 1K OHM - 0.1% | PANASONIC | ERA-2AEB102X | 128 | 0.055 | 7.04
RESISTOR - 0402 - RG - 1K OHM - 0.1% | PANASONIC | ERA-2AEB102X | 128 | 0.055 | 7.04
ALUMINUM CAPACITOR - 33 MFD 63V | VISHAY | MAL215097812E3 | 1 | 0.54 | 0.54
DIODE | VISHAY | SA24A-E3/54 | 3 | 0.088 | 0.264
DIODE | VISHAY | SA24A-E3/54 | 1 | 0.088 | 0.088
HI SPEED DIFFERENTIAL AMPLIFIER | ANALOG DEVICES | AD8132ARMZ | 64 | 2.1 | 134.4
Octal, 14-Bit, 40/65 MSPS, Serial LVDS, 1.8 V Analog-to-Digital Converter | ANALOG DEVICES | AD9257BCPZ-65 | 8 | 84 | 672
1.8 V, 6 LVDS/12 CMOS Outputs Low Power Clock Fanout Buffer | ANALOG DEVICES | ADCLK846BCPZ | 2 | 4.9 | 9.8
1A, LOW DROPOUT CMOS LINEAR REGULATOR | ANALOG DEVICES | ADP1706ARDZ-1.5R7 | 1 | 2.672 | 2.672
FPGA - Field Programmable Gate Array FPGA - Arria V GX 11320 LABs 544 IOs | ALTERA | 5AGXBB1D4F35C4N | 1 | 322.2 | 322.2
FERRITE BEAD SM 220 OHM 200MA 0402 | MURATA | BLM15EG221SN1 | 2 | 0.06 | 0.12
FERRITE BEAD - 0805 - 330 OHM | MURATA | BLM21PG331SN1D | 2 | 0.02 | 0.04
CAPACITOR - 0402 - .001 MFD (1nf) - 50V | CALCHIP | GMC04X7R102K50NT | 2 | 0.025 | 0.05
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K25NT | 64 | 0.01 | 0.64
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | MURATA | GRM155R71C104KA88D | 64 | 0.0014 | 0.0896
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K25NT | 24 | 0.01 | 0.24
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K25NT | 24 | 0.01 | 0.24
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | MURATA | GRM155R71C104KA88D | 258 | 0.0014 | 0.3612
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | MURATA | GRM155R71C104KA88D | 89 | 0.0014 | 0.1246
CAPACITOR - 0402 - 100 pf - 50V | MURATA | GCM1555C1H101JA16D | 1 | 0.006 | 0.006
CAPACITOR - 0402 - 1 pf - 50V | MURATA | GRM1555C1H1R0BA01D | 128 | 0.007 | 0.896
CAPACITOR - 0402 - Cx - 1pf - 50V | MURATA | GRM1555C1H1R0BA01D | 64 | 0.007 | 0.448
CAPACITOR - 0603 - 1 MFD - 10V | CALCHIP | GMC10Y5V105Z10NT | 8 | 0.01 | 0.08
CAPACITOR - 0805 - 10 MFD - 16V | CALCHIP | GMC21X5R106K16NT | 9 | 0.055 | 0.495
CAPACITOR - 0805 - 2.2 MFD - 16V | PANASONIC | ECJ-2FB1C225K | 2 | 0.08 | 0.16
CAPACITOR - 1206 - 4.7 MFD - 10V | CALCHIP | GMC31X7R475K10NT | 1 | 0.11 | 0.11
CAPACITOR - 1210 - 100 MFD - 6.3 V - X5R | MURATA | GRM32ER60J107ME20L | 9 | 0.17 | 1.53
CAPACITOR - 1210 - 10 MFD, 50 VOLT, X5R | TAIYO YUDEN | UMK325BJ106KM-T | 2 | 0.191 | 0.382
CAPACITOR - 1210 - 10 MFD, 50 VOLT, X5R | TAIYO YUDEN | UMK325BJ106KM-T | 1 | 0.191 | 0.191
LOW VALUE CHIP RESISTOR - 0.1 OHM | BOURNS | CRL1206-F-W-R100-E | 1 | 0.042 | 0.042
3.125 Gbps LVDS Buffer with Transmit Pre-Emphasis and Receive Equalization | TEXAS INSTRUMENTS | DS25BR100TSD/NOPB | 1 | 4.1 | 4.1
3V LVDS Single CMOS Differential Line Receiver | NATIONAL | DS90LV012ATMF/NOPB | 1 | 0.65 | 0.65
QUAD RECEIVER | NATIONAL | DS90LV048ATMTC/NOPB | 3 | 1.71 | 5.13
QUAD SERIAL CONFIGURATION DEVICE | ALTERA | EPCQ256SI16N | 1 | 30 | 30
MAX II - CPLD DEVICE | ALTERA | EPM240F100C5N | 1 | 5.5 | 5.5
Right Angle Female Connectors For Daughter Cards: Type C - Press fit 55 pins | ERNI | 354865 | 2 | 1.42 | 2.84
RIGHT ANGLE MALE CONNECTOR FOR DAUGHTER CARD: TYPE C | ERNI | 923830 | 4 | 9.66 | 38.64
Right Angle Male Power Modules For Daughter Cards - 3 pins | ERNI | 114402 | 1 | 2.54 | 2.54
ERMET POWER_6POLE | ERNI | 254963 | 1 | 5.41 | 5.41
ERMET - ZD 10 ROW | ERNI | 973046 | 1 | 4.87 | 4.87
SOCKET PINS | AMP/TYCO | 2-5331272-7 | 8 | 0.236 | 1.888
FUSE - 4 AMP - U115 | LITTLEFUSE | 251004 | 1 | 0.16 | 0.16
FUSE - 2 AMP - U0100, U116, U117 | LITTLEFUSE | 251002 | 3 | 0.217 | 0.651
HOLE_PANEL |  |  | 3 | 0 | 0
JTAG | SAMTEC | TSW-105-07-G-D | 3 | 0.35 | 1.05
LED | LUMEX | SSL-LX2473ID | 2 | 0.182 | 0.364
POWER SUPPLY SEQUENCER | TEXAS INSTRUMENTS | LM3880MFE-1AB/NOPB | 1 | 0.95 | 0.95
NEGATIVE 3A REGULATOR - -2.5C - -25V | LINEAR TECHNOLOGY | LT1185CQ#PBF | 1 | 4.01 | 4.01
Dual, 26VIN, 4A DC/DC uModule Regulator | LINEAR TECHNOLOGY | LTM4619EV#PBF | 1 | 16.75 | 16.75
Ultralow Noise EMC 36VIN, 3A DC/DC μModule Regulator | LINEAR TECHNOLOGY | LTM8033EV#PBF | 1 | 11.95 | 11.95
3.3V, 1.5A, UCAP, LDO | MICREL | MIC37151-3.3WR | 1 | 1.95 | 1.79
3.3V, 1.5A, UCAP, LDO | MICREL | MIC37301-1.8WR | 2 | 2.01 | 4.02
3.3V, 1.5A, UCAP, LDO | MICREL | MIC37302WR | 1 | 2.45 | 2.45
ULTRA LOW QUIESCENT CURRENT 150 mA uCAP LOW DROPOUT REGULATOR | MICREL | MIC5225-3.3YM5 | 1 | 0.45 | 0.45
DIODE | FAIRCHILD | MMBD 914LT1 | 3 | 0.039 | 0.117
AMPLIFIER | MOTOROLA | MMBT 3906T | 2 | 0.033 | 0.066
3.3V 1:4 ANYLEVEL DIFFERENTIAL INPUT TO LVDS FANOUT BUFFER TRANSLATOR | ON SEMICONDUCTOR | NB6N14SMNG | 1 | 5.26 | 5.26
RESISTOR - 0402 - 10K OHM | CALCHIP | RM04F1002CT | 2 | 0.01 | 0.02
RESISTOR - 0402 - 1K OHM - 0.1% | PANASONIC | ERA-2AEB102X | 1 | 0.01 | 0.01
RESISTOR - 0402 - 100 OHM - 0.1% | SUSUMU | RG1005P-101-B-T5 | 11 | 0.069 | 0.759
RESISTOR - 0402 - 10K OHM | CALCHIP | RM04F1002CT | 22 | 0.01 | 0.22
RESISTOR - 0402 - 1K OHM - 0.1% | PANASONIC | ERA-2AEB102X | 2 | 0.01 | 0.02
RESISTOR - 0402 - 24.9K OHM | CALCHIP | RM04F2492CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 2K OHM - 0.1% | PANASONIC | ERA-2AEB202X | 7 | 0.055 | 0.385
RESISTOR - 0402 - 3.01K OHM | PANASONIC | ERJ-2RKF3011X | 1 | 0.035 | 0.035
RESISTOR - 0402 OHM - 402 OHM | CALCHIP | RM04F4020CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 4 | 0.01 | 0.04
RESISTOR - 0402 - 60.4 OHM | CALCHIP | RM04F60R4CT | 4 | 0.01 | 0.04
RESISTOR - 0402 - 7.5K OHM | PANASONIC | ERJ-2RKF7501X | 1 | 0.0027 | 0.0027
RESISTOR - 0603 - 54.9 OHM - 0.1% | PANASONIC | ERA-3AEB54R9V | 128 | 0.039 | 4.992
RESISTOR - 0805 - 0 OHM | CALCHIP | RM10J000CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 1.21K OHM | CALCHIP | RM10F1211CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 124K OHM | PANASONIC | ERJ-6ENF1243V | 1 | 0.005 | 0.005
RESISTOR - 0805 - 130 OHM | CALCHIP | RM10F1300CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 162K OHM | CALCHIP | RM10F1623CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 2.21K OHM | CALCHIP | RM10F2211CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 2.37K OHM | PANASONIC | ERJ-6ENF2371V | 1 | 0.005 | 0.005
RESISTOR - 0805 - 200 OHM | CALCHIP | RM10F2000CT | 4 | 0.01 | 0.04
RESISTOR - 0805 - 28K OHM | CALCHIP | RM10F2802CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 49.9 OHM | CALCHIP | RM10F49R9CT | 2 | 0.01 | 0.02
RESISTOR - 0805 - 93.1K OHM | ROHM | MCR10EZPF9312 | 1 | 0.008 | 0.008
2Gbps LVDS/LVPECL/CML to LVDS Repeater/Translator | TEXAS INSTRUMENTS | SN65LVDS100D | 1 | 2.83 | 2.83
MULTIPOINT LVDS QUAD DIFFERENTIAL LINE DRIVER | TEXAS INSTRUMENTS | SN65MLVD047PW | 3 | 2.23 | 6.69
SINGLE BUS BUFFER GATE WITH 3 STATE OUTPUT | TEXAS INSTRUMENTS | SN74AHC1G125DCKR | 1 | 0.484 | 0.484
DIODE | FAIRCHILD | SS14 | 2 | 0.066 | 0.132
CAPACITOR - 10 MFD - 35V - D Size | NEMCO | PCT10/35D | 1 | 0.42 | 0.42
TP |  |  | 3 | 0 | 0
Low Quiescent Current, Programmable-Delay Supervisory Circuit | TEXAS INSTRUMENTS | TPS3808G01DBVR | 1 | 1.24 | 1.24
OSC MEMS BLANK 5.0X3.2 LVDS - 120 MHz - U27 | MICREL | DSC8123BI2 | 1 | 6.437 | 6.437
OSC MEMS BLANK 5.0X3.2 LVDS - 80 MHz - U18 | MICREL | DSC8123BI2 | 1 | 6.437 | 6.437
ASSEMBLY OF APHENIX_CAL_ADC (APM14_ADC) | EDMOND MARKS TECHNOLOGIES | SPHENIX_CAL_ADC | 1 | 262.25 | 262.25
SOLDER PASTE STENCIL | APPLICAD | SPHENIX_CAL_XMITTER3 | 2 | 300
ONE-TIME MACHINE PROGRAMMING AND DOCUMENTATION | APPLICAD | SPHENIX_CAL_XMITTER3 | 1 | 250
SET-UP FOR SMT ASSEMBLY | APPLICAD | SPHENIX_CAL_XMITTER3 | 1 | 300
TOTAL |  |  |  |  | 1873.9771
Total Parts Cost: |  |  |  |  | 1354.8471
Total Board Fabrication Cost: |  |  |  |  | 256.88
Total Board Assembly Cost: |  |  |  |  | 262.25
Total Board Cost: |  |  |  |  | 1873.9771
Total Board Fab NRE |  |  |  |  | 500
Total Assembly NRE |  |  |  |  | 850
AD9257BCPZ-65 Quote:

## DigitizerXMITBoards
Sphenix WBS 1.5.3: Digitzer XMIT Boards
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | UNIT | MODULE
|  |  |  | COST | COST
PC BOARD | ELECTROTEK | cal_xmitter_3 | 1 | 308.61 | 308.61
TOOLING | ELECTROTEK | cal_xmitter_3 | 1 | 500 | 0
TEST FIXTURE | ELECTROTEK | cal_xmitter_3 | 1 | 0 | 0
CAP POLYMER 39UF 20% 35V SMD | PANASONIC | 35SVPF39M | 1 | 1.2068 | 1.2068
DIODE | VISHAY | SA24A-E3/54 | 1 | 0.0805 | 0.0805
1A, LOW DROPOUT CMOS LINEAR REGULATOR | ANALOG DEVICES | ADP1706ARDZ-2.5R7 | 1 | 1.5 | 1.5
FERRITE BEAD SM 220 OHM 200MA 0402 | MURATA | BLM15EG221SN1 | 4 | 0.06 | 0.24
FERRITE BEAD - 0805 - 330 OHM | MURATA | BLM21PG331SN1D | 2 | 0.035 | 0.07
CAPACITOR - 0402 - .001 MFD (1nf) - 50V | CALCHIP | GMC04X7R102K50NT | 1 | 0.03 | 0.03
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K50NT | 8 | 0.03 | 0.24
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K50NT | 2 | 0.03 | 0.06
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | CALCHIP | GMC04X7R104K16NT | 38 | 0.02 | 0.76
CAPACITOR - 0603 - 10 MFD - 10V - 6.3 V | MURATA | GRM188R60J106ME47J | 4 | 0.067 | 0.268
CAPACITOR - 0805 - 0.22 MFD - 50V | KEMET | C0805C224K5RACTU | 2 | 0.02232 | 0.04464
CAPACITOR - 0805 - 4.7 MFD - 25V | CALCHIP | GMC21X7R475K25NT | 1 | 0.043 | 0.043
CAPACITOR - 1206 - 10 MFD - 25 VDC - X5R | MURATA | GRM31CR61E106KA12L | 1 | 0.09 | 0.09
CAPACITOR - 1210 - 100 MFD - 6.3 V - X5R | MURATA | GRM32ER60J107ME20L | 2 | 0.34 | 0.68
3V LVDS Single CMOS Differential Line Receiver | NATIONAL | DS90LV012ATMF/NOPB | 1 | 0.65 | 0.65
QUAD RECEIVER | NATIONAL | DS90LV048ATMTC/NOPB | 3 | 1.71 | 5.13
ARRIA GX | ALTERA | EP4CGX22CF19C7N | 1 | 50 | 50
16 MBIT SERIAL CONFIG | ALTERA | EPCS16SI8N | 1 | 15.81 | 15.81
Right Angle Female Connectors For Daughter Cards: Type C - Press fit 55 pins | ERNI | 354865 | 2 | 1.42 | 2.84
Right Angle Male Power Modules For Daughter Cards - 3 pins | ERNI | 114402 | 1 | 2.54 | 2.54
ERMET - ZD 10 ROW | ERNI | 973046 | 1 | 4.87 | 4.87
FUSE HOLDER | AMP/TYCO | 2-5331272-7 | 2 | 0.236 | 0.472
FUSE - 1 AMP | LITTLEFUSE | 251001 | 1 | 0.25 | 0.25
TRANSCEIVER | AVAGO | AFBR-5921ALZ | 1 | 29.88 | 29.88
HOLE_PANEL |  |  | 2 | 0 | 0
JTAG | SAMTEC | TSW-105-07-G-D | 1 | 0.35 | 0.35
LED | LUMEX | SSL-LX2473ID | 2 | 0.182 | 0.364
CHIP COILS FOR HIGH FREQUENCY MONOLITHIC TYPE | MURATA | LQG15HN9N1J02D | 1 | 0.015 | 0.015
2A, 36V DC/DC STEP-DOWN uMODULE REGULATOR | LINEAR TECHNOLOGY | LTM8023EV#PBF | 2 | 8.14 | 16.28
Differential LVPECL to LVTTL Translator | ON SEMICONDUCTOR | MC100EPT21DTG | 2 | 4.86 | 9.72
LVPECL CLOCK OSCILLATOR - OSC XO 80.000MHZ LVPECL SMD | CONNOR WINFIELD | P123-80.0M | 1 | 20 | 20
RESISTOR - 0402 - 10K OHM | CALCHIP | RM04F1002CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 10K OHM | CALCHIP | RM04F1002CT | 10 | 0.01 | 0.1
RESISTOR - 0402 - 130 OHM | CALCHIP | RM04F1300CT | 2 | 0.01 | 0.02
RESISTOR - 0402 - 15K OHM | PANASONIC | ERJ-2RKF1502X | 2 | 0.003 | 0.006
RESISTOR - 0402 - 1K OHM | CALCHIP | RM04F1001CT | 3 | 0.01 | 0.03
RESISTOR - 0402 - 200 OHM | CALCHIP | RM04F2000CT | 4 | 0.01 | 0.04
RESISTOR - 0402 - 24.9 OHM | PANASONIC | ERJ2RKF24R9X | 1 | 0.0027 | 0.0027
RESISTOR - 0402 - 2K OHM | CALCHIP | RM04F2001CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 9 | 0.01 | 0.09
RESISTOR - 0402 - 60.4 OHM | CALCHIP | RM04F60R4CT | 4 | 0.01 | 0.04
RESISTOR - 0402 - 806 OHM | CALCHIP | RM04F8060CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 82.5 OHM | CALCHIP | RM04F82R5CT | 2 | 0.01 | 0.02
RESISTOR - 0402 - 825 OHM | PANASONIC | ERJ-2RKF8250X | 2 | 0.0027 | 0.0054
RESISTOR - 0805 - 154K OHM | PANASONIC | ERJ6ENF1543V | 1 | 0.0022 | 0.0022
RESISTOR - 0402 - 49.9K OHM | CALCHIP | RM10F4992CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 78.7K OHM | PANASONIC | ERJ-6ENFF7872V | 1 | 0.0039 | 0.0039
RESISTOR - 0805 - 953K OHM | PANASONIC | ERJ-6ENF9533V | 1 | 0.0039 | 0.0039
DIFFERENTIAL TRANSLATOR REPEATER | TEXAS INSTRUMENTS | SN65LVDS100D | 1 | 2.83 | 2.83
1.5 to 2.5 Gbps Transceiver | TEXAS INSTRUMENTS | TLK2501IRCP | 1 | 17.87 | 17.87
TP | NEVIS | TP | 3 | 0 | 0
Programmable Low-Power Precision LVDS Oscillator - 80 MHz | MICREL | DSC8123BI2 | 1 | 6.437 | 6.437
PCB ASSEMBLY | APPLICAD | SPHENIX_CAL_XMITTER3 | 1 | 95 | 95
SOLDER PASTE STENCIL | APPLICAD | SPHENIX_CAL_XMITTER3 | 2 | 300
ONE-TIME MACHINE PROGRAMMING AND DOCUMENTATION | APPLICAD | SPHENIX_CAL_XMITTER3 | 1 | 250
SET-UP FOR SMT ASSEMBLY | APPLICAD | SPHENIX_CAL_XMITTER3 | 1 | 300
TOTAL |  |  |  |  | 595.645
Total Component cost |  |  |  |  | 192.035
Total PC Board cost |  |  |  |  | 308.61
Total Assembly cost |  |  |  |  | 95
Total Board Cost |  |  |  |  | 595.645
Total Board Fab NRE |  |  |  |  | 500
Total Assembly NRE |  |  |  |  | 850

## DigitizerCrateController
Sphenix WBS 1.5.3: Digitizer Crate Controller
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | UNIT | MODULE
|  |  |  | COST | COST
PC BOARD | PAL PILOT | cal_crate_control4 | 1 | 87.1 | 87.1
NRE | PAL PILOT | cal_crate_control4 | 1 | 500
DIODE | VISHAY | SA24A-E3/54 | 1 | 0.08 | 0.08
1A, LOW DROPOUT CMOS LINEAR REGULATOR | ANALOG DEVICES | ADP1706ARDZ-1.2R7 | 1 | 2.05 | 2.05
1A, LOW DROPOUT CMOS LINEAR REGULATOR | ANALOG DEVICES | ADP1706ARDZ-2.5R7 | 1 | 1.5 | 1.5
TRANSCEIVER | FINISAR | FTLF8524E2GNL | 1 | 39.02 | 39.02
FERRITE BEAD SM 220 OHM 200MA 0402 | MURATA | BLM15EG221SN1 | 7 | 0.06 | 0.42
FERRITE BEAD - 0805 - 330 OHM | MURATA | BLM21PG331SN1D | 4 | 0.02 | 0.08
CAPACITOR - 0402 - .001 MFD (1nf) - 50V | CALCHIP | GMC04X7R102K50NT | 2 | 0.03 | 0.06
CAPACITOR - 0402 - 0.01 MFD (10nf) | CALCHIP | GMC04X7R103K50NT | 5 | 0.03 | 0.15
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | CALCHIP | GMC04X7R104K16NT | 61 | 0.02 | 1.22
CAPACITOR - 0402 - 0.1 MFD (100nf) - 16V | CALCHIP | GMC04X7R104K16NT | 2 | 0.02 | 0.04
CAPACITOR - 0603 - 0.1 MFD (100nf) | CALCHIP | GMC10X7R104K25NT | 1 | 0.02 | 0.02
CAPACITOR - 0603 - 10 MFD - 10V - 6.3 V | MURATA | GRM188R60J106ME47J | 2 | 0.06 | 0.12
CAPACITOR - 4.7 MFD - 0603 - 16V - 10% - X5R | TDK | C1608X5RR1C475K080AC | 5 | 0.06 | 0.3
CAPACITOR - 0805 - 10 MFD, 16V, X5R | CALCHIP | GMC21X5R106K16NT | 2 | 0.06 | 0.12
CAPACITOR - 0805 - 1 MFD, 16V, X7R | CALCHIP | GMC21X7R105K16NT | 1 | 0.03 | 0.03
CAPACITOR - 0805 - 4.7 MFD - 25V | CALCHIP | GMC21X7R475K25NT | 2 | 0.04 | 0.08
CAPACITOR - 1206 - 10 MFD - 25 VDC - X5R | MURATA | GRM31CR61E106KA12L | 1 | 0.09 | 0.09
CAPACITOR - 1206 - 4.7 MFD, 50 VOLT, X5R | TAIYO YUDEN | UMK316BJ475KL-T | 1 | 0.1 | 0.1
CAPACITOR - 1210 - 10 MFD - 16V - Y5V | CALCHIP | GMC32Y5V106Z16NT | 2 | 0.06 | 0.12
CAPACITOR - 1210 - 10 MFD, 50 VOLT, X5R | TAIYO YUDEN | UMK325BJ106KM-T | 1 | 0.34 | 0.34
CAPACITOR - 1210 - 47 MFD, 6.3 VOLT, X5R | MURATA | GRM32ER60J476ME20L | 2 | 0.21 | 0.42
CONNECTOR - LEMO RA | LEMO | EPL.00.250.NTN | 2 | 5.32 | 10.64
CONNECTOR - RT ANGLE - 26 PIN HEADER | 3M | 3429-5202 | 1 | 1.94 | 1.94
QUAD RECEIVER | NATIONAL | DS90LV048ATMTC/NOPB | 3 | 1.71 | 5.13
1 TO 10 LVDS CLOCK DISTRIBUTION | NATIONAL/TI | DS90LV110ATMT/NOPB | 2 | 7.29 | 14.58
CYCLONE 4 | ALTERA | EP4CGX22CF19C7 | 1 | 50 | 50
1 Mbit SERIAL CINFIGURATION DEVICE | ALTERA | EPCS4SI8N | 1 | 13.8 | 13.8
Right Angle Female Connectors For Daughter Cards: Type C - Press fit 55 pins | ERNI | 354865 | 2 | 1.42 | 2.84
Right Angle Male Power Modules For Daughter Cards - 3 pins | ERNI | 114402 | 1 | 2.54 | 2.54
ERMET - ZD 10 ROW | ERNI | 973046 | 2 | 4.87 | 9.74
2 AMP FUSE | LITTLEFUSE | 0251002.MRT1L | 1 | 0.22 | 0.22
SOCKET PIN | AMP/TYCO | 2-5331272-7 | 2 | 0.236 | 0.472
HOLE_PANEL |  | HOLE_PANEL | 3 | 0 | 0
2:4, LVDS Output Fanout Buffer | IDT | 8SLVD1204-33NLGI | 1 | 6.38 | 6.38
In-System Programmable, Ultra-Low Jitter Zero Delay and Fan-Out Buffer, Differential | LATTICE SEMICONDUCTOR | ispPAC-CLK5406D-01SN48C | 1 | 4 | 4
JTAG | SAMTEC | TSW-105-07-G-D | 2 | 0.35 | 0.7
LED | LUMEX | SSL-LX2473ID | 2 | 0.18 | 0.36
Ultralow Noise EMC 36VIN, 3A DC/DC μModule Regulator | LINEAR TECHNOLOGY | LTM8033EV#PBF | 1 | 11.95 | 11.95
LVDS CLOCK OSCILLATOR | PLETRONICS | LV7745DEV-156.25M | 1 | 8.57 | 8.57
LVPECL CLOCK OSCILLATOR - OSC XO 60.000MHZ LVPECL SMD | MICREL | DSC8102AI2 | 1 | 7.07 | 7.07
RESISTOR - 0402 - 1.69K OHM | CALCHIP | RM04F1691CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 25 | 0.01 | 0.25
RESISTOR - 0402 - 10K OHM | CALCHIP | RM04F1002CT | 15 | 0.01 | 0.15
RESISTOR - 0402 - 110 OHM | CALCHIP | RM04F1100CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 150 OHM | CALCHIP | RM04F1500CT | 3 | 0.01 | 0.03
RESISTOR - 0402 - 1K OHM | CALCHIP | RM04F1001CT | 5 | 0.01 | 0.05
RESISTOR - 0402 - 2.49K OHM | CALCHIP | RM04F2491CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 24.9K OHM | CALCHIP | RM04F2492CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 24.9 OHM | PANASONIC | ERJ2RKF24R9X | 1 | 0 | 0
RESISTOR - 0402 - 2K OHM | CALCHIP | RM04F2001CT | 5 | 0.01 | 0.05
RESISTOR - 0402 - 4.75K OHM | CALCHIP | RM04F4751CT | 1 | 0.01 | 0.01
RESISTOR - 0402 - 402 OHM | CALCHIP | RM04F4020CT | 2 | 0.01 | 0.02
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 7 | 0.01 | 0.07
RESISTOR - 0402 - 53.6 OHM | CALCHIP | RM04F53R6CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 154K OHM | CALCHIP | RM10F1543CT | 1 | 0.01 | 0.01
RESISTOR - 0805 - 93.1K OHM | ROHM | MCR10EZPF9312 | 1 | 0.01 | 0.01
1.8V HIGH SPEED DIFFERENTIAL LINE RECEIVER | TEXAS INSTRUMENTS | SN65LVDS4RSET | 1 | 1.11 | 1.11
2Gbps LVDS/LVPECL/CML to LVDS Repeater/Translator | TEXAS INSTRUMENTS | SN65LVDS100D | 3 | 2.83 | 8.49
MULTIPOINT LVDS QUAD DIFFERENTIAL LINE DRIVER | TEXAS INSTRUMENTS | SN65MLVD047PW | 7 | 2.23 | 15.61
TP | NEVIS | TP | 3 | 0 | 0
USB-3.1 CONNECTOR STANDARD A R/A DIOP TYPE BLUE INSULATOR | AMPHENOL | GSB4111312HR | 1 | 1.79 | 1.79
PCB ASSEMBLY | APPLICAD INC. | cal_crate_control | 1 | 375 | 375
SOLDER PASTE STENCILS | APPLICAD INC. | cal_crate_control | 2 | 300
ONE TIME MACHINE PROGRAMMING AND DOCUMENTATION | APPLICAD INC. | cal_crate_control | 1 | 250
SET-UP FOR SMT ASSEMBLY | APPLICAD INC. | cal_crate_control | 1 | 300
TOTAL |  |  |  |  | 687.092
Total Parts Cost: |  |  |  |  | 223.202
Total Board Fabrication Cost: |  |  |  |  | 87.1
Total Board Assembly Cost: |  |  |  |  | 376.79
Total Board Cost: |  |  |  |  | 687.092
Total Board Fab NRE |  |  |  |  | 500
Total Assembly NRE |  |  |  |  | 850

## DigitizerBackplane
Sphenix WBS 1.5.3: Digitizer Back Plane
Date: 8/10/2015
Sphenix WBS 1.5.3: Digitizer Crate Backplane
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | UNIT | MODULE
|  |  |  | COST | COST
PC BOARD | ELECTROTEK | cal_backplane_2 | 1 | 387.6 | 387.6
TOOLING | ELECTROTEK | cal_backplane_2 | 1 | 500
TEST FIXTURE | ELECTROTEK | cal_backplane_2 | 1 | 0
Vertical Male Connectors For Backplanes: Type C - 55 Pins - PRESSFIT | ERNI | 043138 | 42 | 2.2 | 92.4
Vertical Female Power Modules For Backplanes | ERNI | 114404 | 21 | 2.33 | 48.93
ERMET FEMALE PM 6 PIN RC | ERNI | 254927 | 20 | 5.18 | 103.6
VERTICAL MALE ZD CONNECTOR | ERNI | 973056 | 20 | 4.32 | 86.4
VERTICAL MALE ZD CONNECTOR | ERNI | 973056 | 22 | 4.32 | 95.04
10.30mm (.405") EXTreme Zpower Connector, 10 Press fit tails, Select Gold (Au) Plating, for 3.10mm (.125") Thich PC Board | MOLEX | 0760010010 | 10 | 2.67 | 26.7
MOUNTING HOLE2.7 |  | MOUNTINGHOLE2.7 | 46 | 0 | 0
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 20 | 0.01 | 0.2
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 46 | 0.01 | 0.46
TAP ASSEMBLY - POWER DISTRIBUTION 25 A | TYCO | 9-55556-0 | 6 | 3.39 | 20.34
ASSEMBLY OF MICROBOONE_BACKPLANE PC BOARDS | APPLICAD INC. | cal_backplane_2 | 1 | 640 | 640
ONE TIME MACHINE PROGRAMMING AND DOCUMENTATION | APPLICAD INC. | cal_backplane_2 | 1 | 150
Total |  |  |  |  | 1501.67
Total Parts Cost: |  |  |  |  | 474.07
Total Board Fabrication Cost: |  |  |  |  | 387.6
Total Board Assembly Cost: |  |  |  |  | 640
Total Board Cost: |  |  |  |  | 1501.67
Total Board Fab NRE |  |  |  |  | 500
Total Assembly NRE |  |  |  |  | 150

## DigitizerJSEB2Board
sPHENIX WBS 1.5.3: Digitizer JEB2 Board
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Vendor | UNIT | MODULE | Notes
[5 empty] | COST | COST
PC BOARD | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 58.61 | 58.61
NRE | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 0 | 0
ELECTRICAL TEST | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 0 | 0
64K I2C™ Serial EEPROM | MICROCHIP TECHNOLOGY | 24LC64IP | 1 | Arrow | 0.43 | 0.43
8 PIN DIP SOCKET | AMP | 2-640463-3 | 1 | DigiKey | 0.05 | 0.05
Low Profile Header, Rt Angle, 4 Wall | 3M | 30310-5002HB | 1 | DigiKey | 0.32 | 0.32
SOLID ALUMINUM CAPACITOR WITH ORGANIC SEMICONDUCTOR ELECTROLYTE - 120 MFD - 20V | VISHAY | 94SP127X0020EBP | 2 | DigiKey |  |  | Obsolete
TRANSCEIVER | AVAGO | AFBR-59R5LZ | 2 | Arrow | 29.99 | 59.98
USB TYPE-B CONNECTOR, RECEPTACLE, RIGHT ANGLE, 4 POSITION, THRU HOLE - Replacement part for 787780-1 | AMP/TYCO | 292304-1 | 1 | DigiKey | 0.31 | 0.31
FERRITE BEAD - 0603 - 120 OHM | MURATA | BLM18PG121SN1D | 2 | DigiKey | 0.0194 | 0.0388
FERRITE BEAD - 0805 - 330 OHM | MURATA | BLM21PG331SN1D | 5 | DigiKey | 0.035 | 0.175
CAPACITOR - 0402 - .01 MFD (10nf) - 50V | CALCHIP | GMC04X7R103K50NT | 20 | DigiKey | 0.03 | 0.6
CAPACITOR - 0402 - .1 MFD (10nf) - 50V | CALCHIP | GMC04X7R104K50NT | 124 | DigiKey | 0.01 | 1.24
CAPACITOR - 0603 - 0.1 MFD (100nf) | CALCHIP | GMC10X7R104K25NT | 1 | DigiKey | 0.03 | 0.03
CAPACITOR - 0603 - 1 MFD - 10V | CALCHIP | GMC10Y5V105Z10NT | 2 | DigiKey | 0.01 | 0.02
CAPACITOR - 0603 - 2.2 MFD - 16V (X5R) | MURATA | GRM188R61C225KE15D | 3 | DigiKey | 0.017 | 0.051
CAPACITOR - 1210 - 10 MFD - 16 VDC - (X7R) | CALCHIP | GMC32X7R106K16NT | 21 | DigiKey | 0.35 | 7.35
EZ-USB FX2LP USB MICROCONTROLLER, 56 PIN SSOP | CYPRESS SEMICONDUCTOR | CY7C68013A-56PVXC | 1 | Arrow | 6.78 | 6.78
CAPACITOR - 10 MFD - 20V - "B" SIZE | PHILIPS | 49MC106B020ASFT | 1 | DigiKey | 0.42 | 0.42
CAPACITOR - 4700 pf 250 VAC CERAMIC SMD | PANASONIC | ECK-TBC472MF | 1 | DigiKey | 1.02 | 1.02
CRYSTAL - 24000 MHz, 20 pf, HC-49/US | ECS | ECS-240-20-4 | 1 | DigiKey | 0.518 | 0.518
CAPACITOR - 220 MFD 4 VDC - SP, POLYMER ALUMINUM SMD | PANASONIC | EEFUE0G221LR | 4 | DigiKey | 2.6395 | 10.5581
ARRIA GX FPGA 780 PIN | ALTERA | EP1AGX50DF780C6 | 1 | Arrow | 250.7 | 250.7
16 MBIT SERIAL CONFIG | ALTERA | EPCS16SI8 | 1 | Arrow | 15.81 | 15.81
FUSE - 1.5 AMP | LITTLEFUSE | 025101.5MXL | 1 | DigiKey | 0.364 | 0.364
FUSE HOLDER | AMP/TYCO | 2-5331272-7 | 2 | Arrow | 0.245 | 0.49
CAPACITOR - 1206 - 10 MFD - 25 VDC - X5R | MURATA | GRM31CR61E106KA12L | 4 | DigiKey | 0.09 | 0.36
HEADER - 2 | SAMTEC | TSW-102-07-G-S | 1 | DigiKey | 0.0586 | 0.0586
HEADER - 3 | SAMTEC | TSW-103-07-G-S | 1 | DigiKey | 0.0886 | 0.0886
HEADER - 10 | SAMTEC | TSW-105-07-G-D | 1 | DigiKey | 0.29 | 0.29
LOW SKEW, 1 TO 2 DIFFERENTIAL TO LVCMOS / LVTTL FANOUT BUFFER | IDT | ICS83026BMI-01LF | 1 | Digi Key | 5.846 | 5.846
LOW SKEW, 1 TO 4 DIFFERENTIAL TO LVDS FANOUT BUFFER | IDT | ICS8543BGLF | 1 | Digi Key | 16.0024 | 16.0024
LED -PCB MOUNT | LEDTRONICS | 555M-2101-001 | 4 | Digi Key | 1.4 | 5.6
CHIP COILS FOR HIGH FREQUENCY MONOLITHIC TYPE | MURATA | LQG15HN9N1J02D | 2 | Digi Key | 0.022 | 0.044
1.5V FAST TRANSIENT 1.5A LDO | LINEAR TECHNOLOGY | LT1963AEST-3.3 | 1 | Digi Key | 3.1696 | 3.1696
1.5A LOW INPUT VOLTAGE VLDO LINEAR REGULATOR, 10 LEAD PLASTIC MSOP | LINEAR TECHNOLOGY | LTC3026EMSE#PBF | 1 | Arrow | 2.2 | 2.2
LVDS CLOCK OSCILLATOR | PLETRONICS | LV7745DEV-100.000M | 1 | Arrow | 13.26 | 13.26
LVDS CLOCK OSCILLATOR | PLETRONICS | LV7745DEV-156.250M | 1 | Arrow | 14.95 | 14.95
5 VOLT LOW DROPOUT REGULATOR | MICREL | MIC39100-5.0WS | 1 | Arrow | 0.8917 | 0.8917
MTHOLE1 | NEVIS | MTHOLE1 | 2 | Digi Key | 0 | 0
PCI_ EXPRESS_X4 | PRINTED ON THE PCB | PCI_ EXPRESS_X4 | 1 |  | 0 | 0
6A, 12V, INPUT NON-ISOLATED WIDE OUTPUT ADJUST POWER MODULE EUS PACKAGE | TEXAS INSTRUMENTS | PTH12000WAD | 2 | Arrow | 7.97 | 15.94
RESISTOR - 0402 - 100K OHM | CALCHIP | RM04F1003CT | 3 | Digi Key | 0.01 | 0.03
RESISTOR - 0402 - 2K OHM | CALCHIP | RM04F2001CT | 5 | Digi Key | 0.01 | 0.05
RESISTOR - 0402 - 4.75K OHM | CALCHIP | RM04F4751CT | 4 | Digi Key | 0.01 | 0.04
RESISTOR - 0402 - 49.9K OHM | CALCHIP | RM04F4992CT | 2 | Digi Key | 0.01 | 0.02
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 3 | Digi Key | 0.01 | 0.03
RESISTOR - 0402 - 1K OHM | CALCHIP | RM04F1001CT | 3 | Digi Key | 0.01 | 0.03
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 2 | Digi Key | 0.01 | 0.02
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 16 | Digi Key | 0.01 | 0.16
RESISTOR - 0603 - 10K OHM | CALCHIP | RM06F1002CT | 4 | Digi Key | 0.01 | 0.04
RESISTOR - 0603 - 1K OHM | CALCHIP | RM06F1001CT | 4 | Digi Key | 0.01 | 0.04
RESISTOR - 0603 - 2.21K | CALCHIP | RM06F2211CT | 2 | Digi Key | 0.01 | 0.02
RESISTOR - 0603 - 2K OHM | CALCHIP | RM06F2001CT | 1 | Digi Key | 0.01 | 0.01
RESISTOR - 0603 - 392 OHM | CALCHIP | RM06F3920CT | 4 | Digi Key | 0.01 | 0.04
RESISTOR - 0603 - 4.75K OHM | CALCHIP | RM06F4751CT | 6 | Digi Key | 0.01 | 0.06
RESISTOR - 0805 - 100K OHM | CALCHIP | RM10F1003CT | 2 | Digi Key | 0.01 | 0.02
RESISTOR - 1206 - 10 MEG OHM | CALCHIP | RM12J1006CT | 1 | Digi Key | 0.01 | 0.01
R-PAC - 51 OHM | CTS | 741X163510JTR | 7 | Digi Key | 0.062 | 0.434
2.5 GBPS TO 3.125 GBPS TRANSCEIVER | TEXAS INSTRUMENTS | TLK3101IRCP | 2 | Arrow | 19.2 | 38.4
TP | NEVIS | TP | 4 |  | 0 | 0
LDO VOLTAGE REGULATOR, 2.5V | TEXAS INSTRUMENTS | TPS79625DCQR | 2 | Arrow | 1.09 | 2.18
TPS SERIES TANTALUM LOW ESR 100 MFD - 10V | AVX | TPSC107K010R0075 | 10 |  | 0.26 | 2.6
ONE TIME DOCUMENTATION | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 |  | 0 | 0
SET-UP FOR SMT ASSEMBLY | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 |  | 0 | 0
COMPUTER AND MOUNTING BRACKETS PC BRACKET STD PCI | KEYSTONE ELECTRONICS | 9203 | 1 |  | 1.59 | 1.59
SCREW - 2-56 X 1/4 SLOT ROUND M/S, 8-8 SS | TOWER FASTENER | 2C25MSRS | 2 |  | 0.14 | 0.28
NUT - 2-56 HEX M/S - 18-8 SS | TOWER FASTENER | 2CNHMS | 2 |  | 0.08 | 0.16
MISC |  |  | 1 |  | 32.54 | 32.54
ASSEMBLY PRINTED CIRCUIT BOARD MICROBOONE_PHENIX_PCIE | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 | APPLICAD | 110 | 110
SOLDER PASTE STENCIL | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 | APPLICAD | 0 | 0
TOTAL | [5 empty] | 683.3698
Total Parts Cost: | [5 empty] | 514.7598
Total Board Fabrication Cost: | [5 empty] | 58.61
Total Board Assembly Cost: | [5 empty] | 110
Total Board Cost: | [5 empty] | 683.3698

## DigitizerClockMaster
sPHENI WBS 1.5.3: Digitzer Clock Master
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Vendor | UNIT | MODULE | Notes
[5 empty] | COST | COST
Engineering Estimate- Parts | [5 empty] | 100
Engineering Estimate- Fab | [5 empty] | 500
Engineering Estimate- Assembly | [5 empty] | 500
TOTAL | [5 empty] | 1100
Total Parts Cost: | [5 empty] | 100
Total Board Fabrication Cost: | [5 empty] | 500
Total Board Assembly Cost: | [5 empty] | 500
Total Board Cost: | [5 empty] | 1100

## TriggerInterface
sPHENI WBS 1.5.3: Trigger Interface Module
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Vendor | UNIT | MODULE | Notes
[5 empty] | COST | COST
Engineering Estimate- Parts | [5 empty] | 30
Engineering Estimate- Fab | [5 empty] | 10
Engineering Estimate- Assembly | [5 empty] | 10
TOTAL | [5 empty] | 50
Total Parts Cost: | [5 empty] | 30
Total Board Fabrication Cost: | [5 empty] | 10
Total Board Assembly Cost: | [5 empty] | 10
Total Board Cost: | [5 empty] | 50

## Misc
sPHENIX WBS 1.5.3: Misc Costs
Last Revision: 02-Feb-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Vendor | UNIT | MODULE | Notes
[5 empty] | COST | COST
Crates |  |  | 1 |  | 1203 | 1203
Misc |  |  | 1 |  | 500 | 500
Crate Total TOTAL | [5 empty] | 1703
Patch Fibers: 2m |  |  | 1 | Fibertronics | 9.89 | 9.89
Power Suppies. 1 per rack, 4 crates per supply | VICOR |  | 1 | VICOR | 7500 | 7500

## ModuleCounts
This sheet summarizes the number of modules required for the Calorimeter Digitizer system based on the total number of towers in the combined EMCal/Hcal subsystems. The number of XMIT modules is deterimned based the requirement that the XMIT board transfer 16 samples per channel from an XMIT group in less then 40 microseconds. That requirement means that 1 XMIT board will be required for every 3 ADC boards. The totals in this spread sheet are used to determine the number of modules required for both detector subsystems.
Last Revision: 02-Feb-2018
Towers |  |  | Totals | Procurement Totals | Notes:
| EMCal Eta: V2.1 Prototype | 8
| EMCal Phi: V2.1 Prototype | 8
| Total EMCal Towers: V2.1Prototype |  | 64
| EMCal Eta: Sector 0 | 48
| EMCal Phi: Sector 0 | 8
| EMCal Sectors: Sector 0 | 1
| Total EMCal Towers: Sector 0 |  | 384
| EMCal Sector Eta: Sectors 1-12 | 48
| EMCal Sector Phi: Sectors 1-12 | 8 | 384
| EMCal Sectors: Sectors 1-12 | 12
| Total EMCal Towers: Sectors 1-2 |  | 4608
| EMCal Sector Eta: Sectors 13-64 | 36
| EMCal Sector Phi: Sectors 13-64 | 8
| EMCal Sectors: Sectors 13-64 | 52
| Total EMCal Towers: Sectors 13-64 |  | 14976
| HCal Eta: V2.1 Prototype | 4
| HCal Phi: V2.1 Prototype | 4
| Total Hcal Towers: V2.1 Prototype |  | 16
| HCal Eta: Modules 1-6 | 24
| HCal Phi: Modules 1-6 | 12
| Total Hcal Towers: Modules 1-6 |  | 288
| HCal Eta: Modules 7-32 | 24
| HCal Phi: Modules 7-32 | 52
| Total Hcal Towers: Modules 7-32 |  | 1248
Sensors
| SiPMs per EMCal Tower | 4
| SiPMs per Inner HCal Tower | 4
| SiPMs per Outer HCal Tower | 5
| EMCal V2.1 Protoype Sensors | 256
| EMCal Sector 0 Sensors | 1536
| Total Sensors: Prepouction Prototypes |  | 1800 | 1800
| EMCal Sector 1-12 Sensors | 18432
| HCal Modules 1-6 Sensors | 1440
| Total Sensors: R&D Productiom |  | 20000 | 22000
| EMCal Sectors 13-64 Sensors | 59904
| HCal Modules 7-32 Sensors- Outer | 6240
| Total Sensors: Production |  | 67000 | 73700
EMCal Electronics
| EMCal SiPM Daughter Boards: V2.1 Protoype | 16 |  |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: V2.1 Prototyp | 4 |  |  | 16 towers/Preamp Board
| EMCal Interface Boards | 4 |  |  | 1 interface/4 Preamp Boards- Min Lot Size of 4
| Calorimeter Controller Boards- EMCal | 4 |  |  | 1 Controller/ 1/2-Sector- Min Lot Size of 4
| EMCal SiPM Daughter Boards: Sector 0 | 96 |  |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sector 0 | 24 |  |  | 16 towers/Preamp Board
| EMCal Interface Board: Sector 0 | 6 |  |  | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards: Sector0 | 0 |  |  | 1 Controller/ 1/2-Sector- Expect to use V2.1 Prototyp
| EMCal SiPM Daughter Boards: Sectors 1-12 | 3744 |  |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sectors 1-12 | 936 |  |  | 16 towers/Preamp Board
| EMCal Interface Board: Sectors 1-12 | 234 |  |  | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards: Sectors 1-12 | 12 |  |  | 1 Controller/ 1/2-Sector
| EMCal SiPM Daughter Boards: Sectors 13-64 | 3744 |  |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sectors 13-64 | 936 |  |  | 16 towers/Preamp Board
| EMCal Interface Board: Sectors 13-64 | 234 |  |  | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards: Sectors 13-64 | 52 |  |  | 1 Controller/ 1/2-Sector
HCal Electronics
| HCal SiPM Boards: V2.1 Prototype | 64 |  |  | Inner HCal only, reuse outer HCal prototype
| HCal Preamps: V2.1 Prototype | 16 |  |  | 1 per tower, Inner and Outer HCal
| HCal Interface: V2.1 Prototype | 1 |  |  | One inner, one outer HCal
| HCal LED Driver: V2.1 Prototype | 2 |  |  | One inner, one outer HCal
| HCal Backplane: V2.1 Prototype | 1 |  |  | Inner HCal only
| HCal Contoller: V2.1 Prototype | 0 |  |  | Use EMCal controller
| HCal Crates: V2.1 Prototype | 0 |  |  | Reuse from prevous prototypes
| HCal SiPM Board: Modules 1-6 | 1440
| HCal Preamps: : Modules 1-6 | 288
| HCal Interface: Modules 1-6 | 12
| HCal LED Driver: Modules 1-6 | 12
| HCal Backplane: Modules 1-6 | 12
| HCal Contoller: Modules 1-6 | 2
| HCal Crates: Modules 1-6 | 1
HCal SiPM Boards: Modules 7-32
| HCal Preamps: Modules 7-32 | 1248
| HCal Interface: Modules 7-32 | 52
| HCal LED Driver: Modules 7-32 | 52
| HCal Backplane: Modules 7-32 | 52
| HCal Contoller: Modules 7-32 | 7
| HCal Crates: Modules 7-32 | 1
Digitizers
| Number of Channel/Digitizer | 64
| Number of Digitizers/XMIT Group | 3 |  |  | To meet readout requirements of 16 samples per channel in less then 40 microSeconds
| Number of XMIT Groups/Crate | 4
| Number of Controllers/Crate | 1
| Number of Crates/Clock Master | 4 |  |  | Assume 1 clock master per rack and 4 crates/Rack
| Number of Digitizers/Sector: Secgtors 0-12 | 6
| Number of Digitizers/Sector: Sectors 13-64 | 5 |  |  | Assume that digitizers don't span sectors for triggering purposes.
| Number of Crates: 1/2 Crate Production | 1
| Number of Crates: 7 Crate Production | 7 |  |  | 6 Full Crates EMCal, 1 Full Crate HCal
| Number of Crates: Final Production | 23 |  |  | 22 Full Crates EMCal , 1 Full Crate HCal
| Digitizer Boards: 1/2 Crate | 7
| Trigger Interface | 0
| XMIT Boards: 1/2 Crate | 0 |  |  | Fabricated during early prototype
| Digitizer Crates: 1/2 Crate | 0 |  |  | Fabricated during early prototype
| Crate Controllers: 1/2 Crate | 6 |  |  | Minimum order quantity
| Digitizer Backplanes: 1/2 Crate | 0 |  |  | Fabricated during early prototype
| Digitizer JSEB2 Boards: 1/2 Crate | 0 |  |  | Recycled from PHENIX
| Clock Masters: 1/2 Crate | 4 |  |  | Minimum order quantity/Prototype round
| Digitizer Boards: 7 Crate System | 84 |  |  | 6 crates for EMCal 1 Crate for HCal
| Trigger Interface | 84
| XMIT Boards: 7 Crate System | 28
| Digitizer Crates: 7 Crate System | 7
| Crate Controllers: 7 Crate System | 7
| Digitizer Backplanes: 7 Crate System | 7
| Digitizer JSEB2 Boards: 7 Crate System | 7
| Clock Masters: 7 Crate System | 2
| Patch Fibers: Xmit 7 Crate System | 28
| Patch Fibers: Controller 7 Crate System | 7
| Patch Fibers: Clock Master 7 Crate System | 2
| Patch Fibers: Trigger 7 Crate System | 84
| Total Fiber Count |  | 121
| Total Racks Required EMCal/Hcal | 2
| Power Systems | 2 |  |  | 1 Power system/rack (4 crates)
| Digitizer Boards: Final Production | 276 | 367
| Trigger Interface | 276 | 360
| XMIT Boards: Final Production | 92 | 120
| Digitizer Crates: Final Production | 23 | 30
| Crate Controllers: Final Production | 23 | 36
| Digitizer Backplanes: Final Production | 23 | 30
| Digitizer JSEB2 Boards: Final Production | 23 | 30
| Clock Masters: Final Production | 6 | 12
| Patch Fibers: XmitFinal Production | 92
| Patch Fibers: Controller Final Production | 23
| Patch Fibers: Clock Master Final Production | 6
| Patch Fibers: Trigger Final Production | 276
| Total Fiber Count |  | 397
| Total Racks Required EMCal/Hcal | 8 |  |  | total of 10 racks required 8 for EMCal and 2 for Hcal. 2 Racks are part of 7 Crate production
| Power Systems | 8 |  |  | 1 Power system/rack (4 crates)