## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Calorimeter Electronics |  | 1.05 |  | Optical Sensors |  | 1.05.01
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Sensor Procurement: Basis of Estimate |  | 1.05.01 |  | Optical Sensors: Summary
| Control Account |  | Description
| Sensor Procurement |  | This account is responsible for the procurement and testing of the optical sensors for the preproduction and production EMCal and HCal detectors.
NOTE: This is the BOE File for the SiPM Optical Sensors
These are for the Calorimeters, both EMCal (WBS 1.3) and HCal (WBS1.4)
These devices were placed under contract with Hamamatsu Photonics in October 2018
This was done before the BOE were refreshed for the 2019 sPHENIX Baseline for PD-2/3..
The actual contract prices and delivery have been incorporated into the sPHENIX P6 baseline.
This included both cost and schedule updates.
Links to EMCal and HCal fabrication were also updated to correctly incorporate the delivery schedule.
This Action was recorded in PCR-02
Note on D16: Eric Mannel:

## Sensor_Procurement_Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-01
[7 empty] | Prepared By: | E.J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 65 v18
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Sensor Procurement: Basis of Estimate |  |  |  | 1.05.01
WBS Dictionary Definition:
This work packages covers the procurement and Q/A testing of the preproduction and production optical sensors for the EMCal and HCal detectors. Procurement of the devices includes writing and the technical documentation required for procurement, tracking the progress of the procurement and validating delivery of devices. The testing and sorting includes performing the tests required to meet the selection and sorting requirements of the EMCal and HCal detectors and sorting the devices in preperation for subsequent assembly steps. Deliverables are appropriate number of tested and sorted devices for the EMCal and HCal detectors along with documenation on the test results.
Estimate Type (check all that apply):
| X | Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
Costing
Guidelines Used in Developing Estimate
The following guidelines were used in the cost estimate: 1) Vendor quote for purchase of preproduction sensors, order placed 5/2017. 2) Vendor budgetary quotation for production sensors. 3) Engineering estimate for test equipment based on equipment already built. 3) University labor is combination of contributed and hourly paid student. 4) BNL labor is for submission of orders and tracking deliveries. The following guidelines were used for the schedule estimate: 1) Documentation generated prior to submission of purchase request, 1 month. 2) 1 month to issue preproduction sensor order, 6 months to issue production order. 3) delivery schedule based on Vendor provided estimates
Details of the Base Estimate (explanation of the Work)
This work package covers the procurement and Q/A of all optical sensors for the proproduction, early production and full production rounds for the EMCal and HCal detectors. Procurement includes writing design specifications, obtaining quotes, placing orders and tracking delivery. Testing includes measuring the operational characteristics of the device and sorting the devices to meet the performace specifications of the HCal and EMCal detectors. Deliverables are all the required sensors for EMCal and HCal, fully tested and sorted to meet the assembly requirements for the EMCal and HCal. A 10% yield loss due to damage or loss in the in-house testing phase is assumed. Testing equipment will be fabricated for the early production and full production
Cost Summary
(follow link for detailed summary)
|  | Task | Cost Basis |  | Total Cost
|  | Optical Sensor:Sector 0 | Quote |  | 0
|  | Optical Sensor: EMCal/Hcal Sensors | Budget Quote |  | 196350 | Sum of two cells; link is to first
|  | Optical Sensor: Production | Budget Quote |  | 654500 | Sum of eight cells; link is to first
|  | Test Stand | Engineering Est |  | 22000
|  | Total Cost |  |  | 872850
Design Uncertainty
Sector 0 Sensors: 0%; Order placed and received
Optical Sensors: EMCal/Hcal Sensors: 25% outdated Budgtary Quote
Optical Sensors: Production: 25%- Outdated Budgtary Quote
Test Stand: 40% Engineeering Estimate
Contributed University labor for for oversite and Q/A testing: 30%
BNL Labor for order placement and tracking: 10%

## 1.05.01Tasks
WBS: 1.05.01
Title: Optical Sensors
Creation Date: 20-Feb-2017
Last Revision Date: 31-March-2019
WBS | Activity ID | Activity Name | Task Description | Duration (d) | Scientist | Engineer | Designer | Technician | Trades | Student | Materials and Supplies | % Design Uncertainty | Materials and Supplies + %Design Uncertainty | Risk Code |  | Notes
1.05.01 |  |  |  |  | Hours | Hours | Hours | Hours | Hours | Hours |  |  |  | Labor | Material
1.05.01 | S211600 | Write Design Change Specifications for Optical Sensors: Sector 0 - Labor | Write the specification documentation for the V2.1 and Sector 0 SiPMS | 10 | [9 empty] | 0 |  | Complete
1.05.01 | S211700 | Write Design Change Specifications for Optical Sensors: Sector 0 - M&S |  | 20 | [10 empty] | 0 | Complete
1.05.01 | S211800 | Order Sensors: Sector 0 - Labor | Provide all the documentation for procurement necessary to the procurement office to order optical sensors for EMCal Sectors 1-12 and HCal modules 1-6. A total of 20,000 devices are required. | 120 | [11 empty] | Complete
1.05.01 | S211900 | Order Sensors: Sector 0 - M&S | Place order for V2.1 and Sector 0 SiPMs | 120 | [11 empty] | Complete
1.05.01 | S212000 | Q/A Delivered Sensors: Sector 0 - Labor | This is the estimated labor for Q/A testing the sector 0 optical sensors | 73 | [11 empty] | Complete
1.05.01 | S212100 | Q/A Delivered Sensors: Sector 0 - M&S | This is the estimated materials required for Q/A testing the sector 0 optical sensors | 73 | [11 empty] | Complete
1.05.01 | S212200 | EMCal/HCal Sensors Tested and Delivered: Sector 0 | This is for test stand and eqipment needed to test the SiPMs | 0 | [11 empty] | Complete
1.05.01 | S212300 | Prepro EMCal/HCal sensors Production: - Provide Requirements to Procurement |  | 10 | [11 empty] | Complete
1.05.01 | S212400 | Prepro EMCal/HCal sensors Production: - Prepare & Send Solicitation | Order optical sensors for EMCal Sectors 13-64 and HCal modules 7-32. A total of 67,000 devices are required. | 50 | [11 empty] | Complete
1.05.01 | S212500 | Prepro EMCal/HCal sensors Production: - Vendor Responses & Selection | This task covers the final selection and contract preperation for EMCal Sector 1-12 and Hcal module 1-6 optical sensors. | 20 | [11 empty] | Complete
1.05.01 | S212600 | Prepro EMCal/HCal sensors Production: - 23K units Contract Award(s) | Milestone | 0
1.05.01 | S212700 | Prepro EMCal/HCal sensors Production: - 77K units Contract Award(s) | Milestone | 0
1.05.01 | S212800 | Prepro EMCal/HCal sensors Production: - Vendor Leadtime FY18 | This is the lead time for the vendor to start production of the optical sensors. | 60
1.05.01 | S212900 | Prepro EMCal/HCal sensors Production: - Vendor Leadtime FY19 | This is the lead time for the vendor to start production of the optical sensors. | 60
1.05.01 | S213000 | Prepro EMCal/HCal sensors Production: - deliver Batch 1: 8K units units 1 - 8K | This is delivery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 122718.75 |  | 3
1.05.01 | S213010 | Prepro EMCal/HCal sensors Production: - deliver Batch 2: 8K units | This is delivery of 12K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 122718.75 |  | 3
1.05.01 | S213100 | Prepro EMCal/HCal sensors Production: - deliver Batch 3: 7K units | This is delivery of 12K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 60830 | 0.25 | 409062.5 |  | 3
1.05.01 | S213200 / S213205 | Prepro Q/A Tested & Sorted devices Batch 1: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 4
1.05.01 | S213210 / S213215 | Prepro Q/A Tested & Sorted devices Batch 2 : 8K units | This task cover the labor for Q/A testing and sorting of 12K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 4
1.05.01 | S213300 / S213305 | Prepro Q/A Tested & Sorted devices Batch 3: 7K units | This task cover the labor for Q/A testing and sorting of 12K optical sensors | 20 |  | 70 |  |  |  | 137 |  |  |  | 4
1.05.01 | S214700 | EMCal/HCal sensors Production: - deliver Batch 4: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S214800 | EMCal/HCal sensors Production: - deliver Batch 5: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S214900 | EMCal/HCal sensors Production: - deliver Batch 6: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215000 | EMCal/HCal sensors Production: - deliver Batch 7: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215100 | EMCal/HCal sensors Production: - deliver Batch 8: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215200 | EMCal/HCal sensors Production: - deliver Batch 9: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215300 | EMCal/HCal sensors Production: - deliver Batch 10: 8K units | This is deilvery of 10K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215310 | EMCal/HCal sensors Production: - deliver Batch 11: 8K units | This is deilvery of 7K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215320 | EMCal/HCal sensors Production: - deliver Batch 12: 8K units | This is deilvery of 7K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 69520 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215400 | EMCal/HCal sensors Production: - deliver Batch 13: 5K units | This is deilvery of 7K optical sensors based on vendor guidance for delivery schedule. | 20 | [6 empty] | 43450 | 0.25 | 136354.1667 |  | 3
1.05.01 | S215500 | EMCal/HCal sensors Production: - delivery complete | Milestone | 0
1.05.01 | S215600 / S215605 | Q/A Tested & Sorted Production devices Batch 4: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S245000 | Procure test stand for SiPMs | This task cover the material for Q/A testing and sorting of optical sensors | 20 | [6 empty] | 22000 | 0.4 | 30800 |  | 4
1.05.01 | S215800 / S215805 | Q/A Tested & Sorted Production devices Batch 5: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S215900 / S215905 | Q/A Tested & Sorted Production devices Batch 6: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216000 / S216005 | Q/A Tested & Sorted Production devices Batch 7: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216100 / S216105 | Q/A Tested & Sorted Production devices Batch 8: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216200 / S216205 | Q/A Tested & Sorted Production devices Batch 9: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216300 / S216305 | Q/A Tested & Sorted Production devices Batch 10: 8K units | This task cover the labor for Q/A testing and sorting of 10K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216310 / S216315 | Q/A Tested & Sorted Production devices Batch 11: 8K units | This task cover the labor for Q/A testing and sorting of 7K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216320 / S216325 | Q/A Tested & Sorted Production devices Batch 12: 8K units | This task cover the labor for Q/A testing and sorting of 7K optical sensors | 20 |  | 80 |  |  |  | 157 |  |  |  | 3
1.05.01 | S216400 / S216405 | Q/A Tested & Sorted Production devices Batch 13: 8K units | This task cover the labor for Q/A testing and sorting of 7K optical sensors | 20 |  | 50 |  |  |  | 98 |  |  |  | 3
1.05.01 | S216500 | Optical Sensor Procurement Complete | Milestone | 0
1.05.01 |  | Total Cost: |  |  | 0 | 1000 | 0 | 0 | 0 | 1962 | 891000 |  | 2048841.6667
|  |  |  | TOTAL Hours | 2962

## ModuleCounts
This sheet summarizes the number of modules required for the Calorimeter electronics based on the total number of towers in the combined EMCal/Hcal subsystems.
Last Revision Date: 01-Feb-2018
Towers |  |  | Totals | Procurement Totals | Notes:
| EMCal Eta: V2.1 Prototype | 8
| EMCal Phi: V2.1 Prototype | 8
| Total EMCal Towers: V2.1Prototype |  | 64
| EMCal Eta: Sector 0 | 48
| EMCal Phi: Sector 0 | 8
| EMCal Sectors: Sector 0 | 1
| Total EMCal Towers: Sector 0 |  | 384
| EMCal Sector Eta: Sectors 1-12 | 48
| EMCal Sector Phi: Sectors 1-12 | 8 | 384
| EMCal Sectors: Sectors 1-12 | 12
| Total EMCal Towers: Sectors 1-2 |  | 4608
| EMCal Sector Eta: Sectors 13-64 | 36
| EMCal Sector Phi: Sectors 13-64 | 8
| EMCal Sectors: Sectors 13-64 | 52
| Total EMCal Towers: Sectors 13-64 |  | 14976
| HCal Eta: V2.1 Prototype | 4
| HCal Phi: V2.1 Prototype | 4
| Total Hcal Towers: V2.1 Prototype |  | 16
| HCal Eta: Modules 1-6 | 24
| HCal Phi: Modules 1-6 | 12
| Total Hcal Towers: Modules 1-6 |  | 288
| HCal Eta: Modules 7-32 | 24
| HCal Phi: Modules 7-32 | 52
| Total Hcal Towers: Modules 7-32 |  | 1248
Sensors
| SiPMs per EMCal Tower | 4
| SiPMs per Inner HCal Tower | 4
| SiPMs per Outer HCal Tower | 5
| EMCal V2.1 Protoype Sensors | 256
| EMCal Sector 0 Sensors | 1536
| Total Sensors: Preproduction Prototypes |  | 1800 | 1800
| EMCal Sector 1-12 Sensors | 18432
| HCal Modules 1-6 Sensors | 1440
| Total Sensors: R&D Productiom |  | 20000 | 23000
| EMCal Sectors 13-64 Sensors | 59904
| HCal Modules 7-32 Sensors- Outer | 6240
| Total Sensors: Production |  | 70000 | 77000
EMCal Electronics
| EMCal SiPM Daughter Boards: V2.1 Prototype | 16 |  |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: V2.1 Prototype | 4 |  |  | 16 Towers/Preamp Board
| EMCal Interface Boards | 4 |  |  | 1 Interface/4 Preamp Boards- Min Lot Size of 4
| Calorimeter Controller Boards- EMCal | 4 |  |  | 1 Controller/ 1/2-Sector- Min Lot Size of 4
| EMCal SiPM Daughter Boards: Sector 0 | 96 |  | 104 | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sector 0 | 24 |  | 30 | 16 Towers/Preamp Board
| EMCal Interface Board: Sector 0 | 6 |  | 8 | 1 Interface/4 Preamp Boards
| Calorimeter Controller Boards: Sector0 | 0 |  | 0 | 1 Controller/ 1/2-Sector- Expect to use V2.1 Prototyp
| EMCal SiPM Daughter Boards: Sectors 1-12 | 1152 |  | 1300 | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sectors 1-12 | 288 |  | 300 | 16 Towers/Preamp Board
| EMCal Interface Board: Sectors 1-12 | 72 |  | 100 | 1 Interface/4 Preamp Boards
| Calorimeter Controller Boards: Sectors 1-12 | 12 |  | 20 | 1 Controller/ 1/2-Sector
| EMCal SiPM Daughter Boards: Sectors 13-64 | 3744 |  | 4200 | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sectors 13-64 | 936 |  | 1100 | 16 Towers/Preamp Board
| EMCal Interface Board: Sectors 13-64 | 234 |  | 300 | 1 Interface/4 Preamp Boards
| Calorimeter Controller Boards: Sectors 13-64 | 52 |  |  | 1 Controller/ 1/2-Sector
HCal Electronics
| HCal SiPM Boards: V2.1 Prototype | 64 |  |  | Inner HCal only, reuse outer HCal prototype
| HCal Preamps: V2.1 Prototype | 16 |  |  | 1 per tower, Inner and Outer HCal
| HCal Interface: V2.1 Prototype | 1 |  |  | One inner, one outer HCal
| HCal LED Driver: V2.1 Prototype | 2 |  |  | One inner, one outer HCal
| HCal Backplane: V2.1 Prototype | 1 |  |  | Inner HCal only
| HCal Contoller: V2.1 Prototype | 0 |  |  | Use EMCal controller
| HCal Crates: V2.1 Prototype | 0 |  |  | Reuse from prevous prototypes
| HCal SiPM Board: Modules 1-6 | 1440 |  | 1600
| HCal Preamps: : Modules 1-6 | 288
| HCal Interface: Modules 1-6 | 12
| HCal LED Driver: Modules 1-6 | 12
| HCal Backplane: Modules 1-6 | 12
| HCal Contoller: Modules 1-6 | 2
| HCal Crates: Modules 1-6 | 1
| HCal SiPM Boards: Modules 7-32 | 6240 |  | 6900
| HCal Preamps: Modules 7-32 | 1248 |  | 1400
| HCal Interface: Modules 7-32 | 52
| HCal LED Driver: Modules 7-32 | 52
| HCal Backplane: Modules 7-32 | 52
| HCal Contoller: Modules 7-32 | 7
| HCal Crates: Modules 7-32 | 1
Digitizers
| Number of Channel/Digitizer | 64
| Number of Digitizers/XMIT Group | 3 |  |  | To meet readout requirements of 16 samples per channel in less then 40 microSeconds
| Number of XMIT Groups/Crate | 4
| Number of Controllers/Crate | 1
| Number of Crates/Clock Master | 4 |  |  | Assume 1 clock master per rack and 4 crates/Rack
| Number of Digitizers/Sector: Sectors 0-12 | 6
| Number of Digitizers/Sector: Sectors 13-64 | 5 |  |  | Assume that digitizers don't span sectors for triggering purposes.
| Number of Crates: 1/2 Crate Production | 1
| Number of Crates: 7 Crate Production | 7 |  |  | 6 Full Crates EMCal, 1 Full Crate HCal
| Number of Crates: Final Production | 23 |  |  | 22 Full Crates EMCal , 1 Full Crate HCal
| Digitizer Boards: 1/2 Crate | 7
| Trigger Interface | 7
| XMIT Boards: 1/2 Crate | 2
| Digitizer Crates: 1/2 Crate | 1
| Crate Controllers: 1/2 Crate | 1
| Digitizer Backplanes: 1/2 Crate | 1
| Digitizer JSEB2 Boards: 1/2 Crate | 1 |  |  | Recycled from PHENIX
| Clock Masters: 1/2 Crate | 1
| Digitizer Boards: 7 Crate System | 84 |  |  | 6 crates for EMCal 1 Crate for HCal
| Trigger Interface | 84
| XMIT Boards: 7 Crate System | 28
| Digitizer Crates: 7 Crate System | 7
| Crate Controllers: 7 Crate System | 7
| Digitizer Backplanes: 7 Crate System | 7
| Digitizer JSEB2 Boards: 7 Crate System | 7
| Clock Masters: 7 Crate System | 2
| Patch Fibers: Xmit 7 Crate System | 28
| Patch Fibers: Controller 7 Crate System | 7
| Patch Fibers: Clock Master 7 Crate System | 2
| Patch Fibers: Trigger 7 Crate System | 84
| Total Fiber Count |  | 121
| Power Systems | 2 |  |  | 1 Power system/rack (4 crates)
| Digitizer Boards: Final Production | 276
| Trigger Interface | 276
| XMIT Boards: Final Production | 92
| Digitizer Crates: Final Production | 23
| Crate Controllers: Final Production | 23
| Digitizer Backplanes: Final Production | 23
| Digitizer JSEB2 Boards: Final Production | 23
| Clock Masters: Final Production | 6
| Patch Fibers: XmitFinal Production | 92
| Patch Fibers: Controller Final Production | 23
| Patch Fibers: Clock Master Final Production | 6
| Patch Fibers: Trigger Final Production | 276
| Total Fiber Count |  | 397
| Power Systems | 6 |  |  | 1 Power system/rack (4 crates)

## 1.05.01Costing
sPHENIX WBS 1.05.01: Optical Sensors
Date: 2/28/17
Last Revision Date: 12-April-2018
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Cost Basis | Date | Unit Cost | Total Cost | Total Cost+10% Yield Factor | % Uncertianty | Total Cost + %Design Uncertainty
Optical Sensor:Sector 0 | Hamamatsu | S12572-015P | 1800 | Quote | 2017-02-14 | 13.85 | 0 | 0 | 0 | 0
Optical Sensor: EMCal/Hcal Sensors | Hamamatsu | S12572-015P | 21000 | Budget Quote | 2014-03-20 | 8.5 | 178500 | 196350 | 0.25 | 245437.5
Optical Sensor: Production | Hamamatsu | S12572-015P | 70000 | Budget Quote | 2014-03-20 | 8.5 | 595000 | 654500 | 0.25 | 818125
Test Stand | TBD |  | 2 | Engineering Est | 2017-03-01 | 10000 | 20000 | 22000 | 0.4 | 30800
[7 empty] | SUM | 872850
Preproduction Quote
Production Budgetary Quote