## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
DAQ/Trigger |  | 1.6 |  | DAQ |  | 1.6.1
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| DAQ/Trigger: DAQ Design |  | 1.6.1.1 |  | DAQ Design Summary
| DAQ/Trigger: DAQ Prototype |  | 1.6.1.2 |  | DAQ Prototype Summary
| DAQ/Trigger: DAQ Production |  | 1.6.1.3 |  | DAQ Production

## DAQ Design Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2017-04-11
[6 empty] | Prepared By: | M.L. Purschke
[6 empty] | DocNo. (refer Rev. Log) | DocDB-XXX
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: DAQ Design |  |  |  | 1.6.1.1
WBS Dictionary Definition:
This work package covers the design of the DAQ system, components, and their interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: We have virtually all requireed hardware in hand from the PHENIX experiment. This will allow us to perform test of all design features where decisions based on test have to be made.
Details of the Base Estimate (explanation of the Work)
This work package covers the design of the data acquisition system. As needed, tests with actual hardware will be performed to validate the design. No procurement or fabrication costs are foreseen.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
0
Contingency
M&S Contigency Rules Applied
Labor Contingency Rules Applied:

## DAQ Prototype Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-04-11
[7 empty] | Prepared By: | M.L. Purschke
[7 empty] | DocNo. (refer Rev. Log) | DocDB-XXX
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
DAQ/Trigger: DAQ Protoype |  |  |  | 1.6.1.2
WBS Dictionary Definition:
This work package covers the prototype of the DAQ system, components, and most interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: We have many requirered components in hand from the PHENIX experiment. We will need to procure some server computers and a small network switch.
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the data acquisition system prototype, which will be used to validate the design with actual front-end hardware, and will be used by the detector groups to test their detectors.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  |  | 0
[5 empty] | Total | 0
Contingency
M&S Contigency Rules Applied
The Procurement estimate is based on quotes and is assigned the standard 10%
Labor Contingency Rules Applied:

## DAQ Production Summary
|  |  | sPHENIX Detector |  |  | Date of Est: | 2017-04-11
Relativistic Heavy Ion Collider
|  |  | BASIS of ESTIMATE (BoE) |  |  | Prepared By: | M.L. Purschke
[6 empty] | DocNo. | DocDB-XXX
(refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: DAQ Prototype |  |  |  | 1.6.1.3
WBS Dictionary Definition:
This work package covers the production of the DAQ system
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: 1) A number of additional DAQ boards need to be procured. The full-sized network switch, and the full complement of computers for the event builder need to be procured.
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the data acquisition production system and its deployment.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  | 634317
Contingency
M&S Contigency Rules Applied
Standard items have been assigned 10%
The DCM-2 carry 40% because of an issue with the availability of the main chip, which might trigger a re-layout of the board
The computers procured in the late stage carry 25% because of the uncertainty of the price development.
Labor Contingency Rules Applied:

## 1.6.1.1 DAQ Design
1.06.01.01 |  | DAQ Design
WBS | Activity | Description | Item | Item price | Total Count | Sum | Basis of Estimate | comments
[5 empty] | TOTAL Materials | 0
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.01.01 | 253600 | DAQ Prototype Design | Similar to existing DAQ | SCI3 PO |  | 0 | Complete
PROF4 PO
1.06.01.01 | 253700 | Specify Front-end Layout | Similar to existing DAQ | SCI3 PO | 96 | 192 | Complete
|  |  |  | PROF4 PO | 96
1.06.01.01 | 253800 | Specify event builder and front-end layout | Similar to existing DAQ | SCI3 PO | 96 | 192 | Complete
|  |  |  | PROF4 PO | 96
1.06.01.01 | 253900 | Specifiy high-level components | Similar to prototype design | SCI3 PO | 160 | 320 | Complete
|  |  |  | PROF4 PO | 160
1.06.01.01 | 254000 | Review the Design | Similar to prototype design | SCI3 PO | 120 | 240 | Complete
|  |  |  | PROF4 PO | 120
|  | Grand Total |  |  | 0 | 0 | All work is complete in WBS 1.06.01

## 1.6.1.2 DAQ Prototype
1.06.01.02 | DAQ Prototype
WBS | Activity | Description | Item | item price | Total Count | Sum | Basis of Estimate | comments
1.06.01.02 | S254100 | Procure additional hardware
|  |  | Server machines | 2107 | 6 | 12642 | Vendor Quote |  | Complete
|  |  | 48port network switch | 8399 | 1 | 8399 | ThunderCat Quote |  | Complete
|  | Grant Total |  |  |  | 0
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.01.02 | 254100 | Select hardware | Similar to existing DAQ | SCI3 PO | 16 | 32 | Complete
|  |  |  | PROF4 PO | 16
1.06.01.02 | 254300 | Setup and install the various operating systems | Similar to existing DAQ | SCI3 PO | 19 | 29
|  |  |  | PROF4 PO | 10
1.06.01.02 | 254500 | Software development - Calorimeters and TPC | Similar to existing DAQ | SCI3 PO | 134 | 595
|  |  |  | PROF4 PO | 461
1.06.01.02 | 254800 | Software Deveopment - INTT FELIX readout test | Similar to prototype design | SCI3 PO | 134 | 334
|  |  |  | PROF4 PO | 200
1.06.01.02 | 254700 | Software Deveopment - INTT FELIX/DCM2 downselect review | Similar to prototype design | SCI3 PO | 134 | 334
|  |  |  | PROF4 PO | 200
1.06.01.02 | 254800 | Software Development - Multiple Subsystem Test | Similar to prototype design | SCI3 PO | 96 | 808
|  |  |  | PROF4 PO | 640
|  |  |  | STUD | 72
1.06.01.02 | 254900 | Installation and testing | Similar to prototype design | SCI3 PO | 96 | 96
|  |  |  | PROF4 PO | 0
1.06.01.02 | 255000 | Review of DAQ prototype results | Similar to prototype design | SCI3 PO | 60 | 120
|  |  |  | PROF4 PO | 60
|  | Grand Total |  |  | 2316 | 2316

## 1.6.1.3 DAQ Production
1.06.01.03 |  | DAQ Production
WBS | Activity | Description | Hours | Item | item price | Total Count | Sum | Basis of Estimate | comments | SCI | PROF | TECH | STUD | CRAFT
1.06.01.03 | 255200 | DAQ Production: Design and layout the various types of front-end boards | 96 | [6 empty] | 64 | 32
1.06.01.03 | 255300 | Procure DAQ Production Boards - Provide Requirements to Procurement | 64 | [6 empty] | 64
1.06.01.03 | 255900 | Procure DAQ Production Boards - Delivery Acceptance |  |  |  |  | 104682
|  |  |  | DCM2 | 12000 | 8 | 96000 | Previous Production
|  |  |  | Partition Module | 1447 | 6 | 8682 | Previous Production
|  |  |  | JSEB2 board | 0 | 6 | 0 | see breakdown
|  |  |  | Crate controller Board | 1209 | 0 | 0 | Previous Production | 0 items - Unclear if sufficient spares
1.06.01.03 | 256000 | DAQ Production Boards: Firmware updates | 1264 | [6 empty] | 64 | 960 | 240
1.06.01.03 | 256100 | Procure DAQ Production Crates - Provide Requirements to Procurement | 160 | [6 empty] | 80 | 80
1.06.01.03 | 256700 | Procure DAQ Production Crates - Delivery Acceptance |  |  |  |  | 64000
|  |  |  | Crates | 8000 | 8 | 64000 | based on recent purchase
1.06.01.03 | 256800 | DAQ Production: Crate installation | 608 | [6 empty] | 32 | 32 | 512 |  | 32
1.06.01.03 | 256900 | DAQ Production: Selecting the right technology and brands | 192 | [6 empty] | 96 | 96
1.06.01.03 | 257000 | Procure DAQ Production SEBs - Provide Requirements to Procurement | 160 | [6 empty] | 80 | 80
1.06.01.03 | 257600 | Procure DAQ Production SEBs - Delivery Acceptance |  |  |  |  | 41040
|  |  |  | SEBs | 2280 | 18 | 41040 | Aberdeen quote
1.06.01.03 | 257700 | Production SEBs - Setup Machines | 40 | [6 empty] | 40
1.06.01.03 | 258500 | Production ATPs - Setup Machines | 40 | [6 empty] | 40
1.06.01.03 | 258800 | Production jSEB Slow control computers - Setup Machines | 40 | [6 empty] | 40
1.06.01.03 | 259600 | Production Buffer Boxes - Setup Machines | 40 | [6 empty] | 40
1.06.01.03 | 257800 | Procure DAQ Production ATPs - Provide Requirements to Procurement | 160 | [6 empty] | 80 | 80
1.06.01.03 | 258400 | Procure DAQ Production ATPs - Delivery Acceptance |  |  |  |  | 98048
|  |  |  | ATPs | 3064 | 32 | 98048 | Aberdeen quote
1.06.01.03 | 258600 | DAQ Production: Procure jSEB Slow control computers | 160 | [6 empty] | 80 | 80
1.06.01.03 | 258700 | Procure DAQ Production jSEB Slow control computers - Delivery Acceptance |  |  |  |  | 16856
|  |  |  | server machine | 2107 | 8 | 16856 | vendor quote
1.06.01.03 | 260500 | DAQ Production: Modify and Debug event builder software | 640 | [6 empty] | 320 | 320
1.06.01.03 | 258900 | Procure DAQ Production Buffer Boxes - Provide Requirements to Procurement | 80 | [6 empty] | 40 | 40
1.06.01.03 | 259500 | Procure DAQ Production Buffer Boxes - Delivery Acceptance |  |  |  |  | 223540
|  |  |  | Buffer boxes | 44708 | 5 | 223540 | RAID-INC quote | pro-rated from 19-unit quote
1.06.01.03 | 259700 | Procure DAQ Production Main Switches - Provide Requirements to Procurement | 192 | [6 empty] | 96 | 96
1.06.01.03 | 260300 | Procure DAQ Production Main Switches - Delivery Acceptance |  |  |  |  | 86151
|  |  |  | Network switch 10GbE | 27983 | 1 | 27983 | Thundercat Quote L 3+4
|  |  |  | Optical Receivers 10G | 300 | 34 | 10200 | Thundercat Quote L 7
|  |  |  | Optical Receivers 40G | 900 | 4 | 3600 | Thundercat Quote L 6 | interconnect between 10 and 2x1GbE
|  |  |  | Optical Receivers 100G | 1595 | 2 | 3190 | Thundercat Quote L 5 | uplink to RCF
|  |  |  | Network Switch 1GbE | 8399 | 2 | 16798 | Thundercat Quote L 1+2
|  |  |  | Network Switch 1000Gbit/s | 994 | 2 | 1988 | Cisco Switch Quote
|  |  |  | additional software licenses | 2799 | 8 | 22392 | Quotes_1.6.1.3!B155
1.06.01.03 | 260400 | DAQ Production: Setting up the switches | 188 | [6 empty] | 88 | 56 | 44
1.06.01.03 | 260600 | DAQ Production: DAQ Software development | 3520 | [6 empty] | 880 | 880 | 1760
1.06.01.03 | 260700 | DAQ Readiness Review | 320 | [6 empty] | 240 | 80
1.06.01.03 | 260800 | DAQ Production: DAQ Ready for Operation
|  | TOTAL Hours | 7964 |  |  | TOTAL Materials | 634317 |  | LABOR Hours Checksum | 7964

## Quotes_1.6.1.3
Quotes
Price pro-rated for 5 rather than 19 machines - $849,452 *5/19 = $223540
https://www.amazon.com/Cisco-WS-C2960X-48TD-L-Catalyst-2960-x-Switch/dp/B00EAM58N8

## DAQ JSEB-2 Board
sPHENIX WBS 1.6.1.3: Digitizer JEB2 Board
DATE: 8/10/15
DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | Vendor | UNIT | MODULE | Notes
[5 empty] | COST | COST
PC BOARD | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 58.61 | 58.61
NRE | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 0 | 0
ELECTRICAL TEST | ELECTROTEK | PCIe_v2 | 1 | ELECTROTEK | 0 | 0
64K I2C™ Serial EEPROM | MICROCHIP TECHNOLOGY | 24LC64IP | 1 | Arrow | 0.43 | 0.43
8 PIN DIP SOCKET | AMP | 2-640463-3 | 1 |  | 0.05 | 0.05
Low Profile Header, Rt Angle, 4 Wall | 3M | 30310-5002HB | 1 |  | 0.32 | 0.32
SOLID ALUMINUM CAPACITOR WITH ORGANIC SEMICONDUCTOR ELECTROLYTE - 120 MFD - 20V | VISHAY | 94SP127X0020EBP | 2 |  |  |  | Obsolete
TRANSCEIVER | AVAGO | AFBR-59R5LZ | 2 | Arrow | 29.99 | 59.98
USB TYPE-B CONNECTOR, RECEPTACLE, RIGHT ANGLE, 4 POSITION, THRU HOLE - Replacement part for 787780-1 | AMP/TYCO | 292304-1 | 1 |  | 0.31 | 0.31
FERRITE BEAD - 0603 - 120 OHM | MURATA | BLM18PG121SN1D | 2 |  | 0.0194 | 0.0388
FERRITE BEAD - 0805 - 330 OHM | MURATA | BLM21PG331SN1D | 5 |  | 0.035 | 0.175
CAPACITOR - 0402 - .01 MFD (10nf) - 50V | CALCHIP | GMC04X7R103K50NT | 20 |  | 0.03 | 0.6
CAPACITOR - 0402 - .1 MFD (10nf) - 50V | CALCHIP | GMC04X7R104K50NT | 124 |  | 0.01 | 1.24
CAPACITOR - 0603 - 0.1 MFD (100nf) | CALCHIP | GMC10X7R104K25NT | 1 |  | 0.03 | 0.03
CAPACITOR - 0603 - 1 MFD - 10V | CALCHIP | GMC10Y5V105Z10NT | 2 |  | 0.01 | 0.02
CAPACITOR - 0603 - 2.2 MFD - 16V (X5R) | MURATA | GRM188R61C225KE15D | 3 |  | 0.017 | 0.051
CAPACITOR - 1210 - 10 MFD - 16 VDC - (X7R) | CALCHIP | GMC32X7R106K16NT | 21 |  | 0.35 | 7.35
EZ-USB FX2LP USB MICROCONTROLLER, 56 PIN SSOP | CYPRESS SEMICONDUCTOR | CY7C68013A-56PVXC | 1 | Arrow | 6.78 | 6.78
CAPACITOR - 10 MFD - 20V - "B" SIZE | PHILIPS | 49MC106B020ASFT | 1 |  | 0.42 | 0.42
CAPACITOR - 4700 pf 250 VAC CERAMIC SMD | PANASONIC | ECK-TBC472MF | 1 |  | 1.02 | 1.02
CRYSTAL - 24000 MHz, 20 pf, HC-49/US | ECS | ECS-240-20-4 | 1 |  | 0.518 | 0.518
CAPACITOR - 220 MFD 4 VDC - SP, POLYMER ALUMINUM SMD | PANASONIC | EEFUE0G221LR | 4 |  | 2.6395 | 10.5581
ARRIA GX FPGA 780 PIN | ALTERA | EP1AGX50DF780C6 | 1 | Arrow | 250.7 | 250.7
16 MBIT SERIAL CONFIG | ALTERA | EPCS16SI8 | 1 | Arrow | 15.81 | 15.81
FUSE - 1.5 AMP | LITTLEFUSE | 025101.5MXL | 1 |  | 0.364 | 0.364
FUSE HOLDER | AMP/TYCO | 2-5331272-7 | 2 | Arrow | 0.245 | 0.49
CAPACITOR - 1206 - 10 MFD - 25 VDC - X5R | MURATA | GRM31CR61E106KA12L | 4 |  | 0.09 | 0.36
HEADER - 2 | SAMTEC | TSW-102-07-G-S | 1 |  | 0.0586 | 0.0586
HEADER - 3 | SAMTEC | TSW-103-07-G-S | 1 |  | 0.0886 | 0.0886
HEADER - 10 | SAMTEC | TSW-105-07-G-D | 1 |  | 0.29 | 0.29
LOW SKEW, 1 TO 2 DIFFERENTIAL TO LVCMOS / LVTTL FANOUT BUFFER | IDT | ICS83026BMI-01LF | 1 | Digi Key | 5.846 | 5.846
LOW SKEW, 1 TO 4 DIFFERENTIAL TO LVDS FANOUT BUFFER | IDT | ICS8543BGLF | 1 | Digi Key | 16.0024 | 16.0024
LED -PCB MOUNT | LEDTRONICS | 555M-2101-001 | 4 |  | 1.4 | 5.6
CHIP COILS FOR HIGH FREQUENCY MONOLITHIC TYPE | MURATA | LQG15HN9N1J02D | 2 |  | 0.022 | 0.044
1.5V FAST TRANSIENT 1.5A LDO | LINEAR TECHNOLOGY | LT1963AEST-3.3 | 1 | Digi Key | 3.1696 | 3.1696
1.5A LOW INPUT VOLTAGE VLDO LINEAR REGULATOR, 10 LEAD PLASTIC MSOP | LINEAR TECHNOLOGY | LTC3026EMSE#PBF | 1 | Arrow | 2.2 | 2.2
LVDS CLOCK OSCILLATOR | PLETRONICS | LV7745DEV-100.000M | 1 | Arrow | 13.26 | 13.26
LVDS CLOCK OSCILLATOR | PLETRONICS | LV7745DEV-156.250M | 1 | Arrow | 14.95 | 14.95
5 VOLT LOW DROPOUT REGULATOR | MICREL | MIC39100-5.0WS | 1 | Arrow | 0.8917 | 0.8917
MTHOLE1 | NEVIS | MTHOLE1 | 2 |  | 0 | 0
PCI_ EXPRESS_X4 | PRINTED ON THE PCB | PCI_ EXPRESS_X4 | 1 |  | 0 | 0
6A, 12V, INPUT NON-ISOLATED WIDE OUTPUT ADJUST POWER MODULE EUS PACKAGE | TEXAS INSTRUMENTS | PTH12000WAD | 2 | Arrow | 7.97 | 15.94
RESISTOR - 0402 - 100K OHM | CALCHIP | RM04F1003CT | 3 |  | 0.01 | 0.03
RESISTOR - 0402 - 2K OHM | CALCHIP | RM04F2001CT | 5 |  | 0.01 | 0.05
RESISTOR - 0402 - 4.75K OHM | CALCHIP | RM04F4751CT | 4 |  | 0.01 | 0.04
RESISTOR - 0402 - 49.9K OHM | CALCHIP | RM04F4992CT | 2 |  | 0.01 | 0.02
RESISTOR - 0402 - 100 OHM | CALCHIP | RM04F1000CT | 3 |  | 0.01 | 0.03
RESISTOR - 0402 - 1K OHM | CALCHIP | RM04F1001CT | 3 |  | 0.01 | 0.03
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 2 |  | 0.01 | 0.02
RESISTOR - 0402 - 49.9 OHM | CALCHIP | RM04F49R9CT | 16 |  | 0.01 | 0.16
RESISTOR - 0603 - 10K OHM | CALCHIP | RM06F1002CT | 4 |  | 0.01 | 0.04
RESISTOR - 0603 - 1K OHM | CALCHIP | RM06F1001CT | 4 |  | 0.01 | 0.04
RESISTOR - 0603 - 2.21K | CALCHIP | RM06F2211CT | 2 |  | 0.01 | 0.02
RESISTOR - 0603 - 2K OHM | CALCHIP | RM06F2001CT | 1 |  | 0.01 | 0.01
RESISTOR - 0603 - 392 OHM | CALCHIP | RM06F3920CT | 4 |  | 0.01 | 0.04
RESISTOR - 0603 - 4.75K OHM | CALCHIP | RM06F4751CT | 6 |  | 0.01 | 0.06
RESISTOR - 0805 - 100K OHM | CALCHIP | RM10F1003CT | 2 |  | 0.01 | 0.02
RESISTOR - 1206 - 10 MEG OHM | CALCHIP | RM12J1006CT | 1 |  | 0.01 | 0.01
R-PAC - 51 OHM | CTS | 741X163510JTR | 7 |  | 0.062 | 0.434
2.5 GBPS TO 3.125 GBPS TRANSCEIVER | TEXAS INSTRUMENTS | TLK3101IRCP | 2 | Arrow | 19.2 | 38.4
TP | NEVIS | TP | 4 |  | 0 | 0
LDO VOLTAGE REGULATOR, 2.5V | TEXAS INSTRUMENTS | TPS79625DCQR | 2 | Arrow | 1.09 | 2.18
TPS SERIES TANTALUM LOW ESR 100 MFD - 10V | AVX | TPSC107K010R0075 | 10 |  | 0.26 | 2.6
ONE TIME DOCUMENTATION | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 |  | 0 | 0
SET-UP FOR SMT ASSEMBLY | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 |  | 0 | 0
COMPUTER AND MOUNTING BRACKETS PC BRACKET STD PCI | KEYSTONE ELECTRONICS | 9203 | 1 |  | 1.59 | 1.59
SCREW - 2-56 X 1/4 SLOT ROUND M/S, 8-8 SS | TOWER FASTENER | 2C25MSRS | 2 |  | 0.14 | 0.28
NUT - 2-56 HEX M/S - 18-8 SS | TOWER FASTENER | 2CNHMS | 2 |  | 0.08 | 0.16
MISC |  |  | 1 |  | 32.54 | 32.54
ASSEMBLY PRINTED CIRCUIT BOARD MICROBOONE_PHENIX_PCIE | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 | APPLICAD | 110 | 110
SOLDER PASTE STENCIL | APPLICAD | MICROBOONE_PHENIX_PCIE | 1 | APPLICAD | 0 | 0
TOTAL | [5 empty] | 683.3698