## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
DAQ/Trigger |  | 1.6 |  | Global Level 1 (GL1) |  | 1.6.3
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| DAQ/Trigger: Global Level 1 Design |  | 1.6.3.1 |  | Global Level 1 Design Summary
| DAQ/Trigger: Global Level 1 Prototype |  | 1.6.3.2 |  | Global Level 1 Prototype Summary
| DAQ/Trigger: Global Level 1 Production |  | 1.6.3.3 |  | Global Level 1 Production Summary

## GL1 Design Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-08
[6 empty] | Prepared By: | M.L. Purschke
[6 empty] | DocNo. (refer Rev. Log) | 76 v8
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: Global Level 1 Design |  |  |  | 1.06.03.01
WBS Dictionary Definition:
This work package covers the design of the DAQ system, components, and their interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: We have virtually all requireed hardware in hand from the PHENIX experiment. This will allow us to perform test of all design features where decisions based on test have to be made.
Details of the Base Estimate (explanation of the Work)
This work package covers the design of the global level 1 system. As needed, tests with actual hardware will be performed to validate the design. No procurement or fabrication costs are foreseen.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Parts Procurement | Catalogue/Quote/Eng Estimate |  | 0
Contingency
M&S Contigency Rules Applied
Labor Contingency Rules Applied:

## GL1 Prototype Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-08
[6 empty] | Prepared By: | M.L. Purschke
[6 empty] | DocNo. (refer Rev. Log) | 76 v8
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: GL1 Protoype |  |  |  | 1.06.03.02
WBS Dictionary Definition:
This work package covers the prototype of the DAQ system, components, and most interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the data acquisition system prototype, which will be used to validate the design with actual front-end hardware, and will be used by the detector groups to test their detectors.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  | 0
Contingency
M&S Contigency Rules Applied
The Procurement estimate is based on quotes and is assigned the standard 10%
Labor Contingency Rules Applied:

## GL1 Production Summary
|  |  | sPHENIX Detector |  |  | Date of Est: | 2019-02-08
Relativistic Heavy Ion Collider
|  |  | BASIS of ESTIMATE (BoE) |  |  | Prepared By: | M.L. Purschke
[6 empty] | DocNo. | 76 v8
(refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: GL1 Prototype |  |  |  | 1.06.03.03
WBS Dictionary Definition:
This work package covers the production of the DAQ system
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: 1) The full complement of additional GL1 boards need to be procured
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the data acquisition production system and its deployment.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  | 28150
Contingency
M&S Contigency Rules Applied
Standard items have been assigned 10%
The DCM-2 carry 40% because of an issue with the availability of the main chip, which might trigger a re-layout of the board
The computers procured in the late stage carry 25% because of the uncertainty of the price development.
Labor Contingency Rules Applied:

## 1.6.3.1 GL1 Design
1.06.03.01 |  | GL1 Design
| Activity |  | Description | unit price $ | quantity | Sum | unit price $ | quantity | Sum | part nr / what | quote / info
[5 empty] | Primary |  |  | Alternate
TOTAL Materials | [5 empty] | 0
Labor |  | 1.06.03.01
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.03.01 | 265500 | GL1 Design: Evaluate Performance Requirements | previous PHENIX trigger | PROF | 48 | 192 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 144
1.06.03.01 | 265600 | GL1: Write design specifications | previous PHENIX trigger | PROF | 48 | 156 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 108
|  | TOTAL Labor |  |  | 0 | 0

## 1.6.3.2 GL1 Prototype
1.06.03.02 |  | GL1 Prototype
WBS | Activity | Description | Items | Unit Price $ | Quantity | Sum | Unit Price $ | Quantity | Sum | Part nr./ What | Quote / Info
[5 empty] | Primary |  |  | Alternate
1.06.03.02 | 265900 | Procure hardware | FPGA Boards | 2953 | 3 | 8859 |  |  | 0 |  | Already bought, BNL internal req. | Complete
|  |  | MTO <->MTP fiber couplers | 130 | 12 | 1560 | 130 | 12 | 1560 | 12 MTP - 12 MTO | Catalog price | Complete
|  |  | MTP <-> MPT fiber couplers | 225 | 6 | 1350 | 225 | 6 | 1350 | 48 -> 4x12 | Catalog price | Complete
|  |  | Fiber patch panel | 450 | 2 | 900 | 450 | 2 | 900 | 48 ports | Catalog price | Complete
|  |  |  | TOTAL Materials |  | 0
Labor |  | 1.6.3.2
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.03.02 | 265700 | GL1 Proto: Select Hardware | previous PHENIX trigger | PROF | 48 | 192 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 144
1.06.03.02 | 265800 | GL1 Proto: Procure Hardware Labor | previous PHENIX trigger | PROF | 24 | 48 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 24
1.06.03.02 | 266500 | GL1 Proto: setup Hardware | previous PHENIX trigger | PROF | 0 | 112
|  |  |  | TECH | 0
|  |  |  | STUD | 26
|  |  |  | SCI | 86
1.06.03.02 | 266100 | GL1 Proto: Develop firmware | previous PHENIX trigger | PROF | 416 | 530
|  |  |  | TECH | 0
|  |  |  | SCI | 114
1.06.03.02 | 266300 | GL1 Proto: Design I/O Transition Module | previous PHENIX trigger | TECH | 64 | 64
|  |  |  | SCI | 0
1.06.03.02 | 266600 | GL1 Proto: test prototype | previous PHENIX trigger | PROF | 240 | 560
|  |  |  | TECH | 0
|  |  |  | STUD | 240
|  |  |  | SCI | 80
1.06.03.02 | 266700 | GL1 Proto: Evaluate performance | previous PHENIX trigger | PROF | 80 | 460
|  |  |  | TECH | 0
|  |  |  | STUD | 200
|  |  |  | SCI | 180
1.06.03.02 | 266800 | GL1 Proto: Update Design Specifications | previous PHENIX trigger | PROF | 80 | 204
|  |  |  | TECH | 0
|  |  |  | SCI | 124
|  | TOTAL Labor |  |  | 1930 | 1930

## 1.6.3.3 GL1 Production
1.06.03.03 |  | GL1 Production
WBS | Activity | Description | Items | Unit price $ | Quantity | Sum | Unit Price $ | Quantity | Sum | Part nr / What | Quote / Info
Primary
1.06.03.03 | 267600 | Procure production GL1 hardware | FPGA Boards | 6000 | 3 | 18000 |  |  |  |  | Internal BNL quote | Only if we have to make a new version of the board.
|  |  | MTO <->MTP fiber couplers | 130 | 40 | 5200 |  |  |  | 12 MTP - 12 MTO | catalog price
|  |  | MTP <-> MPT fiber couplers | 225 | 10 | 2250 |  |  |  | 48 -> 4x12 | catalog price
|  |  | Fiber patch panel | 450 | 6 | 2700 |  |  |  | 48 ports | catalog price
|  |  |  | TOTAL Materials |  | 28150
Labor |  | 1.6.3.3
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.03.03 | 267000 | GL1 Production: Provide Requirements | previous PHENIX trigger | PROF | 0 | 72
|  |  |  | TECH | 0
|  |  |  | SCI | 72
1.06.03.03 | 266900 | GL1 Production: final firmware updates | previous PHENIX trigger | PROF | 406 | 534
|  |  |  | TECH | 0
|  |  |  | STUD | 0
|  |  |  | SCI | 128
1.06.03.03 | 267900 | GL1 Production: install GL1 system | previous PHENIX trigger | PROF | 80 | 560
|  |  |  | TECH | 320
|  |  |  | STUD | 160
|  |  |  | SCI | 0
1.06.03.03 | 268000 / 268010 | GL1 Production: commission GL1 system | previous PHENIX trigger | PROF | 216 | 396
|  |  |  | TECH | 0
|  |  |  | STUD | 0
|  |  |  | SCI | 180
1.06.03.03 | 268100 | GL1 Production: additional firmware improvements | previous PHENIX trigger | PROF | 156 | 156
|  |  |  | TECH | 0
|  |  |  | STUD | 0
|  |  |  | SCI | 0
|  | TOTAL Labor |  |  | 1718 | 1718