## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
INTmediate Tracker (INTT) |  | 3.01 |  | INTT Electronics |  | 03.01.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Silicon Sensor |  | 03.01.02.01 |  | 03.01.02.01 BoE Summary
| Silicon Sensor QA |  | 03.01.02.02 |  | 03.01.02.02 BoE Summary
| HDI Cable |  | 03.01.02.03 |  | 03.01.02.03 BoE Summary
| Extension Cable and Conversion Board |  | 03.01.02.04 |  | 03.01.02.04 BoE Summary
| FPHX Chips |  | 03.01.02.05 |  | 03.01.02.05 BoE Summary
| Control Account |  | Description
| INTT Electronics |  | This account is responsible for procurements of purchasing INTT Electronics complements: silicon sensors, High Density Interconect cables (HDI), extension cables, spares FPHX chips and ROC FVTX.
Note on D21: Eric Mannel:

## Silicon Sensor Summary
[7 empty] | Date of Est: | 2018-01-10
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Silicon Sensors |  |  |  | 03.01.02.01
WBS Dictionary Definition:
Technical Scope: Procurement of silicon sensors Work Statment: - Purchasing of silicon sensors
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
See Silicon Sensors Details
Assumptions Used in Developing Estimate
- The estimate is based on quotation from Hamamatsu Photonics Company (HPK) responsible of the production of silicon strip sensors.
Details of the Base Estimate (explanation of the Work)
The Hamamatsu Photonics Company provides us with quotation for the production of silicon strip sensor for layer 0.
Cost Summary
[5 empty] | Follow Links | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Procurement of silicon sensors |  | Quotation from HPK |  |  | 210000 | 210000
of layer 0
| Total Work Package Cost [$] |  |  |  |  | 210000 | 210000
Contingency
M&S Contigency Rules Applied
Procurement with quotation : 0%
Labor Contingency Rules Applied:

## Silicon Sensor Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
03.01.02 | INTT Electronics | [11 empty] | 210000 | 210000
03.01.02.01 | Silicon Sensors | [7 empty] | 0 | 210000 | 0 | 210000
03.01.02.01.01 |  | Procurement Silicon sensor prototypes | Hamamatsu Compagny | 50000 | Purshased | Quotation | 0 | 0
03.01.02.01.04 |  | Procurement Silicon Sensor mass production | Hamamatsu Compagny | 160000 | Pending | Quotation | 0 | 0

## Silicon Sensor QA Summary
[7 empty] | Date of Est: | 2018-01-10
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Silicon Sensor QA |  |  |  | 03.01.02.02
WBS Dictionary Definition:
Technical Scope: Silicon Sensor Testing at National Central University (NCU) in Taiwan Work Statment: - Cost for setting up the bench test for the silicon sensor testing at NCU
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
See Silicon Sensor QA Details
Assumptions Used in Developing Estimate
- The estimate is based our expertise in the silicon sensor testing for VTX/PHENIX project at BNL
Details of the Base Estimate (explanation of the Work)
The Hamamatsu Photonics Company provides us with quotations for silicon strip sensors prototypes and mass production.
Cost Summary
[5 empty] | Follow Links | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Procurement of silicon sensors |  | Quotation from HPK |  |  | 50000 | 50000
of layer 1,2,3
| Total Work Package Cost [$] |  |  |  |  | 50000 | 50000
Contingency
M&S Contigency Rules Applied
Procurements with quotation : 0%
Labor Contingency Rules Applied:

## Silicon Sensor QA Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.11.2 | INTT Electronics | [11 empty] | 50000 | 50000
1.11.2.2 | Silicon Sensor Layer 1,2,3 | [7 empty] | 0 | 50000 | 0 | 50000
1.11.2.2.2 |  | Procurement prototype 1 | National Central University | 50000 | Pending | Quotation | 0 | 0

## HDI Cable Summary
[7 empty] | Date of Est: | 2018-01-10
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
HDI Cable |  |  |  | 03.01.02.03
WBS Dictionary Definition:
Technical Scope: Procurement for design and production of HDI Cable Work Statment: - Design and fabrication of prototypes and mass production of High Density Interconnect (HDI) Cable.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
See HDI Cable Details
Assumptions Used in Developing Estimate
- The estimate is based on quotations from Yamashita Company responsible for the production of prototype and mass production of High Density Interconnect Cable (HDI).
Details of the Base Estimate (explanation of the Work)
The Yamashita Company provides us with quotations for HDI prototypes and mass production.
Cost Summary
[5 empty] | Follow Links | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Procurement of HDI Layer 1,2,3 |  | Quotation from Yamashita Co. |  |  | 180000 | 180000
| Total Work Package Cost [$] |  |  |  |  | 180000 | 180000
Contingency
M&S Contigency Rules Applied
Procurements with quotation : 0%
Labor Contingency Rules Applied:

## HDI Cable Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
03.01.02 | INTT Electronics | [11 empty] | 180000 | 180000
03.01.02.03 | HDI Cable | [7 empty] | 0 | 180000 | 0 | 180000
03.01.02.03.02 |  | Procurement prototype | Yamashita Compagny | 30000 | Purshased | Quotation | 0 | 0
03.01.02.03.05 |  | Procurement production | Yamashita Compagny | 150000 | Pending | Quotation | 0 | 0

## Ext. and Conv. Cables Summary
[7 empty] | Date of Est: | 2018-01-18
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Extension Cable and Conversion Cable |  |  |  | 03.01.02.04
WBS Dictionary Definition:
Technical Scope: Procurement for design and production of extension cable and conversion cable from TAIYO-KOSAKUSHO co. Work Statment: - Design and fabrication of prototypes and mass production of Extension Cable and conversion board
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
See Extension Cable and Conversion Cable Details
Assumptions Used in Developing Estimate
- The estimate is based on quotations from TAIYO-KOSAKUSHO co. Company responsible for the production of prototype and mass production of Extension Cable and Conversion cable.
Details of the Base Estimate (explanation of the Work)
The TAIYO-KOSAKUSHO co. provides us with quotations for extension cable prototypes and mass production.
Cost Summary
[5 empty] | Follow Links | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Procurement Ext. Cable Layer 0 |  | Quotation from Print Denshi Kenkyuujo Co. |  |  | 450000 | #REF!
| Total Work Package Cost [$] |  |  |  |  | 450000 | #REF!
Contingency
M&S Contigency Rules Applied
Procurements with quotation : 0%
Labor Contingency Rules Applied:

## Ext. and Conv. Cables Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
03.01.02 | INTT Electronics | [11 empty] | 450000 | #REF!
03.01.02.04 | Extension Cable and Conversion Board | [7 empty] | #REF! | 450000 | #REF! | #REF!
1.11.2.5.7 |  | Procurement production | PDK Company | 450000 | Pending | Quotation | 0 | 0

## FPHX Chips Summary
[7 empty] | Date of Est: | 2018-01-10
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
FPHX Chips |  |  |  | 03.01.02.05
WBS Dictionary Definition:
Technical Scope: Procurement for FPHX Chips Work Statment: - Purchasing FPHX Chips from MOSIS.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
See FPHX Chips Details
Assumptions Used in Developing Estimate
- The estimate is based on quotations from MOSIS Company responsible for the production of FPHX Chips.
Details of the Base Estimate (explanation of the Work)
MOSIS Company provides us with quotation for FPHX Chips. This new order of chips will be added to existing FPHX Chips that we have. This will allow enough chips for INTT and some spares.
Cost Summary
[5 empty] | Follow Links | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Procurement FPHX Chips |  | Quotation from MOSIS. |  |  | 43600 | 43600
| Total Work Package Cost [$] |  |  |  |  | 43600 | 43600
Contingency
M&S Contigency Rules Applied
Procurements with quotation : 0%
Labor Contingency Rules Applied:

## FPHX Chips Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
03.01.02 | INTT Electronics | [11 empty] | 43600 | 43600
03.01.02.05 | FPHX Chips | [7 empty] | 0 | 43600 | 0 | 43600
03.01.02.05.01 |  | Procurement FPHX Chips | MOSIS | 43600 | Purshased | Quotation | 0 | 0