## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
INTmediate Tracker (INTT) |  | 3.01 |  | INTT Integration in sPHENIX |  | 03.01.03
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Electronic Services |  | 03.01.03.02 |  | 03.01.03.02 BoE Summary
| Control Account |  | Description
| INTT Integration in sPHENIX |  | This account is responsible for purchasing the fibers' cables, power cables and patch panel as well procurements for spares (if needed) Low voltage and bias voltage power supplies.
Note on D22: Eric Mannel:

## Electronic Services Summary
[8 empty] | Date of Est: | 2018-10-12
[8 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  |  | Control Account Number
Elctronics Services |  |  |  | 3.01.03.02
WBS Dictionary Definition:
Technical Scope: contains work required for INTT electronics services Work Statment: Purchase INTT fibers' cables, power cables, patch panel as well some spares Low and Bias voltage power supplies.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See Electronic Services Details
Assumptions Used in Developing Estimate
- The estimate of purchasing the fibers's cables, power cables and patch panel were estimated by engineers experts based on their previous purchasing of similar items for PHENIX experiment. - The low voltage and bias voltage power supplies spares were estimated based on previous similar purchasing done for FVTX detector in PHENIX.
Details of the Base Estimate (explanation of the Work)
The same items (Fibers cables, power cables, low voltage power supplies and bias voltage power supplies) were purchased previously for FVTX/PHENIX detector.
Cost Summary
[5 empty] | Follow Links |  | Details
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost |  | Cost + Contingency
| Procurements of cables and |  | purchased previousely in FVTX/PHENIX |  |  | 45000 |  | 45000
power supplies
| Total Work Package Cost [$] |  |  |  |  | 45000 |  | 45000
Contingency
M&S Contigency Rules Applied
Procurement cables, power supplies: 0%
Labor Contingency Rules Applied:

## Electronic Services Details
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
3.01.03 | INTT Integration in sPHENIX | [11 empty] | 45000 | 45000
3.01.03.02 | Electronic Services | [7 empty] | 0 | 45000 | 0 | 45000
3.01.03.02.01 |  | Fibers + power cables + patch panel |  | 25000 | Pending | Experience | 0 | 0
3.01.03.02.03 |  | Low Voltage Power Supplies |  | 10000 | Pending | Experience | 0 | 0
3.01.03.02.04 |  | Bias Voltage Power Supplies |  | 10000 | Pending | Experience | 0 | 0