## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
INTmediate Tracker (INTT) |  | 3.01 |  | INTT Construction |  | 3.01.01
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Ladder Assembly |  | 3.01.01.01 |  | 3.01.01.01 BoE Summary
| Stave CFC |  | 3.01.01.02 |  | 3.01.01.02 BoE Summary
| EndRings |  | 3.01.01.03 |  | 3.01.01.03 BoE Summary
| Barrel Assembly |  | 3.01.01.04 |  | 3.01.01.04 BoE Summary
| Support Rails |  | 3.01.01.05 |  | 3.01.01.05 BoE Summary
| INTT Assembly |  | 3.01.01.06 |  | 3.01.01.06 BoE Summary
| Control Account |  | Description
| INTT Construction |  | This account is responsible for the construction of INTT tracker starting from design, fabrication, assembly, testing of: 1) ladders, 2) Staves CFC, 3) EndRings, 4) Barrel Assembly, 5) INTT support Rails, and 6) INTT Final assembly
Note on D22: Eric Mannel:

## Ladder_Assembly_Summary
[8 empty] | Date of Est: | 2018-10-12
[8 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  |  | Control Account Number
Ladder Assembly |  |  |  | 3.01.01.01
WBS Dictionary Definition:
Technical Scope: contains all work required for the construction of ladders Work Statment: Design, fabrication, assembly and survey of ladders
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See Ladder_Assembly_Details
See Ladder_Assembly Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: design technician and mechanical technician for the design and assembly of the prototype ladder were estimated based on BNL official costs. - The cost for the fabrication of fixtures for ladder assembly at BNL craft shop was based on our expertise working with BNL craft shop in the previous project such as a silicon vertex tracker (VTX). - The production cost of ladders was based on our expertise and contact with FNAL experts worked on our past project VTX at FNAL as well our contacts with Instrumentation Division at BNL.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the design labor, fabrication of fixtures, ladder prototypin, and ladders production. Prior to ladders production, there is a Final Design and Safety Review.
Cost Summary
|  | Follow Links |  |  | Details |  | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost |  | Cost + Contingency
| Engineer/Technician Labor at BNL |  | BNL Labor cost Estimate |  |  | 125158 |  | 125158
| Ladder production |  | VTX SOW/Inst. Div BNL |  |  | 66937 |  | 66937
| Total Work Package Cost [$] |  |  |  |  | 192095 |  | 192095
Contingency
M&S Contigency Rules Applied
SOW of Ladder Production of layer-0: 0%
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## Ladder_Assembly_Details
WBS | Description | Item | Location | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
3.01.01 | INTT Construction | [11 empty] | 66937 | 66937
3.01.01.01 | Ladder Assembly | [7 empty] | 0 | 66937 | 0 | 66937
3.01.01.01.05 |  | Fabrication Ladder Assembly Fixtures Prototype | Craft | 3347 | Pending | Experience/SOW | 0 | 0
3.01.01.01.12 |  | Fabrication Final Ladder Assembly Fixtures Prototype | Craft | 3347 | Pending | Experience/SOW | 0 | 0
3.01.01.01.18 |  | Ladder Production: Wire-bonding Encapsulation | Inst. Div.BNL | 60243 | Pending | Experience/SOW | 0 | 0

## Ladder_Assembly_Labor
WBS: 3.01.01
INTT Construction: Ladder Layer 0 | Ladder Assembly
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.01 | Assembly Sensor Module Prototype (PreProduction) | 40 |  |  |  |  | 4913
3.01.01.02 | Testing Sensor Module Prototype (Preproduction) | 34 |  |  |  |  | 4176
3.01.01.04 | Design Ladder Assembly Fixtures Prototype |  | 20 |  |  |  | 2456
3.01.01.05 | Fabrication Ladder Assembly Fixture Prototype | 50 |  |  |  |  | 6122
3.01.01.06 | Assembly Ladder Prototype (Preproduction) | 60 |  |  |  |  | 7369
3.01.01.07 | Testing Ladder Prototype (Preproduction) | 20 |  |  |  |  | 2456
3.01.01.09 | Ladder Protoype (Preproduction) Sucessful | 2 |  |  |  |  | 246
| Fabricaon Final Ladder Assembly Fixtures | 50 |  |  |  |  | 6122
| Ladder Production |  |  | 800 |  |  | 91298
Total Cost |  | Total Cost |  |  |  |  | 125158

## Stave_CFC Summary
[8 empty] | Date of Est: | 2018-10-12
[8 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  |  | Control Account Number
Stave CFC |  |  |  | 3.01.01.02
WBS Dictionary Definition:
Technical Scope: contains all work required for the construction of stave CFC Work Statment: Design, fabrication, and production of the stave for ladders
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See Stave CFC Details
See Stave CFC Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: design technician of the stave of ladder was estimated based on BNL official costs. - The production cost of stave of ladder was based on our expertise with previous work done at LBNL for VTX stave production.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the design labor, fabrication, and production of staves of ladders.
Cost Summary
|  | Follow Links |  |  | Details |  | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost |  | Cost + Contingency
| Technicians/Engineer Labor at BNL |  | BNL Labor cost Estimate |  |  | 52122 |  | 52122
| Stave CFC Production |  | VTX SOW/LBNL |  |  | 27890 |  | 27890
| Total Work Package Cost [$] |  |  |  |  | 80012 |  | 80012
Contingency
M&S Contigency Rules Applied
SOW of stave CFC Production: 0%
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## Stave_CFC Details
WBS | Description | Item | Location | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
3.01.01 | INTT Construction | [11 empty] | 27890 | 27890
3.01.01.02 | Stave CFC | [7 empty] | 0 | 27890 | 0 | 27890
3.01.01.02.04 |  | Procurement Stave Pre-production | LBNL | 3347 | Pending | Experience/SOW | 0 | 0
3.01.01.02.08 |  | Procurement Stave Production | LBNL | 24543 | Pending | Experience/SOW | 0 | 0

## Stave_CFC Labor
WBS: 3.01.01.02
INTT Construction: Ladder Layer 0 | Stave CFC
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.02.01 | Conceptual Design of the Stave | 40 |  |  |  |  | 4913
3.01.01.02.02 | FEA analysis Thermal and Structura | 40 |  |  |  |  | 4913
3.01.01.02.03 | Design Stave Prototype (PreProducon) |  | 20 |  |  |  | 2456
3.01.01.02.04 | Procurement Stave Prototype (PreProducon | 40 |  |  |  |  | 4913
3.01.01.02.05 | Fabricaon Stave Prototype (PreProduction) | 60 |  |  |  |  | 7369
3.01.01.02.06 | Testing Stave Prototype | 20 |  |  |  |  | 2456
3.01.01.02.08 | Procurement Stave Production | 80 |  |  |  |  | 9921
3.01.01.02.09 | Stave Production | 120 |  |  |  |  | 15181
Total Cost |  | Total Cost |  |  |  |  | 52122

## EndRings Summary
[8 empty] | Date of Est: | 2018-10-12
[8 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  |  | Control Account Number
INTT EndRings |  |  |  | 3.01.01.03
WBS Dictionary Definition:
Technical Scope: contains all work required for the construction of INTT EndRings Work Statment: Design, fabrication, and production of the INTT EndRings
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See EndRings Details
See EndRings Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: Engineering design of the INTT EndRings was estimated based on BNL official costs. - The production cost the INTT EndRings was based on our expertise with previous work done at LBNL for VTX space frame production.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the design labor and fabrication of the INTT EndRings at LBNL.
Cost Summary
|  | Follow Links |  |  | Details |  | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost |  | Cost + Contingency
| Engineer/Technician Labor at BNL |  | BNL Labor cost Estimate |  |  | 25155 |  | 25155
| INTT EndRings Production |  | VTX SOW/LBNL |  |  | 13387 |  | 13387
| Total Work Package Cost [$] |  |  |  |  | 38542 |  | 38542
Contingency
M&S Contigency Rules Applied
SOW of INTT Space Frame Production: 0%
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## EndRings Details
WBS | Description | Item | Location | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
3.01.01 | INTT Construction | [11 empty] | 13387 | 13387
3.01.01.03 | EndRings | [7 empty] | 0 | 13387 | 0 | 13387
0 |  | Procurement EndRings | LBNL | 13387 | Pending | Experience/SOW | 0 | 0

## EndRings Labor
WBS: 3.01.01.03
INTT Construction: Ladder Layer 0 | EndRings
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.03.01 | Design of EndRings | 40 |  |  |  |  | 4913
3.01.01.03.04 | Procurement EndRings | 80 |  |  |  |  | 10121
3.01.01.03.05 | Fabricaon EndRings | 80 |  |  |  |  | 10121
Total Cost |  | Total Cost |  |  |  |  | 25155

## Barrel Assembly Summary
[7 empty] | Date of Est: | 2018-10-12
[7 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Barrel Assembly |  |  |  | 3.01.01.04
WBS Dictionary Definition:
Technical Scope: Contains all work required for the barrel assembly Work Statment: Barrel Assembly
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See Barrel Assembly Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: mechanical technician of the barrel assembly was estimated based on BNL official costs.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the technician involve in the assembly of barrels.
Cost Summary
|  | Follow Links |  |  | Details | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost | Cost + Contingency
| Technicians Labor at BNL |  | BNL Labor cost Estimate |  |  | 12067 | 12067
[6 empty] | 12067 | 12067
Contingency
M&S Contigency Rules Applied
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## Barrel Assembly Labor
WBS: 3.01.01
INTT Construction: | Barrel Assembly
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.04 | Barrel Assembly | 60 |  | 40 |  |  | 12067
Total Cost |  | Total Cost |  |  |  |  | 12067

## Support Rails Summary
[8 empty] | Date of Est: | 2018-10-12
[8 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  |  | Control Account Number
Support Rails |  |  |  | 3.01.01.05
WBS Dictionary Definition:
Technical Scope: contains all work required for the construction of support rails Work Statment: Design, fabrication, and production of the support rails
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See Support Rails Details
See Support Rails Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: design technician of the INTT support rails was estimated based on BNL official costs. - The production cost the INTT support rails was based on our expertise with previous work done at LBNL for VTX barrel mount production.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the design labor and fabrication of the INTT support rails.
Cost Summary
|  | Follow Links |  |  | Details |  | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  |  | Cost |  | Cost + Contingency
| Engineer/Technician Labor at BNL |  | BNL Labor cost Estimate |  |  | 43572 |  | 43572
| INTT support rails Production |  | VTX SOW/LBNL |  |  | 11156 |  | 11156
| Total Work Package Cost [$] |  |  |  |  | 54728 |  | 54728
Contingency
M&S Contigency Rules Applied
SOW of INTT Barrel Mount Production: 0%
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## Support Rails Details
WBS | Description | Item | Location | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
3.01.01 | INTT Construction | [11 empty] | 11156 | 11156
3.01.01.05 | Support Rails | [7 empty] | 0 | 11156 | 0 | 11156
3.01.01.05.05 |  | Procurement Support Rails | LBNL | 11156 | Pending | Experience/SOW | 0 | 0

## Support Rails Labor
WBS: 3.01.01.05
INTT Construction: Ladder Layer 0 | EndRings
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.05.0x | FEA analysis | 46 |  |  |  |  | 5650
3.01.01.05.0x | Desgin Support Rails | 80 |  |  |  |  | 10090
3.01.01.05.0x | Final Design | 10 |  |  |  |  | 1265
3.01.01.05.0x | Final Design | 10 |  |  |  |  | 1265
3.01.01.05.0x | Procurement of Support Rails | 80 |  |  |  |  | 10121
3.01.01.05.0x | Production of Support Rails | 120 |  |  |  |  | 15181
Total Cost |  | Total Cost |  |  |  |  | 43572

## INTT Assembly Summary
[6 empty] | Date of Est: | 2017-05-26
[6 empty] | Prepared By: | Rachid Nouicer
DocNo. (refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
INTT Assembly |  |  |  | 3.01.01.06
WBS Dictionary Definition:
Technical Scope: contains all work required to assemble INTT Work Statment: INTT Assembly
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
See INTT Assembly Labor
Assumptions Used in Developing Estimate
- The BNL labor costs: mechanical technician of the INTT assembly was estimated based on BNL official costs.
Details of the Base Estimate (explanation of the Work)
The base estimate cost covers the assembly of INTT.
Cost Summary
|  | Follow Links |  |  | Labor
Entries into the detailed cost summary have been color coded based upon the apropriate levek iof contingency that is applied to the item with green being the lowest contingency and red being the highest. Our cost for the pre-production and contingency is summarized below:
| Task |  | Cost Basis |  | Cost | Cost + Contingency
| Technicians Labor at BNL |  | BNL Labor cost Estimate |  | 27758 | 27758
[5 empty] | 27758 | 27758
Contingency
M&S Contigency Rules Applied
Labor Contingency Rules Applied:
BNL Technicians Labor : 25%

## INTT Assembly Labor
WBS: 3.01.01.06
INTT Construction: | Barrel Assembly
WBS | Task Description | Engineer | Designer | Technician | CRAFT | Net cost | Cost + Contengency
|  | hours | hours | hours | hours
3.01.01.06.01 | Design Assembly Fixtures | 40 |  |  |  |  | 5060
3.01.01.06.02 | Fabrication Assembly Fixtures | 56 |  |  |  |  | 7062
3.01.01.06.03 | Assembly | 40 |  |  |  |  | 5212
3.01.01.06.04 | Testing | 40 |  |  |  |  | 5212
3.01.01.06.05 | INTT Survey at Lab | 40 |  |  |  |  | 5212
Total Cost |  | Total Cost |  |  |  |  | 27758