## Task_Table1
INTermediate Tracker (INTT) Dictionary
WBS |  |  | Name | def
3.01 |  |  | INTT | The INTermediate Tracker for the sPHENIX Experiment at RHIC
3.01 | 03.01.01 |  | INTT Construction | This item contains all the stages required for the construction of the INTT tracker starting from design, fabrication, assembly, testing and survey of major parts: 1) sensor module prototype, 2) ladders, 3) EndRings, 4) barrels, 5) support rails, and 5) detector assembly/survey.
3.01 | 03.01.01 | 03.01.01.1 | Ladder Assembly | Technical scope: design, fabrication, assembly and survey of ladders for barrels 1,2. Prior to ladders of barrels1,2 production, there is a Final Design and Safety Review.
3.01 | 03.01.01 | 03.01.01.2 | Stave CFC | Technical scope: Stave CFC (mechanical support of the ladder made Carbon-Fiber-Composite M55J): this item contains conceptual design, FEA analysis, design, fabrication, testing, and production of staves of ladders for barrels 1,2.
3.01 | 03.01.01 | 03.01.01.3 | EndRings | Technical scope: EndRings are support structures made of Carbon-Peek carrying ladders of given barrel and connected to the rails structures. This item contains all tasks of design and fabrication of EndRings for barrels 1,2.
3.01 | 03.01.01 | 03.01.01.4 | Barrel Assembly | Technical scope: this item contains all tasks of assembly, testing and survey of barrels 1,2.
3.01 | 03.01.01 | 03.01.01.5 | Support Rails | Technical scope: Support Rails are four rails structures made of Carbon-Fiber-Composite carrying the barrels 1, 2. This item contains mechanical FEA analysis, design and production. Prior of production of the support rails, we will have a Final Design and Safety Review.
3.01 | 03.01.01 | 03.01.01.6 | INTT Assembly | Technical scope: this item includes of tasks for design, fabrication of fixtures required for INTT (two barrels together) assembly. Furthermore, it includes assembly, testing and survey of INTT tracker.
3.01 | 03.01.02 |  | INTT Electronics | This item contains design, prototyping and fabrication of silicon sensors, readouts electronics needed by INTT tracker.
3.01 | 03.01.02 | 03.01.02.1 | Silicon Sensor | Technical scope: this item contains design, prototyping, and fabrication of silicon sensors type A and B. The silicon sensors are produce by Hamamatsu (HPK) in Japan.
3.01 | 03.01.02 | 03.01.02.2 | Silicon Sensor QA | Technical scope: this item contains silicon sensors QA testing, evaluation, and posting data in database.
3.01 | 03.01.02 | 03.01.02.3 | HDI Cable | Technical scope: HDI (High Density Interconnect) for barrels 1,2 is a seven layer flexible circuit board to read-out two silicon sensors. The basic layer structure design of HDI is succeeded from FVTX. Each HDI provides power, and bias input lines as well as slow control and data output lines. This item contains all tasks for design, prototyping, fabracation of HDI for barrels 1, 2.
3.01 | 03.01.02 | 03.01.02.4 | Extension Cable and conversion cable | Technical scope: the extension cable and conversion cable are two cables connetected. This long cable (extension cable and conversion board) is between the ROC (Read Out Card) board and the ladder (HDI). This long cable brings all the signals from the ladder (HDI) to the ROC board and power and the control commands from the ROC board to the ladder. This item contains all tasks for design, prototyping, fabrication of extension cable. The design and fabrication of the extension cable are done by TAIYO-KOSAKUSHO Company in Japan.
3.01 | 03.01.02 | 03.01.02.5 | FPHX chips | Technical scope: The FPHX chip consists of a 128-channel front-end ASIC, and was designed by Fermilab for the FVTX/PHENIX detector. Signals from slicon strip sensors are digitized by FPHX chips mounted on HDI. The chip was optimized for fast trigger capability, a trigger-less data push architecture, and low power consumption (50 mW/chip). We have FPHX chips left over (unused) from FVTX/PHENIX detector. This item contains new order of the FPHX chips and it has been delivered in 2018.
3.01 | 03.01.02 | 03.01.02.6 | ROC FVTX | Technical scope: ROC (Read out Card) used by FVTX detector in PHENIX. The ROCs will be reused in INTT. This item contains all steps for testing and evaluation (repair if needed) of the FVTX ROCs existing.
3.01 | 03.01.03 |  | INTT Integration in sPHENIX: | This item contains two tasks carried out by the INTT group required for the integration of INTT in sPHENIX.
3.01 | 03.01.03 | 03.01.03.1 | Detector Monitoring | Technical scope: this item contains tasks for reading out sensors associated with the monitoring of temperature and humidity in INTT tracker.
3.01 | 03.01.03 | 03.01.03.2 | Electronic Services | Technical scope: this item contains parts needed for integration of INTT at the IR: 1) Fibers + Power Cables + Patch Panel, 2) Low Voltage Power Supplies and 3) Bias Voltage Power Supplies, The LV and bias voltage power supplies are already available by FVTX/PHENIX. The cost associated to this WBS is for repair in case it is needed.
3.01 | 03.01.04 |  | Project Management | This item contains Project Management and CD-0 autorization. This item has no cost for INTT.