## Slide 1: sPHENIX Director’s Review 1.2 sPHENIX TPC
Thomas K. Hemmick
April 9-11, 2019
BNL

## Slide 2: The Subsystem
A next-generation TPC operated in continuous readout mode using Gas-Electron Multiplier (GEM) avalanche w/ low Ion Back Flow (IBF).
Front End Electronics (FEE) uses SAMPA chip (developed by ALICE).
Data Aggregation Module (DAM) uses the FELIX board (ATLAS exp)
Charged Tracking in sPHENIX:
TPC provides p-resolution

## Slide 3: The Subsystem Technical Overview
“Wedge”
Zig-Zag Pads
charge
DAM Cards
RHIC Comp Facility
256 pads/FEE
25 FEE/sector
1 DAM/sector
Digitized
Compressed
EBDC 1/DAM
Item | Count
Field Cage | 1
Modules | 72
FEE | 624
DAM | 24
EDBC | 24

## Slide 4: Scope
1.2.1: TPC Mechanics
  TPC Field Cage: v2 prototype; final field cage.
  TPC Modules: v1a prototype; v1b prototype; v2b prototype.
  TPC GEM Production: CERN Shop (mirroring ALICE production)
  TPC High Voltage Systems: (GEM & Central Membrane)
  TPC Assembly: (Modules, Electronics, Testing).
1.2.(2-4): Rn Modules (n=1, 2, 3a, 3b):
  Factory Preparation; Pre-production Module; Module Production
1.2.5: TPC FEE:
  FEE v1 Prototype; FEE v2 Prototype; FEE Production
1.2.6: TPC DAM:
  DAM v1 Prototype; DAM v2 Prototype; DAM Production
1.2.7: TPC Services:
  Laser Calibration System; Gas System; Cooling System
Funding Source Key:
OPC
TEC

## Slide 5: Subsystem Collaborators
L2/L3- Management
Engineering
Additional Scientific
EE:
Mead
Factory Managers
Lots of Students

## Slide 6: Schedule Drivers
S137800 29-May-18
S140800 13-May-20
S121900 25-Jun-21
S121800 26-Mar-21
S121800 25-Jun-21
S140900 10-Dec-19
S143400 11-Mar-21
S132800 14-Aug-19
S134100 29-Sep-20
S119800 3-Feb-20 S120100 13-Aug-20
Module production rates from PHENIX Hadron Blind Detector experience (SBU, BNL, WIS) and ALICE experience (WSU, Yale).
Module production (1/week/factory) is entirely limited by GEM availability.
FEE has SAMPA chip (80 nsec development) & off-the-shelf components.
SAMPA production/testing completion drives board assembly.
Ready to Install
Test to Threshold KPP
FEE Production & Assembly
Module Production
CERN GEM Production
SAMPA Chip Development
Float
Module production rate limited by GEM availability

## Slide 7: Cost Drivers
CERN-produced GEM foils.
SAMPA readout chips via Sao Paulo
DAM (Felix2) ala ATLAS expt.
Costs are driven by M&S.
Most labor contributed.
Exception:
  Pay for former ALICE tech

## Slide 8: Basis of Estimate & Resource-Loaded Schedule
Contributed labor simplifies cost estimate
Estimates dominated by quote/catalog
Estimates benefit from similarity to prior GEM projects:
  ALICE TPC
    WSU (ALICE Factory)
    Yale (ROC validation)
  PHENIX HBD
  COMPASS TRACKERS

## Slide 9: Status and Highlights
Compressed
“Wedge”
Zig-Zag Pads
charge
DAM Cards
RHIC Comp Facility
256 pads/FEE
25 FEE/sector
1 DAM/sector
Digitized
EBDC 1/DAM
Item | Count
Field Cage | 1
Modules | 72
FEE | 624
DAM | 24
EDBC | 24
SAMPA v5 Waveform
Full Chain Readout

## Slide 10: Risk Registry

## Slide 11: Issues and Concerns
SAMPA development is going well thus far:
  Change #1: Implement again an existing design for 80 nsec peaking time (developed by later dropped by ALICE).
  Change #2: Improved coupling to digitizer to allow 20 MHz operation (opted against by ALICE).
If a second engineering run is required prior to production the cost & schedule impact is significant (as coded into our risk registry).

## Slide 12: Summary
The Time Projection Chamber design has benefitted significantly from the R&D for the ALICE upgrades.
The TPC will meet all the performance goals for sPHENIX.
The TPC group has close relations with the Sao Paulo and development of SAMPA v5 is going well.
The TPC schedule is not critical path.
TPC team has a long successful track record working together.
The TPC team benefits from ALICE experience via sPHENIX collaborators (WSU) and R&D partners (Yale).
The sPHENIX TPC is ready for PD-2/3 approval.

## Slide 13: Back Up

## Slide 14: Status and Highlights
Inner Field Cage Mechanically Complete, Electrical Assm Ongoing
SAMPA v5
SAMPA Waveform
X-ray scan measured/analyzed through full chain
Large Field Cage Assm Ongoing
Wagon Wheels Delivered/Accepted
40cm-drift Prototype Test Beam
V1a Module
Sim <138mm>
Meas <114mm>
Limit <106mm>
Test Beam Results