## Minutes of the sPHENIX PMG meeting #36

Present: M.Chamizo-Llatas, J.Dunlop, L. Ruan, J.Touzzolo, B.Wahl , T.Roser, M.A.Pleier, , G.Young, E.O’Brien, M. Anerella. Excused: B.Mueller, C.Lavelle

June 20, 2019

Agenda: https://indico.bnl.gov/event/6334/

The team is working to address the recommendations of the PD review and plans to send a written document to the PMG by August 1, before it is submitted to the POB panel, and to DOE-ONP and BHSO. The sPHENIX team will appoint a standing committee with experts from ALICE (mainly Yale) to provide feedback on the TPC. The PMG suggests to enlarge this committee to include other European experts. The magnet field mapping has been scheduled in P6 for Spring 2022, assuming that it will be done by a CERN team. The CERN team has stated that they will do it if it does not conflict with other CERN priorities. The PMG suggests to have a backup solution and discuss with the magnet division. The sPHENIX preference for a RHIC run in FY22 is as early as possible, i.e. from Sept 2021 to Dec 2021. Discussions with C-AD ongoing to optimize cryo operation between the FY22 run and the field mapping (that will need cryo on).

MVTX review is tentatively scheduled for 29-30 July, and is awaiting confirmation from DOE (now confirmed).

Recommendations to sPHENIX team:

- Submit the document addressing the PD review recommendations to the PMG one week prior to submission to the POB sub-panel, i.e. around August 9, 2019.

- Discuss composition of the standing committee with expert people from STAR and sPHENIX to provide advice on sPHENIX TPC technical aspects.

- Provide information on the status of the upgrade of the infrastructure at the PMGs

Previous recommendations to the sPHENIX team that are still open:

- Discuss with the magnet division the possibility to perform the field map of the sPHENIX magnet

- Open accounts for MVTX and estimate the funds needed until end of CY19 in view of a CR

- Finalize the MoU with C-AD before PD-2/PD-3 review, May 28-30.

- Inform the PMG as soon as the first results of the SAMPA v5 chip are available

Recommendations to the ALD:

- Follow up on the upgrade of the infrastructure at the PMG

Preliminary agenda for the next PMG, July 11:

- Status of recommendations from the PD review

- Address the above PMG recommendations