## Slide 1: Startup Run Coordination: Summary & Improvement
Gregory Marr
RHIC Operations Specialist

## Slide 2: Overview
This run, Operations took the lead role during the Start-up period, and was responsible for providing a machine with sufficient colliding beam at store to begin the physics program.
Despite delays, we provided Physics on schedule.
As reviewed in previous meeting, the results were generally well received, with a few minor notes for improvement.

## Slide 3: The “Wet Run”
Due to delays making phase shifter supplies operational, we began beam operations with configuration from last run.
From Blue cold on 2/14, used 2/15 until 2/24 amid PS checkout work with copies of last run’s ramps.
  2 ramps to 100 GeV
  6 ramps to 255 GeV

## Slide 4: The “Wet Run”
Pros:
  Allowed setup of systems using configurations already known to be good.
  Helps separate common problems from new lattice issues.
  Allowed beam ramps and store setup earlier.
  Beam development was able to advance beyond injection energy even though PS work was not complete.

## Slide 5: The “Wet Run”
Cons:
  Still requires PS checkout, high and low current, shutoff tests, captured key tests, etc. as prerequisite.
  In the long run, only useful if it does not extend the amount of PS group effort & time required.

## Slide 6: Improving Communication
Support groups and operations need to relay information well during startup.
  It would be nice if everybody read each other’s elogs, but it’s not going to happen.
  Example: RMMPS voltage glitches. Noted 2/18, discovered in beam operation 2/25.
Make daily plan more rigid
  As noted in previous review, daily plan changed too frequently. Keep daily plan static, and update adjustments to the shift plan as they arise.

## Slide 7: Injector preparation
Effort continues to complete as many tasks as possible prior to RHIC being beam-ready.
  Next run, injection kicker timing setup can be checked with beam to W-dump and W-line BPM signal
Start-up is the time to push the limits, e.g. intensity.
  Doesn’t mean that should be the starting point for Physics (RHIC parameters included).

## Slide 8: Other recurring themes
AP shifts
  We did not require AP coverage (in the MCR) during startup.
Run Coordinator, Scheduling Physicist role
  Was it better for the Coordinator that they were not dumped into the fray immediately?
Ramp preparation
  Going from a lattice design to a usable ramp is still fraught with problems that are not sorted out before we start losing beam time.

## Slide 9: Summary
Allowing operations to coordinate RHIC startup was in general well-received. With some minor improvements and continued attention to detail, we expect to be able to deliver similar or better performance in upcoming runs.