## Slide 1: sPHENIX Computing Plan - Checkup
January 16, 2019 BNL
Review
1. Tasks
2. Workforce
3. Milestones
4. Committee Recommendations

## Slide 2: Core-Effort Planning

## Slide 3: Workforce Plan
Project Name | Description | Effort | Names
Online Computing | Develop/Maintain online computing tools | 1.0 | M. Purschke
 | Trigger rates, adjustments | 0.2 | U. Colorado
 | 0.2 FTE per subsystem | 1.0 | 
Simulation | Develop/Maintain simulation tools | 1.0 | J. Huang
 | Integration | 0.5 | 
 | Fast Simulators | 0.5 | NPPS
 | Release and QA | 0.5 | NPPS
 | 0.2 FTE per substystem (excluding TPC) | 1.0 | 
TPC/Tracking | Track reconstruction and calibration | 1.0 | C. Roland
 | Achieve 5sec/event track reco | 1.0 | NPPS
 | Mostly distortiion corrections | 1.0 | NPPS
 | Vertex Finding | 1.0 | A. Frawley
Calorimeter | Fast ADC / Clustering | 1.0 | 
 | Calorimeter Calibration | 1.0 | 
 | Simulation/Verification | 1.0 | 
 | Jet-calibration (with TPC) | 1.0 | 
Software Framework | Develop/Maintain offline framework | 1.0 | C. Pinkenburg
 | Release Q&A | 0.5 | NPPS
 | Database, data moving, record keeping | 0.5 | NPPS
 | Distributed workflows | 0.5 | NPPS
 | GPU-acceleration | 0.5 | NPPS
Total |  | 17.2 | (5 NPPS)

## Slide 4: Milestones
2019 (Q4)
  Demonstrate the ability to read time-aligned data from multiple systems
  Deploy 2D & 3D vertex reconstruction
2020
  Demonstrate the ability to build events offline
  First simulation campaign (realistic TPC drift & ExB effects)
  Modeling and Simulation of TPC space-charge distortions
  Implement ACTS tracking, optimize tracking for 5-sec/ev
  Detailed Calorimeter simulation validation
  ADC time-series signal fitting optimization
  Develop calibration strategy, workflow, simulation tools
  Define post-DST data formats
  Implement PANDA/RUCIO for distributed job submission and data management
  Implement Multi-Threading
  Demonstrate ability to run on OSG
2021
  Demonstrate the ability to read time-aligned data from multiple systems
  Second simulation campaign (with optimized tracker)
  Develop/Adopt particle flow algorithms and Optimize Calorimeter Clustering
  Database integration of alignment, detector parameters, and calibrations
  Deploy space-charge correction framework
  Mock data challenge(s) from simulated raw data thru calibration and reconstruction
2022
  Full chain test and QA for all subsystems
  Cosmic running and analysis
  Readiness testing and commissioning

## Slide 5: Review Recommendations
Simulation/Calorimeter Performance
  Revisit the TPC distortions plans and requirements together with teams having a TPC based experiment and long expertise. Example: experts from BNL (STAR) and CERN (ALICE) should review and comment on sPHENIX approach.
  Consolidate the simulation requirements and implementation needs in regards to treatment of distortions, misalignment and other considerations that may introduce uncertainties in the estimate of efficiencies. The timeline for such implementation should be clearly justified.
  Fast simulations should be further investigated. While simulation constitutes a small portion of the total CPU budget, they may provide a path to fast evaluation / analysis.
  The sPHENIX collaboration should identify from within the collaboration the individuals with the knowledge (or hire & grow individuals to have such knowledge) needed to support TPC domain-specific tasks (calibrations, detailed simulations) and furthermore, have their retention in mind.

## Slide 6: Review Recommendations
Framework/Calibration/Reconstruction
  At this stage of maturity of the plan, we highly recommend to work together with the RACF on computing resources plans that would fold in cost decrease and CPU performance increase (Moore’s and Kryder's law scaling) - projections should be updated accordingly.
  Continue work related to DST and postDST format definitions - this will soon be needed.
  The work to improve track finding performance to satisfy the goal of 90% should continue.

## Slide 7: Review Recommendations
DAQ
  Perform a cost/benefit and risk analyses for three event-building scenarios: (a) online, (b) offline before tape storage and (c) on-the-fly for each reconstruction pass.
  We recommend to consider an approach where the first pass reconstruction (asynchronous) is later efficiently deleted from HPSS.

## Slide 8: Review Recommendations
General
  We encourage to continue close collaboration with other teams like ALICE, CBM and other collaborations to benefit from past experience and create synergy.
  The RACF and the department should make it a priority to make collaborative tools available based on inputs and requests from sPHENIX and other groups.
  Investigation of possible synergies with CSI should be re-evaluated and increased.
  Work together with the RACF on cost-benefit analysis (for the computing resources) is needed at this stage of maturity of the plan. sPHENIX and RACF need to carefully coordinate timeline of the new data center and availability of compute and storage resources.
  sPHENIX needs to formalize the process of how and to what level and when collaborating institutions contribute so that external resources - hardware and workforce - can be included in the planning process and leveraged. This will strengthen the collaboration planning and negotiations with BNL. Understanding the process may be dynamic, a more mature support model should be presented at the next review.
  The Computing planning needs to be further developed and delivered by January 2020.
    Priorities, risks and time required for each identified task should be done.
    Develop (together with NPPS and Physics Management) a S&C staffing plan.
  Another pitch for LDRD…
  Another review in summer 2020.