## Slide 1: PMG Agenda
  Issues
  Status Carriage/Cradle contract
  Status of PMP for the I&F and MVTX
  Status of milestones expected to be accomplished in Dec 2019
  Discussion FY20 milestones for PEMP
  Upcoming procurements
  EV for November 1.X and 2.X

## Slide 2: Issues for BNL Management
Thanks to action from Phys Dept & sPHENIX we have ordered 16k additional SiPMs for high eta EMCal. Change request has gone from BNL PPM to Hamamatsu.
MVTX capital accounts are now open. We’re in active discussion with LANL, LBNL, MIT and UT-A on contract documentation. Negotiating the final FY20 contract numbers consistent with the RLS.
Three large (>$250k) sPHENIX contracts with PPM and 3 more on the way in the next 4 weeks.
  At PPM: SBU, UIUC (about to be awarded), Carriage/Cradle
  Contracts being prepared: LANL, LBNL, MIT (all MVTX)

## Slide 3: Status of Carriage/Cradle Order
All documents with PPM except the two packages of final signed drawings.

## Slide 4: Status of PMP for MVTX and I&F
MVTX PMP has been through a number of revisions from both the sPHENIX project team and BNL Management. The only item left to revise is the MVTX milestone table to reflect the fact that funding is flowing two months later than originally expected.
  Finalize the milestone table this week and release to sign.
  We have told DOE-NP that we will share the MVTX PMP with them once it is ready to sign. However they are not interested in signing themselves.
I&F PMP is also in an advanced draft. We are doing EV presuming that the baseline that we presented at the October I&F review is the approved baseline. As with the MVTX PMP, we will review the milestone table one last time prior to signing.
  I recommend that the I&F PMP should not be shared outside the Lab. It is an internal BNL document.

## Slide 5: FY20 MIE Milestones
10 sPHENIX MIE milestones in FY20. Milestones 1, 2 and 3 now complete.
Milestone 2: Production Readiness Reviews of TPC GEM Module factories was successfully completed on Dec 17.
The milestone most at risk is Milestone 6: EMCal electronics preproduction complete. We can meet it but it will require the first article EMCal SiPM daughter card currently being produced by the vendor to be good. We expect the first article to arrive at BNL for testing between the last week of January and the first week of February.

## Slide 6: sPHENIX Procurements Next Six Months
Award Orders submitted to BNL PPM
  Carriage/Cradle (MIE)
  University contracts for 2020 with UIUC and SBU
Prominent Orders for the next six months
  MVTX contracts with MIT, LANL, LBNL and UT-A (non-MIE)
  All production EMCal light guides
  HCal Splice plates and high strength steel HCal sector end plates
  EMCal SiPM daughter cards (sectors 2-12)
  2nd half of W powder order for EMCal
  iHCal scintillating tiles (non-MIE)

## Slide 7: Performance Indices – sPHENIX MIE
DOE SPI or CPI Value Thresholds
0.90 to 1.15
0.85 to 0.89 or 1.16 to 1.25
<0.85 or >1.25
Cumulative SPI | Cumulative CPI
1.02 | 1.03
Cumulative BCWS (Scheduled) | $7,539,613
Cumulative BCWP (Performed) | $7,686,704
Cumulative ACWP (Actual) | $7,468,749

## Slide 8: Cost Performance Report (CPR) – sPHENIX MIE
DOE SPI or CPI Value Thresholds
0.90 to 1.15
0.85 to 0.89 or 1.16 to 1.25
<0.85 or >1.25

## Slide 9: Performance Indices – 1008 Infra and Facility Upgrade
DOE SPI or CPI Value Thresholds
0.90 to 1.15
0.85 to 0.89 or 1.16 to 1.25
<0.85 or >1.25
Cumulative SPI | Cumulative CPI
1.01 | 1.02
Cumulative BCWS (Scheduled) | $9,538,025
Cumulative BCWP (Performed) | $9,590,337
Cumulative ACWP (Actual) | $9,386,408
Based on proposed Baseline

## Slide 10: Cost Performance Report (CPR) – 1008 Infra and Facility Upgrade
DOE SPI or CPI Value Thresholds
0.90 to 1.15
0.85 to 0.89 or 1.16 to 1.25
<0.85 or >1.25
Based on proposed Baseline

## Slide 11: Summary Schedule – sPHENIX MIE and 1008 Infra and Facility Upgrade
1.X
2.X

## Slide 12: EAC and Contingency Profile – sPHENIX MIE

## Slide 13: Baseline/Contingency Log - MIE

## Slide 14: EAC and Contingency Profile – 1008 Infra and Facility Upgrade
Based on proposed Baseline

## Slide 15: Baseline/Contingency Log - 1008 Infra and Facility Upgrade
Based on proposed Baseline

## Slide 16: Critical Path (1x, 2x and 3x Combined)

## Slide 17: Critical Path (1x, 2x and 3x Combined)

## Slide 18: Critical Path (1x, 2x and 3x Combined)

## Slide 19: Critical Path (1x, 2x and 3x Combined)

## Slide 20: Critical Path (1x, 2x and 3x Combined)

## Slide 21: Critical Path (1x, 2x and 3x Combined)

## Slide 22: Back Up

## Slide 23: I&F Upgrade Review Recommendations
Include in P6 the appropriate amount of time and effort associated with preparing for the Operational Readiness Review (ORR) and any other reviews that need to take place between now and January 2023. Done
Evaluate the schedule to see where activities can be advanced to create more schedule contingency. Present a plan to create additional schedule contingency to BNL NPP management by December 2nd, 2019. Done
Consider assigning a project team member to provide oversight and be in close contact with the Procurement and Property Management Division (PPM) for all strategic procurements going forward. There will be a significant number of procurements to place and monitor throughout the life of the project ($9M over this next year alone). Done. A sPHENIX teams meets with PPM weekly
Utilize Laboratory management if key procurements appear to languish in the procurement office. Met with head of PPM and discussed this issues with Berndt. Will continue to discuss procurement issues with PPM head and ALD as issues arise.
Evaluate the benefit of adding resources to support the Office of System Integration as well as mechanical engineering for the purpose of performing Finite Element Analysis (FEA) on current and future designs. Will follow up with Phys Dept

## Slide 24: I&F Upgrade Review Recommendations
Complete the Unreviewed Safety Issue (USI) determination and subsequent changes to the safety Assessment Document (SAD) and Accelerator Safety Envelope (ASE) no later than 6 months prior to bringing cryogens into the 1008 Experimental Hall. The sPHENIX ESH Liaison will work with the sPHENIX project manager and C-AD ESSHQ Division Head to formalize the positive USI evaluation according to the C-AD OPM 1.10.1, Procedure for Identifying Unreviewed Safety Issues for the sPHENIX detector, and in particular, the planned cryogen system for the SC magnet. This evaluation will be completed at least 6 months prior to introducing cryogens or any hazards that may require a change to the Safety Assessment Document.
Confirm the Accelerator Safety Order requirements associated with this project with the BNL Accelerator Safety Officer, including the need for an Accelerator Readiness Review. This should be done by November 30, 2020. The sPHENIX project will undergo reviews in accordance with the SBMS subject area ‘Accelerator Safety’ and will coordinate and schedule readiness reviews with BHSO (IRR and/or ARR) as required by the Accelerator Safety Order. The review requirements will be determined by November 30th, 2020.

## Slide 25: I&F Upgrade Review Recommendations
Review the magnetic mapping schedule activities and determine if they can be modified to reduce the impact to the overall schedule. Done
Develop a plan to perform a magnetic survey of the as-built structure in the IR hall with the solenoid energized. Time has been put in the RLS for this. A Magnet Mapping plan is being drafted and will include a magnetic survey of the IR with the solenoid powered.
Review the procurement schedule activities for the Cradle Carriage to determine if the durations for Vendor Responses and Vendor Selection are too conservative. The current schedule gives us time to react if the bids come in too high. A success-oriented plan would require us to add additional cost risk to the project plan.
Review the plans for the shipment of the Cradle Carriage to ensure there is adequate cost and schedule for shipping the extra-wide load from the vendor to BNL. Done. Included in signed SOW and will be part of RFQ being prepared by PPM