## Slide 1: HiLumi-LHC/LARP Crab Cavity System External Review 5-6 May 2014, BNL
SPS - RF Power and Coupler status
Erk Jensen, Eric Montesinos, CERN BE-RF
on behalf of all people involved, great thanks to all of them !

## Slide 2: FPC – initial design
400 MHz 50 kW CW FPC full reflection all phases
Agreed coaxial line OD 62 mm - ID 27 mm
Coaxial disk window
  Outer titanium flange
  Al2O3 97.6% ceramic
  Inner copper tube
Coupler body
  Massive copper
  316 LN Stainless Steel flanges on both sides

## Slide 3: FPC – initial design
Monitoring ports
  1 port for vacuum gauge
  1 port for e- monitoring
  1 port for arc detector
Coaxial to WG WR2300½H transition without doorknob
DC capacitor included for DC polarization

## Slide 4: FPC – new design
Still agreed sizes on cavity side OD 62 mm - ID 27 mm
Conical vacuum line to increase the diameter of the ceramic in order to avoid arcing on the air side
Ceramic & Air coaxial line increased OD 100 mm – ID 43.5 mm
Robust ceramic Thickness 20 mm

## Slide 5: FPC – new design
Pseudo-conical air extension cooled with forced air
Even if against CERN’s rules regarding joining, as no other way to do it, water cooled antenna
Mandatory vacuum gauge for coupler protection
No more arc detector window neither e- antenna to ease integration

## Slide 6: FPC – new design

## Slide 7: Antenna overheating
Looking at the size of the hook, no way to design a cooling circuit which also cools down the curved part of the hook
Initial design of coupling elements (BNL-ODU) shown overheating up to an unacceptable temperature
New coupling element shapes have been designed allowing acceptable temperature for the three couplers

## Slide 8: Test boxes
Three test boxes will be built allowing the preparation of pair of couplers
They will be made with two plates of Stainless Steel, not copper plated (easier and quicker), and will be water cooled
They will be customized regarding the coupling element for each cavity design

## Slide 9: Schedule May 2014
Cavities to be installed in the SPS in December 2016
Couplers processed 50 kW SW CW all phases Q2-2015
FPC design is missing DT & coupling shape & position (additional delay will impact FPC schedule)
FPC RF processing
SPS-LSS4
2014
2015
2016
2017
2013
DT → →

## Slide 10: Tetrode Amplifiers
No progress, still no water due to LS1 until May 2014
Was operated at 40 kW maximum in 1999
Should be able to provide 50 kW (not guaranteed)

## Slide 11: Power supplies
Existing one will be for the test stand
Two new systems will be bought for SM18 & BA4
Will be one HV power converter for two amplifiers to reduce the cost

## Slide 12: Driver amplifiers, Circulators & Power Loads
Offers received from 10 companies, off the shelves SSA
On-hold awaiting Tetrode amplifier test results in order to correctly define the output power level regarding tetrode amplifier gain
They will be close to the LLRF racks in ECX4
Three sets of LHC 400 MHz 330 kW circulators & LHC loads have been ordered
Loads will be shorten to allow integration onto the table

## Slide 13: Movable table
Phoevos Kardasopoulos

## Slide 14: Tetrodes Amplifiers onto the table
Phoevos Kardasopoulos

## Slide 15: Circulators & power Loads (with adjustable supporting system for integration of all three designs)
Phoevos Kardasopoulos

## Slide 16: Waveguides to FPC
Phoevos Kardasopoulos

## Slide 17: Cryomodule with FPC
Phoevos Kardasopoulos

## Slide 18: Flexible WG (allowing integration of all three designs)
Phoevos Kardasopoulos

## Slide 19: Conclusion
Coupler designs almost completed & test boxes simulations to be completed
  Hook position to be defined
  DT length still to be defined
Tetrode amplifier still to be tested
Integration pre-study of power system completed → ok
Schedule … more and more optimistic if no decisions are taken regarding DT & Antennas !

## Slide 20
Thank you