## Slide 1: Planning and Conducting ARRs
David Freeman (ORNL)
Ian Evans (SLAC)
Accelerator Safety Workshop 2014
DOE Germantown, Maryland
August 6, 2014

## Slide 2: Overview
Recent ARRs
Order 420.2C Requirements
Guide Recommendations
Preparing to Conduct an ARR
Conducting an ARR Site Visit
Post Site Visit Activities
Observations from Recent ARRs

## Slide 3: Recent ARRs
BNL – New Facility, NSLS II
JLAB - Energy Upgrade
FNAL – Mission Transition (power increase)
LBNL – New Facility – BELLA

## Slide 4: Order 420.2C ARR Requirements
ARR required to ensure:
  An appropriate Contractor Assessment System that maintains an internal assessment
  An appropriate Configuration Management Program related to accelerator safety
  Credited Controls and appropriate administrative processes related to accelerator safety (e.g. training, procedures, etc.) are in place.

## Slide 5: Guide Recommendations (420.2-1 and draft 420.2-1A)
ARR is process for assessing readiness.
ARR is not method for achieving readiness.
ARR is a targeted overview and sampling process, not an exhaustive wall-to-wall assessment.
ARR should not use the contractor’s internal readiness process as a substitute for verification of any specific activity.
ARR must be performance-based to be effective.

## Slide 6: Sequence of Events (draft Guide flow chart)
Contractor defines, implements, improves, and completes internal process to achieve readiness
Contractor declares readiness
Readiness Review - last step in process
ARR Team conducts review, issues report
Contractor closes pre-start findings; agrees to monitor post-start findings
ARR Team verifies closure of pre-start findings; issues endorsement of contractor readiness
Contractor request DOE authorization to commence activities
DOE authorized commencement of activities

## Slide 7: Preparing to Conduct ARR
Develop written agreements with site:
  ARR Charge
    Ensure objective and scope are clearly defined
    Ensure scope appropriately addresses ancillary support facilities, systems and equipment as appropriate
  Topical areas to be reviewed
  Lines Of Inquiry (LOIs)
  ARR Team deliverables (closeout presentations/reports)
  Disposition of ARR pre-start and post-start findings

## Slide 8: Preparing to Conduct ARR (continued)
Review Order and Guide
Assemble ARR Team
  Match expertise with topical areas to be reviewed
  Include site personnel on team - beneficial
  Include representation across various sites - adds balance
Review current community management practices - talk with counterparts across the community
Establish clear lines of communication with Team/Site
Establish ARR Team expectations:
  Site declaration of readiness
  Documentation - when/how provided to Team
  Information request and response protocols

## Slide 9: Preparing to Conduct ARR (continued)
Coordinate with Site
  Agenda for any pre-site visit video conference(s)
  Agenda for site review
  Logistics for on-site review
  Laboratory Contact/Support list
ARR Team prepares for site visit
  Maintain ongoing lines of communication across Team
  Assign Team members to topical review areas
  Coordinate team documentation review
  Coordinate team members’ contact with laboratory SMEs

## Slide 10: ARR Site Visit Areas of Emphasis
ARR is a performance-based activity
Keep all parties informed of emerging issues
Avoid Death by PowerPoint
  Formal briefings consume precious field time
  Consider use of pre-site visit video conferencing
Manage Information Flow
  Keep everyone interacting real time
  Ongoing attention to information and interview requests
  Track responses to team requests

## Slide 11: ARR Site Visit Areas of Emphasis
Stay focused
  Manage distractions
  Assess readiness in each ARR topical area
  Identify and prioritize pre and post start findings
  Gain team consensus on significance of issues
  Determine if readiness has been achieved
Pre-start and Post-start findings
  Gain team consensus on pre and post start findings
  Finalize pre/post-start verbiage prior to closeout
  Findings must be carefully worded to ensure success
  Ensure travel schedules do not impact ARR outcome
Close out presentation/ARR Report

## Slide 12: ARR Responsibilities after the Site Visit
ARR Team Report
  Coordinate authorship among team members
  Issue report on agreed upon schedule
  Provide fact check draft to site as scheduled
  Issue final report as agreed upon
Disposition of Pre-start Findings
  Laboratory provides evidence demonstrating closure of pre-start findings
  ARR Team reviews evidence and iterates with Laboratory
  ARR Team concurs that pre-start findings are resolved
  ARR Team Lead issues letter endorsing facility readiness.

## Slide 13: Some Lessons Learned
Lack of clarity in ARR charge can lead to
  confusion that can consume valuable time
  can lead to out-of-context findings
ASE - keep evaluation focused on meeting Order requirements; varied opinions and spirited discussions can consume valuable time.
Use of Lines of Inquiry
  Proven useful during planning stages of ARR
  Useful when viewed as starting point for on site review
  Allowing team members to pursue topics they feel are most important has proven advantageous (rather than constraining review to predetermined list of inquiries)
ARR should not be a review of the lab’s institutional programs (e.g. ES&H, fire protection, cybersecurity, etc.) other than their ability to support the accelerator

## Slide 14: Observations and Thoughts
Continuity of recent ARRs across community beneficial
  ARR approach has evolved based upon experiences gained at various facilities
  ARR approach tailored to meet specific needs of each site
ARR process has become an effective tool in communicating best management practices throughout our community.
The ARR is an evolving process with a growing list of valuable lessons learned.