## Slide 1: Fermilab 700 kW Upgrade Accelerator Readiness Review (ARR)
John E. Anderson Jr.
2014 Accelerator Safety Workshop
6 August 2014

## Slide 2: Overview
700 kW Upgrade Background
ARR Scope
ARR Review Team
ARR CRADs and LOIs
ARR Plan and Results
ARR Lessons Learned and Observations

## Slide 3: Fermilab 700 kW Upgrade Background
Started a yearlong upgrade shutdown in 2012
Changes were to increase protons per hour on target to the NuMI neutrino experimental area
  Previously approved for 514 kW Operations
  ~40% increase in average beam power
Major Upgrade Items
  Repurposed the Recycler Ring (RR) to reduce cycle time of the Main Injector (MI) accelerator (1.87 s → 1.33 s)
    RR previously used for anti-proton storage in support of the Tevatron collider experimental program
    Upgraded to perform proton manipulations (Slip-Stacking) previously done in the MI

## Slide 4: Fermilab 700 kW Upgrade Background
    Moved proton injection and extraction lines
    Removed the anti-proton injection and extraction lines
    Decommissioned anti-proton equipment no longer needed
    Added proton abort kickers
  Upgraded instrumentation in MI, RR, and NuMI experimental areas
  Added additional RF cavities to support the higher beam power
Revised the Radiation Shielding Assessments for the MI, RR and NuMI experimental areas
Developed new SAD Chapters for the MI/RR, and NuMI
Revised the ASE for the new beam power limits
Credited Controls with the exception of beam power limits remained the same

## Slide 5: Main Injector and Recycler Ring

## Slide 6: Fermilab Limited Scope ARR
Modifications to
  Main Injector (MI)
  Recycler
  Neutrinos at the MI (NuMI) areas
Readiness to support 700 kW Operations for the NuMI Experimental Areas
Facility was operating under ASE Revision 3 during the ARR
  MI & NuMI Beam power limit of 514 kW

## Slide 7: Limited Scope ARR Review Team
Team consisted of 5 External and 1 Internal Reviewers
  SLAC, JLab, LBNL participants
  Two consultants formerly employed within accelerator community
  Fermilab participant
3+ DOE Observers
  Office of Science
  Fermi Site Office
  Jefferson Lab Site Office

## Slide 8: Limited Scope ARR CRADs and LOIs
CRADs and LOIs developed to facilitate the review
Required documentation derived from in DOE O 420.2C Safety of Accelerator Facilities Contractor Requirements Document (CRD)
  Safety Assessment Document (SAD)
  Accelerator Safety Envelope (ASE)
  Unreviewed Safety Issues (USI) process
  Accelerator Safety and the Fermilab Contractor Assurance System (CAS)
  Safety Configuration Management (SCM)

## Slide 9: Limited Scope ARR CRADs and LOIs
Accelerator Systems
  Accelerator Operator Training
  Accelerator Operator Qualification Program
  Accelerator Operations Procedures
  Work Planning and Control Related to Accelerator Safety
  Radiological Safety for 700 kW Operations
  Accelerator Credited Controls

## Slide 10: Limited Scope ARR Plan
Limited Scope ARR was a 2 ½ Day Review
  Plenary Sessions were held and well received
    Overview of Fermilab Programs
  Technical Breakout Sessions were keyed to individual team members
    Explore each CRAD through LOIs
    Two Parts
      Overview presentation on how CRAD is implemented
      Performance-based program review
        Discussions with management and staff
        Demonstrations of systems
        Implementation of programs and procedures

## Slide 11: Limited Scope ARR Plan & Results
  Performance-based site visits
    Main Control Room (MCR)
    Booster & Linac Galleries
    MI-60 and MI-65 Service Buildings
Discussions held with ARR Team were productive
4 Pre-start Recommendations
  DOE FSO Approve ASE Director Approve NuMI SAD Chapter Approve 700 kW Operations Dept. Operating Permits Complete operator required reading for 700 kW operations
  Nothing that wasn’t expected

## Slide 12: Limited Scope ARR Results
16 Post-start Recommendations
  Review ASE and streamline the document
  Expand USI training and look at USI integration into SCM
  Several recommendations regarding COO
  Several recommendations regarding CAS
  Useful recommendations to assist with improving and strengthening existing programs
Laboratory and DOE representative liaisons were empowered to verify completion of pre-start actions and report completion to ARR Team chair
  Final report issued
  Post start recommendations tracked to completion

## Slide 13: Limited Scope ARR Results
Limited Scope ARR provided some significant results for Fermilab
  ASE was clarified and streamlined
    Beam Intensity Limits clarified
    Operating limits and surveillance limits were removed
    Common industrial hazard controls were removed
  SCM Program Improved
    Developed a movable shielding database
  COO Program Improved
    Re-worked the Operations Department COO Guide

## Slide 14: Limited Scope ARR Lessons Learned and Observations
Lessons Learned from Fermilab experience
  Planning and dialogue with ARR Team must be started well in advance of the review
  Preparations are resource consumptive and can be chaotic
    ARR is competing with construction, installation or modification activities
    Many times competing with project milestones
    Projects reluctance to move milestones to make room for ARR
      ARR should be included in the project milestones
Observations
  Broad scope ARRs may duplicate other self-assessment efforts when looking at established facilities
  Limited or modified scope ARRs make sense for established facilities

## Slide 15: Limited Scope ARR Lessons Learned and Observations
  The ARR process at the various laboratories has accumulated valuable lessons learned
  Some form of periodic focused Accelerator Safety Implementation reviews as part of the Self-Assessment process likely very useful
    Builds a basis for the use of limited scope ARRs for significant modifications to an existing facility
      Program elements are already established
      Need to verify modification has been integrated into the facility
  Look at the lessons learned regarding ARR program implementation and discussing the ARR topic at this workshop is a step forward in improving the ARR process