## Slide 1
Yellow Report Goals and Plans
Note: Yellow Report Goals and Plans were presented at
EICUG Institutional Board meeting of 10/10/2019 (as early draft)
EICUG Remote Meeting of 10/24/2019
EICUG Remote Meeting of 01/23/2020 (folding in requests from MIT Kick-off meeting on audience, timeline, and YR draft outline)
Here, we will mainly concentrate on the timeline, folding in lab/project planning
Rolf Ent and Thomas Ullrich
on behalf of the EIC User Group Steering Committee
Major input from Elke Aschenauer, Jim Yeck and others on lab/project planning

## Slide 2
Activity Name |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
 | NSAC Long Range Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | NAS Study |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CD0 – assumed |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CD1 (Down-select) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CD2/CD3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | NSAC LRP – assumed |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EIC construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EIC physics case |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EICUG formation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | EICUG meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Expression of Interest |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Physics/Detector book I |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Call for Detectors/ Collaboration Formation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Design of Detectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Down-select to Two Full-Size Detectors |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Detector/IR TDRs, Detector/IR Construction |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DOE Driven
User Group Driven
CD0 = DOE “Mission Need” statement; CD1 = design choice and site selection
CD2/CD3 = establish project baseline cost and schedule
2030
2030
From 2019 EIC Users Group Meeting

## Slide 3
After Kick-Off Meeting
At the kick-off meeting we aim to finetune all sub-groups and how to best structure in detail the study towards the Yellow Report(s). Similarly, we expect the EICUG Software Group to have presented a finalized and documented EIC software package with flexibility to adjust magnet strengths, geometries, detectors and interaction regions.
After the kick-off meeting one could envision the following activities:
Send a finalized short “task list” to the sub-conveners for each sub-group, on what we want out of each WG, as a start/direction.
Offer one or two remote software tutorials around early- to mid-January, such that sub-groups can jumpstart activities.
Conveners start their regular meetings via video/conference.
Sub-conveners submit an outline of their foreseen (<15 page) contributions to the conveners.
The goal is to have by the end of January 2020 all activities well underway.
Further finetuning of this plan will occur as part of the Kick-Off Meeting.
From 10/24/2019 EICUG Remote Meeting
Not exactly followed, but the idea/essence was captured!

## Slide 4
From 01/23/2020 EICUG Remote Meeting
YR Timeline (I)

## Slide 5
From 01/23/2020 EICUG Remote Meeting
YR Timeline (II)

## Slide 6
NEW: Now fold in lab/project planning!
Concentrate on the next two years which are the defining phase.

## Slide 7: Main objectives for the next 2 years
Detector requirements and design as driven by EIC Physics program defined by Community
  EICUG Yellow Report activity
  Different Physics (5) and Detector (7) WGs
    December 2019 Kick-off meeting at MIT
    March 2020 1st meeting at Temple
    May 2020 2nd meeting at Pavia/Italy
    August 3-7 2020 EIC-UG Meeting at Miami
    September 2020 3rd meeting at CUA
    November 2020 4th meeting at UCB/LBL
    January 2021 completion Yellow Report
    July/August 2021 EICUGM at Warsaw/Poland
   critical input for detector proposals

## Slide 8: Main objectives for the next 2 years
Detector Scenarios:
Any general purpose EIC Detector
is complex
Large rapidity (-4 < h < 4) coverage, and beyond (-7 < h < 7)
Electromagnetic and Hadronic Calorimetry
Particle ID detectors (positive p, K, p identification)
Tracking: small (m-vertex) and large radius (gaseous-based) Tracking
detector extends along the beam line: Roman Pots, ZDC, …..
Ancillary Detectors: electron & hadron Polarimetry, luminosity monitors
 Need to understand national and international contributions

## Slide 9: Main objectives for the next 2 years
National and International Contributions:
(non-binding) Expressions of Interest (EoI) to get guidance on detector scope
Discussion Call for EoI for contributions to EIC Detectors during EIC-UG Meeting August 3-7 2020
  (assume discussion session at EICUGM)
Call for EoI for contributions to EIC Detectors August 2020
(issue call after folding in feedback of EICUGM)
Deadline EoI for contributions to EIC Detectors November 2020
(Status report at 4th (final) Yellow Report meeting)
Evaluate EoI and inform Call for Detector Proposal(s) February 2021
(complete after assumed January 2021 Yellow Report
completion, EoI can give guidance on detector scope)
More on this in Detector Complementarity Discussion session and Elke’s intro to this tomorrow!

## Slide 10: Detector Scope
Comprehensive general-purpose detector: rough costs (US accounting) = $300M
Costs included in project are roughly $200M, with $100M assumed to be in-kind.
Costs for one Interaction region included in accelerator scope = ~$200M
If we assume two general-purpose detectors where each has some components that are recycled, costs may be ~$200M each
2nd Interaction region costs (accelerator scope, US accounting) = ~$200M
I.e., if we assume we want two general-purpose detectors (and a 2nd IR) we need to
  Use the $200M project costs to guarantee a successful EIC project (need to deliver on any Key Performance Parameters)
  Assume some recycling of components/detectors in each detector
  Rely on roughly $400M non-DOE scope (NSF, international engagement)
The upside is that in non-US accounting, this is more like $150-200M.*
More on this in Detector Complementarity Discussion session and Elke’s intro to this tomorrow!
* See backup slide

## Slide 11: Main objectives for the next 2 years
Assumption: CD-1 aligned with accelerator timeline
Goal: CD-2 & CD-3 also aligned!
Form EIC Collaboration(s)
  Issue Call for Detector Proposals March 2021
  (consistent with EICUGM assumptions of early 2021)
  Form Detector Review Committee June 2021
    (to guide work in TEC phase)
  Deadline for Proposals September 2021
  (roughly in phase with projected CD-1 date)
  DRC Meeting for Detector Proposal down select November 2021
  Selection of Detector(s) December 2021
  (one or two, pending Expression of Interest response)
  CD-2 September 2022
  CD-3 September 2023
  (CD-2 and CD-3 dates assumed for planning purposes)

## Slide 12
From 01/23/2020 EICUG Remote Meeting, folding in lab/project planning
YR Timeline (I)
Completion of Yellow Report

## Slide 13
YR Timeline (II)
From 01/23/2020 EICUG Remote Meeting, folding in lab/project planning

## Slide 14: Summary
It is crucial to complete the Yellow Report January 2021 to stay in phase with the hoped-for EIC early-CD dates.
We are better off completing a Yellow Report and later making a “v2” or revisiting (parts) of the Yellow Report ~1 year later than running late. Do what you can.
My view:
  At CD-1 we need a plausible scenario reference design for any general-purpose* detector.
  At CD-2 we need a reference design for a general-purpose detector with some of the equipment components known in detail.
  At CD-3 we need to have completed >80% of the full engineering & design of at least one general-purpose detector.
The labs are planning to, in collaboration with the EICUG SC and the DOE/NP, ask for an Expression of Interest to obtain guidance for the detector scope (the expected in-kind contributions, international engagement, one or two detectors, possible accelerator scope in-kind contributions, etc.).
* The scope assumption for the EIC was for one full detector to do the NSAC/NAS Report science, i.e., not a limited day-one detector

## Slide 15: US Project Accounting 101
Assume a detector project in the US with a total project cost of $100M
US projects include contingency – assume about 35%
US projects include costs for R&D (small for detector projects), Project Engineering & Design (10-15%), and pre-operations (few-%) – assume 15%
For the construction phase of the project, a very typical split is:
  50-60% is procurements, and 50-40% is labor – assume 60-40 for this example
US projects include (reduced) overhead, assume here 10%
Net this means that, assuming no contingency and no overhead on procurements, a $100M project corresponds roughly to a $35M cost in detector procurement in the construction phase.
If one assumes the DOE project always has to take care of engineering & design and pre-operations, it changes the above arithmetic, so let’s assume $40M-$45M. Still, it “pays” to have equipment contributed by others.
Similar, to have labor provided as in-kind contribution could also make a large difference in project costs, in the above example ~$30M.