## Slide 1: Magnetic Field Measurements
John Haggerty

## Slide 2: Who?
Felix Bergsma’s group at CERN to make precise 3D map
  http://ep-dep-dt.web.cern.ch/b-field-mapping-magnet-support
  I intend to send him a memo describing what we need ”soon”
  I’ll ask him for a telecon after that
  A visit to his lab at CERN could be a good idea, not sure it’s necessary
“We” will engineer Hall probes for monitoring on or near the TPC
  I just talked to the TPC engineering group today about leaving some space amidst the jungle of power, fiber, cooling, laser, and mechanical supports that they are just beginning to design

## Slide 3: What?
I have contacted them to “pencil in” our mapping on their schedule
Put in place contract (or other method of compensation) with CERN around October 2020, about a year before we could possibly need the mapper
  We’ll have a better picture of the final assembly schedule
I would like to use the Metrolabs Magvector MV2 probe: https://www.metrolab.com/products/magvector-mv2/
  I need to touch base with them again, I think they were introducing some new packaging, maybe we could avoid building our own interface board
  I will investigate the possibility of adding an SPI connection to the FEM so that we readout the field with the FEM; failing that, we need some SPI smarts within about 3m of the probe

## Slide 4: When?
We were encouraged to install the mapping hardware before roll-in (see next slide), which may or may not be feasible
What is certain is that the mapper needs to be installed before summer, 2022

## Slide 5: sPHENIX Installation
Sequential Build Steps | Concurrent Work Streams | CY 2021 |  |  |  | CY2022 |  |  |  | CY2023
Cradle-Base | WBS 2.5.2 Work Wiring, Piping, Cabinets Other AH and IR work QC and Safety Checks |  |  |  |  |  |  |  |  | 
oHCAL Sector 1-13 |  |  |  |  |  |  |  |  |  | 
Magnet Install |  |  |  |  |  |  |  |  |  | 
Inner Support Rings |  |  |  |  |  |  |  |  |  | 
oHCAL Sector 14-32 |  |  |  |  |  |  |  |  |  | 
iHCAL |  |  |  |  |  |  |  |  |  | 
EMCAL |  |  |  |  |  |  |  |  |  | 
Open Shield Wall |  |  |  |  |  |  |  |  |  | 
Carriage and pole tips |  |  |  |  |  |  |  |  |  | 
Move sPHENIX to IR |  |  |  |  |  |  |  |  |  | 
Magnet connect, map | WBS 2.5.2 Work Infrastructure connections to Cradle/Carriage Magnet work Wiring, Piping, Cabinets Other AH and IR work QC and Safety Checks |  |  |  |  |  |  |  |  | 
TPC |  |  |  |  |  |  |  |  |  | 
INTT support structure |  |  |  |  |  |  |  |  |  | 
Beam pipe insert & bake |  |  |  |  |  |  |  |  |  | 
INTT device |  |  |  |  |  |  |  |  |  | 
MVTX device |  |  |  |  |  |  |  |  |  | 
Final beam pipe |  |  |  |  |  |  |  |  |  | 
MBD device |  |  |  |  |  |  |  |  |  | 
ORR Prep and ORR |  |  |  |  |  |  |  |  |  | 
`
ORR
01-Nov-22
Start RHIC
30-Jan-23
FY21 RHIC Run
1/4/21 to 5/13/21
FY22 RHIC Run
9/1/21 to 12/30/21
Start: March 21’
Key Predecessors
AH/IR Rail Mods
Cradle-Base Ready