## Reviews
Review Date | Review | Review type | Agenda | Reviewers | Recommendations or Action Items | Closed | Date of closure | Actions taken to close | Status 2020.02.25
2019-11-26 | Cradle/Base | PRR | https://indico.bnl.gov/event/7107/ | J. Bowers, C. Folz, J. Haggerty, C. Pearson, J. Tuozzolo, J. Mills | 1. Electronic Racks Platforms and support utilities - Are the temporary openings in the platform decking considered a fall hazard? How do we protect workers from accidently falling into an opening as cables are being installed? How do we protect personnel that may be on step ladders while working on the platforms? Address these issues with a plan on how to protect personnel. (AI) 2. Examine seismic loads as part of the overall analysis to ensure that the system or components of the system are not overstressed. Refer to the current IBC, which is adopted by New York State as the applicable standard, or DOE-STD-1020-2002 “Natural Phenomena Hazards Design and Evaluation Criteria for Department of Energy Facilities.” {While the original PHENIX magnets and rail systems were designed to a minimum nominal safety factor of 3.0, seismic safety factors were only required to be greater than 1.0} (AI) 3. The tracks will need reinforcing or replacement as the computed safety factors are unacceptable. The proposed plan should show a cohesive approach to developing and transferring loads from the detector, through the rollers and/or jack system into the concrete floor. This must be resolved prior to the start of procurement of the cradle/carriage. This committee should be reconvened to review the proposed changes. (AI) 4. Analysis of magnetic forces acting on the cradle carriage needs to be completed. A full understanding of the load path for these forces, along with computed stress and deflection results for critical components needs to be established. This committee should be reconvened along with the addition of a magnet scientist/engineer to review this scope prior to the start of carriage/cradle procurement. (AI) |  |  |  | The procurement was allowed to prrceed and bids were opened 2/14/2020. The remaining recommendations and action items have to do with construction and analysis of cradle and base, and the modifications to the rails.
2019-12-17 | TPC GEM | FDR/PRR | https://indico.bnl.gov/event/7182/ | John Haggerty, Glenn Young, Jim Mills, Russ Feder, Mike Anerella, Dick Majka, Rich Ruggiero, Bob Azmoun, Craig Woody, John Kuczewski, Bill Lenz | 1. The drawing packages for the GEM frames and strongbacks should be completed and checked. An assembly drawing of the strongback, pad plane, GEM’s and frames should be developed for form, fit and function. a. The pad plane design should be completed and checked against the frame and strongback drawings. b. A Statement of Work will need to be provided for each procurement package. 2. Consider producing a pad plane prototype for testing the compatibility of the Front End Electronics boards and the development of the cooling system for them. 3. Tests of prototype GEM modules assembled into a wagon wheel are needed to ensure that there are no problems at the edges of the GEM’s when inserted in the wagon wheel. This recommendation is meant to address questions that arose about the GEM tails; here are some specific suggestions: a. Consider adding removable potting material between GEM tails and structure to preclude voltages developing in the gas between them. b. Consider routing exiting R3 GEM tail on opposite sides at different radii to eliminate interference and voltage issues. c. Develop a detailed procedure for potting the GEM tails. 4. GEM foils for the R3 detector should be produced. 5. First articles of each type of GEM module should be produced before mass production of framed GEM’s. 6. The review panel should reconvene when the documentation and testing are more complete and before production commences. A target date for the follow-up review should be established by February 3, 2020. |  |  |  | A number of tests were recommended at the review, which has been discussed in subsequent TPC and TPC engineering meetings. The tests have not shown any problems so far at the edges of the GEM's. A plan for potting the GEM tails has been developed. The SOW and drawing packages are complete or near complete, but final design and checking are still in progress. Gerber files for the pad plane are nearing completion; the board is not routed, but that is in progress. The TPC group is working to make a sector of prototype electronics. Orders for the strongbacks have been placed, pad plane and GEM orders to be released soon. Recommendations and action items have been reviewed in the weekly TPC regularly since the review.
2019-12-17 | TPC GEM Factory Readiness | PRR | https://indico.bnl.gov/event/7211/ | John Haggerty, Glenn Young, Jim Mills, Russ Feder, Bob Azmoun, Chuck Gortakowski, Lori Steigler | 1. Production and test procedures should be modified to reflect the sPHENIX production and archived and controlled in the sPHENIX Vault or docDB. 2. Ensure that electrical equipment is inspected and is in compliance with current electrical regulations. |  |  |  | The WSU factory is well organized and well run; the recommendations are to make sure that the factories document their adherehence to sPHENIX project safety standards.
2020-01-16 | Carriage Rack Safety System | PDR | https://indico.bnl.gov/event/7453/ | John Haggerty, Glenn Young, Jim Mills, Russ Feder, Bob Azmoun, Chuck Gortakowski, Lori Steigler | • Need to add local crash button specifications and circuitry to presentation. - J Vasquez. • Need to add local rest button specifications and circuitry to presentation - J Vasquez. • Safety Rack System should be on a UPS. J. Haggerty. • Scheme for light indicators - J Vasquez. | No |  |  | J. Vasquez will proceed with the design and prototyping, after consulting the ESRC (1/28/2020).
2020-01-22 | Beam Pipe | PRR | https://indico.bnl.gov/event/7379/ | Russ Feder, Ed O’Brien, Camelia Mironov, John Haggerty, and Glenn Young (phone) from sPHENIX, Wolfram Fischer, Joe Tuzollo, Mike Mapes, Chuyu Liu, Sumanta Nayak, and Angelika Drees | 1. Drawings for the beampipe should be completed, checked, and archived in compliance with sPHENIX and CAD procedures. 2. Fabrication of the modified beam pipe should begin as soon as possible after the drawings are checked and archived. |  |  |  | A serious issue was found in the discussion by the committee after the report. The aperture was found to be marginal at injection of p+Au; a modified design with the 40 mm section extending only to ±2.2 m is being developed. The MVTX and MBD groups have been consulted on the ramifications of this.
2020-01-28 | Carriage Rack Interlocks | ESRC | https://indico.bnl.gov/event/7525/ | Ed O’Brien, Joel Vasquez, John Haggerty, Mike Gaffney, Joe Tuozollo, Andrei Poblaguev, Melvin van Essendelft, Joe Levesque, Lee Hammons, Frank Craner, Ray Fliller, Pat Sullivan, Pete Cirnigliaro, Peter Hamblin, Mike Sivertz (recording) | There were two issues of significance raised during the review. 1) Will working on the racks require LOTO? Or will the E-Stop be sufficient for safety? In discussion with Jon Sandberg following the meeting, he informed us that E-Stop is not sufficient for safety. LOTO of the 208V will be required. Or the racks can be manufactured so that the 208V is inaccessible to anyone working on the racks. It has not been decided which option to choose for this yet. 2) It is necessary to perform arc flash calculations for the rack power. Joel will work with Jon Sandberg, PK Feng and the vendors to do the calculations. |  |  |  | J. Vasquez is beginning the design and prototyping. An Interim or Final Design Review will be scheduled when more data are available.
2020-01-29 | MVTX Mechanics/CRU | FDR | https://indico.bnl.gov/event/7165/ | John Haggerty, Russ Feder, Glenn Young, Rob Pisani, Dan Cacace, Rich Ruggiero, Chris Pontieri, Joe Silber, Leo Greiner, Sumanta Nayak | 1. Before proceeding to finalizing design and drawings: a. Finalize discussions with CAD on whether the 40 mm aperture restriction to ±5.6 m is acceptable for all collision species. 2. When the specifications for the composite structures is complete, expected to be in March 2020, confirm feasibility with vendors and/or outside experts soon afterward. Define the specific performance, QA, and dimensional tests that are required. Some balance will be needed between overly tight versus practical and testable specs. The main risk is to schedule, if the specs prove too difficult for vendors to achieve, or too laborious to test. 3. Before final construction: a. Complete Interface Control Documents. b. Complete plans for interlocks and alarms. |  |  |  | The MVTX group has done considerable engineering work to make sure that installation of the MVTX can be accomplished with a 50 mm diameter beam pipe at ±2.2 m. In the meantime, engineering and design continue on the prototype composite structures.
2020-02-04 | Pins/Pucks/Dogbones | PRR | https://indico.bnl.gov/event/7546/ | John Haggerty, Russ Feder, Rich Ruggiero, John Lajoie, Chris Pontieri | 1. Prepare and post the SOW. 2. Procure at least two extra sectors of skins. 3. Inspect bolts for counterfeit markings on delivery. |  |  |  | The procurement of the pucks, pins, and dogbones is under way.
2020-02-05 | HCAL Sector 7-32 Electronics | PRR | https://indico.bnl.gov/event/7585/ | John Haggerty, Stefan Bathe, John Lajoie | 1. In the next two weeks, add to the PRR slides some missing information: a. An introductory slide showing clearly the scope of the production. b. Include the interface boards on slide 3. c. Include a link to quality assurance documents developed for the preproduction sectors. d. Include a link to the electronic design documents. 2. In the next month, document and record the gain and dynamic range of the calorimeter and electronics. 3. Before beginning production, consult the sPHENIX Quality Assurance Coordinator and the sPHENIX Safety Coordinator. |  |  |  | The documentation has been modified, and production will commence.
2019-02-21 | Calorimeter Bias Supplies | PRR | https://indico.bnl.gov/event/7786/ | Haggerty, Woody, Stoll, Lajoie, Boose | Wait for updated data sheet from Wiener |  |  |  | This has been a paper review so far, which waits for final specifications from Wiener.