## Slide 1: sPHENIX Cryogenic Status
Paul Orfin
3/25/2020

## Slide 2: Status
AET still working on Multi-bundle spools #1-5
  Delays in Piping analysis caused schedule slip in AET’s baseline
  Analysis concurrence with piping achieved, AET updating documentation
    IDR data to come 3/26/2020
  Spool #4 and 5 delivery to BNL delayed to 5/10/2020 instead of 4/10/2020
    Still should not impact summer shutdown installation
  Waiting for Updated schedule from AET to determine down stream impacts
    Risk is low since remaining delivery items are based on other more critical path predecessors
LN2 procurement to be completed for bid package to go out in summer
Cryogenic Controls continue to progress

## Slide 3: IDR Documents
General arrangement layout 3-D model.
Detailed design of each of subsystem components 3-D model.
Teflon components list
The following analyses shall be completed for the IDR as described in this SOW:
  ASME B31.3 piping stress/flexibility analysis.
  ASME Section VIII Boiler & Pressure Vessel Code analysis.
  Cold box vacuum vessels: Pressure Vessel analysis
  Process line reliefs and vacuum jacket relief device sizing analysis.
  Lifting lug analysis
  Rigging and structural including modal analysis
  Shipping support and shipping load analysis. Cold box legs/saddle/beam frame analysis.
  Manufacturing plan and test procedures
  Fluid flow pressure drop calculations
  Weight analysis for IP8 cold box

## Slide 4: sPHENIX Cryo Controls
Component review and quotes - on going
Vacuum system components
  Turbos and roughing pumps
Fail last components – Lock valve position in case of signal loss
  Purchased sample parts are obsolete
  Evaluating replacement