## Slide 1: EIC Project Overview Jim Yeck, EIC Project Director
April 23, 2020

## Slide 2: EIC Design Satisfies NSAC and NAS Requirements
Center of Mass Energies 20 GeV – 141 GeV
Maximum Luminosity 1034 cm-2s-1
Hadron Beam Polarization 80%
Electron Beam Polarization 80%
Ion Species Range p to Uranium
Number of interaction regions up to two

## Slide 3: Electron Ion Collider

## Slide 4
  Rapid Cycling Synchrotron (RCS) for electrons and Electron Storage Ring (SR) fit easily into the existing RHIC tunnel
  Two existing detector halls available for interaction regions and detectors
EIC Machine in the RHIC Tunnel
RCS
SR

## Slide 5: EIC Project Scope

## Slide 6: Reference Funding Profile
  CD-1: March 2021
  CD-2: September 2022
  CD-3: September 2023
  CD-4a: September 2029
  CD-4b: September 2031
Chart: Staged CD-4 - $1.97B
| FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31
New Funds Required | 11808963.43 | 30000000 | 75652597.139 | 138432620.705 | 149750087.271 | 149536909.972 | 149808997.7245 | 149822093.9755 | 95273103.0394 | 39795136.796 | 31701740.6906 | 11056924.2659
Reprioritized | 0 | 13000000 | 24000000 | 26000000 | 31000000 | 69000000 | 147000000 | 151410000 | 155952300 | 160630869 | 79989911.1267 | 82389608.4605
  Staged Luminosity
    Operations Start CD-4a
    Full RF Power Installed by CD-4b
  $100M from New York State toward infrastructure

## Slide 7: Reference Schedule

## Slide 8: BNL-JLAB Joint Efforts
TJNAF Visit to BNL – Feb 10, 2020
BNL Visit to TJNAF – Feb 28, 2020
Partnering Agreement Approved
EIC Project Executive Management Team Established: E. Aschenauer, Rolf Ent, Diane Hatton, Allison Lung, Andrei, Seryi, Ferdinand Willeke, and Jim Yeck (Abhay Deshpande, ex officio)
Working on organization and management approach

## Slide 9: Organization
EIC management approach
  Organization structure is being assessed to benefit from TJNAF commitment and prospects for significant international and domestic partners
  EIC Council will be established based on project experience from other projects including LCLS-II, Exascale, and other recent large projects, both DOE and international projects
  Project leadership team to be strengthened and membership and mandates of advisory committees clarified:
    Project Advisory Committee
    Machine Advisory Committee
    Detector Advisory Committee

## Slide 10: EIC Accomplishments
  Accelerator
    Design Task Forces established BNL/TJNAF/Others
    Discussing potential future partnerships for design and construction
  Experimental Program
    Development Timeline and Process Defined
    EIC User Group “Yellow Report” Workshops
    Strong domestic and international interest in two detectors/interaction regions recognized
  Conceptual Design Report (Draft) – Sept 1, 2020

## Slide 11: Timeline to CD-1
May 7, 2020: EIC Program Steering Group Meeting
May 7, 2020: Partnership Agreement Signed
Late May: EIC All Hands Meeting
May 29, 2020: Call for EoI for Contributions to Detectors
June 15, 2020: A/E Services Contract awarded
Mid-June: EIC Director’s Council Meeting
June 30, 2020: Preliminary drafts/full outline of CDR due
June 30, 2020: DRAFT CD-1 documents complete
July 15, 2020: Analysis of Alternatives Team report due
July XX, 2020: Risk Workshop
July 31, 2020: Deadline for drafts of new CDR Material
July 31, 2020: Freeze Design updates for Draft CDR

## Slide 12: Timeline to CD-1
August 1, 2020: Freeze data for DOE Mini Review
Week of August 10, 2020: Independent Review of AoA
August 15, 2020: CD-1 Documents complete
August 25, 2020: AoA Final Report Complete
August 26, 2020: Post Material for DOE Mini Review
August 27, 2020: Project Advisory Committee Meeting
September 1, 2020: DRAFT CDR Complete
September 9-10, 2020: DOE Mini Review
Early October: First Detector Advisory Committee (DAC) Meeting
October 6, 7 or 8, 2020: First Machine Advisory Committee (MAC) Meeting

## Slide 13: Timeline to CD-1
November 1, 2020: Deadline for Detector EoI
November 19, 2020: PAC Meeting
November 23, 2020: Post Material for Director’s Review
November 30, 2020: NEPA Process Complete
Dec 8-10, 2020: CD-1 Director’s/CDR Review
December 15, 2020: Freeze data for DOE CD-1 Review
January 7, 2020: ½ Day Briefing with NP and OPA
January 12, 2021: Final CDR complete
January 12, 2021: Post Material for CD-1 Review
January 26-28, 2021: DOE CD-1 Review
February 2021: Evaluate EoI & Draft Call for Det. Prop.
March 2021 – Initial Plan for Call for Detector Proposals
March 31, 2021 – Goal for CD-1 Approval

## Slide 14: Using the Path to CD-1 to Status
DRAFT

## Slide 15: Post CD-1
April 1, 2021 – Start Preliminary Design
Focused Technical Reviews
March 2022 – Establish preliminary performance management baseline and start using cost and schedule tracking tools, including EVMS
September 2022 – Goal for CD-2 Approval
July 2023 – Goal for CD-3 Approval [pending schedule update to determine when procurements will need to begin]

## Slide 16: EIC Challenges
Affordability – very large project for DOE Office of Nuclear Physics (NP) and Office of Science (SC)
  Reprioritization of funding to EIC
  Critical to ramp up of funding in FY2021 to maintain timeline for DOE Critical Decisions
COVID-19
  Current EIC work is primarily planning and design work which can be done remotely, some R&D stalled
  Indirect impacts are likely to be more significant, including aligning with RHIC operations plans, uncertain fiscal context, design efficiency

## Slide 17: Conclusion
Project Delivery Plans Maturing
  Strong Foundation: pre-conceptual design, cost estimate, schedule
  BNL/TJNAF Collaboration
  Plans aligned with reasonable annual funding projections
  DOE review and approval process is important: CD-1 approval in 2nd Quarter of FY2021
Strong Effort to Develop Experimental Program
  Community engagement essential including “host” role of BNL/TJNAF in the process
  Timeline important for the Yellow Book, Call for Expressions of Interest, Call for Proposals, etc.
  Working to align and integrate within the overall integrated project