## Slide 1: Run-14 Startup
Gregory Marr
Travis Shrey, Vincent Schoefer
Start-up Coordinators

## Slide 2: Overview
For the second year, Operations was in charge of scheduling and executing the Startup plan for the run. This included Au-Au (low and high energy) and 3He-Au setup from pre-beam to declaration of Physics stores.
Given the major installation and ramp reconfiguration, we elected to set up at nominal injection energy and ramp (1.5 beam days) prior to low energy work (3 beam days including DX training).
Physics was once again delivered on schedule (overall delays aside).
  We completed a setup for a run given to us last-minute, with a new species, and complicated mode switching, and still came through.
  “That run was practically imaginary and it got done.”
Noteworthy issues will be discussed.

## Slide 3: Missed during Dry Run or pre-beam setup:
28 MHz RF not set to phase jump at gt.
Stochastic cooling ADO changes
  Tape errors.
GPM DCCT scaling
  Missed that beam injected on first shot.
BPM first turn setup (wide gate)
  Caused delay in combination with DCCT.
Abort kicker voltage alarms
Damper/Artus BPM connection

## Slide 4: Pre-beam delays
Ramp preparation remains as a major, fundamental problem.
  Last-minute, complicated changes…
  Process relies too heavily on a few select personnel, who already have too many tasks to accomplish.
  Ramp design and cloning is rife with errors.
    7.3 GeV had large dipole trim from 2.5GeV cloning.
  It’s a pre-requisite for many other tasks, and ends up delaying multiple system setups.

## Slide 5: Scheduling, personnel issues
Decisions made at the morning meeting were not well executed when the coordinators weren’t present.
  There’s a difference between presenting the plan at 0900 and making the plan at 0900.
A few experts responsible for multiple systems get burdened (unnecessarily?) in the first few days.
Everyone wants the day shift.

## Slide 6: Start-up tasks: your homework
We have made strides in the past by automating tasks (example: power supply checkout streamlined with over 10 automated tape sequences).
Are there other candidates for automation in your own system start up?
MCR is staffed 24/7. Your coverage cannot beat that.
Which tasks could Operations perform in your stead?
Bring us your ideas!

## Slide 7: Summary
I believe the Startup period is in the best hands for the job.
  We should continue to amplify the role of OC in Startup.
We need to continue to work on our availability of experts given the challenge of a fluid schedule of sequential tasks.
Our continued success is owed to the hard work of the Operations staff and those who support us during the Startup period and beyond.