April 2020 Variance Reports sPHENIX MIE and 1008 I&F Upgrade

Explanation

The cumulative SV for WBS 1.X is -$1116K (BCWs = $10,955K, BCWP = $9,839K) for an SPI of 0.90 as of the end of April 2020.

There are notable schedule variances, in excess of -$100K, occurring in four of the seven level-2 areas of the MIE.  A description follows for the major items in each Level-2 WBS.

WBS 1.2 Time Projection Chamber: there are three main areas of SV.

The pad planes for the readout chambers are not yet under construction, causing -$190K of SV, because of a no-bid by the preferred vendor. A new contract is being placed as noted below.

The SAMPA v5 ASIC fabrication is 60% complete, leading to -$132K SV.

The TPC laser system optics design is not fabricated, causing -$83K SV.

WBS 1.3 Electromagnetic Calorimeter: there are three main areas of SV.

The preproduction blocks have been delayed in part because of a QA issue since resolved, coupled with a shutdown of the fabricating laboratory due to COVID-19. This causes -$77K SV.

The mechanical parts and lightguides for the preproduction modules and blocks are under contract and being delivered, but these deliveries are still in progress, causing -$94K SV.

One of the several contracted deliveries of scintillating fibers was delayed by the vendor, due to COVID-19, leading to -$40K SV.

WBS 1.4 Hadron Calorimeter: There is one main area of SV.

The splice plates for the OHCal are not complete, causing -$303K SV.

WBS 1.5 Calorimeter Electronics: These are three major areas of SV.

The SiPM daughter boards for the preproduction modules are under contract but were not all delivered, causing -$25K SV

The various low voltage and bias voltage power supplies were not all delivered, causing -$58K of SV

The preproduction set of calorimeter digitizers are only partially completed by the vendor, causing -$123K of SV.

Impact

WBS 1.2 TPC

The pad plane order is being pursued ahead of schedule in order to be ready for when the GEM foils arrive from CERN. The SAMPA v5 chip is over 60% complete with enough parts delivered to keep the front-end electronics prototyping supplied. The TPC laser system is being designed ahead of when it is needed. None of these items will presently impact the overall schedule for the TPC.

WBS 1.3 Electromagnetic Calorimeter

The block pre-production is not on the present critical path, but the block production run is expected to be on or near the critical path in the future.  An adequate number of light guides and mechanical parts are in hand to supply the module and sector production lines for more than 2 months.  The fiber deliveries were contracted to stay well ahead of schedule, with the current usage affecting blocks that are scheduled to be manufactured only in October.

WBS 1.4 Hadron Calorimeter

The splice plates are needed only by summer 2021.

WBS 1.5 Calorimeter Electronics

The SiPM daughter boards are needed for assembly of the EMCal sector to be built immediately after the one now under construction. The various low voltage and bias supplies are not needed presently, because an adequate number are already in hand to continue all sector testing activities. A sufficient number of digitizers are in hand to support all production and testing activities for the calorimeters as well as to support initial system tests for the DAQ (WBS 1.6).

Correctives

WBS 1.2 Time Projection Chambers

The needed pad planes are on order. The remaining SAMPA chips will be produced in May and packaged and tested over this summer, well ahead of when they are needed for production front-end card fabrication. The laser system components have been selected and will be reviewed for final design during June-July.

WBS 1.3 Electromagnetic Calorimeter

The block factory has restarted and the QA issue noted earlier has been resolved.  All parts needed for the preproduction modules and sectors are in fabrication at vendors with delivery schedules in advance of their need. The vendor of the scintillating fibers has resumed production and has indicated that current and future shipments have resumed.

WBS 1.4 Hadronic Calorimeter

The tender offers for the splice plates have been issued with responses due by early June. Three qualified vendors have indicated they will respond.

WBS 1.5 Calorimeter Electronics

The SiPM daughter boards will be delivered in May. The various voltage supplies are on order. The vendor for the digitizer boards needs to be allowed to return to work post COVID-19, but has arranged for the remaining assembly work to be done at a qualified vendor which in turn is already back in operation.

Top of Form

| WBS 1.02A |  |  |  |  |  | Reporting Period: April 2020 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TPC |  |  |  |  |  |  |  |  |  |  |
|  | BCWS | BCWP | ACWP |  | SV in $ | SV in % | CV in $ | CV in % | SPI | CPI |
| Current: | 416,735 | 128,817 | 144,209 |  | -287,918 | -69% | -15,392 | -12% | 0.31 | 0.89 |
| Cumulative: | 2,052,004 | 1,594,953 | 1,518,768 |  | -457,051 | -22% | 76,185 | 5% | 0.78 | 1.05 |
|  | BAC |  |  |  |  |  |  |  |  |  |
| At Complete: | 4,169,636 |  |  |  |  |  |  |  |  |  |
| Threshold(s) Exceeded: Cumulative Schedule |  |  |  |  |  |  |  |  |  |  |
| Explanation of Variance/Description of Problem: WBS 1.2.2-4.3 – TPC GEM Modules R1,R2,R3 – Procure TPC Module Parts – The prototype vendor for Pad Planes went no bid on production, requiring a new vendor search. This leads to a -$203K of SV. WBS 1.2.5.3 TPC FEE - SAMPA 80 nsec – The SAMPA v5 engineering run chips were reviewed/approved for full production only in April. This leads to -$135K of SV. WBS 1.2.7 TPC Support System - Laser – new conceptual cost-saving design for laser optics approved only in May. This leads to -$84K of SV. WBS 1.2.7 TPC Support System – Gas System – An evaluation to ascertain which existing parts from the PHENIX HBD gas system has delayed purchase of identical parts until the inventory is complete. This leads to -$24k of SV. |  |  |  |  |  |  |  |  |  |  |
| Impact: Impact: WBS 1.2.2-4.3 – TPC GEM Modules R1,R2,R3 – Procure TPC Module Parts – impact none. Pad plane has 139 days float. WBS 1.2.5.3 TPC FEE - SAMPA 80 nsec – Impact none. Chip now approved for full production. On hand/tested chips from first batch allow FEE production to commence w/o delay. SV reflects deliberate choice to fab wafers in two batches. WBS 1.2.7 TPC Support System - Laser impact none. Optics has 244 days float. WBS 1.2.7 TPC Support System – Gas System – Impact none. The system has 95 days float; impact none. |  |  |  |  |  |  |  |  |  |  |
| Corrective Action: WBS 1.2.2-4.3 – TPC GEM Modules R1,R2,R3 – Procure TPC Module Parts – New Pad Planes vendor selected and R3 order placed with requirement for first articles. WBS 1.2.5.3 TPC FEE - SAMPA 80 nsec – Chip approved for full production. Validation enabled using first batch V5 chips. WBS 1.2.7 TPC Support System - Laser – Design concept finalized and preparation for review initiated. WBS 1.2.7 TPC Support System – Gas System – First parts now on order. |  |  |  |  |  |  |  |  |  |  |
| Prepared: |  | Prepared By: |  |  |  | Approved: |  | Approved By: |  |  |
| 5/19/2020 |  | Thomas Hemmick [H5685] |  |  |  | 5/26/2020 |  | Edward O'Brien [18368] |  |  |
| WBS 1.04A |  |  |  |  |  | Reporting Period: April 2020 |  |  |  |  |
| HCal |  |  |  |  |  |  |  |  |  |  |
|  | BCWS | BCWP | ACWP |  | SV in $ | SV in % | CV in $ | CV in % | SPI | CPI |
| Current: | 51,470 | 0 | 11,347 |  | -51,470 | -100% | -11,347 | 0% | 0.00 | 0.00 |
| Cumulative: | 1,731,449 | 1,422,058 | 1,480,499 |  | -309,391 | -18% | -58,441 | -4% | 0.82 | 0.96 |
|  | BAC |  |  |  |  |  |  |  |  |  |
| At Complete: | 4,031,972 |  |  |  |  |  |  |  |  |  |
| Threshold(s) Exceeded: Cumulative Schedule |  |  |  |  |  |  |  |  |  |  |
| Explanation of Variance/Description of Problem: WBS 1.4 S206200 Procure Outer HCAL Lifting Fixtures & Supports - Delivery Acceptance was completed early, leading to $46k in positive schedule variance. WBS 1.4 S205100 Procure Outer HCAL Splice Plates - Delivery Acceptance is running behind schedule, leading to a negative schedule variance of $303k. |  |  |  |  |  |  |  |  |  |  |
| Impact: WBS 1.4 S205100 Procure Outer HCAL Splice Plates - no impact.The splice plates, pucks and pins are only needed when OHCal assembly starts, in May 2021. No other item's production depends upon having these plates |  |  |  |  |  |  |  |  |  |  |
| Corrective Action: WBS 1.4 S205100 Procure Outer HCAL Splice Plates - the design and procurement reviews for these splice plates are complete. Bids have been received by vendors and the contract between BNL and ISU is in place. The ISU RFQ has been posted for these procuements, and will be close May 27th. It is expected the splice plates will be delivered by the vendor by November 2020, about 6 months before they are needed. |  |  |  |  |  |  |  |  |  |  |
| Prepared: |  | Prepared By: |  |  |  | Approved: |  | Approved By: |  |  |
| 5/15/2020 |  | John Lajoie [L5823] |  |  |  | 5/26/2020 |  | Edward O'Brien [18368] |  |  |
| WBS 1.05A |  |  |  |  |  | Reporting Period: April 2020 |  |  |  |  |
| Calorimeter Electronics |  |  |  |  |  |  |  |  |  |  |
|  | BCWS | BCWP | ACWP |  | SV in $ | SV in % | CV in $ | CV in % | SPI | CPI |
| Current: | 14,996 | 108,151 | 27,779 |  | 93,155 | 621% | 80,372 | 74% | 7.21 | 3.89 |
| Cumulative: | 2,216,406 | 1,992,958 | 1,961,764 |  | -223,448 | -10% | 31,195 | 2% | 0.90 | 1.02 |
|  | BAC |  |  |  |  |  |  |  |  |  |
| At Complete: | 5,373,219 |  |  |  |  |  |  |  |  |  |
| Threshold(s) Exceeded: Cumulative Schedule |  |  |  |  |  |  |  |  |  |  |
| Explanation of Variance/Description of Problem: WBS 1.5.1 SiPMS – All SiPMS have been received and tested. This leads to +$3.0K SV WBS 1.5.2 Calorimeter Electronics – EMCal SiPM Boards, Sectors 1-12. The order for the SiPM boards has not been completed. This leads to a -$24.6 SV. WBS 1.5.2 Calorimeter Electronics – EMCal Preamp Testing. The testing of the EMCal preamps has not been completed. This leads to a -$1.0 K SV WBS 1.5.2 Calorimeter Electronics - Test Pulse Board. The re-design of the test pulse board has not been completed. This leads to -$12.9K SV WBS 1.5.2 Calorimeter Electronics – EMCal Crates for controllers. The crates have not been ordered. This leads to -$0.5K SV. WBS 1.5.2 Calorimeter Electronics - EMCal LV - The components for the low voltage power systems for EMCal sectors 1-12 have not all arrived. This leads to -$18.6K SV. WBS 1.5.2 Calorimeter Electronics - EMCal Bias system – The Bias system for EMCal sectors 1-12 have not arrived. This leads to -$43.3K SV. WBS 1.5.2 Calorimeter Electronics – HCal Backplanes – The boards have not yet been received and tested. This leads to a -$2.3K SV. WBS 1.5.3 Calorimeter Digitizer System (Boards) – Not all of the printed circuit boards on order for the 7 Crate system have arrived. This leads to a -$32.6K SV. WBS 1.5.3 Calorimeter Digitizer System (Assembly and Test) – The assembly and testing of the 7-Crate Digitizer system has not started. This leads to a -$90.9K SV. |  |  |  |  |  |  |  |  |  |  |
| Impact: WBS 1.5.1 SiPMs - None. Work is completed WBS 1.5.2 Calorimeter Electronics – EMCal SiPM Boards, Sectors 1-12 – None. The boards for the first sector have been received and tested with 100% yield. The order for the balance of the boards has been placed and is waiting the delivery of the printed circuit boards which is part of the assembly order. The assembly house as indicated a delivery date in early May which is before they are required for EMCal sector assembly. WBS 1.5.2 Calorimeter Electronics – EMCal Preamp Testing – None. The preamp boards for Sectors 1-3 have been delivered to the EMCal group and the Lehigh University group has received the balance of the boards for testing. The projected testing rate is 1 sectors worth of boards per week. The next batch of tested boards will be delivered to BNL in advance of when they will be needed for installation. WBS 1.5.2 Calorimeter Electronics - Test Pulse Board – None. Redesign of the Test Pulse Board has started with a scheduled completion date of mid-May 2020. Several prototype boards have been assembled and can be used for test stands. The production boards are not required until the EMCal and HCal digitizer racks are assembled. WBS 1.5.2 Calorimeter Electronics – EMCal Crates for controllers – None. These are off the shelf devices that are not required until the EMCal is installed into the IR. A number of crates are on hand for testing of EMCal electronics. WBS 1.5.2 Calorimeter Electronics - EMCal LV - None. Existing LV supplies will be used to test all production EMCal sectors. Production LV systems are not required until installation into the assembly hall starts in late 2021. WBS 1.5.2 Calorimeter Electronics - EMCal Bias system – None. There are existing bias supplies that can be used for biasing the the EMCal sectors and HCal modules for testing. Quotes for the calorimeter bias system have been obtained and purchasing process has started. It is expected that BNL will issue the purchase order in early May. WBS 1.5.2 Calorimeter Electronics – HCal Backplanes – The backplane order has been placed, but the backplanes have not been received. The assembler has provided a late-May delivery date. There are sufficient backplanes to keep up with HCal module assembly. WBS 1.5.3 Calorimeter Digitizer System (Boards) – None. Not all of the printed circuit boards for the 7-crate pre-production have arrived. Orders have been placed with a completion of delivery of all boards by May 1, 2020. This does not affect other MIE work, because an adequate number of prototype calorimeter digitizers are at BNL and meet all specifications, and thus are in use to support all calorimeter detector production and testing. There are some 130 days of float in the Calorimeter Digitizer effort relative to the MIE critical path. WBS 1.5.3 Calorimeter Digitizer System (Assembly and Testing)- The boards cannot be assembled for the 7-crate pre-production prototype of the calorimeter digitizers until the b |  |  |  |  |  |  |  |  |  |  |
| Corrective Action: WBS 1.5.1 SiPMs - None. Work is completed WBS 1.5.2 Calorimeter Electronics – EMCal SiPM Boards, Sectors 1-12 – The order has been placed with the assembly house and they have placed orders for materials. Work with assembly house to make sure that boards are delivered before they are required for installation. We will continue to closely monitor the vendors delivery schedule. WBS 1.5.2 Calorimeter Electronics – EMCal Preamp Testing – The Lehigh group is testing preamp boards at a rate that exceeds the installation rate. Work closely with the Lehigh group to maintain the testing rate. WBS 1.5.2 Calorimeter Electronics - Test Pulse Board – The design phase is well along and will be ready to be reviewed for production in June of 2020. Work with sPHENIX project management to make sure that the required design resources are available and that a design review is completed in a timely manner. WBS 1.5.2 Calorimeter Electronics – EMCal Crates for controllers – The manufacturer for the crates has been identified. RFQ for pricing has gone out to prepapare the procurement documentation. WBS 1.5.2 Calorimeter Electronics - EMCal LV – The final design of the EMCal LV distribution system is scheduled to be completed in the summer of 2020. The power supplies and distribution system will be ordered with the components needed for EMCal Sectors 13-64. WBS 1.5.2 Calorimeter Electronics - EMCal Bias system – Work with BNL procurement to get the order placed and monitor the vendors delivery schedule. WBS 1.5.3 Calorimeter Digitizer System (Boards) - Boards are on order with a scheduled delivery date. Will follow up with board manufactures to make sure there are no delays in delivery. WBS 1.5.3 Calorimeter Digitizer System (Assembly and Test) – Prepare documentation and assembly kits so that the boards can be sent out for assembly as soon as they arrive and are inspected. |  |  |  |  |  |  |  |  |  |  |
| Prepared: |  | Prepared By: |  |  |  | Approved: |  | Approved By: |  |  |
| 5/15/2020 |  | Eric Mannel [24903] |  |  |  | 5/26/2020 |  | Edward O'Brien [18368] |  |  |
| WBS 1.06A |  |  |  |  |  | Reporting Period: April 2020 |  |  |  |  |
| DAQ & Trigger |  |  |  |  |  |  |  |  |  |  |
|  | BCWS | BCWP | ACWP |  | SV in $ | SV in % | CV in $ | CV in % | SPI | CPI |
| Current: | 0 | 99,994 | 121,723 |  | 99,994 | 0% | -21,729 | -22% | 0.00 | 0.82 |
| Cumulative: | 222,833 | 322,827 | 213,358 |  | 99,994 | 45% | 109,469 | 34% | 1.45 | 1.51 |
|  | BAC |  |  |  |  |  |  |  |  |  |
| At Complete: | 1,240,177 |  |  |  |  |  |  |  |  |  |
| Threshold(s) Exceeded: Cumulative Cost |  |  |  |  |  |  |  |  |  |  |
| Explanation of Variance/Description of Problem: As detailed last month, we have not received an invoice from Nevis Labs as they are working under a work-from-home order. This has resulted in a virtual shutdown of the administrative processes. |  |  |  |  |  |  |  |  |  |  |
| Impact: There is no impact. The funds allocated for this part of the project have not been invoiced and cannot be costed. |  |  |  |  |  |  |  |  |  |  |
| Corrective Action: None. We need to wait until the virtual shutdown due to the Covid-19 pandemic ends to receive the invoices. |  |  |  |  |  |  |  |  |  |  |
| Prepared: |  | Prepared By: |  |  |  | Approved: |  | Approved By: |  |  |
| 5/26/2020 |  | Irina Sourikova [22419] |  |  |  | 5/26/2020 |  | Edward O'Brien [18368] |  |  |
| WBS 2.02 |  |  |  | Reporting Period: 4/1/2020 - 4/30/2020 |  |  |  |  |  |  |
| SC Magnet (Kin Yip [22397]) |  |  |  |  |  |  |  |  |  |  |

|  | BCWS | BCWP | ACWP | SV in $ | SV in % | CV in $ | CV % | SPI | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current: | 274,139 | 139,533 | 27,978 | -134,606 | -49% | 111,555 | 80% | 0.51 | 4.99 |
| Cumulative: | 1,733,317 | 1,158,974 | 1,003,700 | -574,344 | -33% | 155,273 | 13% | 0.67 | 1.15 |
|  | BAC |  |  |  |  |  |  |  |  |
| At Complete | 5,684,724 |  |  |  |  |  |  |  |  |

Explanation of Variance/Description of Problem:  5 main items contributed to this SV.

1. Five pegpoints on the contract for the helium cryogenics were not complete. These include the remaining/small portion of the submission and approval of the  final design (-$8K); three for the interconnections - one for the approval of the preliminary design, one for the approval of the intermediate design and another one  for the submission of the final design (-$148K); and the late delivery of the bayonet of the RHIC Helium Interface and the overall Engineering  supervision (about -$95K), causing a total of about -$252K of SV.

2. The detailed layout and drawing packages for the LN2 transfer system were only 2/3 complete, and piping supports drawings packages were not quite complete, thus  materials and cable tray supports were not procured, due to the need to coordinate detailed design with the platforms on the carriage/cradle, leading to almost -$51K of SV.

3. The weld maps for the GN2 vent line and the warm piping tie-in to the Bldg.1010B compressor were not complete, leading to -$66K of SV. The weld maps for the GN2 vent  line and the current leads of warm piping were not complete, leading to -$36K of SV. The procurements of reliefs and warm valves were not complete, leading to -$31K of SV.  Finally the various cryo control hardware design delays lead to about -$24K of SV, which is offset a little by early procurement of some control hardware items of +$18K of SV.  The net of  all these is about -$145K.

4. The design for the AC/DC power distribution was not complete, nor was procurement of second half of the parts for magnet AC power distribution, leading to a total of -$49K of  SV.  The schedule for the installation works (for cable tray and cable pull/termination) are changed but was considered as late with respect to the baseline, causing -$74K of SV.   The Power Supply Installation documentation was completed, leading to positive +$23K of SV. There is thus a net -$101K of SV in this area.

5. Mapping probe mounts were not built and probes were not procured for the magnet mapping, leading to -$26K of SV.

Impact: The submission and approval of the final design report for helium process line spools will be completed in May.  This should lead to the delivery of the process line spools in July. The  preliminary design report for the helium interconnection spools has started and should finish by the end of May.   This will not impede the contract for the helium interface.  The locations for piping supports and cable trays are under design in another WBS (2.4.2) as part of the overall design for the platform area and are progressing. The design  work on the LN2 system was partly suspended to advance the BNL review of the Helium system, which is closer to the critical path. The two weld maps are part of design packages,  both having about 300d float, thus will not impede other cryogenics work.   The AC/DC power distribution parts are being procured early, 300d float, to be available well ahead of schedule, thus there is no impact on other schedule areas. The schedule of  installation of cable tray and cable pull/termination has changed and this will not impact the overall schedule as there are also about 250d float.  The magnet mapping concept has been re-evaluated based on review committee device and a decision taken to use an existing mapper operated by a group external to BNL. This  eliminates the need for preparing a custom mapper. The new plan will be reflected in the baseline WBS using a PCR in May.

Corrective Action: The design for the line spools will be completed in May.   Then the preliminary design for the helium line interconnect should be completed by the vendor in May and then the  intermediate design will follow. Since RHIC will run in the summer (this year) due to coronavirus delay, the earliest day that the Cryogenics group can install those spools is  in September and so delivery of the process line spools in July is OK. The design of the carriage platforms is proceeding, and allowances have been made for the location of the  piping supports and cable trays needed for the Superconducting magnet. This will require much of FY2020 to complete but will still be done well ahead of when equipment must be  mounted.   A new contract designer has been added and is at work to collect all service routing information and develop an overall map, design and procurement package for routing and support  of services. The two weld maps are in preparation and are expected by June 2020, preserving over 250d float. The engineering effort in support of this is well advanced.  The first half of the AC power distribution parts are in hand and the second half being ordered. The design is underway.  The cable tray installation and cable pull/termination is now scheduled to be done in early 2021.  An external group (CERN) possessing a suitable mapper has been contacted and agreed to perform the mapping. Arrangements are being developed for this.