## Slide 1: Summary , schedule, cost and resources (and DAQ not covered elsewhere)
Flemming Videbæk
BNL

## Slide 2: STAR Forward Silicon Tracker – Crates, ARC, ARM
HV
Custom-designed DAQ system in a WIENER MPOD HV-cPCI mainframe
3 crates, 6 ARCII, 36 ARM for IST sitting on STAR platform ready to use for FST
72 outer signal cables and patch-panel boards for IST reserved as well. (36 needed)
36 patch panels. 36 available.
Need to make new inner signal cables for FST
ARM
ARC

## Slide 3: Status & plans for DAQ system
The Full system of crates and ARM,ARC boards was exercised in mid September 2019. No issues found
Smaller system are used routinely at test stand at UIC for readout of prototypes
Slow control for FST; primarily HV still need to be integrated back into STAR; small changes relative to IST operation
Long signal cables must be re-installed in STAR

## Slide 4: FST construction workforce
NCKU
  Mechanical Structure and Assembly, QC
    Han-Sheng Li, Pu-Kai Wang, Yi Yang
SDU
  Hybrid and T-boards
    Maowu Nie, Jianing Dong
UIC
  Si-sensors, Assembly with FNAL, Module testing and QC
    Zhenyu Ye, Xu Sun, Andres Aguilar, Gavin Wilks, Shenghui Zhang
BNL
  Support Structure, integration, testing
    Rahul Sharma + STSG+electronics group, Pritwish Trebety, Yu Hu, Flemming Videbaek

## Slide 5: Schedule
Procedure – reevaluation after prototypes assembly
  Input from Zhenyu, Yi, Maowu, Rahul
Procurement of Si delayed particular since the inner sensors could not be tested until now. Longest lead time
As was noted by mini-PAC report FST has substantial delays compared to original plan.
  Difficulties to get required flatness and accuracy on module sedges
  Covid-19 (less of impact, but none the less)

## Slide 6: Schedule input I

## Slide 7: Schedule input II

## Slide 8: Time lines

## Slide 9: Milestones
The table is Zhenyu’s table
Based on info gathered recently as provious two slides
Assumes that production can proceed mid August
Assume run-21 ends July 1, 2021
 | As shown in Feb -- Now
Prototype assembly | 2/28/20 -> 7/25/20
Module testing | 4/30/20 -> 8/15/20
Production (ordering) | 5/31/20 -> 8/15/20
1st batch of Hybrids | 7/31/20 -> 10/8/20
1st batch of mechanical structure | 9/31/20 -> 9/30/20
1st batch of sensors | 12/31/20 -> 2/28/20
Assembly complete | 4/30/21 -> 6/30/20
Supporting structure | 
Design and Fab | (9/31/20) -> 11/30/20
Installation on support (start) | 5/1/21
FST in clean room complete | 6/15/21 -> 7/31/21
Install in STAR | 7/15/21 -> 8/20/21

## Slide 10: Costs
Item | Inst | Estimate | note
Si-Sensors | BNL | 280k$ | Quote from April
T-board connectors | BNL | 5.7k$ | Quote
T-Board assembly | SDU/BNL |  | Quote requested
Cable assembly | BNL |  | Quote requested
Hybrids | SDU | In-kind | 
Mechanical + assy. | NCKU | In-kind | 
Transport boxes | UIC |  | 
Si mounting and wire bonding | FNAL ( UIC) |  | SOW with BNL; Not enough funds; Requested estimate
Support structure | BNL | 50k$ | First estimate from Rahul
Cooling Lines | BNL | ?? | 

## Slide 11: Readiness review for production
Need to procure Si sensors asap; only just being tested inner sectors
Large purchase – need to ensure the are no open ends
Will have a ½ day review on 8/3 Monday
Committee, all non-STAR BNL people
  Jim Stewart
  Jim Mills
  Gerrit van Nieuwenhuizen
  Paul o’Connor
  Grezgor Deptuch

## Slide 12: Agenda
Introduction -> Zhenyu Ye (15’) Detector requirements Design concepts Module Mechanical production -> Yi Yang (25’) Hybrids Mechanical sector production Assembly Tests and QA
Hybrid production and QC – Maowu (15’) Prototype module assembly and performance - Xu Sun (25’) Module assembly at FNAL Tests and QA at UIC (procedures) Performance from the tests Performance in simulation based on the measured response (?) Mechanical integration -> Rahul Sharma (25’) Requirements, Design Support structures Detector support interface Cooling system Summary and Outlook - Flemming Videbaek (25’) Electronics, DAQ and Slow Control Schedule, Milestones, Resources

## Slide 13: Summary
The FST schedule is tight; feasibility do depend on the run/shutdown schedule for run-21 that is yet not determined.
The prototyping has revealed several issues that are almost all solved.
The Si-design is frozen at this point!
  Awaiting review for major procurements to go ahead