## Slide 1: Electronics & DAQ Status
T. Camarda
(with T. Ljubicic)

## Slide 2: DEP/ADC Boards
Boards are in assembly
  expected early Aug
  2 early articles received and tested OK
    some minor issues -- list sent to vendor
5 DEP crates getting assembled in the lab
  enclosure, power supplies, backplanes, etc.
  expected by Aug 1
quick Q&A plan available once the boards arrive
  with final testing assumed to be done after installation in STAR

## Slide 3: DEP/IO (Trigger) Boards
we still need to complete the full setup and verification
  lost 3-4 months so far due to COVID
  need Bob Scheetz and TL to continue…
  on hold until BS & TL available (Sep? Oct?)
Trigger algorithms stalled
  expected to pick this up later in fall/winter

## Slide 4: FCS DAQ
All 11 DAQ PCs installed and working
All 22 DAQ Receiver Boards installed in the PCs
  firmware flashed
  devices drivers ported
  all pass preliminary tests
    full tests need active fibers → Sep
2 MIC boxes (aka fiber patch panels) installed
  fiber patch cables purchased
long fiber bundles purchased and waiting for installation
  this also includes STGC fibers, NB

## Slide 5: STGC DAQ
4+1 spare DAQ PCs ordered
  expected mid-Aug
  space in the same DAQ FCS rack available
    power, network ready
4+1 DAQ Receiver Boards ordered and received
  need firmware programming and assembly → will wait for DAQ PCs (Aug)

## Slide 6: FCS Electronics Installation in ~Sep
FCS rack available and in-place (see Tim’s talk)
Major components:
  5 DEP crates
  TCD fanout unit (with cable to the FCS TCD already in place)
  Network power switches for remote power control (already purchased)
  MIC fiber patchpanel boxes (purchased)
  ethernet
Installation expected to be quick
  also need to install fiber bundles and pull them to the DAQ Room PCs
Verification and further development (firmware, software) will continue in fall/winter 2020

## Slide 7: Summary
generally doing well
managed to “salvage” significant chunks of time lost due to COVID
  Bob & TL remotely
  Mike and Tim also but in the lab/DAQ Room as well!
major part still left are the DEP/ADC boards Q&A once they arrive
DEP/Trigger board system verification and final setup still on “COVID”-hold